## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q1 23-24 | Q2 23-24 | Q3 23-24 | Q4 23-24 | Q1 24-25 (Current) | Reporting Comments
Q1 24-25 | Yarra Valley Water | YV Water | 3078 | Yarra Valley Online Water (YVOW) Replacement | Environment and Water | Customer Relationship Management,Customer Relationship Management | Replace end-of-life customer self-service portal (YVOW) with MyAccount Customer Portal in Salesforce. Reduce call centre volume through customer digital self-service, and improve customer experience with a redesigned, enhanced portal | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 330000 | 1400000 | 2021-07-01 |  | 2022-12-31 | 2024-12-31 | 1886564 | 7974075 | Amber | Amber | Green | Green | Green | All releases completed within the reporting period. Closure activities underway. Note: The delivery budget increase is to reflect the total approved budget for the remaining delivery phases.
Q1 24-25 | Court Services Victoria | CSV | 3794 | Wyndham Law Courts - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | This objective of the project requires the preparation of the new Wyndham site to be a member of the Cenitex GSP INTERNAL network for initial use by Customers and Court staff. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - Waterfall and Agile | 2023-12-20 | 2024-03-29 |  | 2024-06-03 | 0 | 0 | 2024-06-03 |  | 2025-03-31 |  | 1330000 | 1333849 |  |  |  | Green | Green | Comms links being commissioned ready for network commissioning.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3813 | WSV Devices and Office 365 Replacement - Phase 1 Devices | Government and Economy | Systems Management | Phase 1 Devices - Replacement of the oldest 800 end of life (EOL) devices, mitigating the risk of significant rental costs on ageing fleet, and improving device performance, supporting WSV employees to perform their daily operations more efficiently. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-07-01 | 2023-08-31 |  | 2023-12-06 | 521408 |  | 2023-12-15 |  | 2024-07-22 | 2024-10-10 | 885254 |  |  | Green | Amber | Green | Red | 566 devices out of 800 have been deployed. The project is tracking Red as the schedule will be extended to cover completion of device decommissioning and project closure. A Change Request will be raised to rebaseline schedule and transfer residual device roll-outs to BAU for completion returning the project health to Green. No impact to budget.
Q1 24-25 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Initiated |  |  | Agile | 2024-07-01 | 2025-03-31 |  |  | 650000 | [12 empty] | On track
Q1 24-25 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 |  | 9680463 |  | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q1 24-25 | Department of Premier and Cabinet | DPC | 3608 | Workflow Management System for Office of Chief Parliamentary Counsel (OCPC) | Government and Economy | Development and Integration ,Tracking and Workflow | WMS project will provide workflow for managing legal projects to improve management of the projects as per the OCPC standards and timely and accurate reporting to internal and external users to ensure timely publishing on the legislation website. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2021-06-18 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2023-02-24 |  | 2024-07-13 | 2026-11-20 | 2500000 |  | Green | Amber | Amber | Amber | Amber | Due to the extensive requirements our supplier has proposed a new delivery date of May 2026. because of the substantial number of, and technically complex, requirements. The Project Control Board (PCB) has, instead, chosen a new delivery date of November 2026 to avoid a cut-over to the new system during Parliamentary sittings in an election year and to take advantage of the election caretaker period
Q1 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3567 | Wireless Network Refresh | Health | Collaboration ,Communication | Upgrade the Wireless Network Infrastructure at the VCCC to replace legacy hardware. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-10-20 | 2023-07-31 | 2023-08-14 | 2023-08-14 | 0 | 48807 | 2023-08-15 |  | 2025-01-31 | 2025-03-31 | 1600929 | 1552122 |  | Green | Green | Green | Green | Access point upgrades nearing completion 95% complete.
Q1 24-25 | Western Health | WH | 3851 | Western Health - Mental Health Transition (ICT Infrastructure) | Health | Development and Integration | The project will transition and integrate Mental Health ICT infrastructure into Western Health, enabling consistent IT support and management for mental health doctors and clinicians. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-10-30 |  | 2023-11-20 | 0 |  | 2024-01-01 |  | 2024-10-30 | 2025-01-30 | 1960000 |  |  |  | Green | Green | Green | Hardware has been delivered and implementation is underway.
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3797 | Voice to Text Solution | Community Services | Customer Relationship Management | Integrate Voice-to-Text (VTT) technology in the Child Protection Client and Case Management System (CRIS) to enable practitioners to dictate case notes directly into the CRIS reducing manual data entry and increasing accuracy of case notes. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2023-03-02 | 0 |  | 2023-04-03 |  | 2024-08-31 | 2025-06-30 | 2395719 | 2338561 |  | Green | Green | Amber | Amber | Project is progressing however is reporting Amber pending approval of re-phasing of funding.
Q1 24-25 | Melbourne Water | MELB Water | 3808 | Virtualised Software and Server Upgrades | Environment and Water | Systems Management | Project is to upgrade the current version of Virtual software due to end-of-life support and upgrade servers. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-11-29 | 2024-04-01 |  | 2024-05-31 | 0 |  | 2024-05-31 |  | 2025-04-07 |  | 1842537 |  |  |  |  | Green | Green | RFQ Best and final Offer (BAFO) closed in August. Awaiting procurement to issue the contract. Virtual hosts still under management review if this project will upgrade or go with an alternative solution.
Q1 24-25 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2024-10-31 | 22637000 |  | Green | Amber | Green | Green | Green | Overall project status is green. Streams 1 and 4 are completed. Stream 2 and 3 activities are ongoing.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3100 | Victorian Water Register Transform Project | Environment and Water | Management of Process | The project will deliver a new Victorian Water Register(VWR) to improve service delivery, information sharing and to ensure the equitable sharing of water and continuous improvement in the integrity security and reliability of Victoria's water market | Postponed | Customer Satisfaction (Non Financial) | 2023-12-04 | PRINCE2 | 2020-10-25 | 2021-06-30 | 2022-09-30 | 2022-09-30 | 1467715 | 2501098 | 2022-12-05 |  | 2024-06-28 |  | 21450606 | 24225902 | Red | Red | Red | Red | Red | The project remains paused whilst alternate options are being considered.
Q1 24-25 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2025-12-31 | 5135000 | 29519005 | Amber | Amber | Green | Amber | Green | Overall project status green. Project go-live activities are ongoing. Note: Change to delivery cost is due to additional scope merged from other programs as well as budget approved for the subsequent delivery phases.
Q1 24-25 | Victorian Infrastructure Delivery Authority | VIDA | 3967 | Victorian Health Building Authority (VHBA) Integr8 | Transport and Vehicles | Collaboration ,Financial Management,Human Capital / Workforce Management ,Human Resources,Investment Management,Organisational Management | The VHBA Integr8 Program has been established to support VHBA to enact their Machinery of Government changes, with a specific focus on transitioning to the VIDA Information and Technology systems and supporting a smooth transition for VHBA employees. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-09 | 2024-11-11 |  |  | 250000 | [12 empty] | The project governance structure has been established. The Project scope has been finalised, with a Project Plan also being developed.
Q1 24-25 | Essential Services Commission | ESC | 3732 | Victorian Energy Upgrades (VEU) IT System Upgrade | Environment and Water | Analyses and Statistics ,Customer Relationship Management,Development and Integration | The project will deliver a replacement to the existing VEU registry system to improve information access, process management and consumer engagement, meeting new legislative and regulatory requirements. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2023-08-01 | 2024-08-30 | 2024-03-28 | 2024-03-28 | 500000 |  | 2024-03-28 |  | 2025-01-24 | 2025-03-31 | 7709000 |  |  |  | Green | Green | Amber | The project has progressed into Delivery Phase with Vendor. Key deliverables mostly on track with some slippages encountered. Project Variation in progress.
Q1 24-25 | Department of Education | DE | 3862 | Victorian Curriculum and Assessment Authority (VCAA) Student Portal | Education | Communication,Customer Initiated Assistance,Reporting ,Tracking and Workflow | The student portal will provide a new digital channel for senior secondary students to access a range of VCAA services including enrolment details examination timetables and academic records, reducing reliance on paper records. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2023-07-03 | 2023-11-30 |  | 2023-11-30 | 20000 |  | 2024-02-26 |  | 2025-03-31 | 2025-07-21 | 2405203 | 3033573 |  |  | Green | Amber | Green | A change management plan is currently being developed to support the Student Portal with a limited trial planned in October 2024 across two schools. The launch of the portal is expected to be implemented by the beginning of Term 3 in 2025.
Q1 24-25 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2025-12-01 | 56681000 |  | Red | Amber | Amber | Amber | Amber | The overall Program status reported as Amber due to the incomplete Discovery of increased new scope, and the yet to be confirmed impacts to cost and schedule.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2023-12-30 | 2023-12-30 | 3297000 | 2971000 | 2024-03-01 |  | 2025-06-30 |  | 18423392 |  |  |  | Amber | Amber | Amber | The project continues to report amber due to the tight timelines for delivering the enhanced payment requirements by the commencement date. To address this risk within the available timeframe, a risk-based testing approach has been agreed upon. It is anticipated that the Financial Assistance Scheme (FAS) will be initiated in quarter 2 2024-25, and the systems will be delivered, which should return the status to green.
Q1 24-25 | Ambulance Victoria | AVS | 3815 | VACIS Modernisation Device Pilot | Health | Data Management | The project will pilot new Patient Care Record devices for paramedics to reduce administrative time, and improve information access and response performance, enabling paramedics to make timely decisions when treating patients. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-12-01 | 2023-06-30 |  | 2023-07-01 | 700000 | 9732 | 2023-07-27 |  | 2024-12-31 | 2025-01-30 | 3215813 | 3906081 |  | Green | Amber | Amber | Amber | The project is tracking Amber due to a business resourcing constraint that impacts on commencement of the pilot. The resourcing constraint was resolved at the end of Q1 and the project will commence the in-field pilot phase in Q2.
Q1 24-25 | State Revenue Office | SRO | 3965 | Vacant Residential Land Tax 2 | Government and Economy | Development and Integration | From 1 January 2025, VRLT will be expanded to apply to all residential properties in Victoria. From 1 January 2026, VRLT will be further expanded within Greater Melbourne area. This project makes the system changes required to administer the tax. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 35000 |  | 2024-07-01 |  | 2026-06-30 |  | 1927652 | [5 empty] | Amber | Project reporting amber because of some remaining scope uncertainty. Expected to return to green by next reporting period.
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3568 | Unified Communications Infrastructure | Health | Communication | Replace end of life PABX with new Unified Communications infrastructure for Mildura Base Public Hospital (MBPH). This uplift replaces a system that is prone to failure/outages- project will improve patient and staff safety via improved reliability. | Closed - Completed | Risk Reduction (Non Financial) | 2024-07-31 | PRINCE2 | 2021-06-23 | 2023-02-15 | 2023-06-02 | 2023-06-02 | 0 |  | 2023-06-05 |  | 2024-03-22 | 2024-06-28 | 1207979 |  | Green | Green | Amber | Amber | Green | Project is now complete.
Q1 24-25 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | Objective of this program is to implement cyber and information security standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2025-06-30 | 6800000 | 13320000 |  | Amber | Amber | Green | Green | Overall project status is green. On Track with 9 projects streams completed and 7 others in progress.
Q1 24-25 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes to maintain procurement integrity.
Q1 24-25 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes to maintain procurement integrity.
Q1 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3878 | Timetabling Optimisation | Education | Systems Management | The Timetable Optimisation project aims to uplift the Celcat system & data to enable timetabling automation functionality for all BKI classes, and re-design integration with JR Plus to remove manual processing improving efficiency | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2024-06-14 |  | 2024-06-14 | 650000 |  | 2024-06-14 |  | 2024-12-06 |  | 630162 |  |  |  |  | Green | Red | The project status is tracking red due to delays in schedule and delivery of scope. The project team is working to release functionality in phases to ensure realisation of benefits inline with business requirements.
Q1 24-25 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 |  | 12100105 | [5 empty] | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2025-12-31 | 131615000 | 169961000 | Amber | Amber | Amber | Amber | Amber | The project is progressing however continues to report amber due to schedule impacts from previous and current recruitment and productivity challenges. Changes to the structure of vendor contracts and success in recruiting to key positions are expected to improve output. Additionally, there has been endorsement for rationalisation of project scope to prevent budget risk and to provide an opportunity for schedule recovery.
Q1 24-25 | Department of Jobs, Skills, Industry and Regions | DJSIR | 3867 | TAFE Customer Relationship Management (CRM) tool | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery (OTCD) and the TAFE Network collaborate to align services, improving outcomes for students and industry. A modern CRM tool will boost TAFE's ability to enrol students and engage with industry partners. | Closed - Completed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2024-08-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-18 | 2024-03-28 |  | 2024-03-28 | 439600 |  | 2024-03-29 |  | 2024-09-30 |  | 4857000 |  |  |  |  | Green | Green | During the quarter the project has been closed and all key deliverables have been met.
Q1 24-25 | Greater Western Water Corporation | GW Water | 3970 | Systems Support | Environment and Water | Content Management,Data Management,Human Capital / Workforce Management ,Knowledge Discovery ,Knowledge Management ,Management of Process ,Reporting ,Systems Management,Tracking and Workflow | This project was established with a focus on GWWs customer ecosystem uplift to address system billing defects & process issues over a 3 month period by prioritising issues based on severity & impact | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) | 2024-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-04 |  | 2024-07-04 | 1427182 |  | 2024-07-04 |  | 2024-09-30 |  | 1720628 | [5 empty] | Green | Project completed approved scope on time and within budget. Triage of critical defects completed with data defects addressed.
Q1 24-25 | Greater Western Water Corporation | GW Water | 3971 | Systems Readiness | Environment and Water | Communication,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Forms Management,Management of Process ,Records Management ,Reporting ,Systems Management,Tracking and Workflow | This project was established to focus on uplifting the customer ecosystem with a focus on core billing being operationally sound and to support customer facing processes including stabilising IT infrastructure and new service demands | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-04 |  | 2024-07-04 | 1593505 |  | 2024-07-04 |  | 2025-06-30 |  | 4406495 | [5 empty] | Amber | the project status as at the end of Q1 was amber due to complexities with the implemented billing solution. Mitigations in place to understand the complexities and obtain organisational endorsement on a way forward.
Q1 24-25 | Department of Jobs, Skills, Industry and Regions | DJSIR | 3840 | Supplier Data Integrity | Business and Industry | Data Management,Financial Management,Management of Process ,Systems Management | Enhancement of the integrity and management of suppliers throughout the supplier life-cycle, including onboarding, robust bank account verification solution, contract and payment management, and supplier cessation. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2024-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-16 | 2023-03-17 |  | 2023-11-02 | 221143 |  | 2023-11-05 |  | 2024-09-30 |  | 1233177 |  |  |  | Green | Green | Green | The project was successfully completed, meeting key deliverables such as enhancing the supplier onboarding tool, developing a payment integration API, and implementing a bank verification process through a third-party platform.
Q1 24-25 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Postponed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2022-09-14 | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2024-06-28 | 3174023 |  | Green | Green | Green | Green | Green | Due to IT Portfolio Prioritisation decision, SRM Project has been placed on HOLD. The status will be re-reviewed for FY 24/25.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Government and Economy | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 4597071 | [5 empty] | Green | Overall status on track with no blockers.
Q1 24-25 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 |  |  | 2024-07-01 |  | 2026-06-30 |  | 11000000 | [5 empty] | Green | On Track.
Q1 24-25 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Initiated |  |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  |  | 0 | [12 empty] | Business Case is being drafted
Q1 24-25 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2024-11-01 |  | 0 | 0 | [11 empty] | The SVHM Electronic Medical Record (EMR) project has progressed to the next phase as a shared implementation with another health service is explored as the preferred option. Both health services will now commence a readiness assessment to determine the collaboration principles and obtain required approvals to progress to a shared EMR implementation.
Q1 24-25 | Department of Transport and Planning | DTP | 3502 | Speed Change Management Tool Project | Transport and Vehicles | Communication,Content Management,Data Management | The objective of this project is to streamline the speed zone and speed sign change processes. This will be achieved through an integrated Speed Change Management Tool (SCMT). | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2023-01-31 | 2023-04-28 | 2023-05-08 | 0 |  | 2023-06-19 |  | 2024-07-31 | 2025-01-29 | 1029000 |  | Amber | Green | Amber | Green | Green | Overall project status is green. Project has been re-baselined and Bundle 3 build and configuration activities are in progress.
Q1 24-25 | Kardinia Park Stadium Trust | KPST | 3914 | Southern Scoreboard Replacement Project | Culture, Sport and Recreation | Communication,Content Management | Replacement of the life expired Southern Scoreboard at GMHBA Stadium to support event delivery, emergency management and customer fan experience. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Vendor provided methodology | 2024-05-05 | 2024-05-05 |  | 2024-05-05 | 0 |  | 2024-05-06 |  | 2025-03-28 |  | 3000000 | [5 empty] | Green | The project was successfully released to market as part of a tender process to select a supplier to deliver the design and construction of the final solution.
Q1 24-25 | Dental Health Services Victoria | DHSV | 3400 | Smile Squad Network infrastructure | Health | Systems Management | Provision of network infrastructure to smile squad service program | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-07-12 | 2022-01-28 |  | 2022-01-28 | 100000 |  | 2022-01-31 |  | 2023-08-04 | 2024-12-30 | 1964978 |  | Green | Green | Red | Amber | Amber | The projects focus for the next reporting period will be implementation of Smile Squad Network
Q1 24-25 | State Revenue Office | SRO | 3624 | SmartForms Replatforming | Government and Economy | Development and Integration | The State Revenue Office has migrated 50+ digital customer forms, known as SmartForms to a new platform. This helps us to accurately calculate taxes, levies and duties and issue the right exemptions and concessions. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial) | 2024-07-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2023-01-02 |  | 2023-01-02 | 100000 | 100000 | 2023-01-02 |  | 2024-06-30 | 2024-07-31 | 2100000 | 3481846 | Amber | Amber | Amber | Amber | Green | Project closed on 31 July 2024
Q1 24-25 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | Objective of this project is to prepare an options analysis brief outlining best of breed solutions for Timetabling and Journey planning. The analysis will inform a recommended solution to build and implement. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2024-12-18 | 4739268 | 6200337 | Green | Green | Amber | Amber | Amber | Overall project status is amber due to technical issues impacting schedule. Phases 1 and 2 are completed. Phase 3 activities are currently in progress.
Q1 24-25 | State Revenue Office | SRO | 3964 | Short Stay Levy | Government and Economy | Development and Integration | A levy on short stay accommodation in Victoria will be implemented on 1 January 2025. This aims to address the issue of the reduced supply of properties available for long-term accommodation. This project sets up the systems to administer the levy. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 81000 | 60000 | 2024-07-01 |  | 2025-06-30 |  | 3080000 | [5 empty] | Green | Overall project is tracking well against plan
Q1 24-25 | Department of Government Services | DGS | 3827 | Service Victoria - Digital Driver Licence | Government and Economy | Customer Preferences,Systems Management | To digitise the physical driver licence into a digital format, allowing driver licence to be securely stored on the Service Victoria app, providing Victorians a choice to either carry a physical or digital card. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-04 | 2021-05-01 |  | 2021-05-01 | 0 |  | 2021-07-01 |  | 2024-06-30 | 2024-10-21 | 4267632 | 5483000 |  | Green | Green | Green | Green | The project delivered the statewide launch of digital driver licence for full-licence holders in Q4 and is on track for L's and P's in Q2 of 2024-25.
Q1 24-25 | Department of Education | DE | 3962 | Senior Secondary Pathways Reform Transformation | Education | Customer Relationship Management,Data Management,Forms Management,Tracking and Workflow | The Program will digitise streamline and enhance the management of work-based learning delivering an exceptional learning and development experience for every Victorian Secondary School ensuring pathways are optimised for students. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 0 |  | 2024-04-01 |  | 2025-06-30 |  | 14190000 | [5 empty] | Amber | A recently required business process change related to the Statewide Referral and Exemption Initiative has resulted in the need for a technical design change. An impact assessment focusing on the cost and schedule impact is currently underway, this assessment is expected to be complete by end of October 2024.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3849 | Self Insurance Uplifting Oversight of Claims Management Performance | Government and Economy | Business Intelligence | The Self-Insurance (SI) Uplifting Oversight project aims to develop and implement a solution for receiving additional (transactional level) electronic data from Self-Insurer’s (SI’s) more frequently (monthly) and enhance oversight and performance. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-01-08 | 2022-06-30 |  | 2022-09-06 | 0 |  | 2022-12-06 |  | 2025-06-30 |  | 2669306 | 3652379 |  |  | Green | Green | Green | On track
Q1 24-25 | Monash Health | Monash H | 3644 | Security Card Technology Upgrade | Health | Security Management | Replacement of access control card readers and associated hardware across all sites to ensure access control security remains at an appropriate level and can integrate with current and future system requirements. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2022-04-15 | 2023-02-23 |  | 2023-02-23 | 0 |  | 2023-05-03 |  | 2024-05-31 | 2024-08-30 | 2263923 | 2519211 | Amber | Amber | Green | Amber | Amber | The project is at risk due to a schedule delay, as it is awaiting confirmation of procurement activity. Once confirmed, the timeline will be rebaselined and approved by the Project Control Group.
Q1 24-25 | Department of Health | DH | 3844 | Security Access Modernisation | Employment and Workplace | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 |  | 1413388 |  |  |  |  | Green | Green | Project progressing to cost and schedule.
Q1 24-25 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | SCL is a ‘high profile’ program of work creating enhanced security capabilities for schools initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 |  | 3100000 | [5 empty] | Amber | Minor delays to the Cyber platforms pilot deployments caused by additional testing being completed due to the high complexity of the solution. Planning being updated to return project to original completion timelines.
Q1 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3884 | SEC Retail Customer Billing System | Environment and Water | Customer Relationship Management | This project is implementing a Customer Billing System that will enable SEC to launch an Energy Retail Business servicing electricity C&I Customers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-21 | 2024-10-11 | 2024-10-18 |  | 225000 | 258000 | [11 empty] | SEC has selected and on-boarded Customer and Billing vendor. Requirements gathering and design workshops have commenced to develop a solution blueprint with implementation due to commence next quarter.
Q1 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3940 | SEC ETRM System | Environment and Water | Financial Management | This ETRM Solution will provide an integrated suite of systems to meet the SEC’s requirements of Deal capture, Settlements validation, Authorised trader/mandate register and Risk management. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-17 | 2024-10-14 |  |  | 179000 | [12 empty] | A competitive procurement process has been completed with a number of high-quality submissions and the SEC has selected and on-boarded an ETRM software vendor. Requirements gathering and design workshops have commenced to develop an implementation specification with solution build phase due to commence next quarter.
Q1 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3938 | SEC Corporate ERP System | Environment and Water | Financial Management,Human Resources,Supply Chain Management | The SEC Corporate ERP system implementation project will select and implement an integrated Finance, HR and Procurement system to meet the requirements of SEC. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-12 | 2024-11-30 |  |  | 390000 | [12 empty] | A competitive procurement process has been completed with a number of high-quality submissions and the SEC has selected and on-boarded an ERP vendor. Requirements gathering and design workshops have commenced to develop a solution design specification with implementation due to commence next quarter.
Q1 24-25 | Department of Health | DH | 3846 | SDWAN activities and production rollout | Health | Systems Management | Delivering a new resilient, secure and internet centric network solution to all Department of Health and Families, Fairness and Housing sites, supporting the departments move towards cloud based IT services. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-12-01 |  | 2023-12-04 | 0 |  | 2024-01-02 |  | 2025-06-30 |  | 1422000 |  |  |  | Green | Green | Green | Project progressing to cost and schedule.
Q1 24-25 | Department of Education | DE | 3960 | School Saving Bonus (SSB) - Digital Portal and Case Management Solution | Education | Customer Relationship Management | The project will deliver a portal and case management solution to support the Victorian Government's school saving bonus initiative from end to end by ensuring families receive the bonus. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Agile | 2024-09-17 | 2024-09-23 |  | 2024-09-24 | 0 |  | 2024-09-24 |  | 2024-11-25 |  | 2915141 | [5 empty] | Green | Testing in progress for the portal solution. The project is tracking to plan and is performing on scope and on budget.
Q1 24-25 | Victorian Building Authority | VBA | 3809 | Scheduling Audit & Inspection | Property and Planning | Customer Relationship Management | Deliver an integrated system improving Audit & Inspection capability enabling the VBA to uplift capabilities in this space, capture more detailed data for analysis & action, & modernise the back-end office administration & rectification proceses | Closed - Completed | Compliance (Non Financial) | 2024-09-13 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-03-01 | 2023-10-27 |  | 2023-10-29 | 0 |  | 2023-10-30 |  | 2024-07-31 |  | 2290000 | 2359500 |  | Green | Amber | Green | Green | This project is now complete
Q1 24-25 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 |  | 1937205 | [5 empty] | Green | Project currently in detailed design and planning phase with appointed vendor.
Q1 24-25 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 |  | 2022-03-01 |  | 2023-06-30 | 2025-06-30 | 8900000 | 10394000 | Red | Red | Red | Amber | Amber | The revised delivery cost is under review to take into account a project re-baseline and additional scope for a portable bonds scheme
Q1 24-25 | Royal Women’s Hospital | RWH | 3703 | Rostering, Time and Attendance Project | Health | Human Capital / Workforce Management | The Project will upgrade the current Rostering system, delivering performance improvements and new enhanced functionalities. This project is part of an overarching People Systems Improvement Program with Royal Melbourne Hospital and Western Health | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-03 | 2023-09-01 |  | 2023-09-01 | 31980 |  | 2023-09-03 |  | 2024-12-31 | 2025-06-30 | 1140573 |  | Green | Green | Green | Green | Amber | Vendor delay in solution development, requiring additional time to rectify, delaying the schedule of onboarding some users to Q1 2025. The onboarding schedule for the majority of employees is still on track.
Q1 24-25 | Ambulance Victoria | AVS | 3816 | Rostering System Replacement (WMS) | Health | Systems Management | The project will replace the current end-of-life rostering software with a new workforce management solution, minimising software stability and security risks, and improving efficiency in rostering processes to deliver more impact to our community. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-30 |  | 2024-03-31 | 1271134 | 826551 | 2024-04-01 |  | 2025-06-30 |  | 3846467 | 5503186 |  |  |  | Amber | Amber | The project is still tracking as Amber because of risks and issues to project scope and cost. The project team will continue to manage closely.
Q1 24-25 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2024-12-31 | 3760000 | 4349947 | Amber | Amber | Amber | Amber | Amber | Project is continuing to report amber due to delays in confirming scope with key stakeholders. FRV is continuing to work with stakeholders to resolve this issue.
Q1 24-25 | Victorian Electoral Commission | VEC | 3802 | Roll Managment System (RMS) Technical Upgrade | Government and Economy | Systems Management | The project will replace the legacy RMS application with a new and supported technology platform, reducing VEC's risk of using an unsupported platform and enabling system continuity for roll management | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-04-14 | 2023-11-08 |  | 2023-11-10 | 880742 |  | 2023-11-10 |  | 2025-09-30 |  | 7841489 |  |  | Amber | Green | Green | Green | The status of the project remains ‘Green’ with all milestones/deliverables on track. To date the vendor has met all agreed milestones to time cost and quality parameters. System testing to verify functionality is underway as planned. No changes in the risk profile and no issues have been reported.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Road Safety Package includes a number of initiatives. The initiatives with ICT deliverables are: • Computerised Maintenance Management System (CMMS) • Network Security - Improvements to security of the Fixed Digital Road Safety Camera network. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 869178 | 2021-05-24 |  | 2022-04-21 | 2025-06-30 | 6967000 | 13618249 | Green | Green | Green | Green | Green | Overall, the two ICT Road Safety Package initiatives are on track. The Computerised Maintenance Management System (CMMS) initiative was completed in December 2023. This initiative is now closed and CMMS is an operational platform within DJCS. The Network Security initiative is in progress and on schedule for completion by 30 June 2025.
Q1 24-25 | Melbourne Health | Melb H | 3709 | RMH Human Resource Information System (HRIS) Project | Health | Human Capital / Workforce Management ,Human Resources | To deliver a HRIS that will replace HR onboard and end of life eRecruit and address the following operational issues: -Lack of integration -Poor employee manager and candidate experience -Manual and duplicative processes -Strategic planning | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-08-18 |  | 2023-08-21 | 30000 |  | 2023-08-21 |  | 2024-09-30 |  | 4277958 |  | Green | Amber | Amber | Green | Green | Post-go-live hypercare stage is complete.. Updated project to completed.
Q1 24-25 | Fire Rescue Victoria | FRV | 3320 | Response Monitoring and Move-Up Monitoring | Emergencies and Safety | Business Intelligence | • Improve emergency response benchmarks, predicative deployment analysis and aid decision making to improve operational response utilising historical response data. • Efficient resource planning and use based on real time data to inform operation. | Postponed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2024-03-31 | FRV PMF | 2021-06-01 | 2021-10-01 |  | 2021-10-01 | 1 | 0 | 2021-12-01 |  | 2023-06-30 | 2024-06-30 | 3000000 |  | Amber | Amber | Amber | Amber | Amber | The project was placed on hold in March 2024 due to fiscal constraints, pending a review of project feasibility. The delivery end date will be re-baselined following confirmation of project feasibility.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 2956 | Resources Management System Victoria (RMSVIC) Project | Business and Industry | Analyses and Statistics ,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Document Management ,Management of Process ,Records Management ,Tracking and Workflow | The Project will deliver a Resources Management System Victoria (RMSVIC) in Salesforce to replace Resource Rights Allocation and Management (RRAM). Key benefits are a fit for purpose, tailored, flexible system supporting industry and the Regulator | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) | 2024-08-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2019-12-31 | 2020-02-26 | 2020-02-27 | 222500 |  | 2020-02-27 |  | 2021-12-31 | 2024-08-26 | 5920000 | 5757005 | Red | Red | Red | Red | Red | The project delivered the back-end of a system to enable implementation of current legislation. The project was completed with reduced scope, with the ability to configure the deliverables to support the future implementation of new legislation in 2027.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Initiated |  |  | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [12 empty] | The project has been approved to commence procurement activities for the provision of a safety incident management system. Due to resourcing constraints, procurement activities have not yet commenced.
Q1 24-25 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System will be replaced to meet current and future business and reporting requirements. The project delivers a contemporary solution to support forensic investigations for Victoria’s justice system. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-01-07 |  | 2022-01-07 | 0 | 350000 | 2022-01-07 |  | 2023-12-31 | 2025-06-30 | 5650000 |  | Green | Green | Green | Amber | Green | The project scope has been reviewed to address the complexities of the case management requirements. The project is on track to deliver the revised scope within the revised schedule, and within the existing budget.
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2025-03-31 |  | 70000 | 600000 | [11 empty] | Project is working through implementation scenarios and options due to dependency on Bendigo Health PAS and EMR project outcomes. Detailed costings and agreed approach will be confirmed and provided in Q3 FY25.
Q1 24-25 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2025-12-31 | 23495000 |  | Amber | Amber | Amber | Amber | Green | The project has moved from Amber to Green following a re-baseline endorsed by project governance and is now progressing to schedule and budget.
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3585 | Regional Community Care Coordination Platform | Health | Records Management ,Tracking and Workflow | Delivery of a digital medical record for all the Community Services provided by members of the Loddon Mallee Rural Health Alliance to support connected patient care across the region (and between health services). | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-04-01 |  | 2019-04-10 | 0 |  | 2019-04-11 |  | 2021-03-31 | 2024-12-27 | 1330000 | 4528817 | Amber | Amber | Amber | Green | Green | The project has completed a re-baseline to enable core activities to be completed by Dec 2024. This aligns with the requirements by LMHN Board.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3540 | Recovery Service Model Technology and Implementation. | Government and Economy | Customer Relationship Management | Delivery of case management capability using Saleforce platform to enable improved recovery management and planning tools as well as core claims management capability, uplifting the recovery and return to work outcomes for injured workers. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-08-23 |  | 2022-08-24 | 0 |  | 2022-10-03 |  | 2024-11-30 | 2025-02-28 | 39266624 | 37871384 | Amber | Green | Green | Amber | Amber | Overall status is amber due to anticipated budget impacts from the inclusion of additional scope items, including enhancements to the CRM, further support for impacted business units, and additional integration requirements. A Change Request will be raised to rebaseline the budget.
Q1 24-25 | South East Water | SE Water | 3909 | PULSE CX Optimisation Phase 2 | Environment and Water | Customer Relationship Management | This project will deliver significant uplift to SEW's Customer Relationship Management (CRM) and telephony system. This includes uplift to contact centre efficiency, bolstering data security and introducing more self-service options for customers. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Agile | 2024-09-01 | 2024-09-06 |  | 2024-09-06 | 0 |  | 2024-09-09 |  | 2025-04-30 |  | 2649304 | [5 empty] | Red | The project status is RED due to the project unable to secure technical expertise for architecture and design of components of the solution. Project currently sourcing required technical resources/partner for solution design of impacted components in the next quarter and return project to GREEN.
Q1 24-25 | South East Water | SE Water | 3910 | PULSE CX Optimisation Phase 1 | Environment and Water | Customer Relationship Management | Project will deliver improvements to SEW's CRM and telephony platforms that will optimise customer experience improve process efficiencies and increase the productivity of our staff. This will reduce number of enquiries and call handling time. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial) | 2024-08-30 | Agile | 2024-01-25 | 2024-01-31 |  | 2024-01-31 | 0 |  | 2024-02-01 |  | 2024-08-30 |  | 1839480 | 1869710 |  |  |  |  | Green | Project delivered in July with enhancements being trialled with pilot group in contact centre. Benefits being measured and will inform plans for phase 2 which will deliver further uplift across customer contact centre operations. Project closure completed in August.
Q1 24-25 | Department of Transport and Planning | DTP | 3829 | Public Transport Data program (PTDP) (Formerly known as ITDP) | Transport and Vehicles | Business Intelligence,Communication,Customer Initiated Assistance,Customer Preferences,Data Management,Search | Purpose of this program is to improve the Department’s capability to deliver accurate and consistent real-time information for customers whenever, wherever and however they need it. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-11-30 | 2024-03-29 | 2025-01-30 |  | 0 | 0 | [11 empty] | Project initiation activities are ongoing.
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-03 |  |  | 1213286 | [12 empty] | Planning and mobilisation activities are in final stages.
Q1 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3518 | Project Synergy | Employment and Workplace | Development and Integration | This project will consolidate applications, retiring 18 applications and 8 databases, moving to a new single database using Microsoft Dynamics 365 which will reduce implementation processing times, improved data accuracy and processes. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-12 | 2022-12-09 |  | 2022-12-09 | 628000 |  | 2023-02-06 |  | 2024-02-06 | 2024-09-30 | 2036760 |  | Green | Amber | Amber | Amber | Red | Overall Status is behind schedule due to ongoing defects with Phase 2 system deployment. Phase 3 delivery paused while defects are resolved. Project end date cannot be revised until there is clarity on the Phase 3 delivery timeline.
Q1 24-25 | Melbourne Water | MELB Water | 3397 | Project Management Transformation | Environment and Water | Collaboration | Melbourne Water uses an enterprise Project Management tool for managing the capital program. Key issues are; - System functionality, - Performance, - End user experience - Technology that won't reach end-of-support | Closed - Completed | Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2024-08-30 | PMBoK | 2022-04-01 | 2022-07-12 | 2022-10-04 | 2022-10-04 | 0 |  | 2022-10-04 |  | 2023-09-30 | 2024-08-30 | 1293120 |  | Red | Red | Amber | Amber | Green | Solution for the inclusion of Opex projects has been implemented with the remainder of reporting requirements handed over to BAU. Interim project ideas module has been implemented using existing technology, therefore completing the remaining scope items for this project. Project is now closed.
Q1 24-25 | Department of Education | DE | 3900 | Project and Portfolio Management Platform (PPMP) | Education | Data Management,Document Management ,Management of Process ,Reporting ,Investment Management | PPMP will provide a Microsoft Power Platform-based solution that promotes the visibility and control of real-time and accurate project, program and portfolio information by consolidating all data sources into a single source of truth. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-04 | 2024-08-29 |  |  | 415049 | [12 empty] | Procurement is in progress to identify and select a suitable platform and vendor. Contract award and design phase kick-off is expected in October 2024.
Q1 24-25 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Initiated |  |  | PMBoK | 2024-07-26 | 2025-03-21 |  |  | 0 | [12 empty] | Business case is being drafted
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3389 | Prison Industries Enhancement Phase 3 Project (PIE3) | Law and Justice | Management of Process | PIE3 is a key support for Prison Industries’ strategy to transition operations to standard systems. This aims to deliver value for money prison services by exploring ICT opportunities for cost recovery. | Closed - Completed | Cost Reduction (Financial), Increased Revenue (Financial), Social Improvement (Non Financial) | 2024-07-31 | Project Management Excellence | 2021-10-26 | 2022-03-05 |  | 2022-03-05 | 0 |  | 2022-09-05 | 2022-09-05 | 2024-06-30 | 2024-07-31 | 1959548 | 2932750 | Green | Green | Green | Green | Green | The project has completed delivery in line with approved scope, schedule and budget objectives. Project is now in closure.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Postponed |  | 2024-03-31 | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 |  | 150000 | 363395 |  |  |  |  | 0 | [6 empty] | The project's requirements have been gathered and an assessment of the most appropriate system will be complete by the end of December 2024. Following this, development will commence. An accurate costing model has not yet been developed, however initial cost estimates are appearing favourable. Once the delivery platform has been selected, all of the required components are in place to ensure the project can proceed quickly.
Q1 24-25 | Melbourne Water | MELB Water | 3274 | Portal New Services | Environment and Water | Communication,Content Management,Customer Relationship Management | Portal went live in 2019 as a minimal viable product (MVP). In line with the Strategy and Pricing Submission 2021 (Water Plan 5) a roadmap of key enhancements will be delivered to improve customers digital experience. | Closed - Completed | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2024-09-30 | PMBoK | 2021-07-01 | 2021-10-29 |  | 2021-12-22 | 0 |  | 2022-01-10 |  | 2023-06-30 | 2024-09-30 | 2975826 |  | Green | Green | Green | Green | Green | Minimum viable product has been delivered and a business decision has been made not to proceed with any further enhancements at this stage project is now closed.
Q1 24-25 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2025-02-28 |  | 0 | 0 | [11 empty] | The project is on track with procurement planning underway and only minor delays to schedule.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3527 | PeopleCentral Project - Payroll Integrations & Strategic Workforce Experience Portal | Government and Economy | Human Resources | Deliver new functionality in the SuccessFactors platform to improve capabilities in people management (succession and analytics), payroll processes and system authentication, enabling a better employee experience within WorkSafe. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-10-06 |  | 2022-10-10 | 0 |  | 2022-10-11 |  | 2023-06-30 | 2025-01-31 | 2400000 | 3862665 | Amber | Red | Red | Amber | Amber | Project is currently reporting Amber due to delay in the completion of testing. Schedule contingency will be utilised, and testing progress will continue to be closely monitored.
Q1 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2025-12-31 | 6428267 |  | Green | Green | Green | Green | Green | Build phase has commenced with the first iteration being delivered for review.
Q1 24-25 | Peninsula Health | PEN Health | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Initiated |  |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  |  | 340000 | [12 empty] | Initiation Stage activities commencing to plan.
Q1 24-25 | Peninsula Health | PEN Health | 3832 | Peninsula Health Project Lotus (People Hub) | Health | Human Resources | Project Lotus involves the deployment of the cloud-based SAP Success Factors, Human Resources Information System at Peninsula Health. This aims to improve employee experience, boost efficiency, and alleviate administrative burdens. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2023-07-10 | 2023-09-05 |  | 2023-09-05 | 73200 |  | 2023-11-20 |  | 2025-01-31 |  | 3193016 |  |  |  | Green | Green | Green | On track
Q1 24-25 | Peninsula Health | PEN Health | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 |  | 1222641 | 1423459 |  |  | Green | Green | Green | Progress project remains on schedule, however, timelines are very tight
Q1 24-25 | Peninsula Health | PEN Health | 3455 | Peninsula Health Digital Application Oncology/Haematology Management System | Health | Management of Process | Deploy a fit for purpose Oncology & Haematology management system to achieve contemporary efficient & effective chemotherapy prescribing & treatment scheduling. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2024-09-30 | PRINCE2 | 2022-04-05 | 2023-01-02 | 2022-07-01 | 2022-07-01 | 70000 | 95000 | 2023-02-17 |  | 2024-03-29 | 2024-09-30 | 1450000 | 1600000 | Green | Green | Green | Green | Green | Complete
Q1 24-25 | State Revenue Office | SRO | 3765 | Payroll tax Reform | Government and Economy | Development and Integration | This project implements system changes necessary to administer payroll tax changes, such as the temporary COVID surcharge, removing private school exemptions and the sliding scale deduction. These were introduced as part of the 2023 Victorian Budget | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-23 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-03 |  | 2025-06-30 |  | 4772200 | 4473774 | Green | Green | Green | Green | Green | The project is on track to meet benefits schedule and budget.
Q1 24-25 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 |  | 2025-09-30 |  | 3300000 |  |  |  |  | Green | Green | Project has made progress across all 3 workstreams in particular with the Forms Digitisation workstream.
Q1 24-25 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 |  | 1600000 | [5 empty] | Amber | The production go-live schedule was changed to have a single site move into production to determine system viability and to perform a project health check.
Q1 24-25 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2024-11-15 | 3450000 |  | Amber | Green | Green | Green | Amber | We are reporting an amber status for this period due to the current Project Manager's assignment concluding in December. As a result the integration of PES with Delegate, a requirement of the concierge setup, may be deferred until early 2025. The Capital team has confirmed that a new Project Manager will be appointed to ensure the successful delivery of this integration. It is important to note that this potential delay will not impact the project budget.
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 |  | 4930809 |  |  | Green | Green | Amber | Amber | Project resources and scope are still a core challenge. A number of mitigation strategies are being progressed which will see next quarter return to green if the revised project schedule is endorsed.
Q1 24-25 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. Stage 1: LIS planning and procurement Stage 2 (delivery): LIS implementation | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 | [5 empty] | Green | Progressing to schedule.
Q1 24-25 | Department of Health | DH | 3615 | OurService Extensions | Health | Forms Management,Tracking and Workflow | Deliver multiple enhancements to ServiceNow platform, including migration of additional new services and integration with other major corporate systems, that further improves the consistency and customer experience of service. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2022-10-03 | 2023-05-26 |  | 2023-05-26 | 302604 |  | 2023-05-26 |  | 2024-06-30 | 2025-06-30 | 2365565 | 2718629 | Green | Green | Amber | Amber | Green | Project is progressing to schedule and revised cost.
Q1 24-25 | Department of Education | DE | 3897 | Oracle Cloud Program Phase 2 | Education | Assets/Materials Management,Financial Management,Reporting | The project will deliver an integrated Oracle Cloud enterprise resource planning and analytics solution to uplift and modernise finance and procurement systems to deliver consistent financial services support across the Victorian Government. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2023-11-06 | 2023-11-10 |  | 2023-11-12 | 0 |  | 2023-11-13 |  | 2025-05-21 |  | 14120000 |  |  |  |  | Green | Green | The project reported a Green status and is tracking well against scope, budget and schedule.
Q1 24-25 | Yarra Valley Water | YV Water | 2821 | Operational Historian | Environment and Water | Data Management | Acquisition, storage, analysis, and presentation of large volumes of time series data – allowing it to be combined with data from other core systems for analysis and improved decision making. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2018-11-01 | 2019-08-30 | 2019-12-27 | 2019-12-27 | 240000 | 300000 | 2019-12-30 | 2020-01-01 | 2021-12-30 | 2025-03-31 | 4778000 | 8470080 | Green | Green | Green | Green | Green | Core project completed, remaining open for minor enhancements to be undertaken as part of original scope
Q1 24-25 | Department of Transport and Planning | DTP | 3743 | OneView Permits and Permits Portal Phase 2 | Transport and Vehicles | Business Intelligence,Collaboration ,Communication,Tracking and Workflow | Key objectives of this project is to enhance the Permits Portal to support the modernisation of business processes and reduce processing times and provide disruption information to motorists. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-09-18 | 2023-08-01 | 2023-09-18 | 0 |  | 2024-06-30 | 2023-09-18 | 2024-06-30 | 2024-12-31 | 4500000 | 5400000 | Green | Amber | Green | Green | Green | Overall project status is green. Testing and implementation planning activities are ongoing.
Q1 24-25 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2024-12-30 |  | 10000000 | 0 | [11 empty] | Project initiation activities are ongoing.
Q1 24-25 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-12-01 |  | 0 | [12 empty] | The procurement phase has been extended to realise a more robust outcome. Vendor confirmation is planned for quarter 2 2024-25, following approval of contract and funds.
Q1 24-25 | Southern Metropolitan Cemeteries Trust | SMCT | 3266 | Next Gen Business System Program | Health | Customer Relationship Management,Financial Management | The Next Gen Business System Program will replace existing legacy systems with modern CRM and ERP platforms to fully integrate business processes and data across the enterprise, customers, and partners. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-07-26 | 2022-02-28 | 2022-04-30 | 2022-04-30 | 0 | 1500000 | 2022-08-01 |  | 2023-11-24 | 2024-11-04 | 7700000 |  | Green | Red | Red | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 |  | 2026-06-22 |  | 4966804 | [5 empty] | Green | Procurement activities in progress for the Wireless Professional Services and replacement hardware. Networking firmware has been upgraded. Software for the firewall management has been upgraded to address end of life (EoL). Migration and consolidation of device monitoring upgrade complete. SoW in negotiation for phase 2.
Q1 24-25 | Melbourne Water | MELB Water | 3560 | Network Hardware Refresh 22/23 | Environment and Water | Security Management | Melbourne Water is ensuring continued investment in our IT network through ongoing refresh of IT Hardware as it approaches end of life rather than extending support, reducing risk of unplanned network outages. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2023-01-02 | 2023-03-06 | 2023-08-15 | 2023-08-15 | 0 |  | 2023-08-15 |  | 2024-04-04 | 2024-12-20 | 3158890 | 3735377 | Amber | Green | Amber | Green | Green | Vendor to provide trial compact switches. A detailed design and schedule provided by Vendor for the implementation of the Software as a Service (SAAS) offering. The design for log collection and connectivity to be presented to Security and Architects for endorsement. The replaced microwave link has been decommissioned and the hardware removed.
Q1 24-25 | Yarra Valley Water | YV Water | 2822 | Network Communications and IoT Device Management | Environment and Water | Assets/Materials Management | Uplift on existing IT systems to enable rollout of digital water meters, installations of new mechanical meters, and replacement of faulty water meters (both digital and mechanical) that have been commissioned. | Delivery | Cost Reduction (Financial) |  | PRINCE2 | 2019-05-01 | 2020-01-31 | 2020-10-14 | 2020-10-14 | 350000 | 1300000 | 2020-10-19 |  | 2022-06-30 | 2024-11-30 | 3715000 | 5197799 | Amber | Amber | Amber | Green | Green | Project on track post additional resourcing allocations and funding approval. Project nearing completion
Q1 24-25 | Melbourne Water | MELB Water | 3559 | Network Architecture Improvements SDWAN | Environment and Water | Security Management | Network Architecture improvement to SD WAN / Zero trust Model | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-08-26 | 2023-01-16 |  | 2023-01-25 | 0 |  | 2023-01-26 |  | 2023-10-10 | 2025-05-26 | 1189517 | 2895116 | Amber | Amber | Green | Green | Amber | Phase-1 migration of 48 sites to the SDWAN solution has been successfully completed. Final technical enhancements are currently being completed to ensure operational stability. Overall health is amber due to schedule delays related to completing the Pilot at a pumping station and resolving technical issues encountered during Phase-1 rollout.
Q1 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3722 | Mosaiq Migration to Cloud and Upgrade | Health | Systems Management | The project is being implemented in 2 phases: Phase I: Migration Mosaiq application from On premises infrastructure to Elekta Azure Cloud Infrastructure. Phase II: Post Migration application will be upgraded to the latest version of Mosaiq. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-22 | 2024-04-30 | 2024-04-30 | 0 | 20475 | 2024-05-01 |  | 2025-08-31 |  | 1720000 |  |  |  |  | Green | Green | -Project tracking in accordance to plan -Environments built and configured -Penetration testing successful -Network connections (express route and VPN) built and tested -Functional and integration testing completed successfully
Q1 24-25 | Department of Transport and Planning | DTP | 3768 | MOG 2023- Finance and Procurement System Stream | Transport and Vehicles | Collaboration ,Customer Relationship Management,Financial Management,Investment Management,Management of Process ,Organisational Management ,Tracking and Workflow | Purpose of this project is to make necessary changes to DTPs Finance and procurement system to facilitate the Machinery of Government changes announced in December 2022 | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  | 2023-11-30 | 0 |  | 2023-11-30 |  | 2024-09-30 | 2024-12-30 | 2315000 | 3850000 |  | Green | Green | Amber | Green | Overall status of the project is green. Project implementation activities are ongoing.
Q1 24-25 | Department of Transport and Planning | DTP | 3770 | MOG 2023- Core IT System Stream | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Purpose of this project is to make necessary changes in DTP's Core IT System to facilitate Machinery of Government changes announced in 2022 | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  | 2023-11-30 | 0 |  | 2023-11-30 |  | 2024-09-30 | 2024-12-30 | 4418000 |  |  | Amber | Amber | Amber | Green | Overall project status is green. Project implementation activities are ongoing.
Q1 24-25 | Department of Transport and Planning | DTP | 3769 | MOG 2023- Collaboration Tools | Transport and Vehicles | Collaboration ,Content Management,Data Management,Knowledge Discovery ,Knowledge Management ,Records Management | Purpose of this project is to make necessary changes in DTP Records Management System to facilitate Machinery of Government changes announced in 2022. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  | 2023-11-30 | 0 |  | 2023-11-30 |  | 2024-09-30 | 2024-12-30 | 6463000 | 7000000 |  | Green | Green | Amber | Green | Overall project status is green. Project implementation activities are ongoing.
Q1 24-25 | State Revenue Office | SRO | 3966 | Modernisation Platform Establishment and Inbound Correspondence Proof of Value | Government and Economy | Development and Integration | This initiative establishes the technical foundations for the State Revenue Office systems modernisation program. It also delivers a proof of value for an improved way of managing the scanning and processing of inbound correspondence documents. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-08-19 |  | 2024-08-19 | 0 |  | 2024-08-19 |  | 2025-06-30 | 2024-12-31 | 6352200 | [5 empty] | Amber | Overall good progress is made against project objectives. The project is tracking as amber because of some minor delays which are expected to be resolved by the next reporting period.
Q1 24-25 | Dental Health Services Victoria | DHSV | 2909 | Mobile Diagnostic Imaging | Health | Records Management | The objective of this project is to enable Public Oral Health providers to access diagnostic images acquired from School Dental Program in a timely manner, and at the point of care. | Delivery | Social Improvement (Non Financial) |  | PRINCE2 | 2019-06-28 | 2020-09-30 | 2021-11-30 | 2021-11-30 | 0 | 200000 | 2021-12-01 |  | 2023-02-28 | 2024-12-30 | 2972693 |  | Green | Green | Red | Amber | Amber | Project is progress to budget. The focus for the next reporting period is pre implementation activities.
Q1 24-25 | CenITex | CenITex | 3613 | Metro and regional Site refresh | Government and Economy | Assets/Materials Management | Consolidate and replace end of life networking hardware located at customer office locations including routers switches and wireless access points to maintain performance and availability of network service. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2022-12-16 | 2022-12-23 |  | 2022-12-23 | 0 |  | 2023-01-20 |  | 2023-06-30 | 2024-12-01 | 6598602 | 5756302 | Green | Green | Green | Green | Green | The project is progressing with final tasks pending.
Q1 24-25 | Department of Health | DH | 3599 | Mental health and wellbeing website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q1 24-25 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2026-06-30 | 40229527 | 64700000 |  |  | Green | Green | Green | Project is progressing to cost and schedule.
Q1 24-25 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 |  | 7818000 |  |  |  | Green | Green | Green | Project progressing as per plan and targets.
Q1 24-25 | South East Water | SE Water | 3920 | Meeting Room Technology Upgrade | Environment and Water | Assets/Materials Management | Upgrades to the technology across selected meeting rooms, training rooms and board room at SEW's head office in Frankston. Existing technology was installed in 2015 and is being updated to better meet the needs of the hybrid workplace. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-01-01 | 2024-02-09 |  | 2024-02-09 | 0 |  | 2024-02-12 |  | 2024-12-31 |  | 1024450 | [5 empty] | Green | All areas within scope have been fitted out and commissioned with new technology. Warranty items and remaining issues with acoustics in certain areas being resolved.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Government and Economy | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 |  |  | 947722 | [12 empty] | All activities on track
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2024-10-30 |  | 0 | 60000 | [11 empty] | Delays in recruitment and accessing key software provider resources limiting capacity to finalise updated Project Management Plan. Project Planning continues while scope is being confirmed.
Q1 24-25 | Yarra Valley Water | YV Water | 3947 | MAXIMO 2025 UPGRADE | Environment and Water | Data Management | To upgrade Maximo software version 7.6 to version 9 to ensure continued support, enhance operational efficiency and leverage additional functionalities | Initiated |  |  | Agile | 2024-01-01 | 2025-01-15 |  |  | 697090 | [12 empty] | On track
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 |  | 5158000 |  | Green | Green | Green | Green | Green | Project is on track
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3761 | Marine Search and Rescue Radio Replacement | Emergencies and Safety | Communication | The project will connect Marine Search and Rescue units to the Victorian Radio Network and provide 7 base radios, 32 mobile radios and 130 portable radios. | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2023-01-01 | 2023-01-10 |  | 2023-01-10 | 0 |  | 2023-03-01 | 2023-01-11 | 2024-12-01 | 2024-12-31 | 1377000 | 2141072 | Amber | Green | Amber | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Applications and Services (AS) business unit within the Digital Health branch of the Commissioning and System Improvement division. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 |  | 1412500 | 1317500 | Amber | Green | Green | Green | Amber | Project is amber pending resolution of procurement issues impacting schedule.
Q1 24-25 | Environment Protection Authority | EPA | 3861 | MAJ135 - CBD Office Relocation | Environment and Water | Development and Integration | The IT component of the EPA's CBD Office relocation project is focused on supporting the move and establishing IT hardware in the new building. | Closed - Completed | Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) | 2024-09-30 | Agile | 2024-01-01 | 2024-05-30 | 2024-02-20 | 2024-02-21 | 0 |  | 2024-02-21 |  | 2024-07-31 | 2024-09-30 | 1810000 |  |  |  |  | Green | Green | The relocation to EPA’s new office premises was completed on time and the IT scope was fully delivered. Project closure is in progress.
Q1 24-25 | Environment Protection Authority | EPA | 3781 | MAJ128 - Website and intranet refresh | Environment and Water | Collaboration ,Communication,Content Management | Improving EPA’s internal and external channels (website, intranet and reporting tools) to improve user experience and awareness | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Agile and Waterfall | 2023-05-11 | 2023-12-31 | 2023-08-15 | 2023-08-15 | 0 |  | 2023-08-16 |  | 2024-06-28 | 2025-03-31 | 2666000 |  |  | Amber | Green | Amber | Red | The project has been delayed. A project reset and replan is currently underway.
Q1 24-25 | Environment Protection Authority | EPA | 3776 | MAJ127 - Replacing Existing Document Generation Solution | Environment and Water | Document Management | The project will deliver a robust and cost-effective document generation and distribution solution, with availability of operational support based on Australian business hours followed by a quick response and resolution time. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2024-07-31 | Hybrid - Agile and Waterfall | 2023-05-23 | 2023-07-28 |  | 2023-07-31 | 0 |  | 2023-07-31 |  | 2024-05-31 | 2024-07-31 | 1080000 |  | Green | Green | Green | Amber | Green | Project closed
Q1 24-25 | Environment Protection Authority | EPA | 3775 | MAJ126 - Tasking and Coordination Digital Solution (Enhanced Incident Command) | Environment and Water | Human Capital / Workforce Management | Deliver a digital rostering solution with an enhanced Incident Command System (ICS) that consolidates all Incident Command into a single system and integrates directly into EPA HR system | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2023-06-02 | 2023-06-20 |  | 2023-06-20 | 0 |  | 2023-06-20 |  | 2024-05-17 | 2024-12-31 | 1535155 |  | Red | Amber | Amber | Green | Green | The project is progressing well against scheduled milestones. A training provider has commenced and several training sessions have been held.
Q1 24-25 | Environment Protection Authority | EPA | 3489 | MAJ101-Permissions Digital Build Improvement Program | Environment and Water | Business Intelligence,Development and Integration ,Document Management ,Management of Process ,Tracking and Workflow | Delivery of a suite of priority digital enhancements to Dynamics and Portal to realise efficiency improvements for internal and external stakeholders. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2024-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-10-13 |  | 2022-10-26 | 78363 |  | 2022-11-07 |  | 2023-12-31 | 2024-07-01 | 2732021 | 2562335 | Green | Green | Green | Green | Green | Following successful delivery of more than 400 requirements the project is being formally closed.
Q1 24-25 | Department of Jobs, Skills, Industry and Regions | DJSIR | 3833 | Machinery of Government (MOG) changes - IT component | Education | Management of Process | Machinery of Government shifted Training & Skills function to DJSIR in 2023. Major IT systems, applications, databases and data will be moved to a Cenitex managed multi-cloud environment. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2024-08-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-01 | 2023-08-07 |  | 2023-11-29 | 0 |  | 2023-11-29 |  | 2024-06-30 | 2024-08-31 | 1484048 | 1200000 |  |  | Green | Green | Green | Hypercare was successfully completed on 30 August 2024, marking the successful closure of the project.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3934 | Licensing CRM (Customer Relationship Management) FY25 | Government and Economy | Customer Relationship Management | Transition of the remaining 5 license journeys from the legacy mainframe. This completes the transition of License Management capability to the CRM, unifying business processes, centralising data, and enhancing both customer and employee experiences. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 4466242 | [5 empty] | Green | Overall status on track with no blockers.
Q1 24-25 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 |  | 1161000 | [5 empty] | Green | Initial vendor engagement completed. Internal planning commenced, awaiting confirm start date with vendor next quarter.
Q1 24-25 | CenITex | CenITex | 3452 | Legacy Hardware Refresh | Government and Economy | Assets/Materials Management | The project will refresh the core network infrastructure in the data centres, ensuring the infrastructure platform is supported and robust to meet the demands of Cenitex customers. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-11-15 | 2022-05-05 |  | 2022-05-05 | 0 |  | 2022-05-05 |  | 2023-06-30 | 2025-06-30 | 4049735 | 6069833 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q1 24-25 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 |  |  | 1772100 | [12 empty] | On track
Q1 24-25 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  |  |  |  | Green | Green | User acceptance and usability testing has commenced for the kindergarten attendance build. Procurement is in progress for the content management system and business rules engine.
Q1 24-25 | Melbourne Water | MELB Water | 3951 | IT Facilities End of Life Hardware Replacement | Environment and Water | Assets/Materials Management | Replacement of critical IT facilities hardware (Air conditioners Uninterrupted Power Supply batteries) that are coming out of warranty or service contracts and due to 24/7 use require replacement. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-12-05 | 2024-09-09 |  | 2024-09-09 | 0 |  | 2024-09-09 |  | 2025-03-31 |  | 1076437 | [5 empty] | Green | Business Case approved. Sourcing document approved and RFQ released to the suppliers & the tender closed, with the contract awarded and executed 12th September. Purchase Order for equipment was released to the vendor in Sept along with the kick off meeting with the project team.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3904 | Inventory Management System Project | Environment and Water | Business Intelligence | The project will deliver a modern, scalable, fit-for-purpose warehouse management system that will allow stock and inventory to be managed and tracked across all state and regional warehouses. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-01 | 2023-06-30 |  | 2023-12-21 | 101560 |  | 2023-12-21 |  | 2026-11-20 |  | 3259441 | [5 empty] | Green | The overall status and progress for the project is on track. Work is progressing as planned to meet the agreed deliverables.
Q1 24-25 | Melbourne Water | MELB Water | 3950 | Intranet Renewal | Environment and Water | Communication | Renew or replace current Melbourne Water Intranet, including full investigation of options and user impacts. Re-imagine employee access to internal information. | Initiated |  |  | PMBoK | 2024-08-26 | 2024-12-18 |  |  | 0 | [12 empty] | Business Case is being drafted
Q1 24-25 | Transport Accident Commission | TAC | 3789 | Intelligent Information Management | Transport and Vehicles | Systems Management | Implement a dynamic Information Asset Register solution to support TAC’s legislative obligations under the Victorian Protective Data Security Standards. To reduce risk of information security breaches regulatory action and reputational damage. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-04-20 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2024-06-30 | 2024-12-20 | 1198738 | 1436941 |  | Green | Green | Green | Green | Delivery continues despite some technical challenges which have now been resolved SIT testing completed and signed off, production testing underway including UAT. Delivering nearing completion in late November
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3658 | Integrated supervised contact and access solution | Community Services | Customer Relationship Management | Integrate existing case management and support systems (Contact & Access Transport System) for supervised contact and access to eliminate duplicate processes and better support planning and decision making for children in out of home care. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2022-10-13 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2025-06-30 | 1217500 | 2388184 | Green | Green | Green | Green | Green | Project is progressing to cost and schedule.
Q1 24-25 | Department of Education | DE | 3203 | Infrastructure Portfolio Management (IPM) | Education | Investment Management,Management of Process | The project is the implementation of a Software as a Service solution that meets the needs of the department & delivers new infrastructure management capability. The project will deliver procurement, project, program & portfolio level information. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-22 | 2021-10-31 | 2021-11-30 | 2021-12-01 | 111310 |  | 2021-12-01 |  | 2022-12-31 | 2024-10-31 | 6738690 | 17403799 | Amber | Red | Red | Amber | Amber | The project is resolving final defect fixes related to integration and stability issues. All key milestones related to the core system go-live have been completed and the project is tracking to be complete on schedule by October 2024.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3936 | Infrastructure and Service Transition. | Government and Economy | Systems Management | The project will facilitate the transition to WorkSafe’s new Managed Service Provider. This enhances IT infrastructure and business operations resulting in increased staff productivity and a reduction in ongoing vendor costs. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-04-23 | 2024-05-06 |  | 2024-06-11 | 0 |  | 2024-06-11 |  | 2024-12-23 |  | 5250000 | [5 empty] | Amber | The project is tracking Amber due to the Quality associated with IP transfer to the new Managed Service Provider (MSP) which may impact their ability to meet business support expectations increasing the Risk of business disruption. The project is closely monitoring this with technical subject matter experts engaged to fill any knowledge gaps and provide support to the new MSP. Transition to the new MSP occurred in late September. The project will reassess the risk throughout October with the aim to downgrade risk and improve project health by end October.
Q1 24-25 | Transport Accident Commission | TAC | 3929 | Infrastructure and Service Transition | Transport and Vehicles | Systems Management | The project will facilitate the transition to a new Managed Service Provider. This enhances IT infrastructure and business operations, resulting in increased staff productivity and a reduction in ongoing vendor costs. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-05-23 | 2024-05-23 |  | 2024-05-22 | 0 |  | 2024-05-23 |  | 2024-12-23 |  | 3500000 | [5 empty] | Amber | The project is tracking Amber, this reflects the Quality associated with IP transfer to the new Managed Service Provider (MSP), which may impact their ability to meet business support expectations, increasing the Risk of business disruption. The project is closely monitoring this with technical subject matter experts engaged to fill any knowledge gaps and provide support to the new MSP. Transition to the new MSP occurred in late September. The project will reassess the risk throughout October, with the aim to downgrade risk and improve project health by end October.
Q1 24-25 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 |  | 1859425 | [5 empty] | Red | The project status is RED as the overall program implementation is on-hold until internal position (Data Governance Lead) is filled. Data classification and change management activities have been continuing. Plan to return project to GREEN next quarter once key resources on-boarded and project resumes.
Q1 24-25 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 | 2025-06-01 | 1512000 |  | Green | Amber | Amber | Green | Green | The project is tracking well against scope, budget and schedule. Procurement strategy is underway, with expected commencement of selected vendor in quarter 2 2024-25.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3854 | Impact Assessment Strategic Project | Emergencies and Safety | Data Management | This project will deliver improvements to Impact Assessment processes and systems in Victoria, aiming to provide efficient, timely and appropriate support for communities impacted by an emergency. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2023-08-01 | 2024-01-31 |  | 2024-01-31 | 255242 |  | 2024-02-01 |  | 2025-06-30 |  | 6800000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Education | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 |  | 1205132 |  |  |  |  | Green | Green | Project has commenced and is currently on-track according to schedule.
Q1 24-25 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Initiated |  |  | PMBoK | 2024-07-26 | 2025-05-21 |  |  | 0 | [12 empty] | Business case is being drafted
Q1 24-25 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Postponed |  | 2024-03-29 | PRINCE2 | 2022-11-28 | 2023-06-02 | 2024-12-31 |  | 0 | [5 empty] | 0 | [6 empty] | The project is on hold pending approval from governance board to allocate resource and funds.
Q1 24-25 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 |  | 3463000 |  |  |  |  | Green | Amber | Project has identified risks with transition complexity for some corporate and clinical systems. PCG anticipates end delivery date of Dec 2025 or beyond and potential increase in costs. Work is being undertaken to determine the new delivery date and implementation costs.
Q1 24-25 | Victorian Institute of Forensic Medicine | VIFM | 3242 | ICT Infrastructure Migration to the Cloud | Law and Justice | Systems Management | The Cloud Migration project will transfer VIFM forensic services information from aging ICT infrastructure to the Cloud. The project improves the security, efficiency, and resilience of VIFM’s forensic information for Victoria’s justice system. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 | 2022-01-03 | 2022-01-03 | 0 | 585000 | 2022-01-03 |  | 2024-06-30 | 2025-06-30 | 2338000 | 3261000 | Green | Green | Green | Green | Green | The project has completed Phase 1 on schedule and budget. Phase 2 will be completed following the transition of the VIFM Case Management System to a new cloud-based solution, which is funded under the project’s recurrent budget.
Q1 24-25 | CenITex | CenITex | 3213 | Hybrid Cloud Program: Mediation Layer - Stage 1 | Government and Economy | Data Management | Cenitex will work closely with DPC to establish a program that will focus on enabling migration from the existing on-premise data centers to a HICT multi-cloud elastic environment to provide Government with secure and resilient access to the services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-05-25 |  | 2021-06-11 | 0 |  | 2021-06-22 |  | 2022-06-30 | 2024-10-31 | 3650000 | 5900000 | Green | Green | Green | Green | Green | Project closure in progress.
Q1 24-25 | Hume Rural Health Alliance | HRHA | 3550 | Hume Regional Patient Administration System (PAS) | Health | Financial Management,Records Management ,Tracking and Workflow | This project will delivery a regional patient administration system to support patient administration workflows and reporting. The project addresses critical operational and clinical risks to support patient care | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-04-28 |  | 2023-05-01 | 0 | 300000 | 2023-05-01 |  | 2024-12-31 |  | 7700000 | 8200000 | Green | Green | Green | Green | Green | Project is running to plan. Focus on go-live planning
Q1 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 |  | 2643965 | 2888965 |  |  | Green | Green | Amber | Project on track, but carrying risks to schedule and budget
Q1 24-25 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 3826 | Human Resources Information Management | Health | Human Capital / Workforce Management | The project will replace an end-of-life digital system that manages employee records, training and performance, allowing the hospital to efficiently manage its workforce. | Delivery | Workforce Satisfaction (Non Financial) |  | Waterfall | 2022-01-03 | 2022-10-14 |  | 2022-10-14 | 0 |  | 2023-01-02 |  | 2024-08-30 | 2024-10-25 | 3830000 | 4598075 |  | Green | Green | Green | Green | Successful go live of Performance and Training; transition and closure underway
Q1 24-25 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 |  | 2580000 |  |  |  | Green | Green | Green | The project has completed workshops with the vendor that covered the necessary functionality required, integrations and data delivery.
Q1 24-25 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 | 2025-06-30 | 7490000 | 8330412 | Amber | Amber | Amber | Amber | Green | Overall project status is green. Project implementation activities are ongoing.
Q1 24-25 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 |  |  | 900000 | [12 empty] | The Expression of Interest is nearing conclusion with the supplier evaluations completed. Minor delay resulted from departure of the Procurement Manager. A new Procurement Manager has been assigned and the Recommendation Report has now been drafted and is being finalised for discussion at the next Project Control Group.
Q1 24-25 | Fire Rescue Victoria | FRV | 3325 | HRIS | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2025-05-30 | 22392000 |  | Amber | Amber | Amber | Amber | Amber | Project is currently reporting amber due to delays in confirming scope with key stakeholders. FRV is working with stakeholders to resolve this issue.
Q1 24-25 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 | 2023-12-13 | 0 |  | 2023-12-13 |  | 2024-11-19 | 2024-12-20 | 2722712 | 2423557 |  | Green | Green | Green | Green | Progressed with Functional Testing​. Completed data preparation for Parallel Pay run Testing (PPT). Commenced integrations build with integration delivery partner, with cloud platform access granted end of September. Commenced communication plans​ and held first change champion session. A change request is required to realign schedule dates to a new integration item scope increase, will revert to green once approved.
Q1 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Postponed | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2024-09-19 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 |  | 2025-12-20 |  | 13500000 |  |  |  | Green | Green | Amber | Bendigo initial implementation completed and Implementation Planning Study for remaining project phases are complete. Remaining project phases have been paused to evaluate funding options to proceed.
Q1 24-25 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  |  |  | Green | Green | Green | Recruitment and Professional Development Reviews (PDR) modules successfully implemented. Phase 2 planning underway.
Q1 24-25 | Department of Transport and Planning | DTP | 3584 | Heavy Vehicle - Structural Assessment and Permit System (HV-SAPS) | Transport and Vehicles | Customer Initiated Assistance,Management of Process ,Tracking and Workflow | The objective of this project is to automate assessment part of the process of issuing permits for Class 1 vehicles to the heavy vehicle industry. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-11 | 2023-03-31 | 2023-12-18 | 2023-12-18 | 0 |  | 2023-12-18 |  | 2024-09-20 | 2025-10-25 | 6297993 |  |  | Green | Green | Green | Amber | Overall project status is amber due to schedule issues. Project team is working with stakeholders to mitigate the issue.
Q1 24-25 | HealthShare Victoria | HealthShare | 3835 | Healthshare Victoria Long Term Warehouse Management System Solution | Health | Supply Chain Management | The implementation of a scalable Warehouse Management System to support Healthshare Victoria's current & future growth plans, enabling a safer, effective and efficient distribution centre operations | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-12-05 | 2023-09-05 |  | 2023-09-06 | 0 |  | 2023-09-07 |  | 2025-01-31 |  | 6218693 |  |  |  | Amber | Amber | Amber | Overall project status is Amber since 30-Apr-24 and is trending Red due to issues with interface development and end-to-end gaps in the designed solution. These issues are being actively managed by HSV.
Q1 24-25 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2025-07-31 | 2715200 |  |  |  |  | Green | Amber | Project is amber pending resolution of technical issues impacting schedule.
Q1 24-25 | Ambulance Victoria | AVS | 3544 | Health Safety & Claims Management System (HSCS) | Health | Human Capital / Workforce Management | The project will improve HSCS to better identify and manage safety incidents, enhance OHS practices, and improve WorkCover claims management, supporting injured staff returning to work. This update will increase the health and safety of our people. | Closed - Completed | Compliance (Non Financial) | 2024-08-12 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 | 2024-04-30 | 2024-04-30 | 0 | 583785 | 2024-05-01 |  | 2024-07-31 | 2024-08-12 | 695000 |  |  |  |  | Green | Green | Project reached completion within schedule and under budget.
Q1 24-25 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2025-06-30 | 0 | 26026574 | Amber | Green | Amber | Amber | Amber | Project is amber pending resolution of technical issues impacting schedule. These issues are progressively being worked through. Change management activities are also progressing to support a health service go-live.
Q1 24-25 | Greyhound Racing Victoria | GRV | 3887 | Greyhound Whole of Life Tracking (GWOLT) | Business and Industry | Analyses and Statistics ,Business Intelligence,Customer Relationship Management,Management of Process | Digital Whole of Life Greyhound Tracking (DGT) involves the digitised data capture storage and retrieval to automate processes for tracking and recording the location and health of Victorian greyhounds throughout stages of their lives. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-08 | 2025-01-31 |  |  | 0 | [12 empty] | The project is focused on the analysis and design of the future state technology requirements and integration with Greyhound Racing Victoria's existing technology landscape to ensure a best fit solution.
Q1 24-25 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2024-12-31 |  | 0 | [12 empty] | Procurement approach and updated business case have been endorsed. Grampians Health has progressed to exploring a shared EMR program with another Victorian health service. Program timelines remain on track with delivery expected to commence in Q3.
Q1 24-25 | Department of Government Services | DGS | 3682 | Get a birth certificate proof of concept | Community Services | Customer Relationship Management | Develop a proof-of-concept pilot for delivering front-end Births, Deaths and Marriages services as a function of Service Victoria. | Closed - Completed | Customer Satisfaction (Non Financial) | 2024-09-30 | Hybrid | 2022-05-03 | 2022-05-03 |  | 2022-05-03 | 0 |  | 2023-07-01 |  | 2024-12-31 | 2024-09-30 | 2400000 |  | Green | Green | Green | Green | Green | Governance approvals for the closure of this project in Q1 2024–25 have been obtained. The project has been completed and officially closed.
Q1 24-25 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  |  |  |  | Amber | Green | Project continues to deliver foundational activities to uplift spatial data NOTE: Reported delivery costs reflect the current phase of the project. Each phase will provide further clarity on cost.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3685 | FY 2023-24 DEECA Cyber Security Program | Environment and Water | Security Management | FY 20233-24 Cyber Security program will deliver a set of controls processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2023-07-03 | 2023-11-30 | 2023-11-09 | 2023-11-09 | 388000 | 254084 | 2023-11-10 |  | 2024-06-30 | 2024-09-05 | 1508000 | 1641916 |  | Green | Green | Amber | Amber | The project status is AMBER due to solution implementation issues that impacted scope and schedule. Issues have been resolved and the project team is working through solution deployment activities. The end date will be revised upon governance approval.
Q1 24-25 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 |  | 543000000 |  |  | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q1 24-25 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2025-06-30 | 16689890 | 18418852 | Amber | Amber | Amber | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | Design and implement an enterprise Fire and Rescue Services Portal. | Postponed | Compliance (Non Financial) | 2024-03-31 | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2025-06-30 | 2109000 |  | Green | Amber | Amber | Amber | Amber | Delivery is currently on hold due to reprioritisation of IT resources for the cyber incident recovery. The project is expected to recommence in late 2024-25. The delivery end date will re-baselined after recommencement.
Q1 24-25 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Red | The request for tender has been released to a restricted set of bidders later than originally planned. The schedule will be re-baselined by December 2024, upon agreement with the preferred implementation partner.
Q1 24-25 | Melbourne Water | MELB Water | 3734 | Finance System Cloud Transition | Environment and Water | Financial Management | Due to a vendor decision to move all on-premise customers to SaaS by 2024 this project is required to upgrade Melbourne Waters finance system and move to the cloud. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-07-03 | 2024-01-24 | 2024-05-02 | 2024-05-02 | 0 |  | 2024-05-02 |  | 2024-12-17 |  | 1811601 |  |  |  |  | Green | Amber | RFP for Cloud work was delayed due to security review requirements as a result the project won't go live in November as integration work will not be completed on time. Proposed new Go-Live date of April 2025 as this aligns to vendor support and Business change windows to be tabled to the PLT on 01 October. A change request will be submitted.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3577 | Expanding Victoria's Waste Data Systems | Environment and Water | Data Management | The project will deliver new Victorian Circular Economy metrics and expand Victoria’s Waste Data System for the Victorian economy, ensuring reliable, useful and timely data. | Delivery | Compliance (Non Financial) |  | Governance by Sustainability Fund reporting and review | 2020-10-06 | 2021-07-01 |  | 2021-07-01 | 4668000 | 0 | 2021-07-01 |  | 2024-06-30 | 2025-06-30 | 2438000 | 7106000 | Amber | Amber | Amber | Amber | Amber | The project is amber due to delay in data migration. Timelines will be updated once plan has been reviewed and dates confirmed.
Q1 24-25 | V/Line Corporation | V/Line | 3464 | eTicketing | Transport and Vehicles | Customer Preferences,Management of Process | The eTicketing project will implement a system to generate eTicket via electronic means such as email, mobile, improving customer experience by making V/Line long-distance and coach tickets accessible to customers in their preferred format. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-01-27 | 2023-06-30 | 2023-06-30 | 150000 | 216084 | 2023-07-03 |  | 2024-03-29 | 2024-10-25 | 2024792 |  | Amber | Amber | Amber | Amber | Green | The project is on-track with eTicketing platform gone live on 18th September 2024, following completion of end user training and communications. Project closure activities commenced during the reporting period and target to complete next quarter.
Q1 24-25 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 |  | 9510000 | 11019816 |  | Green | Green | Green | Green | Project remains on track to implement stage 1 to PCG expectations.
Q1 24-25 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Amber | Amber | Red | Red | Red | The project is rated 'red' as it is not tracking for completion by the current delivery end date of September 2025. The project schedule will be re-baselined after the Request for Proposal process. Key risks relating to schedule and budget have been identified and are being actively managed by the project team.
Q1 24-25 | CenITex | CenITex | 3596 | Enterprise platforms renewal program | Government and Economy | Customer Relationship Management | Upgrade existing Dynamics 365 platform and implement a system that integrates & meets stakeholder requirements for Customer Engagement Project Services and Finance. Also, mitigate support issues due to end of life of the current platform. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-01-04 | 2023-01-12 |  | 2023-01-12 | 0 |  | 2023-02-03 |  | 2024-06-28 | 2025-03-28 | 1652000 | 1702679 | Green | Green | Amber | Green | Green | Project is tracking to plan.
Q1 24-25 | Suburban Rail Loop Authority | SRLA | 3604 | Enterprise Data and Analytics Platform (eDAR) | Transport and Vehicles | Analyses and Statistics ,Data Management,Reporting ,Visualisation | Delivery of a Data, Analytics and Reporting Platform, integration of core transactional systems, creation of required data models and provision of reporting in a streamlined and efficient manner. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2024-09-27 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-02 | 2023-06-30 | 2023-07-31 | 2023-07-31 | 0 | 506211 | 2023-08-01 |  | 2024-10-31 | 2024-09-27 | 4008009 | 2641717 | Green | Green | Amber | Green | Green | All agreed project deliverables completed and project closed
Q1 24-25 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 |  | 6640340 |  |  | Green | Amber | Amber | Amber | Reporting Amber as it is likely that both the schedule and budget will need to be revised up. 30% of the schedule delivery timeframe confirmed, remaining being baselined
Q1 24-25 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Initiated |  |  | PRINCE2 | 2024-09-30 | 2025-02-06 |  |  | 0 | [12 empty] | Business Case is being drafted.
Q1 24-25 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Agile | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 |  | 2750000 | [5 empty] | Green | Hardware procurement completed; roll-out planning will commence in Q2 with hardware rollout starting in Feb 2025.
Q1 24-25 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 |  | 10148335 | 10592143 | Green | Green | Green | Green | Green | The Enable Program continues to run to the technical go live plan of both active projects with SuccessFactors already live. Time constraints continue to need active project management; however the Enable Program remains overall green as the People Journey and Rostering Project will be fully delivered by the approved end date of October 2025.
Q1 24-25 | Alfred Health | ALFRED | 3571 | EMR Oncology Implementation Project | Health | Records Management | Digitalisation of scheduling and transition of all documentation relating to patient’s treatment, including chemotherapy prescribing and administration, to be electronic within the EMR, improving patient safety and transparency of treatment records. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-04-01 | 2022-12-31 |  | 2022-12-31 | 649302 |  | 2023-01-01 |  | 2025-03-31 | 2024-11-30 | 5031638 |  | Green | Green | Green | Green | Green | Completion In Progress – transitioning to ongoing maintenance
Q1 24-25 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Initiated |  |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 |  | 200000 | 2675777 | [11 empty] | Site IPS workshops were completed for five of the six sites. Project staff are finalising workflow mapping and will complete future state mapping in November. The bossnet consolidation assumptions validation workshop is scheduled for November. We are currently recruiting a change manager. Overall project is Green.
Q1 24-25 | Triple Zero Victoria | TZV | 3700 | Emergency Sector Integration Platform | Emergencies and Safety | Systems Management | Provide a new single, vendor agnostic integration platform to interface into multiple 000VIC data sources that provides reliability and meet current and future anticipated requirements.Integrate CAD to current ESO systems. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2021-08-09 | 2021-12-28 | 2024-02-28 | 2024-02-29 | 570406 | 1400264 | 2024-02-29 |  | 2024-12-31 |  | 5070736 |  |  |  | Amber | Red | Red | The operational readiness of the Emergency Sector Integration Platform is expected by December 2024. The project schedule is at risk due to a delay in architecture review and acceptance, access to technical subject matter experts and resource constraints as a result of unplanned leave. A detailed schedule is being developed to identify the critical path timeline and ensure the platform is handed over to DJCS in 2024-25.
Q1 24-25 | Hume Rural Health Alliance | HRHA | 3632 | Emergency Department Information System (EDIS) Upgrade | Health | Records Management ,Tracking and Workflow | Upgrade of the Albury Wodonga Health emergency department patient management systems which are end of life. | Closed - Completed | Compliance (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) | 2024-04-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-01 | 2023-05-15 |  | 2023-05-16 | 123629 |  | 2023-05-16 |  | 2024-12-01 | 2024-07-31 | 1501292 |  | Green | Green | Green | Green | Green | The project has reached its finalisation stage with the Executive Sponsor confirming its closure. The completion of EDIS at the Albury campus has been achieved.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3668 | EMD (Emergency Management Day) PHASE 2 | Law and Justice | Development and Integration | This project supports management of EMD data for remanded prisoners to avoid unlawful detention or release and reduce legal risk. The objective is to provide a system for SCWA to manage sentences prisoner discharges and documentation for CV. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial) |  | Agile | 2022-05-02 | 2023-03-31 |  | 2023-06-16 | 0 |  | 2023-03-31 | 2023-06-17 | 2024-06-30 | 2025-06-30 | 1466100 | 1362532 | Amber | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule. A schedule extension to June 2025 has been approved to accommodate additional development and multiple production releases.
Q1 24-25 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 3817 | Electronic Referrals | Health | Communication,Customer Relationship Management,Document Management | The eReferral project will implement digital referral processes delivering improved efficiency, more effective prioritisation of urgent referrals, to provide shorter turnaround times for patients and improved provider communication. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Waterfall | 2022-06-01 | 2022-10-31 |  | 2022-11-10 | 0 |  | 2023-07-03 |  | 2024-12-31 |  | 1240000 |  |  | Amber | Amber | Amber | Amber | Procurement activities almost complete. Implementation of Referral Management System commencing.
Q1 24-25 | Dental Health Services Victoria | DHSV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2024-12-20 | 9490000 |  | Green | Green | Red | Amber | Amber | The project is progressing to budget and scope. The project commenced end user training while resolving minor technical issues. The focus for the next reporting period will be pre-implementation activities.
Q1 24-25 | Monash Health | Monash H | 3912 | Electronic Medical Record (EMR) - Maternity | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-15 | 2024-10-31 |  |  | 0 | [12 empty] | The commercial arrangements with the vendor are now finalised, and resource planning is underway.
Q1 24-25 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-03-31 | 8559000 | 8559000 | Amber | Amber | Amber | Green | Green | The project status is ‘Green’. The project is expected to deliver on agreed outcomes and remains on track for completion by 31 March 2025.
Q1 24-25 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Postponed |  | 2023-08-09 | PMBoK | 2021-10-08 | 2022-09-22 | 2025-04-30 |  | 0 | [5 empty] | 0 | [6 empty] | Due to dependencies on a number of projects being successfully implemented during FY23/24 including Document Management System Upgrade and Digital Asset Storage Remediation Program, a decision has been made to pause the ECM project, with an aim to recommence delivery in 24/25.
Q1 24-25 | Melbourne Water | MELB Water | 3708 | Document Management System Upgrade 2023 | Environment and Water | Records Management | Upgrade on-prem document management system and refresh 'as-is' integrations with security improvements so that they work effectively with the new version. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-07-01 | 2023-07-18 |  | 2023-07-18 | 0 |  | 2023-07-18 |  | 2024-03-12 | 2024-11-29 | 1296183 | 1487171 | Green | Green | Green | Green | Red | The project is reported a red status due to a change request is required to include additional scopes of decommissioning the old extranet and upgrading laptop software. The project will move back on track upon governance approval of the additional scope
Q1 24-25 | Yarra Valley Water | YV Water | 3895 | Distribution Management System Release 3.2 | Environment and Water | Visualisation | DMS offers staff a single view of asset networks, including performance data, customer service levels, and contractor interactions. This release adds major updates like shut-off blocks, repeat cust. impact alerts, and DMA zone displays, enhancing cus | Closed - Completed | Efficiency/Productivity (Non Financial) | 2024-07-31 | PMBoK | 2023-07-01 | 2024-01-24 |  | 2024-01-24 | 276423 |  | 2024-02-01 |  | 2024-07-31 |  | 1105691 |  |  |  |  | Green | Green | Project completed
Q1 24-25 | Alfred Health | ALFRED | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  |  | 148217 | [12 empty] | Project initiation on track.
Q1 24-25 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The digital marketplace is meeting agreed timelines for releasing functionality into the production version of Digital marketplace which aligns with the expected benefit delivery throughout the 24/25FY
Q1 24-25 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end-to-end business processes across meter management, billing and alerts & alarms, enabling customer data linkage for meter monitoring, and improving efficiency in water usage monitoring and leakage detection | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 |  | 2020-02-28 | 2025-04-30 | 5123000 | 23100000 | Green | Green | Amber | Green | Green | Business scope and requirements are agreed. Delivery in on track for an October technical readiness. UAT and training to occur post October with go live planned for February. Budget is incremental to reflect a phased delivery and rollout.
Q1 24-25 | Department of Premier and Cabinet | DPC | 3619 | Digital Records & Information Management Shared Services (DRIMSS) | Government and Economy | Content Management,Records Management ,Systems Management,Document Management | The project will implement an improved records and information management system to automate the records and information management process and comply with public records management requirements for the Department | Delivery | Compliance (Non Financial), Cost Reduction (Financial) |  | Agile | 2020-11-15 | 2021-06-25 |  | 2022-09-15 | 0 |  | 2022-12-05 |  | 2024-05-10 | 2024-10-31 | 2099521 |  | Green | Green | Green | Green | Amber | While significant progress has been made this quarter with the migration of all physical records, ratification of an inaugural Information Architecture by the DGS Architecture Review Board and infrastructure finalisation some delays have been incurred. These have been due to issues of recruitment and retention of IT specalists in the team resulting in a delay in business readiness activities and a revision in the migration strategy following detailed analysis. The project team is adapting the project plan to minimise the impact to project timelines and cost which will be submitted to the PCB and reported in the next quarter.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2026-06-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 |  | 19500000 |  | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q1 24-25 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 |  | 6678000 | [5 empty] | Green | Software Release 1.0 in production, in progress for Release 2
Q1 24-25 | Victoria Legal Aid | VLA | 2852 | Digital Legal Aid Program | Law and Justice | Management of Process | VLA will implement a client and case management system to improve client services and access to justice. Integrated management of data across VLA channels will be enabled, allowing for more efficient and consistent treatment and contact occasions. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-02-19 |  | 2019-02-20 | 0 |  | 2019-02-22 | 2022-01-01 | 2021-07-30 | 2024-10-18 | 14500000 | 22350000 | Amber | Amber | Amber | Green | Amber | Victoria Legal Aid (VLA) continues the rollout of its case management system. The rollout had previously been delayed to address issues with another system which is a dependency for this program of work. VLA anticipates that the rollout will be complete by 18 October 2024 (a fortnight later than previously reported, due to scheduling commitments). The Planned Delivery Cost of $14.500m reflects the cost of Stage 1 of this project. The Revised Delivery Cost has been updated to include all 3 stages of the project scope, totalling $22.350m.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Government and Economy | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-01-30 | 4316783 | 4301844 | Amber | Green | Green | Green | Green | Project is on track overall.
Q1 24-25 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-01-30 | 4316783 |  | Amber | Green | Green | Green | Green | Project is on track overall.
Q1 24-25 | Melbourne Water | MELB Water | 3180 | Digital Education and Engagement Services | Environment and Water | Communication | Melbourne Water has a Water Act obligation through the Statement of Obligations to educate schools about Water Literacy and our range of services. This 3 year program will focus on encouraging water literacy across the school community. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-25 | 2021-07-01 | 2021-12-02 | 2021-12-20 | 0 |  | 2021-12-20 |  | 2024-05-30 | 2024-11-29 | 1804843 |  | Green | Green | Green | Amber | Amber | Showcase completed. Focus was intro screen loader how to screen and basemap enhancements - Optimisation work in progress. Procurement drafting a contract variation based on revised deliverables. Amber status due to procurement delays a change request is pending to revert to green.
Q1 24-25 | Department of Health | DH | 3793 | Departmental Data and Reporting Platform Uplift | Health | Data Management | Catalogue and profile all the reporting solutions in two reporting environments HRE and CRT to identify reporting solutions that can be decommissioned or migrated to more suitable, modern environments, thereby reducing ongoing costs. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-25 |  | 2023-09-25 | 101610 |  | 2023-09-25 |  | 2024-12-31 |  | 1398390 | 1448390 |  | Green | Green | Green | Green | Project progressing to cost and schedule.
Q1 24-25 | Monash Health | Monash H | 3911 | Delphi - Oracle Cloud Fusion | Health | Financial Management | The project will implement Oracle software as a service to uplift management of finance, procurement, enterprise performance, project management, supply chain, and warehouse, enabling more efficient and effective business processes for Monash Health. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-08-07 | 2024-09-13 |  | 2024-09-13 | 50000 |  | 2024-09-16 |  | 2025-12-26 |  | 17631000 | [5 empty] | Green | The project has kicked off and planning is underway.
Q1 24-25 | CenITex | CenITex | 3212 | DC Exit, Discovery, Re-Architecture and Migration - Stage 1 | Government and Economy | Data Management | To delivery data centre discovery for all Government Shared Platform clients. In addition to the discovery also design a new landing platform and plan for migration of the services. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2024-08-16 | PRINCE2 | 2021-03-29 | 2021-04-20 |  | 2021-05-06 | 0 |  | 2021-06-10 |  | 2022-06-30 | 2024-08-16 | 5600000 | 5637863 | Green | Green | Green | Green | Green | Project has closed.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3047 | Data & Analytics Hub | Government and Economy | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of cloud technology platforms to uplift Enterprise data management capabilities including a new data warehouse, data lake and advanced analytics environment, reducing manual processes and enhancing evidence-based decision making. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 0 |  | 2020-05-01 |  | 2021-12-31 | 2024-11-29 | 1169000 | 32476637 | Amber | Amber | Amber | Green | Green | Initial program costs were to establish the business unit and develop the Business Case. Current total cost encompasses the original Business Case and the latest FY24 Business Case. The program continues to develop WorkSafe's platform and capability delivering Analytics Guided Payments Product and finalising the foundational technology. Overall health remains green and on track to deliver to schedule and within contingency tolerance.
Q1 24-25 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Initiated |  |  | PMBoK | 2024-07-26 | 2025-02-20 |  |  | 0 | [12 empty] | Business case is being drafted
Q1 24-25 | South East Water | SE Water | 3930 | Cyber & Data Security Uplift | Environment and Water | Security Management | Uplift in SEW's Cyber & Data Security through the implementation and enhancement of key security and governance controls. The project will enhance platform performance to improve data security and minimise risks for the organisation. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Agile | 2023-12-01 | 2024-06-30 |  | 2024-06-30 | 68900 |  | 2024-07-01 |  | 2025-04-30 |  | 1881100 | [5 empty] | Amber | Project initiated and vendor commenced. Initial project planning conducted with first deliverable in design. Project AMBER due to change of key personnel and clarification on priority of key deliverables.
Q1 24-25 | Department of Transport and Planning | DTP | 3772 | Customer Facing Transport Website | Transport and Vehicles | Communication,Content Management,Data Management,Document Management ,Search | Objective of this project is to develop a brand new platform to transfer all non-Registration and Licencing content and experiences to into a new customer facing transport website. | Closed - Completed | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) | 2024-09-23 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-01 | 2023-09-28 |  | 2023-09-28 | 0 |  | 2023-09-28 | 2023-09-28 | 2024-08-30 | 2024-08-31 | 5133448 | 5274608 | Amber | Red | Amber | Amber | Green | Project Completed.
Q1 24-25 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2024-12-31 | 4565000 |  |  |  | Green | Amber | Amber | The project reported amber due to technical development and integration into various health services. Good uptake from the services with backlog of 6 months and interest in current and future modules across Victoria. Deployed Module 1 in one service (Peninsula) two more in deployment Deployed Module 4 at Northern Health two more sites in deployment Built pilot for Module 2 - Scheduled to go live in Q4 In deployment one service in module 5 (Mercy)
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3798 | CRIS-CP integration to Court Services Victoria - Case Management System | Community Services | Customer Relationship Management | Deliver system integration for CRIS-CP and Court Services Victoria's Case Management System, eliminating manual data entry, providing more timely information to case management workers. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2023-03-02 | 0 |  | 2023-04-03 |  | 2025-06-30 |  | 2000376 | 1287463 |  | Green | Green | Green | Green | Project is progressing to cost and schedule.
Q1 24-25 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2025-06-30 | 89200000 | 126956000 | Amber | Red | Red | Red | Red | The project is red due to the technical design of the system for managing criminal cases which has impacted the delivery schedule. The revised completion date is for the delivery of Criminal release. The project has delivered a system capability to manage Civil and Child Protection cases as well as the eDocument capability for court users to file documents electronically pay online and receive automatic notifications.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3876 | Corrections Victoria Intervention Management System (CVIMS) Alcohol and Other Drugs Criminogenic (AOD-C) - Phase 2 | Law and Justice | Development and Integration | To provide enhanced CVIMS functionality to manage and report on AOD-C integrated services delivered at both public and private prisons and integrate CVIMS with CV source systems to improve prison order data integrity. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2022-04-28 | 2023-09-29 |  | 2023-09-29 | 200000 |  | 2024-04-17 |  | 2024-12-31 |  | 892400 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3582 | Core Infrastructure Refresh - Package 1 & 3 | Health | Assets/Materials Management,Systems Management | The Core Infrastructure refresh is a program of works to Refresh Operational Compute & Storage, Refresh, Backup Infrastructure and On-premise Research Compute Infrastructure. It is split into 4 packages to be delivered in a phased approach. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-10-17 | 2023-07-31 | 2023-03-29 | 2023-03-29 | 0 | 40938 | 2023-03-30 |  | 2024-12-31 |  | 1257227 | 1216288 |  | Green | Green | Green | Green | -Migration of Virtual Machines & Storage to new Storage and Compute platform 95% complete. -Application storage re-architecture testing commend. -Ongoing Monitoring and Performance improvements. -Legacy infrastructure decommissioning commenced.
Q1 24-25 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Initiated |  |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-02-28 |  | 415771 | [12 empty] | Business case approved and the project has commenced the procurement phase. In order to maintain procurement integrity, the project will remain in Initiation until the procurement process is complete.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3935 | Continuous Improvement CRM (Customer Relationship Management) | Government and Economy | Customer Relationship Management | CRM Continuous Improvement delivers ongoing enhancements to the CRM. These system enhancements deliver increased efficiencies, streamline processes, and improve the user experience for both WorkSafe employees (Advisors, Inspectors) and clients. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 4840718 | [5 empty] | Green | Overall status on track with no blockers.
Q1 24-25 | Transport Accident Commission | TAC | 3927 | Continuous Delivery 25 | Transport and Vehicles | Systems Management | The Continuous Delivery project provides a robust, scalable and mature mechanism to deliver high business value changes to TAC Claims systems every month. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 3110724 | [5 empty] | Green | On Track.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Government and Economy | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers and the Victorian community | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 |  | 2023-12-11 |  | 2025-12-31 |  | 7321441 | 4707785 |  | Green | Green | Green | Green | The project is tracking well against scope and schedule.
Q1 24-25 | Victorian Gambling and Casino Control Commission | VGCCC | 3918 | Compass – Liquor and Gambling Information System (LaGIS) replacement project | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy compliance management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-08-30 |  | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-06-06 |  | 1650000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule. Initiation completed and delivery commenced on 2 September 2024.
Q1 24-25 | Victorian Gambling and Casino Control Commission | VGCCC | 3883 | Compass - Gambling License System (GLS) replacement project - Release 1 | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-09-06 | 2024-08-30 | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-08-01 |  | 1500000 | [5 empty] | Green | The project is on track, initiation has been completed and the delivery phase has commenced. Note: The project has been renamed "Compass - Gambling License System (GLS) replacement project - Release 1" from "Compass" to better reflect the intended delivery outcomes.
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 |  | 14429000 |  | Green | Green | Green | Green | Green | Project progressing to cost and schedule.
Q1 24-25 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-11-01 |  | 0 | [12 empty] | The program has obtained approval for the business case to implement the Human Capital Management platform across the three departments. The project is now in the process of recruiting key personnel and securing a systems integrator partner to initiate the delivery phase.
Q1 24-25 | State Revenue Office | SRO | 3969 | Commercial and Industrial Property Tax | Government and Economy | Development and Integration | In 2023 the Government announced a transition away from land transfer duty for commercial and industrial properties, replacing it with a more efficient property tax. This project implements the initial system changes necessary to administer the tax. | Delivery | Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-23 | 2024-05-23 |  | 2024-05-23 | 0 |  | 2024-05-23 |  | 2024-12-31 |  | 1649800 | [5 empty] | Green | The project is on track to achieve intended outcomes within scope and budget.
Q1 24-25 | Melbourne Health | Melb H | 3683 | CMI Data Access Project | Health | Data Management,Records Management ,Reporting | The CMI Data Access Project will deliver the disaggregation of data contained in the Mental Health Client Management Interface (CMI). There will be four data repositories created to enable mental health program reporting for NH, WH, RMH and Orygen. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-11-17 | 2023-09-04 | 2023-09-04 | 147800 | 80000 | 2023-09-04 |  | 2024-06-30 | 2025-06-30 | 1122200 | 1190000 | Green | Green | Green | Green | Amber | The project is currently managing delays in some development and planning dependencies. Reports are continuing to be developed, and resource plans have been adjusted to accommodate the revised development timelines.
Q1 24-25 | Box Hill Institute Group | BHIG | 3456 | Cloud Service Migration | Employment and Workplace | Management of Process | Migration of core on-premise business systems to cloud hosting and implementation of new business system capabilities onto a common ERP cloud hosted platform. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2022-04-01 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-09-01 |  | 2024-04-30 | 2025-03-31 | 4557503 | 7782225 | Green | Green | Amber | Amber | Red | The project reported a red status due to a 3-month schedule extension required to complete testing and address defects post-testing for Stream 3 and 4 as well as to understand Stream 5 deployment approach to minimise business impact and maximise adoption. Stream 6 is on target to complete by Q2 2024/25. With the intervention measures now in place the project is expected to return to Green for Q2 2024-25.
Q1 24-25 | Emergency Services and Superannuation Fund | ESS SUPER | 3865 | Cloud Migration | Government and Economy | Business Intelligence,Communication,Data Management,Security Management ,Systems Management | Migrate Applications out of data centre to Cloud enabling ESSSuper to increase staff productivity and improve Information/Cyber security. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2024-09-30 | Waterfall | 2022-11-15 | 2023-02-13 |  | 2023-02-21 | 169000 |  | 2023-06-01 |  | 2024-08-30 | 2024-09-30 | 4974000 |  |  |  | Green | Green | Green | Work in scope of the project has been delivered. Project is now complete.
Q1 24-25 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Green | Green | Green | Green | The project is reporting as green and delivery is progressing as planned.
Q1 24-25 | Hume Rural Health Alliance | HRHA | 3633 | Clinical Information System Upgrade | Health | Records Management | Delivery of an upgraded, supported version of the Clinical Information System at Northeast Health Wangaratta (NHW) to minimise risk of legacy IT infrastructure and reinstate support for this critical system. | Delivery | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-06-22 |  | 2023-06-23 | 80000 | 79200 | 2023-06-26 |  | 2024-08-05 | 2024-11-16 | 2720000 | 2719310 | Green | Green | Green | Green | Green | System integration development is complete. System integration testing underway and User Acceptance Testing on track for August. Significant resourcing change and reduction has been disruptive however project remains on track to align with target delivery date.
Q1 24-25 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 |  | 1314347 | 1335472 |  | Green | Green | Green | Green | Project is tracking as expected.
Q1 24-25 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Education | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 |  | 8000000 |  |  | Green | Green | Green | Amber | The project plan is being re-aligned. Planned delivery date remains on track for initial go live.
Q1 24-25 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2025-09-30 | 138595535 | 136247000 | Green | Green | Green | Green | Green | Following completion of the tender process for an installer, the delivery end date has been revised to 30 September 2025. The project is otherwise tracking well against scope and budget.
Q1 24-25 | Country Fire Authority | CFA | 2151 | CFA Mobile Data Capability and Short Status Messaging (SSM) | Emergencies and Safety | Communication | Development and deployment of the Mobility Data Capability (MDC) platform, incorporating Short Status Messaging, will deliver operational efficiency and safety benefits to members and the community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2027-06-30 | 2850000 |  | Amber | Amber | Amber | Amber | Amber | The project is currently experiencing system integration issues for the SSM component, resulting in an amber status. Due to this, the delivery of this component will be delayed and included in the broader technology upgrade across the emergency sector. This aligns with the delivery timeline for other mobile applications during the same period.
Q1 24-25 | Department of Transport and Planning | DTP | 3501 | CCTV Federation and Third Party CCTV camera access | Transport and Vehicles | Business Intelligence,Communication,Visualisation | The objective of this project is to enable CCTV federation access with external CCTV systems of Melbourne Metro Trains and Southern Cross Station and develop an integrated platform for 3rd Party CCTV camera access. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-01-31 | 2024-04-21 | 2024-04-21 | 0 |  | 2024-04-21 |  | 2024-09-30 | 2025-02-28 | 1940000 |  |  |  |  | Green | Green | Overall project status is green. Project implementation activities are ongoing.
Q1 24-25 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 |  |  | 270000 | [12 empty] | Project planning underway, project manager completed onboarded process and currently focussing on planning key milestones.
Q1 24-25 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2024-11-30 |  | 0 | 1350000 | [11 empty] | An RFP was issued to shortlisted vendors (following a public RFI in 2023). The RFP responses are being evaluated with the preferred vendor anticipated to be appointed in coming months.
Q1 24-25 | Box Hill Institute Group | BHIG | 3786 | Campus Network Infrastructure Upgrade | Employment and Workplace | Systems Management | Replacement of network infrastructure hardware and software assets within data centres and across all campuses that do not meet the minimum operational requirements related to supportability capacity performance reliability and security. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2023-08-01 | 2023-12-22 |  | 2023-12-22 | 129131 |  | 2023-12-22 |  | 2025-02-28 | 2025-05-31 | 6860000 |  |  |  | Green | Amber | Red | The project reported a red status due additional time required by electrical and cabling remediation and fibre optic testing which has paused the network device implementation. A new schedule will be finalised once fibre optic testing results are available in early Q2 2024/25. With the new schedule in place the project is forecasted to return to Green in the next quarter.
Q1 24-25 | Barwon Region Water Corporation | BR Water | 3842 | C1443 - Land Development and New Connections Transformation | Environment and Water | Customer Relationship Management | The Land Development and New Connections Transformation project will redesign and configure services delivered by the Land Development and Connections functions increasing innovation, reliability and customer affordability. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Waterfall | 2021-11-01 | 2022-10-31 |  | 2022-10-31 | 75000 |  | 2022-11-07 |  | 2024-09-30 | 2024-11-29 | 1414000 |  |  |  | Green | Green | Amber | Single resource dependency caused delays in development work. RETURN TO GREEN Project Change Request (PCR003) will be requested to add reporting scope and seek additional time due to the impact of single resource dependency.
Q1 24-25 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 |  | 1477000 |  |  |  | Red | Red | Red | Project is behind schedule baseline due to delay in procurement. RETURN TO GREEN: Progress project change (PCR) request to baseline project using detail from high level design to refine costs and schedule. Target for PCR approval is late Nov '24
Q1 24-25 | Barwon Region Water Corporation | BR Water | 3601 | C1400 - M365 Phase 3 | Environment and Water | Collaboration | The M365 Phase 3 project will deliver M365 components such as O365, OneDrive, Teams & SharePoint to improve information sharing and organisational collaboration to ensure improved compliance and employee experience. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2024-08-30 | Waterfall | 2021-07-01 | 2022-01-31 |  | 2022-02-01 | 88158 |  | 2022-02-01 |  | 2023-06-30 | 2024-08-30 | 1297936 | 2245022 | Red | Red | Red | Red | Green | The program control board has decided to explore alternative solutions for information and records management. The program has successfully delivered Office365 OneDrive and Teams functions that improved organisational collaboration and employee experience. Project change request (PCR003) was approved in AUG 2024 to complete the project with a reduced scope and benefits without the SharePoint component.
Q1 24-25 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Modernise work and asset management capabilities to enable Barwon Water Group to become a more financially sustainable business, keep bills affordable for all, and create positive customer experiences. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 |  |  | 824310 | [12 empty] | Project is currently in the procurement phase with a scheduled complete end date of 31/03/2025. Currently working through the evaluation phase after tender submission closed in early October 2024
Q1 24-25 | Barwon Region Water Corporation | BR Water | 3916 | C1061 - CRM, Customer Portal & Contact Centre | Environment and Water | Customer Relationship Management | Reinvent customer experience and operational efficiency at Barwon Water Group through the implementation of technology solutions in the form of a Customer Relationship Management (CRM), Customer Portal and Contact Centre solution. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 |  |  | 1292283 | [12 empty] | Preliminary business case was developed and approved. Project entered procurement phase with an estimated completion date of 31/03/2025.
Q1 24-25 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Initiated |  |  | Agile | 2024-06-13 | 2024-10-25 |  |  | 0 | [12 empty] | Business Case is being drafted
Q1 24-25 | Royal Women’s Hospital | RWH | 3719 | Business Intelligence & Analytics Replacement System (BIARS) | Health | Business Intelligence | Business Intelligence (BI) and analytics upgrade for infrastructure and software by partnering with external provider. Decommission current BI system (RISE) and provide better system capability for operational reporting requirements. | Delivery | Cost Reduction (Financial) |  | PRINCE2 | 2023-05-01 | 2023-06-01 |  | 2023-06-01 | 100000 |  | 2023-12-04 |  | 2024-11-30 |  | 2671976 |  |  | Green | Green | Green | Amber | Progressing to schedule, some delays to backend technical activities have impacted interim delivery dates.
Q1 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that will increase computational capacity and data storage for improved performance, reliability, security, and future business needs. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-20 |  | 150000 | 447000 | [11 empty] | The project remains in the Initiation stage. A tender was released to the market for the refresh of the BASC system infrastructure in August 2024. Recent project efforts have concentrated on preparing for the tender evaluation phase which is the primary focus for the upcoming quarter.
Q1 24-25 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 650000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 10251000 | Amber | Amber | Amber | Amber | Amber | Review of options for engaging a new vendor. Open market tender, responses received and evaluated.
Q1 24-25 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2025-01-31 |  | 75000 | 245000 | [11 empty] | This project was placed on hold following the 2022 major floods in line with changing organisational prioritisations. Currently planning to bring the project off hold and go out to RFP during 2025.
Q1 24-25 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems to deliver safety and cost benefits. The project will provide access to rehabilitation and reintegration services through in-cell technology. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2025-06-30 | 18868800 | 17649800 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule. Additional scope has been approved for delivery in this project. To accommodate the additional scope the delivery end date has been revised to June 2025 and the delivery cost revised to $17,649,800.
Q1 24-25 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2024-12-31 | 3443281 | 3883649 | Amber | Green | Amber | Amber | Amber | Phase 1 implemented successfully (800 staff). Further implementation across all staff to be completed in early 2025.
Q1 24-25 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2025-03-31 | 6074206 | 6074206 | Red | Amber | Red | Red | Red | Phase 1 (Community Nursing) has reached technical go-live with change and training underway with clinical go-live TBC subject to Union consultation. Phase 2 (community mental health) functional testing underway. Clinical go-live TBC in early 2025.
Q1 24-25 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Initiated |  |  | PMBoK | 2022-01-03 | 2025-12-01 |  |  | 0 | [12 empty] | Project is currently scoping IT deliverables and technical specifications.
Q1 24-25 | Grampians Rural Health Alliance | GRHA | 3484 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 1 & 2 | Health | Development and Integration | Ballarat Base Hospital Redevelopment - ICT Program - Stage 1/2 ICT systems to support the project works, improving patient and staff systems & support. | Delivery | Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-03 | 2022-11-04 | 2022-11-01 | 2022-11-01 | 0 |  | 2023-03-01 |  | 2024-10-25 | 2024-11-29 | 2458647 |  | Green | Green | Green | Green | Green | The project schedule has re-baselined upon governance approval to address some minor delay in building readiness. The project is on track to complete by Q2.
Q1 24-25 | Western Health | WH | 3723 | Bachus Marsh Melton (BMM) EMR Transition - Devices | Health | Systems Management | Provision and integration of Electronic Medical Record (EMR) IT Devices at BMM as part of Western Health system to enable and to provide consistent patient care | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-20 | 2023-08-08 |  | 2023-08-14 | 0 |  | 2023-08-28 |  | 2024-01-16 | 2024-11-25 | 1549000 |  | Green | Red | Green | Green | Green | The project is on track.
Q1 24-25 | WorkSafe Victoria | WorkSafe | 3643 | AWS Integration Platform Replacement | Government and Economy | Systems Management | The Integration and Orchestration platform (IOP) will migrate to an open-source platform, enabling integration with other WSV CRM applications to minimise security risks and service disruptions, improving the efficiency of WSV tech. support efforts | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2024-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-05-02 | 2022-06-30 |  | 2022-07-07 | 0 |  | 2022-08-01 |  | 2023-11-03 | 2024-09-30 | 1100124 | 1144628 | Red | Green | Green | Green | Green | The following deliverables have been completed and the project will move into closure: • Production and non-production environments on AWS to support migration from IBM Private Proprietary Cloud (ICP) of integration workloads. • Detailed current state analysis and confirmation of services. • Updates of ICP services to support new Redhat Open Source on AWS. • Development of automation scripts to support migration. The agreed approach and strategic direction for integration services has been determined and will be delivered by the Strategic Integration Platform project. Per the new strategic direction this project has descoped the deployment of the ROSA platform.
Q1 24-25 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2025-09-25 | 32018000 |  | Amber | Amber | Amber | Amber | Amber | Overall project status is amber due to some delays being incurred during the Test phase. Project team is working with all the stakeholder to address the issue.
Q1 24-25 | Department of Transport and Planning | DTP | 3052 | Automatic Incident Detection (AID) Software Project | Transport and Vehicles | Development and Integration ,Systems Management,Visualisation | The objective of this project is to implement an Automated Incident Detection (AID) system. This system will use data from existing freeway systems and alert the operators and provide a view of road traffic incidents from the nearest CCTV camera. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-06 | 2021-02-28 | 2021-07-07 | 2021-07-30 | 0 |  | 2021-08-16 | 2022-02-28 | 2022-06-30 | 2025-05-31 | 2100000 |  | Green | Green | Green | Green | Green | Overall project status is green. User Acceptance Testing completed. Software deployment in progress
Q1 24-25 | Department of Families, Fairness and Housing | DFFH | 3921 | Automated System Integration of the Victorian Housing Register (online) Application | Community Services | Records Management | Moving the Victorian Housing Register Application to an automated integrated solution, thereby improving the timeliness and capacity to manage an increase in volumes at an office level, improving client experience with faster feedback. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-28 | 2024-06-28 |  | 2024-06-28 | 192450 |  | 2024-07-15 |  | 2025-06-30 |  | 1614264 | [5 empty] | Amber | Project is progressing as AMBER due to complexities identified during the detailed requirements phase. This has led to an extended requirements phase to ensure comprehensive requirements gathering and dependency management. Any potential downstream impacts to project timeline and costs are being assessed with a planned checkpoint in December to inform next period for reporting.
Q1 24-25 | Department of Education | DE | 3956 | Automated Briefing and Correspondence (ABC) Implementation | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 |  | 2657628 | [5 empty] | Green | Validation of base build in progress and commencement of essential build underway. The project is tracking to plan and is performing on scope budget and schedule.
Q1 24-25 | Austin Health | AH | 3494 | Austin Health HR Information Systems | Health | Human Resources | The HRIS project will replace legacy HR Systems for Payroll, Recruitment and On-boarding systems to modernise processes and introduce efficiencies at Austin Health. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-07-31 | 2023-02-01 |  | 2023-02-01 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2024-12-20 | 7800000 | 11043528 | Amber | Amber | Amber | Amber | Amber | Planned activities completed: Payroll Parallel run 1 complete ETL complete for Payroll Parallel run 2 Still reporting amber because of pressure on timeframes
Q1 24-25 | Austin Health | AH | 3721 | Austin Health Financial Management Information System | Health | Financial Management | The Financial Management Information System will replace an end of life system, introducing efficiencies and continuation of financial & supply chain management at Austin Health. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-04-03 | 2024-02-28 |  | 2024-02-28 | 0 |  | 2024-03-18 |  | 2025-03-03 |  | 11414550 |  |  |  | Green | Green | Amber | Completed final round of design workshops and key integration design.
Q1 24-25 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 | 2024-11-05 | 2424764 |  | Green | Green | Green | Green | Green | Next phase of the project is about to commence. PM starting in Oct the schedule and forecast will be updated to reflect new timelines soon, change request to re-baseline the schedule will revert to green.
Q1 24-25 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 |  | 3436310 | 1729890 |  |  | Green | Green | Green | Project has undertaken architectural review to inform how GWWs assets are better managed and maintained across our service delivery areas. Preparation of a business case for the next phase is in progress. NOTE: Reported delivery costs reflect the current phase of the project. Each phase will provide further clarity on cost.
Q1 24-25 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 |  | 7069087 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule. Installation planning is well underway with pilot installations beginning in quarter 1 2024-25.
Q1 24-25 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Initiated |  |  | PRINCE2 | 2024-09-03 | 2025-06-30 |  |  | 200000 | [12 empty] | Business case approved. Procurement planning underway.
Q1 24-25 | Department of Education | DE | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage school land & building assets enabling evidence-based decision making at both DE Corporate & School level & support attestation against Asset Management Accountability Framework. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2024-10-31 | 12956778 | 25565174 | Amber | Amber | Amber | Amber | Amber | The project has been functionally delivered and is pending final signoff of the solution.
Q1 24-25 | Department of Education | DE | 3857 | ARC 4.0 (Expansion and Enhancement - Lessons Plans) | Education | Content Management,Management of Process | To empower educators and learners by creating a comprehensive and user-friendly lesson plan management system within the Arc. This system will streamline lesson planning enhance learning experiences and improve learning outcomes. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2024-02-19 | 2024-02-19 |  | 2024-02-19 | 91318 |  | 2024-03-20 |  | 2024-07-26 | 2025-06-30 | 1034685 | 2609682 |  |  | Green | Green | Amber | Following the successful delivery of the system, the project is moving on to deliver lesson plans for the remaining curriculum areas. The project has experienced a minor delay due to the additional data cleansing required to load the content into the ARC system.
Q1 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 |  | 3157730 |  |  |  | Green | Green | Red | Project currently tracking behind schedule due to delays in implementation build.
Q1 24-25 | Austin Health | AH | 3877 | Anesthetics & Device Integration (AnDI) Project | Health | Development and Integration ,Document Management ,Knowledge Management ,Management of Process | Digitising theatre based documentation and integrating monitoring device data into the Electronic Medical Record, for safer patient outcomes and improved efficiency. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2024-05-27 | 2024-08-05 |  | 2024-08-05 | 0 |  | 2024-08-05 |  | 2025-08-29 |  | 4585000 | [5 empty] | Green | Onboarded all project staff. Current state review (including workshop 1) completed Governance structure established Sign-off of Project Charter Change & Education Management Plan and Testing Plan Integration middleware sourced
Q1 24-25 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 |  | 2947600 | [5 empty] | Green | Discover and Align Phase currently in progress. It will be completed mid-December. Next step - Planning and prioritisation for Build phase.
Q1 24-25 | Triple Zero Victoria | TZV | 3564 | Alternate CAD | Emergencies and Safety | Systems Management | Build an additional platform as a backup/redundancy to support Computer Aided Dispatch platform during planned and unplanned outages. | Postponed | Risk Reduction (Non Financial) | 2024-07-04 | Project Management Excellence | 2021-02-15 | 2023-12-31 | 2022-06-30 | 2023-02-02 | 0 | 1028455 | 2023-08-01 | 2023-07-31 | 2024-02-29 | 2024-09-30 | 5371545 |  | Green | Green | Green | Amber | Red | The Alternate CAD project has been placed on hold pending completion of a viability assessment subsequent to testing outcomes.
Q1 24-25 | Alfred Health | ALFRED | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-02-09 | 25000000 | 33000000 | Amber | Amber | Amber | Amber | Amber | The project is at amber due to recruitment and procurement delays that put delivery schedule and budget at risk. Works are underway to mitigate these risks to ensure project stays on schedule and budget
Q1 24-25 | Grampians Rural Health Alliance | GRHA | 3523 | AD Domain Migration | Health | Systems Management | The AD domain migration project aims to consolidate four separate Grampians Health environments(Ballarat, Edenhope, Horsham and Stawell) into one cloud instance. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2022-11-21 | 2022-12-05 |  | 2022-12-05 | 0 |  | 2022-12-05 |  | 2023-11-30 | 2024-12-20 | 2529763 |  | Green | Green | Green | Green | Green | The project schedule has re-baselined upon governance approval to address some minor delays in one of the remaining work streams. The project is on track to complete by Q2.
Q1 24-25 | South East Water | SE Water | 3923 | Acumen Phase 2 | Environment and Water | Business Intelligence,Data Management | Phase 2 of Acumen will deliver foundation components, including architecture review and data preparation for ingestion and modelling. This will deliver key foundational elements necessary to support future phases. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2024-02-29 |  | 2024-02-29 | 0 |  | 2024-02-29 |  | 2025-04-30 |  | 3600000 | [5 empty] | Green | Phase 2 currently in progress with focus on establishing environments to support ongoing development of the new data & analytics platform. Some technical items more complex than planned, but issues are being managed and impacts minimised.
Q1 24-25 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 |  | 3200000 |  |  |  |  | Amber | Green | The project is advancing at a good constant pace.
Q1 24-25 | Department of Education | DE | 3963 | 50 Early Learning Childcare Centres - Technology Components | Education | Customer Relationship Management | The project will deliver the required technology components in 50 ELC centres to support the Victorian Government initiative in broader early learning, enabling great start for young Victorians. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-15 | 2024-03-15 |  | 2024-03-18 | 0 |  | 2024-03-18 |  | 2032-06-30 |  | 2108035 | [5 empty] | Green | Finalising technology requirements. Project is performing to plan with expected January 2025 launch for the first phase of the project. A post-launch roadmap is in planning.
Q1 24-25 | Yarra Valley Water | YV Water | 3626 | 3G to 4G/5G Telecommunications Infrastructure Upgrades | Environment and Water | Communication | Upgrade comms infrastructure from 3G to 4G to provide continuous visibility to YVW water and sewer infrastructure. 3G comms is coming to end of life so unless it is upgraded to 4G YVW will lose the ability to remotely manage all its infra operations | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-07 | 2021-07-16 |  | 2021-07-16 | 71049 |  | 2021-07-16 |  | 2023-10-31 | 2024-11-30 | 2552948 |  | Green | Green | Green | Green | Green | Project work completed, final vendor invoices to be received in October/November