## table
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q4 16-17 | Q1 17-18 | Q2 17-18 | Q3 17-18 | Q4 17-18 (Current) | Reporting Comments
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2129 | Barwon Health Data Warehouse Refresh | Health | Business Intelligence,Reporting | Barwon Health is undertaking a project to rebuild their current data warehouse to enable us to move from reporting off individual transactional systems to a federated repository of all data required for reporting. | Delivery |  | PRINCE2 | 2013-08-01 | 2016-06-01 |  | 2016-06-01 | 0 |  | 2016-06-01 | 2016-06-01 | 2016-06-30 | 2018-09-28 | 1760000 |  | Green | Green | Green | Green | Green | Project is currently in the closure phase and documentation has been provided to the steering committee.
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2130 | SWARH Accelerated adoption of a Regional E.H.R | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | The 13 SWARH agencies that utilize the SWARH EHR do not have dedicated change management agents to facilitate functionality uptake. The project aims to improve functionality to directly capture information in the Patient Administration System, eMedication Management, Clinical, Emergency, Theatre, appointment scheduling and community workflows. | Closed - Completed | 2018-06-30 | PRINCE2 | 2015-07-01 | 2015-09-20 |  | 2015-09-20 | 0 |  | 2015-09-20 |  | 2017-09-21 | 2018-06-30 | 3045000 |  | Amber | Green | Amber | Amber | Amber | The eleven participating hospitals steadily adopted EHR functionality and moved through the HIMSS levels. However the software vendor was not prepared to provide critical functionality – eMedication Management – in the TrakCare version used by the project. This prevented attainment of the overall project objective of reaching HIMSS level 5.
Q4 17-18 | Alfred Health | ALFRED | 2132 | Alfred Emergency and Trauma Centre Redevelopment - ICT Component and Emergency Department Information System (EDIS) | Health | Systems Management | Expand and refurbish the Alfred Emergency & Trauma Centre facility staged to ensure operational continuity during the indicative 18 months of building works - ICT Component (including infrastructure, hardware, software & EDIS Phase 1) | Closed - Completed | 2018-04-14 | PRINCE2 | 2015-10-01 | 2017-05-15 |  | 2017-05-15 | 336469 |  | 2017-05-15 |  | 2018-04-14 |  | 663531 |  | Green | Green | Amber | Green | Green | Overall Project Status is COMPLETED
Q4 17-18 | Alfred Health | ALFRED | 2133 | Implement eTQC Phase One program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Records Management | Development and Implementation of Phase One of the electronic-Timely Quality Care (eTQC) project that will significantly improve clinical real-time data capture, management and patient care service delivery, to progress towards a fully electronic medical record across Alfred Health. | Delivery |  | PRINCE2 | 2016-04-01 | 2017-10-08 |  | 2017-10-08 | 8237689 |  | 2017-10-08 |  | 2018-12-31 |  | 14574686 |  |  | Green | Green | Green | Green | Project is ON TRACK
Q4 17-18 | Bendigo Kangan Institute of TAFE | BKI TAFE | 2141 | Student Management System Implementation | Education | Records Management | Implementation of new Student Management System across the integrated Bendigo Kangan Institute | Delivery |  | PRINCE2 | 2013-02-01 | 2014-04-01 |  | 2014-04-01 | 82723 |  | 2014-04-01 | 2014-04-01 | 2016-12-31 | 2018-12-31 | 9800000 | 13256145 | Green | Green | Amber | Amber | Amber | The project has be rebase-lined and implemented a tactical remediation team to stabilise the platform and to improve AVETMISS reporting. A strategic approach will be presented to the BKI Board detailing a plan to upgrade the Banner platform and to ensure AVETMISS reporting is stabilised. Therefore any additional funding is yet to be approved and is not currently reflected in the total current projections. The revised timeline would see the project extended to Dec 18
Q4 17-18 | Bendigo Kangan Institute of TAFE | BKI TAFE | 2142 | Human Resources and Payroll Information System Implementation | Education | Human Capital / Workforce Management | Implementation of new Human Resource and Payroll Information System across the integrated Bendigo Kangan Institute | Delivery |  | PRINCE2 | 2015-01-27 | 2017-01-31 |  | 2017-01-31 | 284550 |  | 2017-01-31 | 2017-01-31 | 2017-07-03 | 2018-11-30 | 1241354 | 2115450 | Amber | Green | Amber | Amber | Amber | The HR IS/Payroll Integration Project is continues to be in Solution Implementation Phase. The project go live date was met as targeted in October 17. However there remains a number of issues around data quality data management and processing which require rectification to realise the full benefits of the program. The Payroll module has been implemented and staff are being paid however there remains a an element of manual intervention and issues with GL interface. Prioritisation of the issues has occurred. Project rectification has now been extended to Nov18
Q4 17-18 | CenITex | CenITex | 2149 | Corporate ERP SaaS Solution | Government and Economy | Management of Process | Implement SaaS based ERP - CRM, PPM and Finance subsystems | Delivery |  | PRINCE2 | 2016-07-01 | 2016-08-30 |  | 2016-08-30 | 0 |  | 2016-08-30 | 2016-08-30 | 2018-01-31 | 2018-09-30 | 2049361 |  | Green | Green | Green | Green | Green | Full go live of PPM module (including project timesheets and resource allocations) was completed successfully on 30 April as planned. Interface to Dynamics NAV also completed prior to end of the financial year. Project is now in final stages of closure with transition to Cenitex Business Technology Services underway.
Q4 17-18 | Country Fire Authority | CFA | 2150 | CFA Resource Tracking System (RTS) | Emergencies and Safety | Tracking and Workflow | Provide a Resource Tracking System for all CFA resources using CFA mobile radios to collect and transmit location data. This will allow Incident Controllers to have a near real time view of where all resources are located at major incidents enhancing firefighter safety. | Delivery |  | PRINCE2 | 2010-10-01 | 2013-06-30 |  | 2013-06-30 | 126034 |  | 2013-06-30 | 2013-06-30 | 2017-06-30 | 2018-11-01 | 2500000 |  | Amber | Amber | Amber | Green | Green | Technical solutions have been implemented. The Business Rule has been approved and the Initial release of product is planned for July 2018.
Q4 17-18 | Country Fire Authority | CFA | 2151 | CFA Short Status Messaging (SSM) | Emergencies and Safety | Communication | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | Initiated |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2018-05-31 |  | 0 | [12 empty] | This project is an element of a larger program, which is behind schedule. The project now has a revised delivery date of June 2019. Consultation with a third party supplier is in progress.
Q4 17-18 | Department of Justice and Regulation | DJR | 2152 | Regional Radio Command Service | Emergencies and Safety | Communication | Establish new command and control level voice communication service on the Regional Mobile Radio network. Establish interconnectivity between Regional Radio Command Service, Incident Control Centres and operational facilities | Postponed | 2017-06-30 | Project Management Excellence | 2014-07-01 | 2016-06-30 |  | 2016-06-30 | 8000000 |  | 2016-06-30 |  | 2017-06-30 | 2018-06-30 | 5000000 | [6 empty] | The project has been placed on hold. EMV is exploring possible funding options.
Q4 17-18 | Chisholm Institute of TAFE | Chisholm TAFE | 2153 | Customer Relationship Management Implementation | Education | Customer Relationship Management | To provide an improved service to existing and potential students to maximise the take-up of educational services | Delivery |  | Chisholm PMF (Prince 2 Based) | 2016-06-01 | 2017-05-07 |  | 2017-05-07 | 418304 |  | 2017-05-07 | 2017-05-07 | 2018-03-31 | 2019-06-30 | 3083074 | 3994622 |  | Green | Amber | Green | Amber | Due to rescheduling the system release timeframes, increasing project costs will be incurred.
Q4 17-18 | Department of Health and Human Services | DHHS | 2166 | Melton Community Based Ambulatory Care Centre (MCBACC) | Health | Organisational Management | Implementation of the ICT integration solution between five health providers at the new Melton Community Based Ambulatory Care Centre | Delivery |  | PRINCE2 | 2016-07-07 | 2017-11-30 |  | 2017-11-30 | 223020 |  | 2018-01-01 |  | 2018-12-17 |  | 1187640 | 1410661 |  |  |  | Green | Green | Hardware procurement is complete. Configuration and implementation planning are in progress, along with assessment of security requirements.
Q4 17-18 | Department of Education and Training | DET | 2168 | Exchange Upgrade | Education | Collaboration | The Exchange Upgrade project will upgrade the DET Microsoft Exchange platform from Exchange 2010 to Exchange 2016 (initial plan was to upgrade to Exchange 2013), including migration of all DET users. The system will provide an enhanced email solution for Government school teachers and corporate staff at DET. | Delivery |  | PRINCE2 | 2013-11-11 | 2015-05-14 |  | 2015-05-14 | 214280 |  | 2015-05-14 | 2015-05-14 | 2017-09-22 | 2019-12-13 | 1045087 | 1729459 | Amber | Amber | Amber | Amber | Amber | Build activities have delivered all server infrastructure and the base Exchange 2016 application installation. The IT infrastructure issues have been resolved and the Exchange project, and the integration work activities are scheduled for completion in Quarter 4 2018. This includes a new MIM Adaptor and Skype for Business integration. Robust testing will be followed by a pilot migration of a minimum of 50 mailboxes prior to Christmas 2018. The full mailbox migration and remediation of more than 120,000 email accounts from Exchange 2010 to 2016 is scheduled for the calendar year 2019. The actual timeline and costs for the complete migration will be published following development of detailed schedule and response from market.
Q4 17-18 | Department of Education and Training | DET | 2169 | International Student Information Management System | Education | Management of Process | This project will identify, procure and customise an existing (Off the Shelf) International Student Information Management System to address existing shortfalls and meet current and future business needs for the International Education Division. | Delivery |  | PRINCE2 | 2014-01-02 | 2016-05-31 |  | 2016-05-31 | 201000 |  | 2016-05-31 | 2016-05-31 | 2017-12-08 | 2018-09-28 | 905000 | 1742375 | Amber | Amber | Amber | Amber | Red | The current release of the system software - IT18 is undergoing UAT, with a clean data migration. A Senior Project Manager has been assigned to the project and is working closely with the business and the vendor to streamline the delivery of the high number of outstanding issues impacting functionality and system delivery. It is expected that the outstanding critical and high issues will be rectified in Releases IT19 and IT20, due to be delivered during the second half of 2018. The Department is working with the supplier to ensure the solution is fit for purpose. There is complexity associated with fee recording and disbursements, and the full solution to support fees and disbursements has been subject to negotiation on design, and technical solution. This critical issue is being addressed at Board level. The project status is currently reported red due to repeat schedule delays throughout the project life cycle and system quality issues detected in earlier IT releases. A revised project schedule, scoping and quality aspects are currently being resolved with the supplier.
Q4 17-18 | Department of Education and Training | DET | 2173 | CASES Technology Refresh | Education | Systems Management | The CASES Technology Refresh project will perform the 4 year refresh of Government schools' technology environment to support administration and financial management functions. The scope encompasses a server, workstations, switch, UPS, printer and backup service. | Delivery |  | PRINCE2 | 2014-12-19 | 2016-07-20 |  | 2016-07-20 | 692729 |  | 2016-07-20 | 2016-07-20 | 2017-02-28 | 2018-08-31 | 14707271 | 14950000 | Green | Green | Green | Green | Green | Installation of all IT equipment at schools (network switches, servers, desktops, and printers) is complete. Procurement for the centralised backup ICT solution is complete and rollout to schools is now complete. The out-of-warranty CASES desktops and servers have been collected from all Victorian Government schools and have undergone a three phase data wipe. The centralised backup ICT solution is complete and schools admin data is now being backed-up to the CommVault System. The final item currently underway is the transfer of historical financial data from the legacy back-up system to the new CommVault system.
Q4 17-18 | Department of Education and Training | DET | 2176 | HCM and Local Payroll - Performance (PDP) and Learning Management (LMS) | Education | Human Capital / Workforce Management | A fully integrated payroll, performance, career and learning management capability for DET and its shared service customers through extension and utilisation of DET's PeopleSoft based eduPay shared services arrangement. To deliver an integrated solution for VPS and teaching staff and a systemic, evidence-based response to aid strategic decision making. | Closed - Completed | 2018-06-29 | PRINCE2 | 2015-02-19 | 2016-05-31 | 2016-03-30 | 2016-03-30 | 398000 |  | 2016-03-30 | 2016-03-30 | 2017-06-30 | 2018-06-29 | 3712048 |  | Green | Green | Green | Green | Green | Access to the new learning management system (LearnED) is now available to all Departmental staff. The induction program is in operation for all new Corporate staff and will form the basis for the implementation of future induction programs for Schools as part of business as usual (BAU). The recent inclusion of mandatory OHS training for all DET staff will result in a steep increase in the use of the LearnED among Corporate and School staff. Pilots of school administration eLearning and face-to-face training have been successfully piloted in LearnED. As a result, approximately 200 school administration courses are in the process of being moved from the existing Moodle platform into LearnED as part of BAU. The procurement activity to establish a panel of preferred suppliers for delivery of eLearn development services to the Department is well advanced - the panel will be in place by August 2018. The performance management system is now widely in use across Schools and Corporate business units. The project has transitioned to BAU delivering planned benefits in relation to financial, performance and learning management compliance; provision of an entire workforce view and facilitating capability, career and succession planning; and more timely and accurate reporting.
Q4 17-18 | Department of Health and Human Services | DHHS | 2179 | Health & Hospital Funding Regional ICT cancer Multidisciplinary Meeting Management Project | Health | Customer Preferences | To deliver a software solution to support multidisciplinary team meetings within and across regional integrated cancer services. | Delivery |  | PRINCE2 | 2012-12-01 | 2017-11-14 |  | 2014-05-19 | 500000 |  | 2018-01-03 |  | 2019-03-29 |  | 2000000 |  |  |  |  | Green | Green | Project is progressing to schedule
Q4 17-18 | Department of Health and Human Services | DHHS | 2184 | Real-time prescription monitoring system | Health | Data Management | Implement software that transmits pharmacy records in real-time to a centralised database, enabling doctors and pharmacists to make safer clinical decisions prior to prescribing or dispensing medicines at high risk of misuse. | Delivery |  | PRINCE2 | 2016-01-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-07-01 |  | 2020-06-30 |  | 21227000 | 10893000 |  |  | Green | Green | Green | Project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2186 | Housing Infrastructure Capital Refresh | Community Services | Systems Management | Replace ageing and unsupported hardware for the production and disaster recovery environments of the Housing Integrated Information Program (HiiP). | Delivery |  | PRINCE2 | 2015-05-28 | 2016-12-13 |  | 2016-12-13 | 415000 |  | 2016-12-13 | 2016-12-13 | 2017-03-31 | 2018-08-31 | 5000000 | 5209568 | Green | Green | Green | Green | Amber | Project is progressing but has had schedule delays.
Q4 17-18 | Department of Health and Human Services | DHHS | 2189 | Victorian eReferral Program | Health | Management of Process | The Program aims to make referral processes more efficient, safe and reliable. The focus of the program, while necessarily including a significant technical component, will also be establishing appropriate governance, standardisation in business processes and information and the change management necessary to deliver the planned benefits and client outcomes. | Closed - Completed | 2018-06-30 | PRINCE2 | 2015-07-01 | 2017-04-01 |  | 2017-04-01 | 640607 |  | 2017-04-01 |  | 2018-06-30 |  | 2874201 |  | Green | Green | Green | Green | Green | Project has completed as scheduled.
Q4 17-18 | Department of Premier and Cabinet | DPC | 2190 | ACHRIS Phase 2 Enhancement Project | Culture, Sport and Recreation | Systems Management | The ACHRIS Phase 2 Enhancement Project will deliver new functionality to AVs online application to support the implementation of the Aboriginal Heritage Amendment Act 21016 and a new infrastructure environment to enable the required flexibility, scalability and operational efficiency to implement these changes. | Delivery |  | Agile | 2015-01-01 | 2015-12-30 |  | 2015-12-30 | 42900 |  | 2015-12-30 |  | 2019-06-30 |  | 1950000 |  | Amber | Amber | Amber | Green | Green | Development activities to improve operational efficiencies in the registration of Aboriginal Places has commenced. This is a large piece of work and is expected to take six months. Procedures and processes for in-house operational support have been developed and implemented.
Q4 17-18 | Department of Health and Human Services | DHHS | 2192 | Records Management system upgrade | Community Services | Document Management | Upgrade the current recordkeeping system software and hardware for all existing users. | Closed - Completed | 2018-02-28 | PRINCE2 | 2015-07-12 | 2017-03-07 |  | 2017-03-07 | 227153 |  | 2017-03-07 | 2017-03-07 | 2017-08-28 | 2018-02-28 | 2547340 | 1818134 | Green | Green | Green | Green | Green | The project has delivered its intended result and is now closed
Q4 17-18 | Department of Health and Human Services | DHHS | 2197 | Bendigo Hospital - Electronic Medical Record | Health | Records Management | Electronic Medical Records and Digital Medical Records implementation at the new Bendigo Hospital | Delivery |  | PRINCE2 | 2015-12-23 | 2016-10-05 |  | 2016-10-05 | 11343000 |  | 2016-10-05 | 2016-10-05 | 2018-03-31 | 2019-05-30 | 14987000 |  | Amber | Amber | Amber | Amber | Amber | The project has experienced delays due to vendor delivery performance. The project continues to progress design and configuration activities.
Q4 17-18 | Department of Health and Human Services | DHHS | 2200 | Integration Solution Replacement | Health | Development and Integration | Replacement of the integration solution to support Victorian acute public health services with ongoing capability to integrate patient and clinical information within and across health services. | Delivery |  | PRINCE2 | 2016-07-01 | 2016-11-30 |  | 2016-11-30 | 0 |  | 2016-12-01 |  | 2020-06-30 |  | 16000000 |  |  |  | Green | Green | Green | The project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2203 | Windows Server Remediation Program | Community Services | Systems Management | Upgrade, replace or decommission outdated servers and database instances. | Delivery |  | Agile | 2016-06-01 | 2016-06-29 |  | 2016-06-30 | 53000 |  | 2016-06-30 |  | 2019-06-30 |  | 11800000 | 2666385 | Green | Green | Green | Green | Green | Project is progressing to schedule.
Q4 17-18 | Department of Premier and Cabinet | DPC | 2204 | Single Digital Presence | Government and Economy | Content Management | The Victorian Government will make it easier for Victorians to find, access and understand government information by redesigning and re-platforming Premier & Cabinet websites, including vic.gov.au. This project will also reduce the cost and risk associated with digital services and help us create new services faster. | Delivery |  | Agile | 2015-09-17 | 2016-06-30 |  | 2016-06-30 | 118800 |  | 2016-06-30 | 2016-06-30 | 2018-06-30 | 2020-02-28 | 4200000 | 4942000 | Green | Green | Green | Green | Green | At the end of Q4 2017-18, the Single Digital Presence delivered the website alpha.vic.gov.au. This 'alpha' version of vic.gov.au is a high level prototype that tests changes to the way the Victorian Government delivers information online. These changes include, making content easier to find and read, joining up related information, providing a consistent look and feel, and improving accessibility. The 'alpha' phase of this site will run through Q1 2018/19. During this time we will gather, rank and act on what users are telling us about their experiences of this site. Features and capability are continuing to be added to the platform as different use cases from content owners across the Department of Premier and Cabinet are addressed. The platform is awaiting approval to be released under an Open Source license.
Q4 17-18 | Department of Health and Human Services | DHHS | 2205 | Unique Patient Identifier | Health | Development and Integration | Implementation of a state-wide Enterprise Master Patient Index (EMPI) to support the objectives of Health 2020, the Clinical Information Exchange (CIE), improved analytic capability and access to My Health Record. | Delivery |  | PRINCE2 | 2016-07-01 | 2016-12-10 |  | 2016-12-10 | 0 |  | 2017-02-01 |  | 2019-12-31 |  | 17100000 |  |  |  | Green | Green | Red | The project has experienced delays due to an extended infrastructure procurement and delivery period, which is being addressed.
Q4 17-18 | Eastern Health | EH | 2208 | Eastern Health - Electronic Medical Record | Health | Customer Relationship Management,Management of Process ,Records Management | Build a single Longitudinal Medical Record which ensures that relevant critical information for the provision of patient care is available in the one place at the time of clinical decision making, and ensures presentation in a comprehensive, consistent and contextual manner. | Closed - Completed | 2018-05-02 | Cerner Consulting Framework | 2015-01-01 | 2015-09-30 |  | 2015-09-30 | 1027020 |  | 2015-09-30 |  | 2017-12-31 |  | 18852980 |  | Green | Green | Green | Green | Green | Project completed successfully
Q4 17-18 | Gippsland Health Alliance | GHA | 2209 | Electronic Medical Record and Community Health (EMRCH) | Health | Customer Relationship Management | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | Delivery |  | PMBoK | 2016-02-02 | 2017-10-30 |  | 2017-11-01 | 554038 |  | 2018-01-09 |  | 2019-12-31 |  | 7419045 |  |  |  | Green | Amber | Green | Status changed from Amber to green following pushback of the go-live date to November 26th 2018
Q4 17-18 | Hume Rural Health Alliance | HRHA | 2210 | Goulburn Valley Health Redevelopment | Health | Systems Management | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | Initiated |  | PRINCE2 | 2016-04-20 | 2018-06-30 |  |  | 400000 | [12 empty] | Detailed design of the ICT infrastructure for the redevelopment build is complete. Project has finalised budget and high level schedule. Project preparing to tender for services to undertake the work.
Q4 17-18 | Goulburn-Murray Rural Water Corporation | GMR Water | 2215 | ECMS Upgrade / Replacement | Environment and Water | Document Management | The existing Records and Document Management System is not meeting the organisation's requirements. The objective of this project is to define the organisation's requirements and to source and implement an Enterprise Content Management System (ECMS) that meets the organisation's current and future requirements for Records, Documents and Information Management. | Delivery |  | PRINCE2 | 2016-01-18 | 2017-02-28 |  | 2017-02-28 | 37238 |  | 2017-02-28 |  | 2018-09-06 |  | 1557208 |  | Green | Green | Green | Green | Green | The project is in the implementation go/live phase, with cutover expected to complete by early August. A number of data migration trials have been completed successfully and user training has been delivered.
Q4 17-18 | Grampians Rural Health Alliance | GRHA | 2217 | Regional EMR/HIE Implementation | Health | Records Management | The development and implementation of shared electronic medical records across the Grampians region | Delivery |  | PRINCE2 | 2015-08-01 | 2016-06-30 |  | 2016-06-30 | 1206242 |  | 2016-06-30 | 2016-06-30 | 2017-03-31 | 2018-12-31 | 1493758 | 2219510 | Amber | Green | Green | Green | Green | Project is on track to complete the project as per revised baseline project plan.
Q4 17-18 | Grampians Wimmera Mallee Water Corporation | GWM Water | 2218 | Water Treatment Plant PLC Replacements | Environment and Water | Business Intelligence | Renewal of PLCs (Programmable Logic Controllers) at priority Water Treatment Plants to replace redundant technology. | Delivery |  | PRINCE2 | 2014-08-12 | 2016-09-30 |  | 2016-09-30 | 164327.1 |  | 2016-09-30 | 2016-09-30 | 2019-06-30 | 2019-06-30 | 1069673 |  | Green | Green | Green | Green | Green | Project is on track.
Q4 17-18 | Hume Rural Health Alliance | HRHA | 2221 | Patient Administration System (PAS) replacement project | Health | Organisational Management | A replacement Patient Administration System (PAS) to address problems associated with running multiple PASs at AWH and end of life technology. The replacement PAS will be adopted by 17 health services within the Hume Region | Delivery |  | PRINCE2 | 2014-02-01 | 2015-12-31 |  | 2016-01-31 | 1900000 |  | 2018-10-31 | 2018-06-01 | 2020-12-31 | 2018-08-31 | 23500000 | 100000 |  |  | Amber | Amber | Green | A project review has been completed. The review concluded the regional project should be split into three smaller projects delivered by the large health services in Hume. The regional project is in the process of being closed and will be superseded on by three new projects in the next reporting period.
Q4 17-18 | Monash Health | Monash H | 2222 | Healthcare Billing System Phase 1 | Health | Financial Management | Implementation of an enterprise billing system for selected services across Monash Health. | Closed - Completed | 2018-05-07 | PRINCE2 | 2015-11-16 | 2016-04-01 |  | 2016-04-01 | 202050 |  | 2016-04-01 |  | 2017-02-01 | 2018-04-01 | 2200000 |  | Green | Amber | Green | Green | Green | System has gone Live
Q4 17-18 | Melbourne Health | Melb H | 2224 | Enterprise Billing System | Health | Financial Management | Implementation of an Enterprise Billing System will enable Melbourne Health to achieve a centralised approach for managing patient billing services and improving revenue collection across all clinical areas. | Delivery |  | PRINCE2 | 2016-03-01 | 2016-05-01 |  | 2016-05-01 | 0 |  | 2016-05-01 |  | 2018-08-01 | 2018-11-07 | 4800000 | 4854146 | Green | Green | Green | Amber | Amber | Phase 2 was intended to be implemented across four stages. Initial preparatory work for all Phase 2 services has been completed in Phase 1 this includes capturing the billing process standard billing rules and integration requirements. The time and resource pressures of the approaching EMR and the impact that this major program of work will have on the business area resources and system vendors that the PBRC project will rely upon for data feeds necessitates a review of scope. Cardiology remains a key focus for completion in phase 2, however capability to complete radiology and pharmacy billing feeds as well is under review and may need to be deferred. Pathology billing has been de-scoped. Furthermore, the EMR will bring about billing data changes that must be accommodated, especially with regard to changes in ED and IPM feeds during stage 1 of EMR.
Q4 17-18 | Melbourne Health | Melb H | 2226 | CAFM Project - Computer Aided Facilities Management | Health | Assets/Materials Management | Implementation of an electronic Computer Aided Facilities Management system that will provide functionality for: Help desk; Task triage; Resource allocation; Job Management; Maintenance & Scheduled Management; Contract Management; Asset & Life Cycle Management; Property and Estate Management; Facility Condition Assessment and Maintenance management. | Postponed | 2018-06-29 | Hybrid - Agile and PRINCE2 | 2015-11-01 | 2015-11-01 |  | 2015-11-01 | 100000 | [12 empty] | Melbourne Health are in the process of reviewing project funding options. The project has been placed on hold until a funding source is confirmed
Q4 17-18 | Melbourne Water | MELB Water | 2230 | Q04323 - Developer Funded Works System | Environment and Water | Assets/Materials Management | The Developer Funded Works System replacement project will migrate an existing system and separate database to an enterprise capability for asset management that is consistent with the Melbourne Water asset information and asset management processes. | Closed - Completed | 2018-06-18 | PRINCE2 | 2013-09-02 | 2016-01-25 |  | 2016-01-25 | 0 |  | 2016-01-25 | 2016-01-25 | 2016-09-30 | 2018-06-30 | 3455000 | 4348081 | Amber | Amber | Amber | Amber | Green | Project went live successfully on June 18 without issues. Hyper care after go Live is active.
Q4 17-18 | Metropolitan Fire and Emergency Services Board | MFESB | 2241 | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and Safety | Content Management | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | Delivery |  | MFB Project Management Framework (PME) | 2013-07-01 | 2014-07-09 |  | 2014-07-09 | 60737 |  | 2014-07-09 | 2014-07-09 | 2017-06-30 | 2018-07-27 | 1200000 | 1810000 | Green | Amber | Amber | Amber | Green | The delay to the EDRMS project rollout has been resolved with the project on track for completion by end of July 2018. This follows approval on 28 May 2018 to extend the budget and revise the project schedule end date.
Q4 17-18 | Metropolitan Fire and Emergency Services Board | MFESB | 2243 | Legacy SAN Storage Refresh | Emergencies and Safety | Systems Management | Replacing legacy and upgrading network storage. | Delivery |  | MFB Project Management Framework (PME) | 2015-07-01 | 2015-10-01 |  | 2015-10-01 | 0 |  | 2015-10-01 | 2015-10-01 | 2017-06-30 | 2019-06-30 | 1500000 | 1230000 | Green | Green | Amber | Amber | Amber | A project scope change has been approved and project work has commenced. The data backup storage phase will be completed in September 2018, and production storage implementation completed in May 2019. Project close is scheduled for June 2019.
Q4 17-18 | Metropolitan Fire and Emergency Services Board | MFESB | 2244 | Mobile Data for Vehicles Pilot | Emergencies and Safety | Communication | Pilot project of mobile data devices installed in fire appliances to receive and display relevant event information. | Delivery |  | MFB Project Management Framework (PME) | 2015-07-01 | 2016-02-04 |  | 2016-02-04 | 0 |  | 2016-02-04 | 2016-02-04 | 2017-06-30 | 2018-09-28 | 1750000 | 2092000 | Green | Amber | Amber | Amber | Amber | 95 per cent of training has now been completed. Sign-off on a number of Maintenance & Support Agreements and formal hand over of IT support is still to be completed.
Q4 17-18 | Monash Health | Monash H | 2247 | Electronic Medical Record | Health | Records Management | Implementation of an Electronic Medical Record (EMR) system, including clinical documentation, results viewing, and medications management | Delivery |  | PRINCE2 | 2016-01-01 | 2016-02-01 |  | 2016-01-01 | 0 |  | 2017-08-01 |  | 2019-12-31 |  | 57700000 |  |  |  | Green | Green | Green | Current state review completed. Design currently in progress. Program tracking as planned.
Q4 17-18 | Peninsula Health | PEN Health | 2253 | Rostering Time & Attendance | Health | Human Resources | Enterprise electronic Rostering system | Delivery |  | Adaption of Prince II in conjunction with Vendors PM Planning | 2015-05-01 | 2015-12-31 |  | 2015-12-31 | 566654 | 569834 | 2015-12-31 | 2015-12-31 | 2017-10-15 | 2018-08-31 | 1847451 | 1327617 | Amber | Green | Green | Green | Green | Delivery against revised Milestones continuing.
Q4 17-18 | Peninsula Health | PEN Health | 2254 | Electronic Health Record - Clinical Documentation | Health | Records Management | Clinical Documentation | Delivery |  | Adaption of Prince II in conjunction with Vendors PM Planning | 2016-10-01 | 2016-11-15 |  | 2016-11-15 | 200000 | 0 | 2017-02-20 | 2017-02-20 | 2018-03-28 | 2018-09-06 | 2500000 | 4052449 | Green | Amber | Green | Green | Green | Progressing to plan.
Q4 17-18 | Victorian Ports Corporation Melbourne | VPCM | 2262 | Vessel Traffic Services Systems Upgrade | Transport and Vehicles | Communication | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | Initiated |  | VPCM (PMBoK) | 2015-12-03 | 2017-06-09 | 2018-09-28 |  | 0 | 251394 | [11 empty] | The pre-implementation phase of the project is nearing completion with tender evaluation in the process of being finalised. The implementation phase of the project is currently scheduled to commence early in Q2 of FY 2018/19, and forecast for completion late 2019.
Q4 17-18 | Public Record Office Victoria | PROV | 2263 | Digital Archive Program | Government and Economy | Content Management | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | Delivery |  | Hybrid - Agile and PRINCE2 | 2015-07-01 | 2015-07-01 |  | 2015-07-01 | 200000 |  | 2015-07-01 | 2015-07-01 | 2018-06-30 | 2019-03-31 | 4062000 |  | Green | Green | Amber | Green | Green | Currently on track to meet revised implementation date of early 2019 based on previous quarter update noting rebaseline due to procurement delays.
Q4 17-18 | Victoria Police | VicPol | 2265 | BlueConnect - Mobile Technology | Law and Justice | Collaboration ,Data Management | Handheld, mobile devices to put critical information into the hands of frontline police and allow them to feed it back into the organisation’s intelligence from the field. | Delivery |  | PRINCE2 | 2015-11-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 |  | 2021-06-30 | 2019-06-30 | 95185400 | 117757400 | Amber | Red | Amber | Amber | Amber | The project remains on target to complete rollout of 9100 devices by 30 June 2019.
Q4 17-18 | Public Transport Victoria | PTV | 2271 | Vehicle Passenger Information System (VPIS) A & C Class | Transport and Vehicles | Communication | Procure and implement a system using commercial-off-the-shelf (COTS) products to provide reliable and dynamic on-tram passenger information. | Closed - Completed | 2018-06-04 | PTV Investment Lifecycle | 2015-05-01 | 2016-02-29 |  | 2016-02-29 | 0 |  | 2016-02-29 |  | 2017-05-30 | 2018-05-29 | 8732000 | 10160000 | Amber | Amber | Green | Green | Green | Project reached practical completion on 4 June 2018.
Q4 17-18 | Public Transport Victoria | PTV | 2275 | Train Control Monitoring System (TCMS) for South Morang and Hurstbridge | Transport and Vehicles | Systems Management | To deliver a modern Train Control Monitoring System 'instance' at Epping to replace the standalone WESTCAD and SIGVIEW workstations and to support more efficient train control operations on the South Morang and Hurstbridge lines. | Postponed | 2018-04-30 | PTV Investment Lifecycle | 2016-10-21 | 2016-10-21 |  |  | 50000 | [12 empty] | The project is currently on hold. MMRA have transferred initial funding ($5.94m) to PTV which is insufficient to deliver the proposed scope. PTV is therefore proposing to use a portion of this funding to develop a business case for submission in the 2019/20 budget cycle to identify the full scope, benefits and additional funding required to deliver the TCMS South Morang and Hurstbridge project.
Q4 17-18 | Public Transport Victoria | PTV | 2276 | PTV Intranet Update | Transport and Vehicles | Communication | Redesign and review/develop/migrate content from PTV's existing intranet to a new cloud-hosted solution in order to enhance capability for collaboration, information and knowledge management. | Closed - Completed | 2018-04-24 | PTV Investment Lifecycle | 2016-10-21 | 2016-10-21 |  | 2016-10-21 | 342812 |  | 2017-10-04 | 2017-10-04 | 2018-03-08 | 2018-04-10 | 1161406 |  |  |  | Green | Amber | Green | The new intranet was successfully launched on Tuesday 24 April 2018. Project has reached practical completion and is finalising decommissioning of old intranet and close out activities.
Q4 17-18 | Public Transport Victoria | PTV | 2278 | myki and PTV Website Integration and Development | Transport and Vehicles | Development and Integration | The project will include a complete website redesign focused on user experience and integration of the myki portal and the PTV website. | Delivery |  | PTV Investment Lifecycle | 2015-12-16 | 2016-10-21 |  | 2016-10-21 | 200499 |  | 2016-10-21 | 2016-10-21 | 2017-11-08 | 2019-06-27 | 3634100 | 6999501 | Green | Green | Amber | Red | Green | Project was rebaselined on 19 June. The first version of the PTV Beta website went live in Q2 2018 and includes additional mapping functionality, design updates, improved disruption information and much more. PTV has received both positive & constructive feedback that is currently being assessed in order to deliver an improved experience on the final version of the new website. Work is now underway to integrate fare estimation and myki management which will be rolled out in 2019.
Q4 17-18 | Victoria Police | VicPol | 2279 | BlueConnect - Intelligence Management | Law and Justice | Content Management,Data Management,Knowledge Management | A new intelligence capability to bring together Victoria Police’s multiple data sources to deliver quick, easy access to intelligence to better inform police. | Delivery |  | PRINCE2 | 2015-07-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 |  | 2021-06-30 | 2019-06-30 | 103304700 |  | Green | Amber | Amber | Amber | Amber | The project is on track to deliver its full functionality by 30 June 2019. The overall project status is rated Amber given the short term targets being under pressure. Mitigations are in place to address these issues.
Q4 17-18 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2280 | ICT Redevelopment Stage 3 Hardware Tender | Health | Systems Management | Fit-out of new IT infrastructure to support hospital redevelopment objectives | Delivery |  | PRINCE2 | 2013-07-01 | 2014-06-30 |  | 2014-06-30 | 0 |  | 2014-06-30 | 2014-06-30 | 2018-12-31 | 2020-03-31 | 1180000 |  | Green | Green | Green | Green | Green | Project progressing to schedule
Q4 17-18 | Victoria Police | VicPol | 2283 | Body Worn Camera (BWC) | Law and Justice | Collaboration ,Development and Integration | Victoria Police will procure and deploy BWCs capable of capturing direct and objective audio and video face-to-face interactions, in an operational context between police members and the public, and real-time capture of video evidence of the scene of an incident. | Delivery |  | PRINCE2 | 2015-07-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 |  | 2021-06-30 | 2020-06-30 | 42643000 |  | Amber | Amber | Amber | Amber | Amber | Phase 1 of the project (Pilot) is progressing to schedule for a successful Pilot commencement by the end of April 2018. The overall health of the project remains AMBER due to the tight delivery schedule.
Q4 17-18 | South East Water | SE Water | 2284 | Trade Waste Information System | Environment and Water | Assets/Materials Management | The project will deliver a new solution for South East Water to manage our Trade Waste business. This new solution replaces a VB6 application and will enhance customer service by enabling mobility and improved analytical reporting | Delivery |  | Agile | 2014-09-15 | 2018-03-20 | 2018-05-30 | 2018-03-30 | 0 | 800000 | 2018-04-02 | 2018-05-31 | 2018-12-18 | 2020-12-28 | 0 | 4000000 | Amber |  |  |  | Green | Options with timings and approach have been reviewed internally. Steering committee has approved to progress to RFT to select a solution partner. RFT responses have been submitted and scoring is underway.
Q4 17-18 | Transport Accident Commission | TAC | 2286 | Claims Business Model | Transport and Vehicles | Customer Initiated Assistance | The Claims Business Model program of work aims to deliver solutions that enables balance between claims management effort and liability management across the business, and through that, empowering clients , making it easier to work with the TAC, and improving the efficiency of the management of claims. | Closed - Completed | 2018-04-12 | PRINCE2 | 2013-11-01 | 2014-06-30 |  | 2014-06-30 | 704927 |  | 2014-06-30 |  | 2018-06-30 |  | 39290751 | 54295073 | Green | Green | Amber | Green | Green | The project is complete and came in on budget.
Q4 17-18 | Victorian Auditor-General's Office | VAGO | 2290 | ERP Solution Replacement | Government and Economy | Financial Management | Replace aging Components of existing ERP solution and provide additional functionality. | Initiated |  | Agile | 2016-09-02 | 2018-05-01 | 2018-12-01 |  | 0 | [12 empty] | WoVG ERP and Finance platforms have been awarded to SAP and Oracle respectively. VAGO is now reviewing these new options with DPC and DTF before confirming final solution
Q4 17-18 | VicRoads | VicRoads | 2291 | ICT/ITS Infrastructure Transformation Program (Switch Program) | Transport and Vehicles | Systems Management,Security Management | This project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support VicRoads current and future ICT and Intelligent Transport System requirements. | Delivery |  | PRINCE2 | 2016-05-09 | 2017-08-17 |  | 2017-08-17 | 1250634 |  | 2017-08-17 |  | 2020-02-28 |  | 7649366 | 16609366 |  | Green | Green | Green | Green | Project is on track. ICT Workplace productivity uplift and remote access upgrade projects have been merged with this project. Design completed and build process continues and migration planning has commenced.Work to re-design the fiber connectivity for the Freeway Management System (FMS) was completed. This provided the full scope of work required for connectivity of ITS systems within the target infrastructure environment. VicRoads has approved funds to undertake the establishment of required network connectivity for FMS and this work is nearing completion allowing the transition of ITS systems from the current data centre into VicRoads new hosting environment. Alpha pilot completed for email and calendar. Business pilot is about to commence.
Q4 17-18 | Department of Premier and Cabinet | DPC | 2306 | Service Victoria | Government and Economy | Customer Initiated Assistance | Service Victoria will create a new whole of government service capability to enhance the delivery of government transactions with citizens, enable the delivery of a more effective customer experience and create new distribution channels for simple, high volume transactions. | Closed - Completed | 2018-06-30 | Waterfall and agile methodologies used. | 2015-07-01 | 2017-06-30 |  | 2017-06-30 | 0 |  | 2017-06-30 |  | 2018-06-30 |  | 96100000 |  | Green | Green | Green | Green | Green | Service Victoria has helped make government transactions faster, simpler and easier. In 2017-18 the Department of Premier and Cabinet completed the development of Service Victoria, the inaugural, dedicated customer service delivery agency. The initial three-year program was completed on time and under budget.
Q4 17-18 | Public Transport Victoria | PTV | 2308 | Regional Radio Communications Network | Transport and Vehicles | Assets/Materials Management | The project involves modernisation of the following legacy systems; the train control centre (Centrol) Voice Communications Systems (VCS); the In-cab Communications Equipment (ICE) in the V/Line fleet; and the voice communications network service. | Delivery |  | PTV Investment Lifecycle | 2012-03-01 | 2014-02-27 |  | 2014-02-27 | 7250000 |  | 2014-02-27 | 2014-02-27 | 2018-04-03 | 2020-06-30 | 47104000 |  | Amber | Green | Green | Amber | Green | The Project is largely complete with the RRCN/DTRS integration being the last major activity. The forecast practical completion date has been revised in line the Network Configuration Working Group and the RRCN Project Steering Committee approvals to end June 2020. There are no budget issues to report.
Q4 17-18 | VicRoads | VicRoads | 2309 | Sydney Coordinated Adaptive Traffic System (SCATS) Connectivity Migration Project | Transport and Vehicles | Systems Management | Supply, Install and Manage the communication service for all the Managed Traffic Signal Sites. Supply, Install and provide a communication service for all unmanaged Traffic Signal Sites. | Delivery |  | PRINCE2 | 2016-09-01 | 2017-06-15 |  | 2016-05-31 | 1000000 |  | 2017-06-16 | 2017-06-16 | 2018-02-16 | 2018-12-07 | 5500000 |  | Green | Green | Amber | Green | Green | Handover activities and additional site implementation approved by the project authority is ongoing and will be completed by December 2018.
Q4 17-18 | VicRoads | VicRoads | 2310 | CityLink Tullamarine Widening (CTW) Section 3 Project | Transport and Vehicles | Development and Integration | This project includes the upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals). It provides integration, testing, and configuration of ITS devices to communication network and control systems and upgrade of backend systems and infrastructure to support the managed motorway. | Closed - Completed | 2018-06-10 | PRINCE2 | 2015-10-01 | 2016-03-01 |  | 2016-04-01 | 238683 |  | 2016-04-01 | 2016-04-01 | 2017-12-31 | 2018-06-30 | 12591000 |  | Green | Green | Green | Green | Green | Project successfully completed as per schedule.
Q4 17-18 | VicRoads | VicRoads | 2311 | CityLink Tullamarine Widening (CTW) Section 1 & 2 Project (M80 Upgrade ) | Transport and Vehicles | Development and Integration | This project includes the integration, testing and configuration of ITS devices to communication network and backend control systems, provide upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals) and infrastructure to support the managed motorway. | Delivery |  | PRINCE2 | 2016-07-01 | 2017-07-01 |  | 2016-05-01 | 0 |  | 2017-08-01 |  | 2018-12-30 |  | 2400000 |  |  | Green | Green | Green | Green | Project is on track. ICT component of the project is complete. Dynamic speed management system is under planning stage.
Q4 17-18 | VicRoads | VicRoads | 2312 | Dynamic Variable Speed Limit (DVSL) Project - Phases 2 & 3 | Transport and Vehicles | Development and Integration | The development of a new DVSL system integrated with Coordinated Ramp Signal and Lane Use Management System to maximise freeway capacity, minimise flow breakdown and improve traffic safety in congested conditions. | Initiated |  | PRINCE2 | 2016-06-30 | 2018-07-01 |  | 2018-07-01 | 0 | [12 empty] | Project is on track. Procurement activities are being planned.
Q4 17-18 | Victorian Building Authority | VBA | 2319 | Business Systems Transformation | Government and Economy | Customer Relationship Management | The BST program is intended to progressively re-engineer VBA regulatory processes and implement new integrated applications which will replace legacy systems and manual processes, to: mitigate technology risk, enhance risk based regulation, reduce regulatory burden, increase efficiency and reduced cost; and, improve consumer outcomes | Delivery |  | Hybrid - Agile and PRINCE2 | 2014-10-01 | 2016-06-30 |  | 2016-06-30 | 986248 |  | 2016-06-30 |  | 2019-07-01 | 2019-07-01 | 12375133 | 14096950 | Green | Green | Green | Green | Green | Due to several legislative reforms being introduced and the VBAs rapidly evolving operating environment the BST program has been reviewed. The VBA Board and CEO approved the withdrawal of the BST R2 tender from market. The BST project has adopted a phased approach based on a robust governance approach driven by business priorities. The VBA is now working on a new RFT targeting this phased approach; Phase 1 will be the Building Activity Management System due to be implemented on 1 July 2019 in line with legislative reforms. This phase focusses on the replacement of the building Permit Levy System which will require the VBA to allocate building permits. The BST Release 1 (VBA360) remains in use and successfully utilized by both internal and external stakeholders.
Q4 17-18 | Victorian Registration and Qualifications Authority | VRQA | 2323 | EPSILON | Education | Customer Relationship Management | The EPSILON project will replace the existing legacy system "DELTA" to enable VRQA to meet its legislative obligations with respect to apprentices and trainees. | Delivery |  | PRINCE2 | 2014-07-07 | 2016-02-29 |  | 2016-02-29 | 373000 |  | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2019-03-18 | 2310749 | 4759042 | Red | Green | Green | Green | Green | The Commonwealth Department of Education and Training advised on 18th May 2018 that the Australian Apprenticeships Management System (AAMS) project had failed and was not progressing. Prior to this the Epsilon Project Board took a decision to re-design Epsilon to integrate with the Training and Youth Internet Management System (TYIMS) instead of AAMS, eliminating dependence on the AAMS Project. The Project Board has approved and submitted a Business Case for this change and budget is now being sought from the Department of Education (DET) to fund the necessary changes. The Epsilon project is targeting a go-live early in 2019 subject to receiving approval to proceed.
Q4 17-18 | Western Health | WH | 2325 | Western Health Electronic Medical Record (EMR) Project | Health | Customer Relationship Management,Management of Process ,Records Management | Implementation of the Statewide Electronic Medical Record (EMR) Solution to provide a clinical information system for the hospital | Delivery |  | PRINCE2 | 2014-12-01 | 2015-08-19 |  | 2014-12-01 | 0 |  | 2015-11-02 |  | 2018-12-31 |  | 19980000 |  |  |  | Green | Red | Amber | There are a number of issues that the organisation is actively addressing to enable the project to go live on schedule in November 2018.
Q4 17-18 | WorkSafe Victoria | WorkSafe | 2334 | Digital Claims File | Government and Economy | Tracking and Workflow | The electronic document management system which is currently used for Invoices and Certificates of Capacity will be expanded to include all other Claims File documents. | Closed - Completed | 2018-05-31 | PMBoK | 2015-07-01 | 2016-08-31 |  | 2016-08-31 | 1246158 |  | 2016-08-31 | 2016-08-31 | 2017-12-31 | 2018-04-30 | 4753842 |  | Green | Green | Green | Green | Green | Project closed.
Q4 17-18 | Department of Justice and Regulation | DJR | 2340 | Mobile Camera Replacement (MCR) Project | Law and Justice | Assets/Materials Management | MCR Project is the procurement of a replacement mobile camera system for the IMES business unit. The mobile camera system is the key component of the mobile camera service provided to the State by Serco Traffic Camera Services. | Delivery |  | Project Management Excellence | 2012-12-03 | 2014-02-19 |  | 2014-02-19 | 1568992.5 | 1568992 | 2014-02-19 | 2014-02-19 | 2015-12-21 | 2019-10-30 | 2826500 | 15531008 | Amber | Amber | Amber | Amber | Amber | The MCR Project is for the procurement of mobile road safety camera systems (MRSCS) to replace the current aging systems. The MRSCS program is the key component of services provided to the State by Serco Traffic Camera Services. The procurement of replacement MRSCS was recently finalised and contracts for the supply of cameras will be signed shortly. Project delivery has commenced and is expected to be completed in 2019.
Q4 17-18 | Department of Justice and Regulation | DJR | 2343 | Australian Communications and Media Authority (ACMA) Compliance | Emergencies and Safety | Communication | This project moves five agencies from their existing radio systems onto shared, multi-agency radio systems, in order for the agencies to comply with new ACMA regulations. The project also includes the procurement of new radio terminals and associated services under a state-based managed services contract. | Delivery |  | Project Management Excellence | 2013-07-01 | 2017-06-30 |  | 2017-06-30 | 4604445 |  | 2017-06-30 |  | 2019-05-19 |  | 20486000 | 40328170 |  | Green | Green | Green | Amber | Procurement design programming and delivery of: • 1402 radio terminals to Corrections Victoria for implementation across nine Correctional facilities and Security & Emergency Services Group (SESG) transport units commenced in June 2018 and is due for completion by end 2018; • 2364 radio terminals for the Victorian State Emergency Service. State-wide deployment will commence in July 2018 and is due for completion by November 2018; • 750 radio terminals for Life Saving Victoria - State-wide deployment commenced in June 2018 and is due for completion by April 2019; and • 3614 radio terminals for Victoria Police. Regional deployment commenced in June 2018 and is due for completion by November 2018. Additionally: • Procurement design and commencement of build activities enhancing the State’s regional mobile radio network provided by Telstra: The network upgrades have been occurring incrementally since February 2018 and are due for completion in May 2019; • The design build and training activities associated with the integration of enhanced radio communications with the 000 call-taking and dispatch centre (Emergency Services Telecommunications Authority) is complete. Minor delays in delivery have occurred putting some pressure on the schedule. Overall the project is still expecting to be complete by May 2019.
Q4 17-18 | Department of Justice and Regulation | DJR | 2344 | Births, Deaths and Marriages (BDM) Core System Replacement Project | Law and Justice | Systems Management | The replacement of the BDM core system will provide a scalable and robust design with enhanced functionality and migrated data. | Delivery |  | Project Management Excellence | 2013-10-01 | 2014-06-30 |  | 2014-06-30 | 1518095.36 |  | 2014-06-30 | 2014-06-30 | 2017-06-19 | 2018-09-30 | 13925000 | 20598000 | Green | Amber | Amber | Amber | Amber | Functional Acceptance Testing of solution is nearly complete and a large part of User Acceptance Testing has been completed successfully and Business Readiness is being conducted with BDM. Data cleansing and migration activities are ahead of schedule and numerous trial data migrations have been completed. A suitable go-live date is still being determined between the vendor and the business under direction of the Steering Committee.
Q4 17-18 | Department of Justice and Regulation | DJR | 2345 | CV-CATS-APB (Adult Parole Board) Case Workflow System | Law and Justice | Tracking and Workflow | The provision of an electronic database and case workflow system for the APB that aligns to a re-engineered set of business processes to deliver a significantly improved and enhanced user experience. | Delivery |  | Project Management Excellence | 2014-04-01 | 2015-11-20 |  | 2015-11-20 | 996219 |  | 2015-11-20 | 2015-11-20 | 2016-12-15 | 2018-10-31 | 3811985 | 22527630 | Amber | Green | Green | Green | Green | An original approved budget of $4.2 million was allocated in 2014. This underestimated the complexity in future Adult Parole Board (APB) processes and requirements, to deliver a new case workflow system. A new project and budget approach was subsequently approved. This established the delivery of the Callinan Review Measure into a three phased project, to deliver the new system. The 3 phases of the project: Phase 1: Completed in December 2015. Phase 2: Completed in October 2017 Phase 3: On track for delivery in October 2018. Project completion date has been revised in line with the end of Phase 3.
Q4 17-18 | Department of Justice and Regulation | DJR | 2348 | Prisoner Transport Order System (PTOS) | Law and Justice | Customer Relationship Management | The PTOS Project will deliver an integrated transport order and information management system for implementation across Corrections, Police and DHHS to provide transport orders to the contractor and management information for all prisoner transports. | Delivery |  | Project Management Excellence | 2014-11-04 | 2014-12-04 |  | 2014-12-04 | 180000 |  | 2014-12-04 | 2014-12-04 | 2016-09-05 | 2018-12-31 | 3761184 | 7540249 | Green | Green | Green | Amber | Amber | The Prisoner Transport Order System (PTOS) implementation was completed on 14 November 2017 across Corrections, Police, Youth Justice and transport contractor (G4S). The reporting component, PTOS-BI (Business Intelligence), is outstanding however this has no impact on prisoner transport itself. The PTOS-BI component is not part of the operational prisoner transport system but will provide a tool to analyse data on prisoner transports being conducted by Victoria Police, Corrections Victoria and the contractor, G4S. This is now performed manually. The development of the PTOS-BI function was outsourced however will be transferred to the Corrections Victoria Information Technology (CVIT) branch for CV to assume direct responsibility for delivery. The transfer is expected to be completed in July 2018, at which time CVIT will develop a delivery schedule. It is anticipated that development of PTOS BI reporting will be completed by the end of 2018.
Q4 17-18 | Department of Justice and Regulation | DJR | 2352 | Community Correctional Services (CCS) Accommodation Expansion Program | Law and Justice | Knowledge Management | IT fitout for sites being constructed or modified to accommodate additional staff for Community Correctional Services (CCS) and other business units across Victoria. The number of sites requiring IT treatment has been confirmed as 49 sites. | Delivery |  | Project Management Excellence | 2015-07-29 | 2016-01-18 |  | 2016-01-18 | 88043 |  | 2016-01-18 |  | 2016-12-30 | 2019-06-30 | 2610975 | 6895000 | Green | Green | Green | Green | Green | 26 sites successfully delivered up to 30 June 2018. Project is expected to deliver 5 sites in the 6 months to December 2018, and a further 4 sites by June 2019.
Q4 17-18 | Department of Justice and Regulation | DJR | 2353 | Police Digital Radio Upgrade Project ('PDRUP') | Emergencies and Safety | Communication | Migrate Victoria Police outside of the metro (MMR network) area from the legacy (analogue unencrypted) radio network (StateNet Mobile Radio ('SMR')) to the new (digital and encrypted) network (Regional Mobile Radio ('RMR')) | Delivery |  | Project Management Excellence | 2015-09-07 | 2016-01-14 |  | 2016-01-14 | 0 |  | 2016-01-14 |  | 2017-08-07 | 2018-11-30 | 14100000 | 35500000 | Green | Green | Green | Green | Green | The Regional Mobile Radio (RMR) Network contract has been executed. Procurement design and configuration activities are progressing. The digital radio network upgrade to regional police is on track with the roll-out expected to be complete by the end of October, and encryption switched on in November 2018.
Q4 17-18 | Department of Justice and Regulation | DJR | 2354 | New Infringements ICT System | Law and Justice | Management of Process | The ICT component of the program involves the procurement of an end-to-end commercial off-the-shelf (COTS) system to replace its current legacy infringement management system, VIMS, addressing all changes under the Fines Reform Act (2014). | Delivery |  | Project Management Excellence | 2015-10-27 | 2016-08-31 | 2017-12-31 | 2016-08-31 | 0 |  | 2016-08-31 | 2016-08-31 | 2017-12-31 | 2019-02-28 | 43054000 | 57400000 |  | Amber | Amber | Amber | Amber | The first stage implementation of the VIEW System took place on 31 December 2017. Negotiations with the State's service provider are underway regarding the scheduling of Phase 2. Current discussions with service provider indicate that Phase 2 will be delivered in early 2019.
Q4 17-18 | Department of Health and Human Services | DHHS | 2355 | Parkville Precinct Electronic Medical Record | Health | Development and Integration | Implementation of an Electronic Medical Record into Melbourne Health, Peter MaCallum Cancer Centre and The Royal Women's Health Services. | Initiated |  | PRINCE2 | 2016-07-01 | 2018-06-01 |  | 2018-06-01 | 0 | [12 empty] | Following confirmation of project funding in May 2018, the project is moving out of initiation phase and into establishment and planning for delivery.
Q4 17-18 | Department of Justice and Regulation | DJR | 2357 | Emergency Alert Phase 4 - Delivery | Emergencies and Safety | Communication | Secure service continuity and delivery of a national telephony based emergency warning system, ensuring a more sustainable EA service: a service that remains up to date and relevant to community use and demand, maintains an acceptable performance standard and incurs minimal capital expenditure and cost surprises. | Initiated |  | Project Management Excellence | 2016-05-06 | 2016-05-06 | 2018-06-30 |  | 0 | [12 empty] | Due to a failed market tender process in August 2017, the project has been delayed by approximately 14 months and is at a critical stage. A second market approach in March 2018 failed to obtain an offer within the budget estimates - as a result, jurisdictions are discussing alternative funding sources. The resolution of these issues will determine the next phase of the project.
Q4 17-18 | Barwon Region Water Corporation | BR Water | 2363 | Customer Relationship Management System | Environment and Water | Customer Relationship Management | Current customer systems are disparate and no longer meet business needs and expectations. This project's objective is to implement a CRM Solution to replace a suite of existing solutions, enabling improved levels of service, greater efficiency in service provision and deliver digital customer transformation. | Initiated |  | PMBoK | 2016-11-01 | 2016-11-01 | 2017-04-30 | 2016-11-01 | 0 | [12 empty] | Project initiation is being finalised. There has been no change to the status of this project nor any incurred costs.
Q4 17-18 | Chisholm Institute of TAFE | Chisholm TAFE | 2364 | Network Refresh | Education | Assets/Materials Management | To refresh and improve the network infrastructure to improve functionality, availability and security | Delivery |  | Chisholm PMF (Prince 2 Based)\nBusiness Case Approved and Tender Documentation Completed and Reviewed. | 2016-11-01 | 2016-11-01 |  | 2017-12-31 | 300000 |  | 2018-03-01 |  | 2019-12-31 |  | 9700000 |  |  |  |  | Green | Green | On track
Q4 17-18 | Chisholm Institute of TAFE | Chisholm TAFE | 2365 | Systems Integration | Education | Development and Integration | To improve productivity, data integrity, functionality and reduction in operating costs | Delivery |  | Chisholm PMF (Prince 2 Based)\nBusiness Case Approved.\nAnalysis and Discovery Phase - in progress. | 2016-11-01 | 2017-07-31 |  | 2017-07-31 | 45000 |  | 2017-07-31 |  | 2018-12-31 |  | 1155000 |  |  | Green | Green | Green | Green | Due to a number of dependencies and competing priorities, a requirement for additional resources has been identified and is being sourced.
Q4 17-18 | Chisholm Institute of TAFE | Chisholm TAFE | 2366 | Migration to Cloud | Education | Security Management | To migrate the on-site server environment to cloud services to improve availability, improve security, reduce risk and reduce operating costs. | Delivery |  | Chisholm PMF (Prince 2 Based)\nBusiness Case Approved. | 2016-11-01 | 2017-06-30 |  | 2017-06-30 | 119428 |  | 2017-06-30 |  | 2018-12-31 |  | 1080572 |  |  | Green | Green | Green | Green | Project is on target
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2367 | Business System Support Reporting - HCM and Payroll Implementation | Employment and Workplace | Financial Management | Replatform of existing HCM/Payroll solution to a cloud based system for DELWP to align with WoVG strategy. | Delivery |  | PRINCE2 | 2016-11-03 | 2016-11-03 | 2017-02-28 | 2017-12-19 | 1450000 |  | 2018-02-01 |  | 2019-02-28 |  | 8861300 |  |  |  |  | Green | Amber | Project schedule pressure resulting from testing phase and multiple test streams running in parallel. Risks and issues have been identified and are being managed through the project governance control mechanisms. Project budget and scope is being managed within agreed project tolerance.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2369 | Smart Planning - Planning Portal | Property and Planning | Content Management | The Planning Portal Project will provide an easily identifiable web-based entry point for the community and government to access a comprehensive and integrated set of planning policies, legislation, planning scheme information, guidelines and services. Introduced as part of the 2016-17 Victorian Budget | Delivery |  | PRINCE2 | 2016-07-01 | 2017-09-25 |  | 2017-09-25 | 396430 | 454174 | 2017-09-25 | 2017-10-23 | 2018-06-30 | 2019-03-27 | 1475609 | 1375203 |  | Green | Green | Green | Amber | Portal project is currently redesigning and rescheduling including the solution for Planning Schemes and Histories due to change in rollout approach to councils. and design review of Simple Interactive Map .
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2370 | Planning Scheme Information Management System | Property and Planning | Content Management | The system will support the full amendment life-cycle from creation to Gazettal. The project is phased over two stages. The first will see production use by internal areas (DELWP and Panels Victoria) and the second stage will be used by pilot councils. Introduced as part of the 2016-17 Victorian Budget | Delivery |  | PRINCE2 | 2016-07-01 | 2016-07-01 | 2017-01-02 | 2017-01-08 | 4035793 |  | 2018-01-01 | 2018-01-01 | 2018-04-27 | 2018-09-03 | 3424386 | 3382000 |  |  |  | Red | Green | The project will be complete on September 3rd 2018.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2371 | Smart Planning Online Permits | Property and Planning | Management of Process | Pilot the online lodgement of Planning Permit applications. This includes refreshing the Greenlight applicant and register interface and integrating the Departments WestPac payment gateway for online payments. Introduced as part of the 2016-17 Victorian Budget | Delivery |  | Hybrid - Agile and PRINCE2 | 2016-07-01 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 566687 | 1105996 | 2017-09-11 | 2017-12-06 | 2018-06-30 | 2018-08-17 | 3591152 | 3331343 |  | Green | Green | Amber | Amber | Heritage Design was delayed but completed in this period. Ministerial Permits testing on track with go live due 17/8/18
Q4 17-18 | Department of Education and Training | DET | 2373 | Victorian Training Information System (VTIS) | Education | Management of Process | This project is to replace the Skills Victoria Training System (SVTS). This project was previously known as HESG IT Business System Replacement. | Delivery |  | PRINCE2 | 2015-02-23 | 2017-03-30 |  | 2017-03-30 | 1910590 |  | 2017-03-30 | 2017-03-30 | 2018-01-31 | 2018-08-22 | 15821697 | 26738090 | Red | Red | Amber | Amber | Amber | The Project has reached its second milestone, enabling the commencement of User Acceptance Testing for the first component of the new solution. In response to the issues raised in the last reporting period, the Department has continued its efforts to collaborate with the Vendor to ensure the remaining milestones will be delivered to achieve the Business outcomes. In addition, the Project is now validating the Go Live approach for the new system, in line with the delivery progress, and the expected impacts to the internal Stakeholders and the Registered Training Organisations.
Q4 17-18 | Department of Health and Human Services | DHHS | 2376 | Immunisation Provider System (ImPS) Replacement | Health | Data Management | Implementation of a computerised solution to allow local governments and other stakeholders in Victoria to manage local immunisation programs including vaccine stock control and data reporting. | Closed - Terminated | 2018-06-30 | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | 2015-02-05 | 2015-04-30 |  | 2015-04-30 | 0 |  | 2016-07-01 |  | 2018-06-30 |  | 1000000 |  |  |  | Amber | Amber | Green | Project closed and not proceed to implementation in its current form.
Q4 17-18 | Department of Health and Human Services | DHHS | 2377 | Modelling and Payments System (MAPS) | Health | Financial Management | Replacement for the budget modelling, payments and National Health Reform reporting platforms - the Budget and Payments System Modeller (BPS Modeller), the Budget and Payments System (BPS) and the National Health Funding Body Payments System (NHFBPS) - with an integrated, single solution. | Delivery |  | PRINCE2 | 2016-05-23 | 2016-06-07 |  | 2016-06-07 |  |  | 2016-06-07 | 2016-06-07 | 2017-08-09 | 2018-08-31 | 2856060 |  | Amber | Amber | Green | Amber | Green | System has successfully been delivered. Project close activities underway.
Q4 17-18 | Department of Justice and Regulation | DJR | 2378 | Hosting Services Project | Law and Justice | Content Management | SecureWorx currently provides a number of hosting services for DJR. The provision of hosting services is an ongoing requirement for a number of key applications within Corrections Victoria (CV). The project will manage the procurement and transition of hosting, monitoring, disaster recovery, penetration testing and performance testing services for CV. | Delivery |  | Project Management Excellence | 2016-06-15 | 2017-01-31 | 2018-01-31 | 2018-02-01 | 0 | 941800 | 2018-02-02 |  | 2018-10-31 |  | 4250000 |  |  |  |  | Green | Green | The project has carried out a detailed market assessment that established a greater value for money and conformance to requirements, compared to that of the current contracted hosting arrangements. A formal RFT was conducted and a recommended vendor was selected. Contracts were executed in February 2018. The delivery phase started February 2018 and is expected to end by October 2018 for the selected, in-scope CV applications.
Q4 17-18 | Goulburn Valley Region Water Corporation | GVR Water | 2382 | Financial Management Information System | Environment and Water | Financial Management | Upgrade of Goulburn Valley Water's existing and aging financial management information system | Postponed | 2018-06-29 | Internal GVW Project Management Methodology | 2016-03-01 | 2017-03-31 |  | 2017-03-31 | 105567 |  | 2017-03-31 | 2017-03-31 | 2018-03-31 | 2019-02-28 | 1382285 | 1894433 | Green | Amber | Amber | Amber | Amber | GVW have placed this project on hold and are waiting results from an independent review to determine an appropriate path forward.
Q4 17-18 | Parks Victoria | PARKSVIC | 2387 | IT Infrastructure Refresh Program | Environment and Water | Systems Management | Technology Infrastructure replacement and modernisation program updating core IT infrastructure and associated services, network infrastructure, and end user devices. | Initiated |  | PRINCE2 | 2016-10-21 | 2018-06-29 |  | 2018-01-30 | 0 | 0 | [11 empty] | Overall Program schedule is 'On Track'. Initiation activities proceeding as planned and resourced by BAU. Core Infrastructure Refresh project is finalising procurement activities. Network Refresh project EOI activities have encountered slight delays with this stage of the procurement expected to conclude next quarter.
Q4 17-18 | Royal Children's Hospital | RCH | 2390 | Payroll Project | Health | Human Resources | Delivery of high quality, real-time and contemporary payroll end to end solution. The original Payroll and Rostering Project has been split into two projects; 1. Payroll project (this project) and 2. Rostering, Time and Attendance project. | Closed - Completed | 2018-06-30 | PRINCE2 | 2015-11-01 | 2016-10-18 |  | 2016-10-18 | 429523 |  | 2016-10-18 |  | 2018-06-30 |  | 4291695 |  | Green | Green | Green | Green | Green | Project completed.
Q4 17-18 | State Revenue Office | SRO | 2391 | LPR #2&3 - Land Ownership, NOAs and Land Usage Vicroads. | Government and Economy | Financial Management | This project is part of the Better Revenue Management System program to redesign the Land Tax administration business processes to achieve operational efficiencies, improve effectiveness of managing land ownership data (using Notice of Acquisition (NOA Data and Vicroads Data) and to extend the life of SRO's revenue management system. | Delivery |  | PRINCE2 | 2015-09-17 | 2016-09-30 |  | 2016-09-30 | 1505896 |  | 2016-09-30 | 2016-09-30 | 2018-04-13 | 2018-09-24 | 3881729 | 4017510 | Green | Amber | Green | Green | Green | Release 5 was successfully delivered in production on 22 January. This release delivered PEXA NOA and AVOKA integration. Work continued as scheduled on the remaining 3 releases 6 (VicRoads & Usage) 7 (Municipal Returns Data Part 1) and 8 (Quality Check and MRD Part 2). An exception report was produced in January to account for variations to costs for remaining releases and deferment of some of the scope of Release 7 to release 8. This was approved by the project board and programme management. Planned project delivery costs continue to track closely to the approved budget of $5.523M. The project delivery remains on track to be completed by the end of Q1, excepting the 1 month warranty period for the last release.
Q4 17-18 | Treasury Corporation of Victoria | TCV | 2392 | Treasury System Review | Government and Economy | Financial Management | Review of front office treasury software and resulting replacement | Closed - Completed | 2018-05-31 | PRINCE2 | 2016-11-16 | 2017-04-17 |  | 2017-04-17 | 205245 |  | 2017-04-17 | 2017-04-17 | 2017-12-31 | 2018-05-31 | 2363000 | 1904103 | Green | Amber | Green | Green | Green | The primary objective of implementing a new front office treasury system was completed in January 2018 while a related but not time critical sub-project was completed in May 2018 finalising the project.
Q4 17-18 | Emergency Services Telecommunications Authority | ESTA | 2395 | Multi-Agency Communications Gateway | Emergencies and Safety | Management of Process | Delivery of a common interface with ESTA's Computer Aided Dispatch (CAD) system to improve operational dispatch data flow between ESTA and the Emergency Services Organisations, particularly to facilitate mobile devices in the field. | Delivery |  | ESTA Project Management Methodology | 2016-05-01 | 2017-04-07 |  | 2017-04-07 | 600000 |  | 2017-04-07 |  | 2018-12-30 |  | 5000000 | 4400000 | Green | Green | Amber | Amber | Amber | First stage of the build is in production and the design for second stage of the build has been completed.
Q4 17-18 | CenITex | CenITex | 2396 | Operating System Upgrade Across Windows Fleet | Health | Assets/Materials Management | To upgrade servers in the customer environment to a supported server operating system | Delivery |  | PRINCE2 | 2016-02-08 | 2016-02-22 |  | 2016-02-23 | 0 |  | 2016-02-24 | 2016-02-24 | 2018-06-30 | 2019-06-30 | 3570000 |  | Green | Green | Green | Green | Amber | A series of migrations and decommissions were completed during the quarter. Ongoing investigations have identified several services that cannot be migrated as planned - alternative migration paths and timeframes need to be defined and agreed so a formal variation can be submitted to the PCB for approval, with the aim of completing all possible migrations in scope by end of FY 18/19. Project is still well within budget.
Q4 17-18 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2398 | Electronic Medical Record Project | Health | Customer Relationship Management,Knowledge Management ,Records Management | Implementation of further EMR modules to provide a clinical information system for the hospital. | Postponed | 2017-12-31 | PRINCE2 | 2016-08-01 | 2017-11-30 |  | 2017-11-30 | 50000 | [12 empty] | Project postponed until project funding confirmed
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2401 | Resource Rights Allocation and Management (RRAM) Enhancement Project | Government and Economy | Data Management,Management of Process | RRAM is used by the earth resources regulator (ERR) and the industry to administer and regulate mining and petroleum tenement activities in Victoria. The project aims to deliver enhancements to RRAM's functionality and application by the regulator and industry. | Initiated |  | PRINCE2 | 2017-01-01 | 2018-12-31 | 2018-08-08 |  | 0 | [12 empty] | The key activities undertaken in quarter 4 were: (1) finalise the business process; (2) establish a business support team; (3) appoint a project manager; (4) rebuild the project team; and (5) review the system architecture.
Q4 17-18 | Department of Education and Training | DET | 2402 | Youth Engagement System | Education | Management of Process | An integrated IT solution which will capture data on disengaged students and students in out-of-home care. It will provide a more comprehensive picture of these key cohorts to ensure they receive the support they need to achieve educational success. | Delivery |  | PRINCE2 | 2016-10-03 | 2017-06-29 |  | 2018-06-29 |  |  | 2018-06-29 |  | 2018-12-01 |  | 1787139 | [5 empty] | Amber | Core system solution design and development has been completed. Planned procurement for specialist integration suppliers has been delayed due to technical issues related to data integration. These issues are currently being investigated.
Q4 17-18 | Department of Treasury and Finance | DTF | 2404 | ERP - Financial System | Government and Economy | Financial Management | DTF are replacing its legacy Finance and procurement systems | Delivery |  | PRINCE2 | 2017-01-01 | 2018-01-31 | 2017-12-20 | 2017-12-20 | 550000 |  | 2018-01-01 |  | 2018-10-08 |  | 5250000 |  |  |  |  | Amber | Amber | The Project is on track, however a series of workshops are being conducted with SMEs to review the design and seek endorsement which are being finalised. After SME's endorsement approval workshops will be undertaken with DPC and DTF CFOs.
Q4 17-18 | Eastern Health | EH | 2405 | Eastern Health - PCMS Project | Health | Customer Relationship Management | Replacement of five (5) existing Patient Administration Systems with the Patient and Client Management System (PCMS) solution. | Delivery |  | HTS PCMS Implementation Methodology | 2016-08-22 | 2017-06-30 |  | 2017-06-30 | 634225 |  | 2017-06-30 | 2017-06-30 | 2018-12-31 | 2019-12-31 | 12038173 |  | Green | Green | Green | Amber | Red | A major dependency of retesting and reintegration of the Electronic Medical Record with the Patient and Client Management System has been realised and an additional 12+ months of work is required that had been unforeseen. An increase to planned project costs is required to fund the additional work effort and extended time frame. Eastern Health is progressing activity to identify potential funding sources.
Q4 17-18 | Eastern Health | EH | 2406 | Eastern Health - Angliss and Maroondah Hospitals Emergency Department IS Replacement | Health | Customer Relationship Management | Emergency Department information system replacement at Angliss and Maroondah Hospitals. | Delivery |  | Cerner Consulting Framework | 2016-10-10 | 2017-03-30 |  | 2017-03-30 | 366750 |  | 2017-03-30 | 2017-03-30 | 2018-06-30 | 2019-06-30 | 1725550 |  | Green | Green | Green | Amber | Amber | Work continues in the project planning and preparation activities for the project. The project has remained amber due to the suspension of the proposed go-Live dates pending confirmation of the readiness of the application for use at Angliss and Maroondah Hospital. The Steering Committee is considering new go-Live dates.
Q4 17-18 | Melbourne Polytechnic | MelbPoly | 2407 | Network Modernisation (WAN) | Education | Communication | Development of a high speed wide area network for interconnecting Melbourne Polytechnic Tech School campuses at Epping and Greensborough | Delivery |  | PMBoK | 2017-01-30 | 2018-03-26 | 2017-09-25 | 2017-09-25 |  |  | 2017-09-26 | 2017-09-26 | 2018-05-31 | 2018-08-31 | 1589000 |  |  |  |  | Green | Green | Installation completed as scheduled. Production WAN in place between the two Tech Schools at Epping and Greensborough campuses. The network will be activated when building construction works complete at the two sites. The project end date has been revised to incorporate the post-delivery phase for proper closure of the project.
Q4 17-18 | Northern Health | NH | 2411 | EMR Project-EMR Readiness phase | Health | Analyses and Statistics ,Collaboration ,Communication,Organisational Management ,Records Management | Implementation of an Electronic Medical Record at Northern Health including all sites | Initiated |  | PRINCE2 | 2016-10-18 | 2018-05-01 | 2019-05-06 |  | 0 | 4130000 | [11 empty] | EMR funding for 2017/2018 was unsuccessful. Feedback has been sought. Continue to prepare NH for an EMR through current state analysis actvities and review of current ICT clinical applications. An options analysis is underway in relation to EMR vendors and prefered approach to EMR for Northern. This will inform a revision of the business case for re submission.
Q4 17-18 | Peter MacCallum Cancer Centre | Peter MAC | 2412 | Radiotherapy Treatment Planning System | Health | Tracking and Workflow | Implementation of a new centralised Treatment Planning System at Peter Mac’s main Parkville site and satellite campuses. | Delivery |  | PRINCE2 | 2016-12-07 | 2017-02-07 |  | 2017-02-07 |  |  | 2017-02-22 |  | 2018-09-24 |  | 5118235 |  |  |  | Green | Green | Green | Project in execution phase.
Q4 17-18 | VicRoads | VicRoads | 2413 | Fines Reform Project | Transport and Vehicles | Development and Integration | Fines Reform is a mandatory legislative project driven by the Department of Justice and Regulation’s Infringement Management Enforcement Services. VicRoads must implement a range of system and business process changes in order to meet its legislative obligations. | Delivery |  | PRINCE2 | 2017-01-09 | 2017-06-15 |  | 2016-12-12 | 200000 |  | 2017-01-09 | 2017-01-09 | 2018-03-30 | 2018-10-01 | 4102616 | 4200000 | Amber | Amber | Amber | Amber | Amber | VicRoads has delivered its system changes on 31/12/17. However, the overall project status is amber as issues remain regarding DJR's new Civica system readiness. VicRoads is seeking advice from DJR on when the outstanding Fines Reform scope might be ready for implementation. Based on preliminary discussion with DJR, forecast completion is revised to the 29th of March 2019.
Q4 17-18 | Yarra Valley Water | YV Water | 2416 | Trade Waste Management system | Environment and Water | Assets/Materials Management | Create a new system for managing sewer quality and trade waste agreements | Delivery |  | Agile | 2016-05-04 | 2016-11-30 |  | 2016-11-30 | 404714 |  | 2016-11-30 |  | 2018-07-18 | 2019-03-28 | 2006304 | 3290286 | Green | Green | Green | Green | Green | Project is tracking to plan
Q4 17-18 | CenITex | CenITex | 2418 | Data Centre Network Design and Infrastructure Establishment | Government and Economy | Assets/Materials Management | Design and establish software defined networking (SDN) capabilities at government shared platform data centres | Delivery |  | PRINCE2 | 2017-05-01 | 2017-07-31 |  | 2017-08-01 | 0 |  | 2017-10-24 | 2017-10-24 | 2018-06-30 | 2018-11-30 | 2780216 |  |  |  | Green | Green | Green | Full production hardware has been tested installed and racked - base configuration has been completed and commissioned. Workload configuration activities have commenced in line with project schedule.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2420 | Implement Office 365 | Employment and Workplace | Collaboration | Implement and roll out Office 365 to all DELWP staff | Closed - Completed | 2018-06-30 | PRINCE2 | 2016-01-31 | 2016-06-30 |  | 2016-06-30 | 76772 |  | 2016-06-30 | 2016-06-30 | 2017-08-31 | 2018-06-30 | 1226392 |  | Green | Amber | Green | Green | Green | All activities have been completed. The project is completing transition activities and project closure.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2421 | Crown Land Information Improvement Project (CLIIP) | Environment and Water | Data Management | The Crown Land Information Improvement Project (CLIIP) will deliver a modern web based IT solution for the management of Crown land information and associated business processes. The new solution will replace a number of legacy systems and provide a range of Web and Mobile capabilities. | Delivery |  | Hybrid - Agile and PRINCE2 | 2016-09-01 | 2017-07-02 |  | 2017-07-02 | 30000 |  | 2017-07-02 | 2017-07-02 | 2019-07-30 | 2019-11-01 | 3619688 |  | Green | Green | Green | Green | Green | Project is on Schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise.
Q4 17-18 | Department of Education and Training | DET | 2422 | eduPass Parent, Carer, Guardian (PCG) | Education | Security Management | eduPass Parent, Carer and Guardian (PCG) will provide near real-time provisioning capability of identities and managed access for Parents, Carers and Guardians as well as enabling self-service registration and account management. The decommissioning of the legacy iDaptive toolset will also be undertaken. | Delivery |  | Agile | 2014-10-16 | 2017-04-01 |  | 2017-04-01 | 299254 |  | 2017-04-01 | 2017-04-01 | 2018-03-17 | 2018-07-19 | 1688005 | 1398097 | Green | Green | Amber | Green | Green | Project development activities are now complete. Movement of application to corporate shared farm is underway.
Q4 17-18 | Department of Education and Training | DET | 2423 | eduSafe Plus | Education | Human Capital / Workforce Management | The eduSafe project will deliver one consolidated IT system to replace the separate OHS, Workers Compensation and Workplace incident management systems currently in use at DET. | Initiated |  | PRINCE2 | 2017-01-09 | 2017-01-09 | 2018-09-28 |  | 0 | [12 empty] | Following extensive market analysis conducted during 2017 an Open Invitation to Supply (ITS) was issued to the market on 2nd November 2017 with the response period closing on the 6th December 2017. A detailed evaluation process has been conducted on the submissions to identify a shortlist of vendor solutions. The evaluation has been extended to enable a thorough risk assessment of shortlisted options prior to identifying a preferred vendor which is now expected in August 2018. Implementation costs and timeframes will be confirmed once the preferred vendor is endorsed and implementation approach agreed.
Q4 17-18 | Department of Education and Training | DET | 2424 | CASE and Matter Management | Education | Customer Relationship Management | Case management solution to support the consolidated requirements for Legal Division, Employee Conduct Branch and Integrity and Assurance Division. | Initiated |  | PRINCE2 | 2016-11-07 | 2018-02-28 | 2018-06-29 |  | 0 | 542792 | [11 empty] | Market research was conducted during 2016 and a decision to source a solution was endorsed in January 2017. A market approach was conducted via an Expression of Interest (EOI). A discovery exercise was completed with the highest ranked supplier from the EOI evaluation and the preferred supplier was confirmed following internal approvals. Contract negotiations have been completed and contract executed on 29 June 2018. Implementation is due to commence early in the first quarter of the new financial year, 2018-19
Q4 17-18 | Department of Health and Human Services | DHHS | 2425 | Replacement Client Management System for the Health Complaints Commissioner, Mental Health Complaints Commissioner, Mental Health Tribunal and the Office of the Chief Psychiatrist | Health | Tracking and Workflow | The replacement Client Management System Project is seeking to replace three existing systems in place for these four Bodies. Existing contracts are nearing end of life and a new system must be procured. The Bodies seek a Commercial of-the-Shelf (COT) | Delivery |  | Agile | 2017-04-01 | 2017-05-08 |  | 2017-05-08 | 245950 |  | 2017-05-08 | 2017-05-08 | 2018-11-15 | 2018-11-23 | 1132458 | 1456789 |  |  | Green | Green | Amber | The solution has been implemented and is in use at the Office for the Health Complaints Commissioner. Some risks have been identified in delivery to the three remaining user groups; however the project is progressing to schedule.
Q4 17-18 | Melbourne Water | MELB Water | 2431 | Q05754 - Site Security Upgrade Project (Phase 2) | Environment and Water | Security Management | Intrusion Detection for 16 sites and 200 E-Locks | Delivery |  | PRINCE2 | 2016-10-20 | 2017-05-01 |  | 2017-05-01 |  |  | 2017-05-01 | 2017-05-01 | 2018-02-12 | 2018-09-30 | 1624000 | 1624000 | Green | Green | Green | Amber | Green | All sites now commissioned and operational with the exception of one (PLT agreement reached to exclude this site due to existing site AC power issues). All sites will be handed over to BAU support by end of July. Further site improvements and decommissioning scheduled for completion in September dependent on approval of a project Change Request.
Q4 17-18 | Monash Health | Monash H | 2434 | PABX Upgrade Stage 1 - Clayton & Dandenong | Health | Systems Management | PABX systems have reached end of life and need to be replaced with latest technology. | Delivery |  | PRINCE2 | 2017-09-01 | 2018-02-28 |  | 2018-02-28 | 1 |  | 2018-07-02 |  | 2019-08-01 |  | 3660000 | [5 empty] | Green | Tender has been awarded. Project planning has commenced
Q4 17-18 | Monash Health | Monash H | 2435 | Patient Flow Manager - Phase 2 Monash Health Rollout | Health | Routing and Scheduling | Patient Flow Manager (PFM) system has been successfully implemented at the Monash Children's Hospital. This project will extend the implementation of PFM across all Monash Health campuses. | Closed - Completed | 2018-04-03 | PRINCE2 | 2017-05-01 | 2017-04-19 |  | 2017-04-19 | 0 |  | 2017-04-19 | 2017-04-19 | 2017-12-30 | 2018-04-12 | 1054000 |  | Green | Green | Green | Green | Green | Go-Live on schedule for 12th April
Q4 17-18 | Public Transport Victoria | PTV | 2437 | Bus Passenger Information Displays (PIDs) Implementation Program | Transport and Vehicles | Assets/Materials Management | Rebuild PID solution architecture and supply, install and commission PIDs with real time metro train and bus information across regional and metro locations. | Delivery |  | PTV Investment Lifecycle | 2017-06-21 | 2017-06-27 | 2017-06-21 | 2017-06-21 | 0 |  | 2017-10-30 | 2017-10-30 | 2018-04-05 | 2018-08-31 | 1089462 |  |  |  | Green | Amber | Green | Cranbourne: Steering committee scope approved a change to reduce the number of PIDs from 3 to 2 due to space limitations at the installation location. Final delivery items for PIDS at all scoped locations delayed due to the issue with installing the 4G network which was resolved following escalation to Telstra. Frankston implementation has been delayed due to the LXRA station upgrade project timelines. Forecast completion date now Q1 2018/19.
Q4 17-18 | Public Transport Victoria | PTV | 2438 | Operator Payment System Modernisation - Releases 2 to 4 | Transport and Vehicles | Systems Management | Replace the PASS suite of programs (PASS Payments and Bus IT), myriad of spread sheets and manual processes related to operator contract and performance management and operator payments. Decommission of PASS Payments and Bus IT. Releases 2 to 4 and roll out of the Operator Portal. | Delivery |  | PTV Investment Lifecycle | 2017-03-31 | 2017-03-31 |  | 2017-03-31 | 0 |  | 2017-03-31 | 2017-03-31 | 2018-09-30 | 2018-10-01 | 7169100 | 11554100 | Green | Green | Green | Amber | Amber | Project has implemented Release 3 (MR4 - Trains and Trams). Release 2 (Ferry Nightrider and Transdev) and Release 4 (School Bus and Metro Bus) delivery is currently underway but running behind the schedule. The vendor is finalising the new schedule with the PTV project team. Once finalised it will be presented to PSC for approval. It has also been identified that there is insufficient budget to complete the project. The majority of required funding has been approved with further funding expected to be approved in Q1 2018/19. Forecast Go Live date of the final release remains as 1 October 2018.
Q4 17-18 | VicRoads | VicRoads | 2440 | Practical Safe Driving Program(PSDP) | Transport and Vehicles | Communication | The Practical Safe Driving Program (PSDP) is aimed at beginner drivers and their supervising drivers, as a means of imparting knowledge, skills and behaviours to lay the foundations for safe driving. A key feature of the program includes an online learning capability delivered and administered through a Learning Management System. | Closed - Completed | 2018-05-15 | Agile | 2017-02-06 | 2017-06-07 |  | 2016-11-30 | 300000 |  | 2017-06-08 |  |  |  | 1800000 |  | Green | Amber | Green | Green | Green | Project has gone live on 5th of March. Project handover completed.
Q4 17-18 | VicRoads | VicRoads | 2441 | R&L Digital Services Transformation (Stage 3) | Transport and Vehicles | Customer Initiated Assistance | Digital Services Transformation Stage#3 continues to rollout key vicroads transactions online including Individual and partner transactions and mandatory legislative projects. Further enhancements to Partner Transactions. | Closed - Completed | 2018-06-27 | Agile | 2017-05-30 | 2017-06-30 |  | 2017-05-01 | 0 |  | 2017-07-03 |  |  |  | 4949000 |  | Green | Green | Green | Green | Green | Project Completed and successfully handed over to BAU.
Q4 17-18 | VicRoads | VicRoads | 2442 | Customer Management & Productivity Platform | Transport and Vehicles | Customer Relationship Management | This Initiative will deliver foundational aspects of enterprise wide Customer Relationship Management (CRM) platform that enables proactive , responsive and personalised customer service across multiple channels | Delivery |  | Agile | 2017-05-30 | 2017-06-30 |  | 2017-05-01 | 0 |  | 2017-07-03 | 2017-07-03 |  | 2018-12-21 | 4230000 | 8157454 | Green | Green | Green | Amber | Green | Project is on track. Project has been re-baselined due to additional scope inclusion and functionality enhancements that were approved by the project authority. Thus project has received additional funding. Previously identified complexities have been addressed.Development is progressing and business change activities are underway.
Q4 17-18 | VicRoads | VicRoads | 2443 | Medical Review Reform | Transport and Vehicles | Customer Relationship Management | This initiative will leverage off the CRM platform to implement enhanced workflow, automated decision support, and service level management to deliver more reliable and efficient back office support systems for Medical Review processes, | Delivery |  | Agile | 2017-05-01 | 2017-06-01 |  | 2017-06-01 | 0 |  | 2017-06-01 | 2017-06-01 | 2018-06-30 | 2018-12-21 | 1930000 | 4334060 | Green | Green | Green | Amber | Green | Project is on track. Project has been re-baselined due to additional scope inclusion and functionality enhancements that were approved by the project authority. Thus project has received additional funding.The project is continuing to deliver enhancements and work is in progress for wider business implementation including the delivery of online forms.
Q4 17-18 | VicRoads | VicRoads | 2444 | Digital Learners Kit | Transport and Vehicles | Customer Initiated Assistance | This initiative will enhance the learning to drive process and strengthen the Graduate Licencing System (GLS ) and is aligned with the Towards Zero Strategy. Delivered via a suite of online and mobile tools to streamline capture of 120 hours driving data, with improved accuracy, data quality and user experience. | Delivery |  | Agile | 2017-05-30 | 2017-07-12 |  | 2017-07-12 | 0 |  | 2017-11-08 |  | 2018-09-01 |  | 7540000 | 8346000 |  |  | Green | Amber | Amber | Project status is amber as the timing of the release date of the myLearners product is unclear. Test phase of the project is completed. Awaiting confirmation of dates for the pilot and roll out.
Q4 17-18 | Yarra Valley Water | YV Water | 2448 | Optimise YVW's Meter Reading Contract | Environment and Water | Management of Process | Implement productivity efficiencies across our meter reading contract | Delivery |  | Agile | 2017-06-15 | 2017-09-29 |  | 2017-09-29 | 250000 |  | 2017-10-02 |  | 2018-12-31 |  | 1000000 | 1007000 |  |  | Green | Green | Green | Project is in delivery and on track
Q4 17-18 | Yarra Valley Water | YV Water | 2449 | Asset Compliance Management System | Environment and Water | Assets/Materials Management | Implement an audit compliance system for our asset infrastructure | Delivery |  | PRINCE2 | 2016-02-17 | 2017-09-11 |  | 2017-09-11 | 738574 |  | 2017-09-11 | 2017-09-11 | 2018-05-31 | 2018-09-30 | 763346 |  |  | Green | Green | Green | Green | Implementation has been deferred to September 2018 to procure suitable mobile devices and address application security.
Q4 17-18 | Barwon Region Water Corporation | BR Water | 2450 | Customer Experience - Website | Environment and Water | Customer Initiated Assistance | The current Website does not provide our customers with the service they need. The objective of this project is to replace the website with a customer centric design that digitalises the services our customers need | Delivery |  | PMBoK | 2017-07-01 | 2017-08-01 |  | 2017-08-01 | 88500 |  | 2017-08-01 | 2017-08-01 | 2018-06-30 | 2018-09-28 | 1458708 |  |  | Green | Green | Green | Green | Project continues to run to plan. Risk areas around schedule are primarily aligned to 'single point of failure' resource risks.
Q4 17-18 | Central Gippsland Region Water Corporation | GIPP Water | 2451 | Customer Information & Billing System Upgrade | Environment and Water | Business Intelligence | Upgrade and enhancement of billing system to delivery further online, digital and crm capabilities | Delivery |  | Agile | 2017-07-01 | 2017-07-01 |  | 2017-07-01 | 202600 |  | 2017-07-01 | 2017-07-01 | 2018-06-30 | 2018-10-31 | 1871600 |  |  | Green | Green | Green | Green | Project progressing well with high risk areas such as data migration and standard billing complete. Other key areas such as payments call centre and delinquency are also complete. Formal training of end users is underway.
Q4 17-18 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | A new case management system for the Magistrates’ Court and the Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information. | Delivery |  | Project Management Excellence (PME) | 2017-07-01 | 2017-07-01 |  | 2017-05-02 |  |  | 2017-07-01 |  | 2021-06-30 |  | 89200000 |  |  |  | Green | Green | Green | No major issues identified at present. The Procurement Phase of the project is progressing well having completed the EOI process resulting in an approved shortlist of suppliers who will undertake the Competitive Dialogue and RFP stages.
Q4 17-18 | Court Services Victoria | CSV | 2453 | Supreme Court Digital Strategy | Law and Justice | Organisational Management | The Digital Strategy project is laying the foundation for the Court's technology infrastructure and delivering efficiencies and access through system, network and associated process improvements. | Delivery |  | PMBoK | 2016-01-01 | 2016-06-30 |  | 2016-07-01 | 0 |  | 2016-09-01 | 2016-09-01 | 2018-06-30 | 2019-06-30 | 6424000 | 6681898 |  |  | Green | Green | Green | Project is on track and within scope. The delivery end date is funding based so the revised end date is a reflection of the continuation of the program of works.
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2454 | Transport Information Management System (TIMS) | Government and Economy | Data Management,Development and Integration ,Management of Process | This project will replace the legacy Marine Safety System (MSS), Transport Safety Audit, Accreditation and Reporting System (TSAARS) and VSMQS systems with a new cloud-based Salesforce CRM system supported by third party integration. | Delivery |  | PRINCE2 | 2017-05-09 | 2017-06-30 |  | 2017-05-11 | 0 |  | 2017-06-30 | 2017-06-30 | 2018-06-30 | 2018-08-17 | 1554471 | 1687216 |  | Green | Green | Green | Green | The project has taken on additional scope to include the Partner Community Portal development. Revised implementation date is now 26 July 2018 with decommissioning of legacy systems to be completed in August 2018.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2457 | Raster Data Platform - Phase 2 | Employment and Workplace | Data Management | Establishment of an on-demand service for storing, accessing, delivering and processing geospatial raster data. The service will provide flexible infrastructure that can be used to meet a range of user needs related to raster data. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-09-04 | 2017-09-04 |  | 2017-12-29 | 0 |  | 2018-04-02 |  | 2018-12-21 |  | 1300000 | 1425492 |  |  |  |  | Green | Project is on Schedule. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise.
Q4 17-18 | Department of Health and Human Services | DHHS | 2458 | Briefing and Correspondence Information project | Community Services | Records Management | The objective of the CBS project is to provide a single, integrated document tracking solution to manage all departmental, Ministerial and Cabinet briefings and executive correspondence processes, including the management of drafting authored versions and approval workflows. | Delivery |  | PRINCE2 | 2017-09-21 | 2018-01-31 |  | 2018-01-31 | 147840 |  | 2018-02-08 | 2018-02-08 | 2018-08-31 | 2019-02-28 | 1813120 | 2644565 |  |  |  | Green | Amber | Project is progressing Amber due to schedule delays and is being re-baselined as a result. Project name changed from Complete Briefing System.
Q4 17-18 | Department of Health and Human Services | DHHS | 2459 | Data rich website and portal | Health | Data Management | Development of a data rich, interactive website and completion of plans to design an interactive clinical portal as recommended in Targeting Zero. | Closed - Completed | 2018-06-30 | Agile | 2017-02-01 | 2017-09-20 |  | 2017-09-20 |  |  | 2017-10-09 |  | 2018-06-30 |  | 1190000 |  |  |  | Green | Amber | Green | Project now closed with the remaining Portal piece of the project to be delivered by the VIME project.
Q4 17-18 | Department of Health and Human Services | DHHS | 2460 | VAHI Information Management Environment (VIME) and Portal | Health | Data Management | Development of a next generation information management approach, leveraging where feasible existing infrastructure, data sources and systems to enable the Agency to create and (along with the data rich website and portal initiative) report accurate, reliable and actionable performance information for health service boards, executives, clinical leaders and the public. | Initiated |  | Agile | 2017-04-26 | 2018-02-15 | 2018-07-31 |  | 130000 | 131850 | [11 empty] | Project name has changed from Data Storage Visualisation and Reporting Services Solution. Planning and project initiation document development is being finalised.
Q4 17-18 | Department of Health and Human Services | DHHS | 2461 | Electronic Document Records Management System | Community Services | Records Management | An implementation project to rollout an Electronic Document Records Management System to all staff in the department. | Delivery |  | PRINCE2 | 2017-04-25 | 2017-09-29 |  | 2017-09-30 |  |  | 2017-10-02 |  | 2019-06-29 |  | 3000000 |  |  |  | Green | Green | Green | Project is progressing to schedule
Q4 17-18 | Department of Health and Human Services | DHHS | 2462 | Family Safety Victoria Central Information Point | Community Services | Data Management,Knowledge Management ,Records Management | The Central Information Point (CIP) is a key reform which includes the establishment of a co-located team of data custodians from Victorian Police, Corrections Victoria, DHHS and Courts. This project will develop the IT systems used to create and deliver CIP reports in line with legislative requirements. | Delivery |  | Agile | 2017-03-13 | 2018-01-29 | 2017-06-30 | 2017-07-03 | 0 |  | 2017-07-04 |  | 2019-06-30 |  | 7199594 |  |  |  |  | Green | Green | First phase systems successfully delivered. Ongoing budget and plans being agreed.
Q4 17-18 | Department of Health and Human Services | DHHS | 2463 | Family Safety Victoria Hub Client Relationship Management | Community Services | Customer Relationship Management | This project will deliver a base CRM to support the initial roll out of FSV hubs and with incremental enhancements to continue throughout the lifecycle of the project. | Delivery |  | Agile | 2017-04-17 | 2018-01-29 | 2017-07-07 | 2017-07-10 | 0 |  | 2017-07-11 |  | 2021-06-30 |  | 6840000 |  |  |  |  | Green | Green | First phase systems successfully delivered. Ongoing budget and plans being agreed.
Q4 17-18 | Department of Health and Human Services | DHHS | 2464 | Feedback Management System | Community Services | Development and Integration | A new system is required to handle compliments, feedback, complaints and privacy investigations. | Delivery |  | Agile | 2016-12-31 | 2017-07-25 |  | 2017-07-25 | 117000 |  | 2017-07-25 | 2017-07-25 | 2017-12-06 | 2018-07-13 | 1080000 | 1208913 |  | Green | Green | Green | Green | Project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2466 | Office 365 | Community Services | Collaboration | The department is implementing Office 365 as a part of its ICT Workplace modernisation program. O365 is a cloud hosted productivity tool suite allowing staff anywhere access to core office applications e.g. email, word, excel, and a series of advanced applications to support collaboration, document storage/sharing, data analysis, teamwork and planning. | Delivery |  | PRINCE2 | 2016-12-08 | 2017-09-15 |  | 2017-09-18 | 0 | 100029 | 2017-09-19 |  | 2019-06-29 |  | 4899971 | 5742730 |  |  | Amber | Green | Green | Project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2467 | Open User Interface Services Agreement Management System (SAMS2) Application Upgrade | Community Services | Development and Integration | The Service Agreement Management System (SAMS2) manages more than 3,900 funding agreements with 2,900 organisations for DHHS, DET, ACFE and DJR. This project is to upgrade the systems to the current supported version to enable the application of the latest security patches and improved capabilities. | Delivery |  | Agile | 2017-11-08 | 2018-01-31 |  | 2018-01-31 | 0 |  | 2018-02-01 | 2018-02-01 | 2018-07-22 | 2019-02-28 | 1500000 | 1820000 |  |  |  | Green | Amber | Project is progressing but has had schedule delays.
Q4 17-18 | Department of Health and Human Services | DHHS | 2468 | Personal Hardship Assistance Programs (PHAP) | Community Services | Customer Relationship Management,Financial Management | The Personal Hardship Assistance Program (PHAP) provides assistance to those affected by a significant incident in Victoria (e.g. flood, bushfire or house fire). Department of Health and Human Services assesses claims and determines whether the applicants are entitled to a relief and re-establishment payments and provides the granted funds. | Closed - Completed | 2018-06-22 | Agile | 2017-02-05 | 2017-03-20 |  | 2017-03-20 | 0 |  | 2017-03-20 | 2017-03-20 | 2018-03-01 | 2018-06-22 | 2409992 | 1978560 |  | Green | Green | Green | Green | The project has delivered its intended result and is now closed
Q4 17-18 | Department of Health and Human Services | DHHS | 2469 | Radiation Licensing System (RELIC) Replacement | Health | Systems Management | The Radiation Registration and Licensing (RELIC) system is utilised by the Environmental Health Regulation & Compliance Unit to administer their Act & legislation. RELIC is approaching end of life and unable to meet new business needs such as reduced data entry, integration with other departmental systems and remote access. | Closed - Merged | 2018-06-30 | Agile | 2017-10-20 | 2017-11-05 |  | 2017-11-05 |  |  | 2017-11-06 |  | 2019-06-30 |  | 2400000 |  |  |  | Green | Green | Green | Project is closed as scope has been fully transferred to Regulatory Licensing and Registration Platform.
Q4 17-18 | Department of Health and Human Services | DHHS | 2470 | Video Conferencing Core Upgrade | Community Services | Communication | Increasingly, the Department seeks to connect offices via video services for Departmental briefings and to facilitate day to day operations. The current video conferencing is unable to support business need as the service regularly reaches capacity and does not include video streaming capabilities. | Delivery |  | PRINCE2 | 2016-12-08 | 2017-04-21 |  | 2017-04-24 | 18358 |  | 2017-12-21 | 2017-12-21 | 2018-06-29 | 2018-07-31 | 893575 | 1011934 |  |  |  |  | Green | Project progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2471 | Webseal Upgrade | Community Services | Security Management | The department uses security technology Webseal to allow users to access corporate applications. The newer version will enhance functionality to improve secure authenticated access to corporate and web enabled systems. The new authentication technology includes the ability to federate user authentication, improving access/usability for end users by reducing multiple login requirements. | Delivery |  | PRINCE2 | 2015-03-02 | 2016-07-01 |  | 2016-07-04 | 362250 |  | 2016-07-04 |  | 2018-11-04 |  | 627750 | 1083255 |  |  |  |  | Amber | Project is progressing but has had schedule delays.
Q4 17-18 | Department of Health and Human Services | DHHS | 2472 | Windows Upgrade | Community Services | Systems Management | To upgrade the department's standard operating environment on desktops and laptops to Windows 10. | Delivery |  | PRINCE2 | 2017-03-20 | 2017-04-01 |  | 2017-04-02 | 100000 |  | 2017-04-02 |  | 2019-06-30 |  | 3900000 | 3949662 |  |  | Amber | Green | Red | Project experienced delays due to technical problems which are being addressed. Project name changed from Windows 10 Upgrade.
Q4 17-18 | Emergency Services Telecommunications Authority | ESTA | 2473 | Computer Aided Despatch (CAD) Upgrade | Emergencies and Safety | Systems Management | ESTA’s Computer Aided Dispatch (CAD) system requires upgrading to the latest version to take advantage of features required to meet future emergency services needs. | Initiated |  | ESTA Project Management Methodology | 2017-09-18 | 2017-09-18 | 2019-06-30 |  | 0 | [12 empty] | An expression of interest is currently in the marketplace.
Q4 17-18 | Environment Protection Authority | EPA | 2474 | EDISON (Environment Data Information System Online ) | Environment and Water | Analyses and Statistics ,Business Intelligence | Enable EPA to effectively manage more data from more sources more often, now and into the future. Collect, store, curate and share environment data (air, water, land, waste). | Delivery |  | Agile | 2017-01-21 | 2018-03-30 | 2017-12-19 | 2018-01-31 | 230000 | 255000 | 2018-02-26 |  | 2018-11-30 |  | 745000 |  |  |  |  | Green | Amber | EPA is in the process of re-establishing the project with an alternative implementation team. It is expected that the project schedule status will come back on track (green) in Q1
Q4 17-18 | Environment Protection Authority | EPA | 2475 | Electronic Document and Records Management System (EDRMS) | Environment and Water | Document Management ,Knowledge Management ,Records Management | Implement a Electronic Document and Records Management System (EDRMS) | Delivery |  | Agile | 2017-05-01 | 2018-06-29 | 2018-02-15 | 2018-02-15 | 75000 |  | 2018-02-16 | 2018-08-06 | 2018-06-29 | 2018-11-30 | 1011326 |  |  |  |  | Red | Green | Following initial delays, the implementation partner has now commenced the design phase and the project is back on track.
Q4 17-18 | Health Purchasing Victoria | HPV | 2476 | Victorian Health Sector -Common Catalogue (Project 076) | Health | Data Management | Develop common catalogue data and master data processes for the state | Delivery |  | PRINCE2 | 2017-07-01 | 2017-12-31 |  | 2017-12-31 | 404188 |  | 2018-01-01 |  | 2018-12-31 |  | 1395812 |  |  |  |  | Amber | Amber | The major tasks for this quarter include running a key design decisions forum drafting the design and starting the configuration.
Q4 17-18 | Holmesglen Institute of TAFE | Holmesglen TAFE | 2477 | SDDC and EUC | Education | Assets/Materials Management | Update of SDDC and implementation of EUC for users | Delivery |  | PRINCE2 | 2017-04-13 | 2017-07-27 |  | 2017-07-27 | 0 |  | 2017-07-27 |  | 2018-07-31 |  | 2229000 |  |  | Green | Green | Green | Green | Project is on track in terms of scope, budget and time
Q4 17-18 | Melbourne Water | MELB Water | 2479 | Q05572 - Disaster Recovery Servers to Cloud | Environment and Water | Data Management | Prepare the groundwork for enabling infrastructure (servers and storage) from the cloud. | Delivery |  | PRINCE2 | 2015-08-17 | 2017-09-19 |  | 2017-09-19 | 0 |  | 2017-09-19 | 2017-09-19 | 2018-03-30 | 2018-08-08 | 1898000 | 2241024 |  | Green | Green | Amber | Amber | Issues with vendor installation of additional appliances. Live DR test deferred. Physical server restore test completed successfully but remote backup testing currently not successful. Risk of project exceeding current budget.
Q4 17-18 | Melbourne Water | MELB Water | 2480 | Q05582 - Improvements to Portfolio, Program and Project Management | Environment and Water | Investment Management,Management of Process | Develop an integrated approach and implementation of a solution to plan, manage, deliver and monitor capital investment across Melbourne Water at a portfolio, program, project and task/activity level. | Closed - Completed | 2018-06-29 | PRINCE2 | 2016-03-02 | 2017-09-13 |  | 2017-09-13 |  |  | 2017-09-13 |  | 2018-02-28 | 2018-03-28 | 2476000 | 2476000 |  | Green | Green | Green | Green | Application is live. Project is completed and in handover having delivered improvements and further enhancements.
Q4 17-18 | North East Region Water Corporation | NE Water | 2481 | Customer Billing System | Environment and Water | Customer Relationship Management,Knowledge Management ,Management of Process | Procure a new Software solution for billing customers | Postponed | 2018-03-20 | Systems Engineering | 2017-07-01 | 2017-12-31 |  |  | 0 | [12 empty] | This project has been postponed on approval by North East Water Board at the March 2018 Board Meeting. The project was to replace and upgrade the Corporations Billing System however through the open Tender process vendors it has been identified that our current internet speed and telecommunications can not support a value for money upgrade. As the benefits will not be realised this investment has been postponed for approx. 2 yrs until telecommunications providers make higher speeds available that are compatible with vendors products. We are seeking an alternative solution from our existing vendor to modify our current billing system in the interim period with an approx. cost of $250K.
Q4 17-18 | Parks Victoria | PARKSVIC | 2482 | Asset Management System | Environment and Water | Assets/Materials Management | Implementation of an Assets Management technology solution for Built Infrastructure Assets in order to support Parks Victoria compliance with the Victorian Asset Management Accountability Framework. | Initiated |  | Hybrid - Agile and PRINCE2 | 2017-07-01 | 2018-06-24 | 2018-09-14 |  | 0 | [12 empty] | Procurement process is progressing with completion expected in next quarter. Delivery Phase will be initiated once contract is signed and project delivery resources are assigned. The Business Case has been updated (V2.0) to include detailed cost analysis following completion of the Market Engagement process.
Q4 17-18 | Parks Victoria | PARKSVIC | 2483 | Digital Customer Engagement | Environment and Water | Content Management | The Digital Customer Engagement project aims to transform Parks Victoria’s approach to engaging customers through the use of digital channels. | Delivery |  | Agile | 2017-07-01 | 2017-11-16 |  | 2017-11-16 | 199673 |  | 2017-11-20 |  | 2019-06-28 |  | 4293327 |  |  |  | Green | Green | Amber | Core platform build activities completed in May 2018. The project requires a richer dataset than is currently available and concerns exist regarding the timing for this data collection. This has been escalated with the stakeholders and is being closely monitored.
Q4 17-18 | Parks Victoria | PARKSVIC | 2484 | ParkConnect (Phase 2) | Environment and Water | Customer Relationship Management | Expansion of the Customer Relationship Management (ParkConnect) solution to include Traditional Owners, Strategic Partnerships, Education and Events. Also, enhancements to functionality for existing business areas. | Delivery |  | Agile | 2017-07-01 | 2017-09-29 |  | 2017-09-29 | 281000 | 214531 | 2017-10-02 | 2017-10-02 | 2018-06-29 | 2018-10-31 | 2200000 | 2266469 |  |  | Green | Green | Amber | The project has made fortnightly releases delivering continued improvements for the current business areas. New areas for Traditional Owners and the Commercial Partnerships portal have been introduced. Work on Events has been delayed following staff attrition. Key positions have recently been filled and development work on Events has commenced. As a result the project will not be completed in September 2018 and a 1-month extension to project schedule has been agreed; the financial impact of this is currently under review.
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2485 | Barwon Health Emergency Department Information System (EDIS) Project | Health | Data Management,Document Management ,Knowledge Management ,Reporting ,Tracking and Workflow | Barwon Health is undertaking a project to replace its existing Emergency Department Clinical Information System due to withdrawal of support in the Australian market by the vendor | Delivery |  | Vendor specific methodology | 2016-03-01 | 2017-08-29 |  | 2017-08-29 | 120000 | 1 | 2017-08-30 |  | 2019-08-26 |  | 6580000 | 7082299 |  |  | Green | Green | Green | Project is on track.
Q4 17-18 | State Revenue Office | SRO | 2486 | Commercial Passenger Vehicle Service Levy | Government and Economy | Financial Management | This project will deliver functionality to enable the collection and administration of the levy, which is part of the Government's proposed reforms to the commercial passenger vehicle industry (i.e. taxi, hire cars and ride share services). | Delivery |  | PRINCE2 | 2017-02-27 | 2017-07-07 |  | 2017-07-07 | 32908 |  | 2017-07-07 |  | 2019-06-28 |  | 1467092 | 1137007 |  | Green | Green |  | Green | Stages 2 and 3 were successfully delivered in production on 22 January and 26 March respectively. These stages delivered Return Lodgement Payment and other functionality building on the web portal that was implemented in Q2. During Q3 the remaining component functionality to enable effective administration of the levy was rescheduled and packaged up in a final stage 4 that is planned to be delivered in 2 releases in May and June. An exception report is pending to formalise the changes to the delivery schedule. This will complete the project delivery, excepting the warranty period that will come into effect once the commencement date for the levy is proclaimed. In Q3 the planned delivery costs were reviewed in conjunction with the review of the schedule for delivering the remaining component functionality and resulted in a downward revision to the remaining costs and the project is now tracking well under the approved project budget of $1.5M.
Q4 17-18 | State Revenue Office | SRO | 2487 | Vacant Residential Land Tax | Government and Economy | Financial Management | This project will deliver functionality to enable the collection and administration of a tax on vacant residential property, which is part of the Government's reforms to help reduce the pressure on house prices and rents by allowing Melbourne’s current housing stock to be used more efficiently. | Delivery |  | PRINCE2 | 2017-03-07 | 2017-04-12 |  | 2017-04-12 | 13368 |  | 2017-04-12 | 2017-04-12 | 2018-03-26 | 2018-09-24 | 1042148 | 1383407 |  | Amber | Green | Green | Green | Stages 2 and 3 were successfully delivered in production on 22 January and 26 March respectively. These stages delivered Objections Debtors Report Refunds and other functionality. During Q3 there was a major review of the requirements and costs for the remaining component functionality (i.e. Debt Recovery; Compliance; Reporting; Litigations). This resulted in the creation of 2 additional stages 4 and 5 that will be delivered in Q4 and Q1. There will also be a final stage 6 to be delivered in Q1 to deliver identified critical functional improvements. The inclusion of 3 additional stages will extend the project delivery by a further 6 months through to the end of Q1 2018-19 not including a 3 month warranty period in Q2. The planned delivery costs have also increased and additional funding was requested in an exception report that was approved by the project board and programme management. The project was re-baselined to reflect the changes in budget and schedule
Q4 17-18 | V/Line | V/Line | 2489 | New Training Platform | Transport and Vehicles | Development and Integration | Staff Training LMS to improve quality and quantity | Initiated |  | Hybrid - Agile and PRINCE2 | 2017-09-01 | 2018-05-31 |  |  | 500000 | 678383 | [11 empty] | Project status On Hold awaiting rescope due to Employees Vote NO to Changing EA as an option to facilitate the introduction of A New Vision for Training at V/Line
Q4 17-18 | V/Line | V/Line | 2490 | Electronic Rostering - Workforce management | Transport and Vehicles | Human Capital / Workforce Management | Electronic Rostering System & Workforce management | Initiated |  | Agile | 2018-01-18 | 2018-05-31 | 2019-06-28 |  | 250000 | 1540300 | [11 empty] | Project initiation and discovery commenced with recruitment and formulation of go-to-market strategy. Proof-of-concept to be planned and implemented by Jun-19.
Q4 17-18 | V/Line | V/Line | 2491 | TRACKR Development Phase 1 | Transport and Vehicles | Systems Management | Replacement of train scheduling, train rostering and day of operation system | Delivery |  | Agile | 2016-06-15 | 2017-01-31 |  | 2018-04-03 | 247150 |  | 2018-04-03 |  | 2018-12-31 |  | 1415790 | [5 empty] | Amber | Delays to recruitment of dedicated test resources delayed test planning and execution
Q4 17-18 | VicRoads | VicRoads | 2492 | Australian Disability Parking Solution | Transport and Vehicles | Management of Process | Purpose of this project is to streamline and standardise the Disability Parking Application, Assessment and Management processes. | Initiated |  | Agile | 2017-07-01 | 2018-12-21 |  |  | 0 | [12 empty] | User community consultation in progress. Solution design in progress.
Q4 17-18 | VicRoads | VicRoads | 2493 | Character field extension project | Transport and Vehicles | Development and Integration | This initiative is to implement changes into the core backend VicRoads Registration & Licensing systems to remove existing database, screen and system limitations on character field data length. | Initiated |  | PRINCE2 | 2017-05-01 | 2018-05-31 | 2018-08-30 |  | 0 | [12 empty] | Project is in planning phase with competing priorities with other important regulatory initiatives. This project is likely to be put on hold due to the above reason.
Q4 17-18 | VicRoads | VicRoads | 2494 | Drink drug package implementation program - ICT stream | Transport and Vehicles | Development and Integration | The Drink Drug Package Implementation Program is a mandatory legislative project that is to implement required ICT changes to support a range of legislative changes targeting drink driving offenders included within Road Safety Act Amendments 2016 and 2017. | Delivery |  | PRINCE2 | 2017-07-18 | 2017-08-30 |  | 2017-06-01 | 0 |  | 2017-09-01 | 2017-09-01 |  | 2019-03-29 | 3452954 |  |  | Red | Green | Amber | Amber | Stage 1 was delivered by 31st January 2018. Stage 2 was implemented on 30th April 2018. Over all status amber due to pending releases of stage 2 changes. Planning for stage 3 has commenced which will be managed as separate project.
Q4 17-18 | VicRoads | VicRoads | 2495 | ICT Workplace Productivity Platform Uplift | Transport and Vehicles | Collaboration | This initiative is to design and uplift the workplace productivity suite (Mail & Calendar and Unified Communications) that supports a workplace productivity platform to meet the demands of transport services. | Closed - Merged | 2018-05-07 | PRINCE2 | 2017-08-17 | 2017-08-17 |  | 2017-08-17 | 0 |  | 2017-08-17 |  | 2020-02-28 |  | 1350000 |  |  | Green | Green | Green | Green | This project has been merged with ICT/ITS Infrastructure Transformation program.
Q4 17-18 | Victoria Police | VicPol | 2496 | Police Assistance Line and Online Reporting | Law and Justice | Customer Initiated Assistance | Two new channels for the public to report non-urgent events: Police Assistance Line (PAL) & Online Reporting (OLR). PAL will enable triage, reporting and receipt enquiries. OLR will provide the public with the ability to securely create incident reports online without the need to attend or phone a police station | Delivery |  | PRINCE2 | 2016-07-01 | 2017-06-30 |  | 2017-06-30 | 0 |  | 2017-06-30 |  | 2021-06-30 | 2020-12-31 | 212200000 |  |  | Green | Green | Green | Green | The project is on schedule for a soft launch in early 2019 and a phased ramp-up to achieve full capability is scheduled to be in place by 2020.
Q4 17-18 | Victorian Electoral Commission | VEC | 2497 | EMS2 | Government and Economy | Development and Integration | Re-write of Election Management System | Delivery |  | Agile | 2017-03-01 | 2017-05-01 |  | 2017-05-01 | 50000 |  | 2017-05-01 | 2017-05-01 | 2018-06-30 | 2019-12-31 | 2000000 |  |  | Green | Amber | Green | Green | The project is green and is tracking to scope time and budget. This is a reflection of the performance of the new Program Manager driving the project to success.
Q4 17-18 | WorkSafe Victoria | WorkSafe | 2499 | End User Computing - Implementation of Enabling Technologies | Government and Economy | Communication | Implementation of Exchange online, MS Office 365, Skype for Business, Windows 10 | Delivery |  | PMBoK | 2017-07-01 | 2017-07-01 |  | 2017-07-01 | 0 |  | 2017-07-01 | 2017-07-01 | 2018-06-30 | 2018-10-31 | 3981297 |  |  | Green | Green | Green | Green | Project tracking to plan
Q4 17-18 | WorkSafe Victoria | WorkSafe | 2500 | Website Replatforming | Government and Economy | Communication | Use human centred design to build a new client-centric WorkSafe website using Drupal 8 | Delivery |  | PMBoK | 2017-07-01 | 2017-07-01 |  | 2017-07-01 | 0 |  | 2017-07-01 |  | 2019-01-31 |  | 3000000 |  |  | Green | Green | Green | Green | Project tracking to plan
Q4 17-18 | Yarra Valley Water | YV Water | 2501 | Corporate Procurement and Contract Management System | Environment and Water | Supply Chain Management | Implement a new corporate procurement governance and contract management system | Delivery |  | PRINCE2 | 2016-10-20 | 2016-10-20 |  | 2017-11-22 | 244000 |  | 2018-01-08 |  | 2018-08-09 |  | 2115800 |  |  |  |  | Green | Green | On track for incremental roll out.
Q4 17-18 | Yarra Valley Water | YV Water | 2502 | Enterprise Hosting Platform Replacement | Environment and Water | Systems Management | Replacement of Enterprise application hosting platform | Delivery |  | PRINCE2 | 2016-08-03 | 2017-06-09 |  | 2017-06-09 | 209121 |  | 2017-06-09 | 2017-06-09 | 2018-06-30 | 2019-01-29 | 3937879 | 7194879 |  | Green | Green | Amber | Amber | Performance issues with the database technology has resulted in project delays.
Q4 17-18 | Northern Health | NH | 2510 | Laboratory Information System (CV) | Health | Analyses and Statistics ,Business Intelligence,Development and Integration ,Document Management ,Financial Management,Management of Process ,Tracking and Workflow | Implementation of a Laboratory Information System | Delivery |  | PRINCE2 | 2017-03-30 | 2017-03-30 |  | 2017-03-30 | 0 |  | 2017-10-02 |  | 2019-01-08 |  | 1600000 |  |  |  | Green | Green | Green | Project tracking well to date to perform end to end testing by end of next month.
Q4 17-18 | Melbourne Health | Melb H | 2514 | Network Infrastructure Upgrade Project | Health | Communication | Upgrade of Network IT Infrastructure to provide robust, reliable network communication capability, including comprehensive WiFi network coverage across Melbourne Health agency campuses in readiness for EMR. Including Parkville Precinct Interconnect. | Delivery |  | PRINCE2 | 2017-07-03 | 2017-12-22 |  | 2018-01-01 | 0 |  | 2018-01-01 |  | 2019-12-20 |  | 11105000 |  |  |  |  | Green | Green | Review of design documents has taken longer due to additional technical components available for consideration with the advent of WiFi standard improvements. The preliminary pre-ordering of equipment and parallel cabling prep has continued, so no impact to schedule.
Q4 17-18 | South East Water | SE Water | 2515 | Digital Utility Proof of Concept | Environment and Water | Assets/Materials Management,Business Intelligence,Development and Integration | to establish the baseline platform and functionality to manage IoT devices. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-12-18 | 2018-04-12 |  | 2018-04-12 | 250000 | 250000 | 2018-04-13 |  | 2018-10-05 |  | 0 | 1350000 |  |  |  |  | Green | The project is progressing well with milestones being met. The team is currently designing mock ups for end user system that will be leveraged throughout the POC as well as the Pilot. Technical Infrastructure & Architectural pieces are also being put in place.
Q4 17-18 | Department of Health and Human Services | DHHS | 2517 | Health Care Home ICT Enablement | Health | Development and Integration | ICT activities to support the Department's Health Care Home initiative; allowing health services to upload discharge summaries pathology results and radiology results to My Health Record and to view My Health Record data. | Delivery |  | PRINCE2 | 2017-09-01 | 2017-12-22 |  | 2017-12-22 | 0 |  | 2018-01-02 | 2018-01-02 | 2018-06-30 | 2019-06-30 | 4445000 | 5445000 |  |  |  | Green | Green | The agreed project scope has expanded in terms of My Health Record functionality and health service coverage.
Q4 17-18 | CenITex | CenITex | 2518 | Corporate Remedy Fix the Foundations | Government and Economy | Management of Process | BMC suite toolset uplift and functionality review linked to strategic objectives | Delivery |  | PRINCE2 | 2017-10-02 | 2017-10-25 |  | 2017-10-26 | 0 |  | 2017-10-27 | 2017-10-27 | 2018-06-30 | 2018-10-31 | 1720355 | 1306001 |  |  | Green | Green | Green | Project continues to transfer existing monitoring configurations to the new environment. Integration points between the new environment and other applications are currently being worked through with BMC.
Q4 17-18 | Northern Health | NH | 2519 | Infrastructure and Network refresh | Health | Development and Integration ,Visualisation | To design and implement a highly reliable and highly available infrastructure and network across NH sites to underpin the future EMR | Delivery |  | PRINCE2 | 2017-12-10 | 2018-02-05 |  | 2018-02-05 |  |  | 2018-03-26 |  | 2019-09-10 |  | 5000000 |  |  |  |  | Green | Green | Tender evaluation has progressed well. Preferred supplier to be selcted in the coming week and contracting to commence
Q4 17-18 | Royal Women's Hospital | RWH | 2521 | EMR Network and Site Infrastructure Upgrade | Health | Organisational Management ,Security Management | To replace and upgrade legacy network, security and wireless infrastructure so that an appropriately secure, reliable and performing infrastructure can be in place to support clinicians and patient access to electronic medical record information. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-09-01 | 2017-10-19 |  | 2017-10-19 | 0 |  | 2017-11-14 |  | 2019-11-01 |  | 4976044 |  |  |  | Green | Green | Green | Project kicked-off with the successful supplier. Various workshops and audit activities were undertaken as part of a Discovery phase. This provided background for the Detailed Design and any supporting works to be undertaken internally to fully support the new solution.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2522 | Fuel Management System (FMS) | Emergencies and Safety | Data Management | Fuel Management System is a component of the Emergency Management Information System (EMIS) . This system supports and manages the complete life-cycle of the Planned Burning process in DELWP and replaces the functionality within Burns & Works. | Delivery |  | Hybrid - Agile and PRINCE2 | 2015-05-11 | 2015-05-12 |  | 2015-05-12 | 67500 |  | 2015-07-01 | 2015-07-01 | 2018-12-31 | 2019-06-30 | 1900000 |  |  |  | Green | Green | Amber | Delay due to change in solution architecture approach. Project is currently rescheduling. The revised objective will target delivery of an end to end FMS application by end of June 2019
Q4 17-18 | Western Health | WH | 2523 | Single Sign On (SSO) Project | Health | Security Management | Single Sign On (SSO) enables users to access multiple applications without the need to sign in to authenticate them each time they access a different application and allows them to roam quickly between computers . | Delivery |  | PRINCE2 | 2016-10-11 | 2017-04-06 |  | 2017-04-06 | 0 |  | 2017-05-01 |  | 2018-12-31 |  | 1176000 |  |  |  | Green | Green | Green | Proof of Concept has been rolled out to Emergency Department and all wards at Williamstown Hospital and users are being enrolled to the Single Sign On environment.
Q4 17-18 | Goulburn Valley Region Water Corporation | GVR Water | 2524 | Asset Management Information System Replacement Project | Environment and Water | Assets/Materials Management | Carry out the collection and validation of asset data Undertake an AMIS Process Review Implement a software solution that meets the requirements of the organisation | Delivery |  | Internal GVW Project Management Methodology | 2016-11-23 | 2017-12-08 |  | 2017-12-08 | 50000 |  | 2018-01-02 |  | 2021-03-31 |  | 2405000 |  |  |  |  | Green | Green | Tender documentation has largely been developed and now determining appropriate tender process
Q4 17-18 | Goulburn Valley Region Water Corporation | GVR Water | 2525 | Intelligent Metering | Environment and Water | Assets/Materials Management | Installation of intelligent meters in four towns to provide data to target peak demand reduction, leading to: 1 . A permanent reduction in peak day water usage through leakage reduction. 2. Deferral of water network capacity upgrade projects | Delivery |  | GVW Internal Project Management Methodology | 2017-07-01 | 2018-03-02 |  | 2018-03-02 | 10000 |  | 2018-07-31 |  | 2021-06-30 |  | 1790000 |  |  |  |  | Green | Green | Project yet to commence
Q4 17-18 | Independent Broad-based Anti-corruption Commission | IBAC | 2526 | Case Management System | Law and Justice | Tracking and Workflow | A system that provides for comprehensive case management, from the receipt of a complaint to the conclusion of an investigation. | Delivery |  | Agile | 2015-07-14 | 2016-05-02 |  | 2016-05-02 | 74518 |  | 2017-12-21 | 2017-12-21 | 2018-12-31 | 2019-02-25 | 1300000 |  |  |  | Green | Green | Green | Due to a request from the vendor the delivery of the project schedule was extended by two weeks in order to fully meet the requirements for phase one.
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2527 | Future Workplace Program | Government and Economy | Collaboration ,Document Management ,Records Management | Implement Office 365 to better support workforce collaboration, mobility and productivity. Replace manual paper based approval processes with digital forms and electronic workflows. Uplift hardware, network capacity and identity management platforms | Delivery |  | PRINCE2 | 2017-07-03 | 2018-02-28 |  | 2018-03-22 | 2000000 |  | 2018-03-22 |  | 2019-06-30 |  | 10000000 | 15000000 |  |  |  | Green | Amber | The Program is in delivery and running to schedule. An additional four Electronic Document Workflow projects have been added to the program scope and are at initiation phase this has required an increase in program budget and a revised end date.
Q4 17-18 | Department of Treasury and Finance | DTF | 2528 | SRIMS Infrastructure Refresh and Feasibility Assessment | Government and Economy | Financial Management | SRIMS is the State Resource Information Management System. This project will conduct a feasibility assessment of SRIMS 2025 and deliver upgraded infrastructure to deliver current projected capacity demands. | Delivery |  | PRINCE2 | 2017-10-02 | 2018-03-30 | 2017-12-01 | 2018-01-10 | 250000 |  | 2018-01-10 | 2018-01-10 | 2018-06-30 | 2019-01-31 | 0 | 1250000 |  |  |  | Amber | Amber | The project remains in Amber due to Stage 1 - Infrastructure Refresh having additional work performed. Stage 2 and Stage 3 has been has agreed to be delayed with the revised completion date of Jan 2019.
Q4 17-18 | Western Region Water Corporation | WR Water | 2529 | Project Pinnacle | Environment and Water | Visualisation | The purpose of this Project Pinnacle is to implement water operation management application and will run for a period of 12 months as part of an Intelligent Water Networks trial. This application will support fault management and water quality. | Delivery |  | PMBoK | 2016-11-01 | 2017-02-01 |  | 2017-02-14 | 50000 |  | 2017-02-14 | 2017-02-14 | 2018-09-30 | 2018-12-31 | 915106 | 2083007 |  |  | Green | Green | Green | On Track
Q4 17-18 | Royal Children's Hospital | RCH | 2530 | Rostering, Time & Attendance Project | Health | Human Capital / Workforce Management | Implement an enterprise electronic rostering, time and attendance solution. The system will cover rostering, hours worked and time capture to deliver a full 'work to pay' solution. | Initiated |  | PRINCE2 | 2018-01-01 | 2018-06-30 | 2018-12-31 |  | 330000 | 620000 | [11 empty] | Initiation has identified requirements for consolidation and optimization of the pilot roll-out of the Rostering, Time & Attendance system prior to an enterprise-wide scale up. The initiation phase timeline and budget has been revised to complete this activity.
Q4 17-18 | Melbourne Water | MELB Water | 2533 | Inflo CS16 Upgrade | Environment and Water | Content Management,Document Management | Upgrade content management system to current version | Delivery |  | Agile | 2017-01-25 | 2017-06-30 |  | 2017-11-23 | 0 |  | 2017-11-24 | 2017-11-24 | 2018-10-26 | 2018-10-26 | 1645120 |  |  |  |  | Green | Green | All integrations completed. External penetration testing has been completed with no observed major issues.
Q4 17-18 | Melbourne Water | MELB Water | 2534 | Windows 10 Desktop SOE Enterprise Deployment | Environment and Water | Collaboration ,Communication,Content Management | Planning for testing and deployment phases underway | Delivery |  | PMBoK | 2017-08-15 | 2018-01-31 |  | 2018-01-31 | 0 |  | 2018-01-31 | 2018-01-31 | 2018-05-30 | 2018-08-01 | 800000 | 1342535 |  |  |  | Green | Green | Eighty percent complete at end of June with minor works to be carried out throughout August. Tracking under budget.
Q4 17-18 | Department of Health and Human Services | DHHS | 2536 | Technology Modernisation | Property and Planning | Systems Management | The department seeks to modernise technology to enable staff flexibility in how they work and collaborate, through a technology replacement approach. To support the Workplace of the Future. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-04-10 | 2017-12-31 | 2017-07-10 | 2017-07-11 | 298000 |  | 2017-07-12 |  | 2019-06-30 |  | 6900000 |  |  |  |  | Green | Green | Project is progressing to schedule.
Q4 17-18 | VicRoads | VicRoads | 2537 | National Driver Licence Facial Recognition System (NDLFRS) | Transport and Vehicles | Development and Integration | The National Driver Licence Facial Recognition System (NDLFRS) is an initiative led by Attorney-General's Department (AGD) under the auspices of the National Identity Security Strategy. The NDLFRS will form a component of the overarching National Facial Biometric Matching Capability (NFBMC), which is intended to provide biometric capabilities across a network of government data sources. Matching services involving the Department of Immigration and Department of Border Protection have already become operational within the framework. | Delivery |  | PRINCE2 | 2017-08-01 | 2017-10-30 |  | 2017-07-01 | 0 |  | 2017-11-01 | 2017-11-01 |  | 2018-09-18 | 2960000 | 3889540 |  |  | Green | Green | Green | Project is on track. Working with the Commonwealth on (1) Policy and Legal agreements regarding the transfer and usage of Victorian Driver Licence data; and (2) Technical systems interface development. Both are expected to be completed by the end of this calendar year 2018 leaving Q1/Q2 2019 for data transfer and Agency on-boarding of the service.
Q4 17-18 | Court Services Victoria | CSV | 2538 | In-Court Technology | Law and Justice | Communication | The eCourts project is to fully upgrade in court technology - including cabling and infrastructure to the Supreme Court's courtrooms and mediation rooms. | Delivery |  | PMBoK | 2017-01-01 | 2017-06-30 |  | 2017-07-01 |  |  | 2017-09-01 |  | 2021-06-30 |  | 11748000 | 10911000 |  |  | Green | Green | Green | Project is on-track and within scope.
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2539 | SWARH Transformation Program - Tranche 1 | Health | Knowledge Management ,Management of Process ,Organisational Management ,Security Management ,Systems Management,Tracking and Workflow | Program seeks to replace technical components that are past/facing end-of-life, utilise current & new technologies to improve service availability, sustainability & reliability, and refresh the SWARH organisation – its people, processes and tools. | Delivery |  | PRINCE2 | 2017-09-01 | 2017-11-28 |  | 2017-11-28 | 300000 | 1 | 2018-01-03 |  | 2018-08-31 |  | 3141000 |  |  |  |  | Green | Green | Transformation Program - Tranche 1 covers 3 Projects. Updates for each: (1) Workforce Development Project – complete (2) ITSM Phase 1 – Design build and testing complete in the process of training and rolling out to production environment (3) Storage and Compute – Detailed design complete, hardware installed and Citrix environment currently being built.
Q4 17-18 | Department of Education and Training | DET | 2540 | Premiers Reading Challenge | Education | Customer Relationship Management | The build of a replacement application and a new Mobile App for the annual Premiers’ Reading Challenge that supports children’s engagement with reading – the foundation for all education and development. | Initiated |  | Hybrid - Agile and PRINCE2 | 2017-02-15 | 2018-07-25 | [15 empty] | Evaluation of the Request For Quote (RFQ) has concluded. The awarding of the contract is on track for early July 2018.
Q4 17-18 | Office of Public Prosecutions | OPP | 2541 | Virtual Storage Integrator (VSI) & Storage Refresh | Law and Justice | Data Management | ICT Data Storage Refresh (Production & Disaster Recovery Sites). | Delivery |  | PRINCE2 | 2018-03-16 | 2018-03-23 |  | 2018-03-23 |  |  | 2018-03-23 | 2018-03-23 | 2018-06-30 | 2018-08-31 | 1049853 |  |  |  |  | Green | Amber | There have been delays caused by gaps found in the proposed solution based on the initial requirements. An alternative solution has been sourced by Vendor at no cost to OPP. The project is currently in POC (Proof of Concept) with a revised completion date forecast for 31 August 2018.
Q4 17-18 | Department of Premier and Cabinet | DPC | 2542 | My Victoria | Business and Industry | Analyses and Statistics ,Data Management,Knowledge Management ,Visualisation | An innovative digital platform using open data displaying Government infrastructure, and incorporating location intelligence such as demographics and market analysis in a map-based interface. My Victoria will help business make informed decisions. | Delivery |  | Agile | 2017-05-30 | 2017-08-01 |  | 2017-08-01 | 100000 |  | 2018-02-26 |  | 2018-07-13 |  | 3050000 |  |  |  |  | Green | Green | MyVictoria is approximately 2 weeks behind schedule due to increased testing requirements however MyVictoria will still be delivered within budget. Feedback from peak bodies departments and agencies within Victoria has been positive. Showcases have been held with selected external stakeholders who have given positive feedback on the product. MyVictoria Release 1 is almost complete with just re testing of new data to be completed.
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2543 | BASC Uplift project | Government and Economy | Assets/Materials Management | This project will procure additional specialist servers and data storage resources that will replace end of life components and uplift capacity based on business requirements. | Delivery |  | PRINCE2 | 2017-08-24 | 2018-10-31 | 2017-10-31 | 2017-11-14 | 0 |  | 2018-04-13 |  | 2018-10-29 |  | 9662000 |  |  |  |  | Green | Green | The project has progressed with the implementation of the BASC hardware and software and the uplift of the UPS.
Q4 17-18 | Department of Health and Human Services | DHHS | 2544 | Clinical Information Sharing | Health | Development and Integration | ICT activities to support the implementation of a Clinical Information Sharing Platform to facilities sharing of information between health services. | Delivery |  | PRINCE2 | 2017-10-01 | 2018-01-31 |  | 2018-01-31 | 0 |  | 2018-02-01 |  | 2020-12-31 |  | 18180000 |  |  |  |  | Green | Green | Project procurement is progressing to schedule.
Q4 17-18 | CenITex | CenITex | 2545 | Software Defined DC Hosting Services | Government and Economy | Assets/Materials Management | Transform the current hosting services into a modern, software defined data centre | Delivery |  | PRINCE2 | 2018-01-03 | 2018-01-16 |  | 2018-01-17 |  |  | 2018-02-19 |  | 2019-06-30 |  | 2197700 |  |  |  |  | Green | Green | Hardware vendor procurement process has been completed. Statement of work for VMWare configuration has also completed. Engagement has commenced to plan the physical installation of the hyperconvergence environment - design phase for VMWare environment is underway.
Q4 17-18 | WorkSafe Victoria | WorkSafe | 2546 | IBM Transformation | Government and Economy | Systems Management | Transition to new supplier, transformation, data centre migration and implementation of Service Now. | Delivery |  | PMBoK | 2017-11-20 | 2017-11-20 |  | 2017-11-20 | 0 |  | 2017-11-20 |  | 2018-12-10 |  | 2436940 | 2683940 |  |  |  | Green | Amber | The project overall is tracking amber due to changes in schedule for data centre migrations. From a cost perspective, the project is tracking to approved budget.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2547 | Business System Support Reporting - Finance | Employment and Workplace | Customer Relationship Management | Implementation of core financial and budgeting solution for DELWP. The project will be implementing cloud-based solutions with integration into existing solutions within the DELWP environment | Initiated |  | PRINCE2 | 2018-02-01 | 2018-09-30 | [15 empty] | Preparation for RFT for Systems Integration partner finalisation. Confirmation of business requirements and scope for delivery. Engagement with procurement support partner completed.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2548 | Workplace 2020 - Application Refresh | Employment and Workplace | Communication | Reduce email platform hosting, storage and maintenance costs​ and supporting a flexible and mobile workforce​, by providing a consistent and integrated user experience leveraging Office 365​ | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-02-05 | 2018-03-29 |  | 2018-04-23 | 60000 |  | 2018-09-07 | 2018-09-07 | 2019-06-30 | 2019-06-30 | 2240000 | [5 empty] | Amber | Project rescheduling to align to device refresh and WoVG resourcing scheduling
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2549 | Workplace 2020 - Device Refresh | Employment and Workplace | Financial Management | Establish a sustainable funding model by implementing a workforce Personas model in order to modernise and rationalise the End User Computing device fleet | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-12-04 | 2018-02-28 |  | 2018-03-23 | 100000 |  | 2018-08-02 |  | 2019-03-29 |  | 2360000 | [5 empty] | Amber | Project is behind schedule due to vendor supply issues with providing hardware.. Project is on track to deliver future savings
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2550 | Workplace 2020 - Communication and Collaboration | Employment and Workplace | Communication | Leveraging on Office 365 investments and existing collaboration tools ​to shift from traditional phone systems to soft phones, and integrate with existing collaboration solutions and platforms | Postponed | 2018-04-11 | Hybrid - Agile and PRINCE2 | 2017-11-27 | 2018-06-29 |  |  | 40000 | [12 empty] | Completion of initiation has been delayed to focus resources on Device and Application streams.
Q4 17-18 | Energy Safe Victoria | ESV | 2551 | Certificates of Electrical Safety | Emergencies and Safety | Management of Process | Review and replacement of existing legacy system into ESV's ESVConnect constituent portal. | Delivery |  | Agile | 2018-02-05 | 2018-05-04 | 2018-03-29 | 2018-04-18 | 0 | 384000 | 2018-04-22 |  | 2018-11-15 |  | 0 | 1736000 |  |  |  |  | Green | Proceeding as planned
Q4 17-18 | Public Transport Victoria | PTV | 2552 | PTV Digital Workplace - Email and Calendar | Transport and Vehicles | Communication | This project will transition all PTV staff from Windows 7 & Lotus Notes to Windows 10 Office 365 and Notes 9. This project is PTV's component of a DEDJTR wide program. | Delivery |  | PTV Investment Lifecycle | 2017-03-10 | 2017-08-27 |  | 2017-08-27 | 55836 |  | 2017-08-28 | 2017-11-16 | 2018-10-12 | 2018-11-16 | 2444164 |  |  |  |  | Green | Amber | There have been some technical challenges and deployment delays which the project is managing. Forecast practical completion has been revised by a month to mid-November 2018.
Q4 17-18 | Yarra Valley Water | YV Water | 2560 | CC&B Upgrade | Environment and Water | Financial Management | Upgrade Customer Care and Billing application to v2.6 | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-01-08 | 2018-03-05 |  | 2018-03-13 | 831000 |  | 2018-03-13 | 2018-03-13 | 2018-09-30 | 2018-11-30 | 1196200 |  |  |  |  | Green | Green | Upgrade on track, cutover is dependant on Enterprise Hosting Platform replacement project.
Q4 17-18 | Department of Environment, Land, Water and Planning | DELWP | 2561 | Digital Cadastre Modernisation Project | Property and Planning | Knowledge Management | The Digital Cadastre Modernisation project has a mission to upgrade of the State's digital cadastre for land use management | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-02-12 | 2018-09-30 | [15 empty] | The initial stage of work currently underway is pure data capture and cleansing
Q4 17-18 | Public Transport Victoria | PTV | 2562 | Metropolitan Train Control (Metrol) Replacement | Transport and Vehicles | Systems Management | Replacement of the Metrol signalling control system with a Core Train Control and Monitoring System (TCMS); Replacement of Train Operational Reporting System (TOPS) with Performance Reporting System (PRS); Upgrade of the PRIDE passenger info system. | Delivery |  | PTV Investment Lifecycle | 2005-07-01 | 2006-08-21 |  | 2006-08-21 | 1100 |  | 2007-03-06 | 2007-03-06 | 2018-07-31 | 2018-10-30 | 92498900 |  |  |  |  | Amber | Amber | In January 2018 the Steering Committee approved schedule changes to accommodate LXRA capital works and Build 5 interfaces. Build 5 (the final build) is scheduled to be deployed by 11 Oct 2018. Practical completion continues to be forecast for October 2018.
Q4 17-18 | Eastern Health | EH | 2563 | Single Billing System Project | Health | Data Management,Development and Integration ,Financial Management | Deliver a single billing system to replace up to 17 legacy systems used for patient accounts billing for Eastern Health | Delivery |  | PRINCE2 | 2017-07-01 | 2018-02-04 | 2018-03-28 | 2018-03-28 | 508851 |  | 2018-04-17 |  | 2020-06-30 |  | 6839088 | [5 empty] | Amber | Delivery of the Single Billing System will be re-planned around the Patient Client Management System Project re-planning that is occurring. Target for replanning to be completed by November 2018
Q4 17-18 | Coliban Region Water Corporation | Coliban Water | 2564 | Billing CRM SRM System Project | Environment and Water | Customer Relationship Management | The project will design and adopt new business practices and technology for billing, revenue, customer solutions and customer service to enable the organisation to efficiently and effectively deliver value to customers | Initiated |  | Agile | 2018-02-04 | 2018-08-31 |  |  | 700000 | [12 empty] | Phase 1 technical and business initiation activities are in progress and on track for planned completion at the end of August 2018
Q4 17-18 | Melbourne Water | MELB Water | 2565 | Asset management system upgrade | Environment and Water | Assets/Materials Management | Asset management core system upgrade to current version | Delivery |  | Agile | 2017-10-18 | 2018-03-26 |  | 2018-05-18 | 0 |  | 2018-05-18 |  | 2019-03-05 |  | 2122131 | [5 empty] | Green | Initial build in development environment in progress. System testing commenced. Improvement requirements prioritised with workshops in progress. Project assessing a pure Agile implementation approach for further Asset Management System improvements.
Q4 17-18 | Coliban Region Water Corporation | Coliban Water | 2567 | Digital Customer Metering Program | Environment and Water | Data Management | To automate manual meter reading to improve business intelligence, asset management and network planning | Delivery |  | PMBoK | 2016-01-18 | 2017-07-25 |  | 2017-07-25 | 72000 |  | 2017-07-25 |  | 2023-06-30 |  | 5448000 |  |  |  |  | Green | Green | Program is on target
Q4 17-18 | Westernport Region Water Corporation | WPR Water | 2568 | Business Transformation Project | Government and Economy | Systems Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | WPW is looking to replace its current ICT managed services environment services solution which includes Part 1: Corporate System Replacement and Part 2: IT Managed Services environment | Delivery |  | PRINCE2 | 2017-07-01 | 2018-05-07 | 2018-01-30 | 2018-03-19 | 2089200 | 135000 | 2018-05-07 |  | 2020-06-30 |  | 0 | 1954200 |  |  |  |  | Green | The project is within the project schedule and currently on time and within budget.
Q4 17-18 | VicRoads | VicRoads | 2569 | NHVR Initiatives Project | Transport and Vehicles | Collaboration ,Development and Integration ,Management of Process | The National Heavy Vehicle Regulator(NHVR)Initiatives project will assist VicRoads to provide the NHVR with visibility of the entirety of the heavy vehicle fleet across Australia, and assist the NHVR in its role in the Australian Government reform. | Delivery |  | Agile | 2018-03-19 | 2018-05-14 |  | 2018-05-15 | 154000 |  | 2018-05-31 |  | 2018-12-21 |  | 3000000 | [5 empty] | Amber | Project is in amber status due implementation issues. Implementation is broken in to two parts with phase 1 implementation on 1st October 2018 (MVP) and phase 2 release late November 2018.
Q4 17-18 | Department of Justice and Regulation | DJR | 2570 | Justice eProcurement Implementation (JEPI) Project | Law and Justice | Management of Process | Implementation of department wide electronic sourcing and contract management system. | Delivery |  | Project Management Excellence | 2016-06-30 | 2017-11-24 |  | 2017-11-24 |  |  | 2018-01-01 | 2018-01-01 | 2018-11-12 | 2018-12-24 | 1530000 |  |  |  |  | Amber | Amber | The Zycus software has been configured to meet DJR requirements. Initial DJR testing of the system has commenced. A slower than expected analysis of DJR requirements has led to an overall slippage of the implementation from August to October 2018.
Q4 17-18 | Department of Justice and Regulation | DJR | 2571 | EPSE - Catalogue, Purchasing and Supplier Enhancement Project | Law and Justice | Management of Process | The EPSE project will implement a series of improvements to the system and processes staff use to make purchases, as well as supplier enhancements including a supplier portal. | Delivery |  | Project Management Excellence | 2017-06-26 | 2018-01-30 |  | 2018-01-30 |  |  | 2018-02-01 |  | 2018-11-23 |  | 2296400 |  |  |  |  | Amber | Amber | Initial stages are complete with the rollout of 'purchase to pay' policy processes and training to over 1000 staff. Current stages for supplier enhancements and additional system modules are now in delivery with Pilot of Supplier Portal commencing on 13 August 2018.
Q4 17-18 | Department of Health and Human Services | DHHS | 2572 | The Victorian Protective Data Security Framework and Standards reporting to Office of the Victorian Information Commissioner | Community Services | Security Management | To undertake a security risk profile assessment against the Victorian Protective Data Security Standards (VPDSS) and develop a Protective Data Security Plan for submission to OVIC by August 2018. | Delivery |  | PRINCE2 | 2017-08-16 | 2017-09-04 |  | 2017-10-26 |  |  | 2017-11-02 |  | 2018-08-31 |  | 1000000 |  |  |  |  | Green | Green | Project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2573 | After hours Child Protection Service Rostering Solution implementation | Community Services | Development and Integration | A new system is proposed to replace existing manual paper based systems to improve usability and visibility of roster, time and attendance information for managers and staff, reduce administration burden, reduce errors, improve reporting and analysis | Delivery |  | PRINCE2 | 2016-06-25 | 2016-07-20 |  | 2016-07-20 | 10520 |  | 2017-03-06 | 2017-03-06 | 2018-07-31 | 2018-08-31 | 1191316 | 1197623 |  |  |  | Green | Green | Solution delivered and project close activities underway.
Q4 17-18 | Department of Health and Human Services | DHHS | 2574 | HiiP Financial Reporting | Community Services | Development and Integration | The primary objective of the project is to provide a consolidated platform for all housing financial management. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-09-25 | 2018-07-31 | 2018-04-18 | 2018-04-18 | 400000 |  | 2018-04-24 |  | 2019-06-30 |  | 3407062 | [5 empty] | Green | Project is progressing to schedule.
Q4 17-18 | Department of Health and Human Services | DHHS | 2575 | Bond Loans Streamlining Project | Community Services | Forms Management | To move Bond Loan processing by DHHS to an entirely electronic platform. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-03-05 | 2018-04-27 |  | 2018-04-27 | 0 |  | 2018-04-28 |  | 2018-11-30 |  | 1758252 | [5 empty] | Amber | Project is progressing but has had a scope change and is being re-baselined as a result.
Q4 17-18 | Department of Health and Human Services | DHHS | 2576 | Human Capital Management System | Employment and Workplace | Human Capital / Workforce Management | Implementation of a cloud based Human Capital management system will uplift and modernise the department's human resources systems and deliver consistent human resources services across the department and secondly across the Victorian Public Service. | Delivery |  | Agile | 2017-11-30 | 2018-06-04 | 2018-03-29 | 2018-03-29 | 300000 |  | 2018-04-03 |  | 2020-06-30 |  | 8987000 | [5 empty] | Amber | Project scope and management issues are being addressed.
Q4 17-18 | Department of Health and Human Services | DHHS | 2577 | Victorian Health Incident Management System - Central Solution (VHIMS CS) | Health | Development and Integration | The project provides a new single common scalable and efficient incident and feedback management platform capable of capturing the new streamlined VHIMS2 dataset through a web browser to the 50 Victorian public health services. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-09-01 | 2017-11-10 |  | 2018-05-22 | 200000 |  | 2018-05-22 |  | 2018-09-30 |  | 2158298 | [5 empty] | Green | Project progressing to schedule.
Q4 17-18 | Grampians Rural Health Alliance | GRHA | 2578 | DjHS Paient Administration System Upgrade | Health | Investment Management | Upgrade of Patient Administration System at Djerriwarrh Health Services, including moving to a region hosted environment. | Initiated |  | PMBoK | 2018-06-18 | 2019-04-29 | [15 empty] | Project has been initiated and the scope is defined and contained in the PID. A Governance Structure has been established and the groups that make up this structure have met with the terms of reference for each group establishing the governance framework. The project activity is progressing against the current schedule and is being reported as on track (green).
Q4 17-18 | VicRoads | VicRoads | 2579 | Service Oriented Licencing and Registration (SOLR) | Transport and Vehicles | Development and Integration | Purpose of this project is to create a modern services based platform to work in parallel with VicRoads Registration and Licencing mainframe system. | Initiated |  | Agile | 2018-06-06 | 2018-08-30 | [15 empty] | Business case has been completed following successful proof of concept. Awaiting funding decision to be made by executive leadership team.
Q4 17-18 | Transport Accident Commission | TAC | 2580 | Employee Experience & Enablement | Transport and Vehicles | Customer Initiated Assistance | Application Remediation - Ensuring all TAC applications are compatible with Windows 10 and Office 365 before implementing. | Delivery |  | PRINCE2 | 2018-03-26 | 2018-04-03 |  | 2018-04-04 | 0 |  | 2018-06-01 |  | 2018-10-31 |  | 1864995 | [5 empty] | Green | As a minor concern the TAC application survey has highlighted that over 100 software applications exist without ITSS awareness or support. The project is working with the business to ensure as little disruption as possible during the transition phase and will develop a strategy to handle the testing on Windows 10.
Q4 17-18 | Department of Justice and Regulation | DJR | 2581 | 50 Franklin Street Fit-out | Law and Justice | Organisational Management | Multi staged IT fit-out for new premises at 50 Franklin St to co-locate Corrections Victoria staff and other DJR business units (17 level building). | Delivery |  | Project Management Excellence | 2018-03-07 | 2018-04-16 |  | 2018-04-16 |  |  | 2018-04-17 |  | 2018-12-31 |  | 4587466 | [5 empty] | Green | The precise go live dates for the three stages in September, October and November are still to be confirmed. ICT works comprising procurement, configuration and deployment are well advanced for the first two stages. ICT works for the third stage have not yet commenced and are pending receipt of the the proposal from the department's ICT vendor.
Q4 17-18 | Department of Health and Human Services | DHHS | 2582 | Victorian Alcohol and Drug Collection Implementation | Health | Data Management,Reporting | The Victorian Alcohol and Drug Collection (VADC) implementation supports Victorian-Government funded alcohol and drug treatment service providers to submit data to the Department each month in accordance with the specification and business rules. | Delivery |  | PRINCE2 | 2016-05-27 | 2016-12-31 |  | 2017-06-22 | 130900 | 161700 | 2017-07-01 |  | 2018-12-31 |  | 727000 | 1320000 |  |  |  |  | Red | Delivery to the project schedule has been impacted by resource constraints and external dependency delays, which are being addressed.
Q4 17-18 | Public Transport Victoria | PTV | 2586 | Train Control and Monitoring System (TCMS) Urgent Remediation Work - Phase 2 | Transport and Vehicles | Analyses and Statistics | Introduction of additional fault alerting and network monitoring capabilities in the TCMS. | Initiated |  | PTV Investment Lifecycle | 2018-03-15 | 2018-06-29 |  |  | 50000 | [12 empty] | Project expected to commence delivery in Q1 2018/19.
Q4 17-18 | Eastern Health | EH | 2587 | RosterOn project | Health | Human Capital / Workforce Management | Implement a new rostering, time and attendance system for all areas of Eastern Health. Objective is to replace manual, disparate administrative processes with automated electronic systems. | Initiated |  | PRINCE2 | 2015-10-12 | 2018-08-10 |  |  | 190135 | [12 empty] | The project has been mobilised in preparation for commencing implementation activities. The Business Case and the Steering Committee Terms of Reference were approved in early July'18. Initial implementation activities have commenced with design workshops. Recruitment is underway for the project team personnel. The high-level schedule is complete and the detailed (GANTT) schedule for stages 1 and 2 (system design, development, testing and Change Management) is complete. Activities for stage 3 (Rollouts, beginning in April 2019) will be added to the detailed schedule over the coming months.
Q4 17-18 | City West Water Corporation | CW Water | 2591 | HRIS (1003210) | Environment and Water | Human Capital / Workforce Management | Anew system to support the strategic environment and address existing issues around departments not having a dedicated HR system to perform HR processes and reporting requirements. | Delivery |  | Waterfall and Agile | 2017-08-24 | 2018-04-12 |  | 2018-04-12 | 122000 |  | 2018-04-12 |  | 2019-09-30 |  | 2935906 | [5 empty] | Green | Overall, this project is going well within budget and timeline.
Q4 17-18 | City West Water Corporation | CW Water | 2592 | HSEQ (1006412) | Environment and Water | Data Management | This project is focused on providing CWW with an integrated and consistent approach to managing Health, Safety, Environment, Quality & Risk frameworks (processes policies procedures etc.). | Delivery |  | Waterfall and Agile | 2017-08-24 | 2018-04-12 |  | 2018-04-12 | 93000 |  | 2018-04-12 |  | 2019-02-01 |  | 1213348 | [5 empty] | Green | Overall, the project is progressing well within budget and timeline.
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2594 | HRIS Project | Government and Economy | Data Management,Human Capital / Workforce Management ,Human Resources,Organisational Management | The core outcomes include: a simpler flexible mobile friendly more comprehensive HR self-service processes; streamlined and efficient payroll operations processes; and a single source of authoritative workforce and organisational structure data. | Delivery |  | PRINCE2 | 2017-11-13 | 2017-11-13 |  | 2017-11-13 |  |  | 2018-04-02 | 2018-05-01 | 2019-03-31 | 2019-03-31 | 1830000 | [5 empty] | Green | The project has commenced with terms of reference endorsed project initiation document distributed for approval milestones and project plan established. Deliverables for this quarter include commencement of data remediation work and business requirements for feasibility study on proposed system.
Q4 17-18 | Department of Economic Development, Jobs, Transport and Resources | DEDJTR | 2595 | GEMS 2.0 | Government and Economy | Business Intelligence,Data Management,Knowledge Management ,Reporting | This project will deliver improved accessibility, user interface and user experience for the Global Engagement Management System (GEMS). | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-05-08 | 2018-10-02 |  |  | 1300000 | [12 empty] | The Project brief is being progressed through the project control board (PCB).
Q4 17-18 | VicRoads | VicRoads | 2596 | Human Resource Information System (HRIS) | Transport and Vehicles | Development and Integration ,Human Capital / Workforce Management ,Human Resources | Objective of this project is to implement a fully integrated centralised and mobile friendly solution to provide one stop shop for people and culture function | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-04-16 | 2018-07-30 | [15 empty] | Project is on track. Procurement activities are ongoing.
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering and Time & Attendance Project | Health | Management of Process | This project will introduce a software solution which will enable; process automation, improve accuracy and timeliness and provide better user experience through inclusion of mobile technologies as standard operating model. | Delivery |  | TBC | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 |  | 3443281 | [5 empty] | Green | Project approved and delivery phase commenced. Development of the detail project plan in progress.
Q4 17-18 | CenITex | CenITex | 2598 | 80 Collins Street South Tower Fit-Out Design | Government and Economy | Assets/Materials Management | Develop office fit-out design and workplace strategy for Cenitex staff in new accommodation | Delivery |  | PRINCE2 | 2018-04-26 | 2018-05-14 |  | 2018-05-15 | 0 |  | 2018-05-16 |  | 2020-08-31 |  | 1625096 | [5 empty] | Green | Concept design submission has been successfully completed. Currently working on schematic design which is planned to be completed during Q1 FY18/19.
Q4 17-18 | South West Alliance of Rural Health | SWARH | 2599 | Barwon Health PROMPT Rebuild | Health | Document Management | Barwon Health is undertaking a full rebuild of the PROMPT document management system. The rebuild will ensure that the new PROMPT is extensiblemaintainable and sustainable for future needs adding value to Health Services safety and quality programs. | Delivery |  | TBC | 2018-04-19 | 2018-05-30 |  | 2018-06-01 | 1 |  | 2018-06-04 |  | 2019-06-30 |  | 1300000 | [5 empty] | Green | Tender BH_2018-1010 was released 4/6/2018. Currently evaluating Tender responses and selection.
Q4 17-18 | VicRoads | VicRoads | 2600 | V-Plates Redevelopment Project | Transport and Vehicles | Management of Process | Purpose of this project is to redevelop the V-plates website and automation of the business processes related to V-plates functions. | Initiated |  | Agile | 2018-05-21 | 2018-07-23 | [15 empty] | Project is at initiation/planning stage. Detailed planning workshops are in progress.
Q4 17-18 | WorkSafe Victoria | WorkSafe | 2602 | IAAS Transition | Government and Economy | Systems Management | Transition of IT infrastructure services to an external provider. | Delivery |  | PMBoK | 2017-09-01 | 2017-10-18 |  | 2017-10-18 | 0 |  | 2017-10-18 | 2017-10-18 | 2018-06-30 | 2019-01-31 | 834030 | 1091006 |  |  |  |  | Amber | Project is reporting amber, due to changes in schedule for transition to service and IT Operations Management completion.
Q4 17-18 | Department of Health and Human Services | DHHS | 2603 | Regulatory Licensing and Registration Platform | Health | Systems Management | Replacement of the Radiation Registration and Licensing (RELIC) system utilised by the Environmental Health Regulation & Compliance Unit to administer their Act & legislation. Development of a platform configurable for other DHHS regulatory units. | Delivery |  | Agile | 2017-10-20 | 2017-11-05 |  | 2017-11-05 |  |  | 2017-11-06 |  | 2019-06-30 |  | 2400000 | [5 empty] | Green | Project is progressing to schedule.
Q4 17-18 | Wannon Region Water Corporation | WAN Water | 2604 | Works Management System | Environment and Water | Assets/Materials Management | Replacing two legacy works management systems. | Delivery |  | PRINCE2 | 2017-07-01 | 2018-08-01 |  | 2018-08-01 | 50000 |  | 2018-08-01 |  | 2018-12-14 |  | 1200000 | [5 empty] | Green | Project tracking well.
Q4 17-18 | City West Water Corporation | CW Water | 2605 | Data and Analytics (1006380) | Environment and Water | Data Management | This project has been created to deliver an enterprise data platofrm with an ongoing capability to manage and make data available to the business through storage, integration and accessibility. | Initiated |  | Blend of Waterfall and Agile | 2017-02-02 | 2018-06-30 |  |  | 191000 | [12 empty] | This is a 3 phased approach to project delivery is via an initial pilot and 2 additional phases of wider business rollout - with the entire project to conclude in 2020.
Q4 17-18 | City West Water Corporation | CW Water | 2606 | Digital Metering - E2E pilot (1006692) |  | Assets/Materials Management,Collaboration | This project (proof of concept) has been created to deliver the IT Stream of the bigger Digital Metering Program, a joint program amongst the 3 water retailers (SEW, YVW, CWW). | Initiated |  | Blend of Waterfall and Agile | 2017-11-02 | 2018-06-30 |  |  | 380000 | [12 empty] | The CWW overall program is being delivered, managed and monitored by the Strategy and Planning team. Implementation will require further detailed planning and analysis.
Q4 17-18 | City West Water Corporation | CW Water | 2607 | Disaster Recovery (1003418) | Environment and Water | Security Management ,Systems Management | ​This project has been created to provide a workable and compliant Distaster Recovery Solution that allows CWW to recover systems and operate the core business in the event of a disaster being declared concerning the ADC (Active Data Centre ). | Initiated |  | blend of Waterfall and Agile | 2017-03-15 | 2018-06-30 |  |  | 20000 | [12 empty] | A full scope of deliverables will be reviewed in Q1 FY 18-19
Q4 17-18 | City West Water Corporation | CW Water | 2608 | PCI Compliance (1007060) | Environment and Water | Security Management | The Payment Card Industry (PCI) Data Security Standard (DSS) Version 3.2 is a suite of requirements set by the PCI DSS Council, composed of representatives from the major credit card companies. | Initiated |  | PRINCE2 | 2017-12-31 | 2018-06-30 | [15 empty] | This project is at its very early stage.
Q4 17-18 | Melbourne Convention and Exhibition Centre | MCEC | 2610 | People Systems Project | Government and Economy | Human Capital / Workforce Management | People Systems Project (formerly Human Resources Information System - HRIS) | Delivery |  | PRINCE2 | 2015-11-11 | 2016-02-10 |  | 2016-04-29 | 1 |  | 2017-02-16 | 2016-06-01 | 2019-02-08 | 2019-02-28 | 1080000 | [5 empty] | Amber | Vendor integration challenges have resulted in project delivery time to move out.
Q4 17-18 | Melbourne Convention and Exhibition Centre | MCEC | 2613 | Wireless Infrastructure Upgrade | Government and Economy | Communication,Systems Management | Upgrade all of the wireless infrastructure across all of Melbourne Convention and Exhibition Centre. | Closed - Completed | 2018-06-28 | PRINCE2 | 2016-02-24 | 2017-02-23 |  | 2017-04-04 | 1 |  | 2017-08-08 |  | 2018-06-28 |  | 1840304 | [5 empty] | Green | Wireless project completed on time and within budget.