## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q1 22-23 | Q2 22-23 | Q3 22-23 | Q4 22-23 | Q1 23-24 (Current) | Reporting Comments
Q1 23-24 | Country Fire Authority | CFA | 2151 | CFA Short Status Messaging (SSM) | Emergencies and Safety | Communication | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2024-06-30 | 2850000 |  | Green | Green | Green | Amber | Amber | The project is reporting an Amber status due to system integration issues. The project team continues to work with the vendor to resolve the issues.
Q1 23-24 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2280 | Royal Victorian Eye and Ear Hospital - ICT Redevelopment Stage 3 Hardware Tender and Implementation | Health | Systems Management | Fit-out of new IT infrastructure to support hospital redevelopment objectives | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2013-07-01 | 2014-06-30 |  | 2014-06-30 | 0 | 0 | 2014-06-30 | 2014-06-30 | 2018-12-31 | 2024-03-30 | 0 | 1550266 | Green | Green | Green | Green | Green | Awaiting final Occupancy Permits and FF&E will begin based on the timings. Equipment is delivered and in storage and ready to be installed.
Q1 23-24 | Northern Health | NH | 2411 | Northern Health EMR Program | Health | Analyses and Statistics ,Collaboration ,Communication,Organisational Management ,Records Management | Implementation of an Electronic Medical Record at Northern Health including all sites | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2023-09-04 | PRINCE2 | 2016-10-18 | 2018-05-01 | 2021-02-01 | 2021-02-02 | 0 | 0 | 2021-02-08 |  | 2022-12-18 | 2023-09-04 | 38700000 | 46024365 | Amber | Amber | Green | Amber | Green | The roll out was extremely successful. We are now moving the project team to a business as usual operation mode.
Q1 23-24 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2024-06-30 | 89200000 | 126956000 | Red | Red | Red | Amber | Amber | • The overall project status is amber given the additional funding received to support continued delivery in FY2023/24. The project schedule remains at risk given delays against baseline delivery schedule.
Q1 23-24 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 |  | 9680463 |  |  |  |  | Green | Green | The overall health of the Project is on-track.
Q1 23-24 | Goulburn Valley Region Water Corporation | GVR Water | 2524 | Asset Management Information System Replacement Project | Environment and Water | Assets/Materials Management | Implement mature, industry proven Asset Management Information and Geographic Information Systems meeting the requirements of the organisation, delivering improvements and efficiencies not previously achievable with the current solutions | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Internal GVW Project Management Methodology | 2016-11-23 | 2017-12-08 |  | 2017-12-08 | 50000 |  | 2018-01-02 |  | 2021-03-31 | 2024-06-30 | 2405000 | 4898673 | Green | Green | Green | Amber | Amber | The project budget and schedule has been revised. The new schedule is currently off track by approximately 2 weeks due to delays in completing data loading activities. The solution delivery date is now the 20th of December.
Q1 23-24 | Department of Transport and Planning | DTP | 2561 | Digital Cadastre Modernisation Project | Property and Planning | Knowledge Management ,Data Management | Digital Cadastre Modernisation will bring the authoritative map of Victoria’s property boundaries further into the digital age, ensuring that one of the State’s most important datasets is accurate, useful, and easy to maintain. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-02-12 | 2018-09-30 |  | 2018-09-30 | 0 | 200000 | 2018-11-16 |  | 2023-12-30 | 2023-12-30 | 0 | 47200000 | Green | Green | Green | Green | Green | All work-streams are on track - no intervention or actions required
Q1 23-24 | Coliban Region Water Corporation | Coliban Water | 2567 | Digital Customer Metering Program | Environment and Water | Data Management,Assets/Materials Management,Business Intelligence,Reporting | To automate manual meter reading to improve business intelligence, asset management and network planning to enable benefits for customers. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial) |  | PMBoK | 2016-01-18 | 2017-07-25 |  | 2017-07-25 | 72000 |  | 2017-07-25 |  | 2023-06-30 | 2024-06-30 | 5448000 | 9001000 | Amber | Green | Green | Green | Green | Deployment in Bendigo progressing according to plan.
Q1 23-24 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2024-10-31 | 3443281 | 7326930 | Red | Red | Green | Green | Amber | 5 EBA awards in final stage of testing. All awards are to be built, tested and deployed by 31 January 2024 to increase flexibility for rolling out units. Roll out to commence from November 2023 until December 2024.
Q1 23-24 | Department of Education | DE | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage school land & building assets enabling evidence-based decision making at both DE Corporate & School level & support attestation against Asset Management Accountability Framework. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2023-10-31 | 12956778 | 22169291 | Green | Green | Green | Green | Amber | AIMS Corporate Release 3 (CR3) and Corporate Release (CR4) Delivery is progressing. Complex design requirements have delayed the build of the Computer-Aided Design module. The estimated completion of Corporate Release 3D is now expected to be October 2023. This will not cause delay to the overall project.
Q1 23-24 | Victorian Rail Track | VicTrack | 2797 | Transport and Government Secure Network (TGSN) | Transport and Vehicles | Routing and Scheduling | To upgrade VicTrack's fixed Telecommunications network. The current network has various elements which are obsolete or becoming obsolete there is lack of spare equiments and reduced vendor support. 3 years project to deliver new technology. | Delivery | Risk Reduction (Non Financial) |  | VicTrack PMF | 2019-06-03 | 2019-10-01 | 2020-03-02 | 2020-03-02 | 0 | 0 | 2020-03-02 |  | 2023-06-30 | 2024-03-31 | 69000000 | 74400000 | Amber | Amber | Green | Green | Green | Reporting Green and progressing with migrations as planned with target completion early 2024.
Q1 23-24 | Department of Health | DH | 2812 | Oracle Financials Upgrade | Community Services | Financial Management | The project will deliver an Oracle upgrade to the latest release of Oracle Cloud platform including the Chart of Accounts rationalisation and standard business processes to provide DH and DFFH with an efficient financial and procurement system. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-05-20 | 2019-12-31 | 2019-11-29 | 2019-11-29 | 1885550 | 964956 | 2021-05-05 |  | 2022-12-30 | 2024-06-30 | 25475450 | 33287973 | Amber | Amber | Amber | Amber | Red | Program has completed the detailed process and design requirements for the ERP Stream. Consideration is underway for inclusion of Oracle EPM which would result in avoidance of cost to remediate legacy technology. Program is Red pending approval of additional funding and re-baselining of the end to end integrated schedule which is expected to be completed in the next reporting period.
Q1 23-24 | Yarra Valley Water | YV Water | 2821 | Operational Historian | Environment and Water | Data Management | Acquisition, storage, analysis, and presentation of large volumes of time series data – allowing it to be combined with data from other core systems for analysis and improved decision making. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2018-11-01 | 2019-08-30 | 2019-12-27 | 2019-12-27 | 240000 | 300000 | 2019-12-30 | 2020-01-01 | 2021-12-30 | 2023-11-30 | 4778000 | 7355080 | Green | Green | Green | Green | Green | Project technical deliverables progressed Asset framework structure established Data remediation work progressed with slight delay due to resourcing constrained, low level risk contained by project Project team training completed Change management strategy defined
Q1 23-24 | Yarra Valley Water | YV Water | 2822 | Network Communications and IoT Device Management | Environment and Water | Assets/Materials Management | IoT device telecommunications services and device management platform. | Delivery | Cost Reduction (Financial) |  | PRINCE2 | 2019-05-01 | 2020-01-31 | 2020-10-14 | 2020-10-14 | 350000 | 1300000 | 2020-10-19 |  | 2022-06-30 | 2024-11-30 | 3715000 | 3715059 | Green | Green | Green | Green | Amber | Project schedule delayed due to resource impacts. This is being reviewed and escalated with project team and stakeholders
Q1 23-24 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end to end business processes across meter management, billing and alerts & alarms. This will enable customer data to be exposed via the portal and internal CSO views as well as monitoring meter and water usage behaviour. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 |  | 2020-02-28 | 2024-04-30 | 0 | 19000000 | Green | Green | Green | Green | Green | New connections work has commenced. Go live date is due April 2024
Q1 23-24 | Department of Transport and Planning | DTP | 2825 | Automated Vehicle Monitoring Replacement (AVMR) | Transport and Vehicles | Analyses and Statistics ,Assets/Materials Management,Systems Management,Communication | The tram AVM system is used for the preparation management and monitoring of all tram services across the tram network. It is used to communicate with drivers and monitor and record tram location and status. | Postponed |  | 2022-07-01 | PTV Investment Lifecycle | 2018-07-02 | 2020-06-30 | 2023-12-18 |  | 2800000 | 0 |  |  |  |  | 0 | [6 empty] | Project is on hold.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 2832 | Practice Management System | Law and Justice | Tracking and Workflow | This project will replace the existing VGSO's Practice Management System to provide streamlined processes improved information sharing and increased data capture. | Delivery | Cost Avoidance (Financial), Increased Revenue (Financial) |  | Project Management Excellence | 2018-08-31 | 2018-09-07 |  | 2018-09-07 | 0 |  | 2019-09-30 |  | 2021-04-01 | 2023-12-31 | 1400000 | 1500000 | Green | Green | Amber | Amber | Green | A decision has been made to not proceed with the last module of the Practice Management System. Finances are being finalised for project closure.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2026-06-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project's delivery date has been extended as a result of numerous constraints such as limited resources and service provider availability caused by the pandemic significant delays in quality responses from providers global shortages affecting product availability for trials, a review of the State Victorian Radio Network Service Delivery Model and the inclusion of Department of Energy Environment and Climate Action requirements for Regional Mobile Radio network onboarding.
Q1 23-24 | Victoria Legal Aid | VLA | 2852 | Digital Legal Aid Program | Law and Justice | Management of Process | VLA will leverage technology and data to significantly improve client service, productivity and access to justice. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-02-19 |  | 2019-02-20 | 0 |  | 2019-02-22 | 2022-01-01 | 2021-07-30 | 2023-12-31 | 14500000 | 5850000 | Green | Green | Amber | Green | Amber | The system continues to be well received as it is rolled out to regional offices. There are some challenges with document management, which are actively being worked through with Microsoft. This has caused delays, resulting in an Amber status.
Q1 23-24 | Western Health | WH | 2868 | Western Health - Electronic Medical Record (EMR) Phase 2 | Health | Records Management | This project represents the next phase of the EMR at Western Health (WH) on its path towards bringing it to a fully digital hospital which is expected to provide improved efficiency and quality of care across the continuum of the organisation. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-05-29 | 2020-02-03 | 2019-07-05 | 2019-07-05 | 0 |  | 2021-02-22 |  | 2025-12-31 | 2026-09-30 | 64400000 | 71885129 | Amber | Green | Amber | Amber | Green | Has returned to GREEN status following successful project Phase 2.1 'Go-Live'.
Q1 23-24 | Department of Education | DE | 2886 | FSD-Oracle Cloud Program | Education | Analyses and Statistics ,Systems Management,Financial Management | The project will integrate Oracle Cloud applications to improve information consolidation & analysis across government by utilising common application tools, reducing ongoing maintenance & costs by aligning to Common Corporate Platform Program. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-29 | 2020-06-30 | 2020-09-30 | 2020-11-02 | 0 | 3391959 | 2020-11-02 |  | 2021-11-01 | 2024-04-30 | 2861041 | 5324616 | Green | Amber | Amber | Amber | Amber | The project is currently reporting a status of Amber. The project has been paused with the agreement of the Project Control Board whilst a procurement activity is in progress to change the delivery approach by engaging a System Integrator. Upon the completion of this process, the project deliverables and timelines will be revised.
Q1 23-24 | Bendigo Kangan Institute of TAFE | BKI TAFE | 2903 | Student Journey Transformation | Employment and Workplace | Customer Relationship Management,Data Management,Development and Integration ,Records Management ,Reporting | The program will deliver capability and user experience improvements across the end-to-end student lifecycle. The program is necessary to transform people, process and systems from a highly manual environment, using complex and out of date systems. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-01-07 | 2019-12-20 |  | 2019-12-20 | 2174000 | 1700000 | 2020-01-06 |  | 2022-09-30 | 2023-12-22 | 1966000 | 31135470 | Green | Green | Amber | Amber | Amber | The project remains in Hypercare as appropriate stability of data for AVETMISS reporting has not met the transition threshold. Transition to BAU is on track for December 2023
Q1 23-24 | Department of Justice and Community Safety | DJCS | 2906 | Prison Industries Enhancement Phase 2 Project | Law and Justice | Management of Process | The primary purpose of the PIE project is to deliver value for money prison services by exploring ICT opportunities for Prison Industries (PI) cost recovery, as well as through promoting PI as a preferred supplier to internal business units. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Project Management Excellence | 2019-09-02 | 2020-03-27 | 2020-04-30 | 2020-05-01 | 0 |  | 2020-05-04 | 2020-10-29 | 2020-10-30 | 2023-12-22 | 2140000 | 3611746 | Green | Green | Amber | Amber | Green | The project is tracking to budget, scope and schedule.
Q1 23-24 | Dental Health Services Victoria | DHSV | 2909 | Mobile Diagnostic Imaging | Health | Records Management | The objective of this project is to enable Public Oral Health providers to access diagnostic images acquired from School Dental Program in a timely manner, and at the point of care. | Delivery | Social Improvement (Non Financial) |  | PRINCE2 | 2019-06-28 | 2020-09-30 | 2021-11-30 | 2021-11-30 | 0 | 200000 | 2021-12-01 |  | 2023-02-28 | 2024-01-31 | 2972693 |  | Amber | Amber | Amber | Green | Green | Project is progressing against rebaselined schedule. Integration testing is continuing.
Q1 23-24 | Department of Transport and Planning | DTP | 2931 | Human Capital Management (HCM) Project | Transport and Vehicles | Customer Initiated Assistance,Human Capital / Workforce Management ,Human Resources,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DoT as the initial tranche of the broader WoVG program managed by OneVPS. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2023-09-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-02-03 | 2020-06-30 | 2021-07-30 | 2021-08-02 | 0 |  | 2021-08-09 |  | 2022-07-04 | 2023-09-29 | 0 | 31100000 | Red | Green | Green | Green | Green | Project successfully completed. Phase 2 of the project is reported separately.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 2937 | ACCS eCAM Replacement | Government and Economy | Customer Relationship Management | Replacement of eCam and Lotus Note systems with SalesForce, and associated applications to manage conciliation cases. Benefits realised include significant reduction in manual effort, improved usability as well as reducing legacy system dependencies. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2022-06-17 | PMBoK | 2020-02-03 | 2020-06-30 | 2021-02-12 | 2021-02-26 | 0 | 1278689 | 2021-02-26 |  | 2021-07-30 | 2022-03-31 | 4642607 |  | Red | Red | Red | Red | Red | The project is currently paused, pending a decision on alignment with the case management system.
Q1 23-24 | Greater Western Water Corporation | GW Water | 2939 | Billing and Collection | Environment and Water | Assets/Materials Management,Customer Initiated Assistance,Customer Preferences,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Knowledge Management ,Management of Process ,Records Management ,Reporting ,Routing and Scheduling,Tracking and Workflow | Replacement of the core Billing and Collections system with a modern ‘fit-for-purpose’ solution to allow GWW to better serve our customers and bring operational efficiencies | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-09-23 | 2021-01-31 | 2021-05-25 | 2021-05-25 | 790000 | 4575000 | 2021-05-25 |  | 2023-06-30 | 2024-06-30 | 39965000 | 87956847 | Amber | Amber | Amber | Red | Amber | Reporting Comments: Revised business case has been approved in July in alignment with revised implementation date. Development activities nearing completion with focus on data and testing. Activities for next quarter shift to business readiness and User testing. Reason for Amber: Continued high risks associated with complex program. Delivery risks associated with data migration. testing outcomes and business readiness.
Q1 23-24 | Victorian Funds Management Corporation | VFMC | 2943 | Data and Analytics | Business and Industry | Analyses and Statistics | The project will deliver an Enterprise Data Management Platform to underpin VFMCs comprehensive data and IT transformation strategy which will enrich and validate multiple sources of investment data into one centralised location. | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2023-09-30 | Agile | 2018-08-13 | 2019-10-02 |  | 2019-10-02 | 778436 |  | 2020-02-03 |  | 2021-06-30 | 2023-09-30 | 19181333 | 16590836 | Green | Green | Green | Green | Green | The delivery phase of this project is now completed as of 30/09/2023, as such we have revised the project duration. The project cost has also been revised to exclude ongoing licensing and operational costs from this date forth.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 2956 | Resources Management System Victoria (RMSVIC) Project | Business and Industry | Analyses and Statistics ,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Document Management ,Management of Process ,Records Management ,Tracking and Workflow | The Project will deliver a Resources Management System Victoria (RMSVIC) in Salesforce to replace Resource Rights Allocation and Management (RRAM). Key benefits are a fit for purpose, tailored, flexible system supporting industry and the Regulator | Postponed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) | 2023-09-08 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2019-12-31 | 2020-02-26 | 2020-02-27 | 222500 |  | 2020-02-27 |  | 2021-12-31 | 2023-09-30 | 5920000 | 6680000 | Red | Red | Red | Red | Red | The project is red due to the technical barriers to integrating to DEECA systems (Machinery of Government changes), extending delivery times beyond the funded period. The project is on hold until Financial Year 23-24 funding is confirmed to re-commence work. Alternative funding sources are currently being evaluated, and a program rescope and refreshed procurement approach designed with initial re-costing.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Road Safety Package includes a number of initiatives. The ICT initiatives in this package include: • Computerised Maintenance Management System (CMMS) • Network Security - Improvements to security of the Fixed Digital Road Safety Camera network. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 869178 | 2021-05-24 |  | 2022-04-21 | 2025-06-30 | 6967000 | 11918282 | Amber | Amber | Amber | Green | Green | The overall package including CMMS and Network Security is on track. The Transport Accident Commission (TAC) Memorandum of Understanding (MOU) was executed by the Department of Justice and Community Safety (DJCS) and the TAC on 19 April 2021. TAC has agreed in principle on the time extension (from 30 June 2023 to 30 June 2025). The revised delivery date has been extended to 30 June 2025.
Q1 23-24 | Transport Accident Commission | TAC | 3000 | AV Uplift TAC | Transport and Vehicles | Communication,Visualisation | Audio Vision (AV) equipment uplift to meet contemporary business needs of staff so they are able to present digital content from their device to other meeting participants and run web conferences with external parties. | Closed - Completed | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2023-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-04-16 | 2020-04-16 |  | 2020-04-16 | 0 |  | 2020-04-16 |  | 2020-12-31 | 2023-09-30 | 1612500 | 3415672 | Amber | Green | Green | Green | Green | Project completed within revised schedule , scope and budget.
Q1 23-24 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution as part of Barwon Health (BH) Strategy and supportive of the broader DHHS and Government policy goals and focused on improving the quality and safety of the patient care that BH delivers. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2024-05-31 | 6074206 |  | Green | Amber | Red | Red | Red | Extensive project re-planning has taken place in collaboration with the Barwon Health Community EMR vendors. Detailed end-to-end design has been presented to the steering committee, with the aligned detailed project schedule to be finalised by 31/10/23.
Q1 23-24 | Department of Education | DE | 3025 | eProcurement Solution Implementation | Education | Supply Chain Management ,Management of Process | This project will implement the eProcurement Solution for end-to-end source to contract functionality and contract management replacing the current Ariba platform which is approaching end of life. | Postponed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2022-01-18 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-06 | 2020-10-18 |  | 2020-10-18 | 0 |  | 2020-10-19 |  | 2021-06-30 |  | 1573670 |  | Red | Red | Red | Red | Red | This project which is part of a WoVG eProcurement initiative remains on hold at the request of the Department of Premier and Cabinet whilst processes are aligned across departments that will enable the benefits of common systems to be realised.
Q1 23-24 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | Design and implement an enterprise Fire and Rescue Services Portal. | Delivery | Compliance (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2024-04-30 | 2109000 |  | Green | Green | Amber | Amber | Green | A variation has been approved to recommence the project in Q2 2023-24. Work has commenced to update project schedule, budget and allocate resources
Q1 23-24 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2024-06-30 | 3760000 | 4349947 | Amber | Amber | Amber | Amber | Amber | A variation has been approved to recommence the project in Q2 2023-24. Project is currently reporting amber whilst resource pipeline constraints are being mitigated.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Initiated |  |  | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2023-12-30 |  | 3297000 | 2971000 | [11 empty] | The Initiation end date has been revised to 30 December 2023, to accommodate the FAS CMS (Case Management System) Request for Tender. The Project has a revised projected 'go live date' within the first quarter of FY24/25, the downstream schedule impact is that the delivery end date is now 30 September 2024. The Project Management Plan has been updated and the amendments have been approved by the Project Control Group. The schedule has been re-baselined accordingly.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3047 | Data & Analytics Hub | Government and Economy | Analyses and Statistics ,Business Intelligence,Data Management | The Data & Analytics Program will deliver cloud technology platforms to uplift WSV's enterprise data management capabilities including a new enterprise data warehouse, data lake and an advanced analytics environment. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 0 |  | 2020-05-01 |  | 2021-12-31 | 2024-06-30 | 1169000 | 32070956 | Amber | Amber | Green | Green | Amber | Initial program costs were to establish the business unit and develop the Business Case. Current total cost encompasses the original Business Case (spanning FY22, FY23), and the latest FY24 Business Case. The program continues to develop WorkSafe's platform and capability, delivering Analytics, Guided Payments Product and finalising the foundational technology. Program is tracking Amber. Work is progressing to fill resource gaps and a detailed planning exercise is underway.
Q1 23-24 | Department of Transport and Planning | DTP | 3052 | Automatic Incident Detection (AID) Software Project | Transport and Vehicles | Development and Integration ,Systems Management,Visualisation | The objective of this project is to implement an Automated Incident Detection (AID) system. This system will use data from existing freeway systems and alert the operators and provide a view of road traffic incidents from the nearest CCTV camera. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-06 | 2021-02-28 | 2021-07-07 | 2021-07-30 | 0 |  | 2021-08-16 |  | 2022-06-30 | 2023-12-30 | 2100000 |  | Green | Green | Green | Green | Green | Overall project status is green. Infrastructure set up and detail design completed. Development work is ongoing.
Q1 23-24 | Department of Premier and Cabinet | DPC | 3066 | Wage Inspectorate Victoria case management system | Employment and Workplace | Management of Process ,Records Management ,Reporting | Design and build a case management system to support end-to-end regulatory operations of the Wage Inspectorate Victoria. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-25 | 2020-12-03 | 2020-05-25 | 2021-01-11 | 135000 |  | 2021-01-11 |  | 2022-03-31 | 2023-11-02 | 1434372 | 4560820 | Green | Green | Green | Green | Green | The final phase (i.e., phase 4) of the project will now be delivered in four sub phases - GWSS, CSS, CE/MVP, CE/DROP2 all of which will be delivered by 31 October2023.
Q1 23-24 | Department of Education | DE | 3070 | Student Insight Platform Establishment & Digital Enrolment Product | Education | Development and Integration ,Management of Process ,Organisational Management | The Digital Enrolment component on the Student Insight Platform will ease the school administrative burden, improve data quality and security and deliver efficiencies for managing student information for parents, schools, and staff. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-08-03 | 2021-06-30 | 2021-04-21 | 2021-04-21 | 2553958 | 773357 | 2021-04-21 |  | 2022-06-30 | 2023-12-31 | 15500000 | 4674250 | Green | Green | Green | Green | Green | The Digital Enrolment product has been successfully extended to additional pilot schools. During the first half of this financial year, the Digital Enrolment product has been undergoing enhancements in preparation for additional implementations in 2024.
Q1 23-24 | Yarra Valley Water | YV Water | 3076 | Land Development System (easyACCESS) Replacement - Foundation | Environment and Water | Customer Relationship Management | Replacement of the end of life land development customer portal (easyACCESS), including optimisation of the existing processes to deliver productivity savings and uplift the overall customer experience. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 662000 | 1700000 | 2021-07-01 |  | 2026-06-30 | 2023-10-31 | 2681995 | 6793284 | Green | Green | Green | Green | Green | Design and delivery review of items in scope accelerated plan underway. Salesforce review of roadmap and delivery method complete. Business case for next phase being prepared
Q1 23-24 | Yarra Valley Water | YV Water | 3078 | Yarra Valley Online Water (YVOW) Replacement | Environment and Water | Customer Relationship Management,Customer Relationship Management | Replacement of the end of life customer self service portal (YVOW), including a redesign of the customer experience. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 330000 | 1400000 | 2021-07-01 |  | 2022-12-31 | 2024-06-30 | 1886564 | 5278564 | Green | Green | Green | Green | Amber | With WCAG 2.1 AA Compliance being in scope plus additional cyber security measures, additional CX resources & development retrofitting requirements led to the need to revise the overall end to end delivery cost.
Q1 23-24 | Yarra Valley Water | YV Water | 3079 | Distribution Management System (DMS) | Environment and Water | Customer Relationship Management | Distribution Management System which provides staff with a single view of our asset networks including performance data, customer service levels, and contractor interactions. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2023-06-30 | PRINCE2 | 2020-07-01 | 2020-09-28 |  | 2020-09-28 | 0 |  | 2020-09-28 | 2020-10-12 | 2023-06-30 | 2023-12-31 | 6002000 | 6503600 | Green | Green | Green | Green | Green | Project completed. Further enhancements works will be done as a new project
Q1 23-24 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Postponed | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2023-09-19 | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 650000 | 2022-06-24 |  | 2024-03-22 | 2024-12-30 | 8200000 | 10251000 | Green | Green | Green | Green | Amber | Vendor has submitted a request for additional funding for build which exceeds contract budget tolerances. Project is placed on hold while future paths are considered.
Q1 23-24 | Department of Health | DH | 3094 | Digital Registration for Food Businesses - FoodTrader | Business and Industry | Data Management | Deliver a single online registration portal for Victorian food businesses and an application assessment, compliance management and reporting database for use by councils in managing registrations under the Food Act 1984. | Closed - Merged | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2023-07-20 | Agile | 2019-06-28 | 2020-04-14 |  | 2020-07-06 | 184000 | 500000 | 2020-08-17 |  | 2022-06-30 | 2022-12-31 | 2044600 |  | Amber | Red | Red | Red | Red | Project is closed following contract termination for convenience with the supplier. Scope transferred and being delivered by new project.
Q1 23-24 | Department of Health | DH | 3095 | Windows Server Re-Platform and Re-Hosting | Health | Systems Management | The project will upgrade, re-host or decommission outdated servers and database instances to ensure continuity of infrastructure support of services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-01 | 2020-07-12 |  | 2020-07-17 | 494548 |  | 2020-09-10 |  | 2021-06-30 | 2023-09-30 | 1048885 | 1669366 | Green | Green | Green | Amber | Green | Project progressing and only 12 servers remaining to be decommissioned. Schedule to be extended to complete these and will be updated in next reporting period once Steering Committee has formally endorsed.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3100 | Victorian Water Register Transform Project | Environment and Water | Management of Process | The project will deliver a new Victorian Water Register(VWR) to improve service delivery, information sharing and to ensure the equitable sharing of water and continuous improvement in the integrity security and reliability of Victoria's water market | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-25 | 2021-06-30 | 2022-09-30 | 2022-09-30 | 1467715 | 2501098 | 2022-12-05 |  | 2024-06-28 |  | 21450606 | 24225902 |  |  | Amber | Amber | Red | The project is red due to additional complexity identified as the program work progresses. Additional effort is required to deliver the project's outcome. A review of the plan has been initiated to manage the additional complexity and effort.
Q1 23-24 | Western Health | WH | 3125 | Western Health - Identity Access Management (IAM) | Health | Security Management | An IAM system is the means to provide a secure and trusted identity of employees across Western Health. This is currently housed and managed by Melbourne Health and this project will migrate the IAM from Melbourne Health to Western Health | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-30 | 2021-01-29 |  | 2021-04-19 | 0 |  | 2021-04-19 |  | 2022-02-28 | 2024-02-12 | 1896000 | 1859000 | Green | Green | Green | Green | Green | Single-Sign-On stage of the project is complete. Lifecycle management components now being implemented as the final deliverables.
Q1 23-24 | Department of Transport and Planning | DTP | 3128 | Smarter Roads Program - Situational Awareness Platform (formerly-Creating More Road Space) | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Communication,Knowledge Discovery | Objective of this project is to develop a enterprise wide Situational Awareness (SA) Platform. The platform will provide a view of the metro transport network and provide situational awareness for the operators in the Traffic Management Centre (TMC). | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-05 | 2021-06-30 | 2021-06-14 | 2021-06-14 | 0 |  | 2021-06-21 |  | 2022-06-30 | 2023-12-31 | 0 | 42136473 | Amber | Amber | Amber | Amber | Green | Overall project status is green. Optimal reality to go live in October. Training in progress..
Q1 23-24 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2023-12-31 |  | 75000 | 245000 | [11 empty] | GVW is currently reviewing the schedule for this project following recent major floods.
Q1 23-24 | Department of Transport and Planning | DTP | 3147 | Smarter Roads Program - Data Fusion Model | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Customer Initiated Assistance,Customer Preferences | Objective of this project is to provide: 1.Multi-modal journey planning that encompasses tools to help them re-plan and understand alternative journey options in real time. 2. Real-time disruption information to customers to plan their journey. | Delivery | Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-08-02 |  | 2022-06-30 | 2023-12-29 | 0 | 23354499 | Green | Green | Green | Green | Green | Overall project status is green. Delivery continuing, pre-release testing in progress.
Q1 23-24 | Alfred Health | ALFRED | 3156 | ARIA Database Merge and Managed Service Implementation | Health | Records Management | Database merge and consolidation of Alfred Health Radiation Oncology Application “ARIA” to a single instance, cloud-based, vendor-managed and hosted service | Closed - Completed | Cost Avoidance (Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2023-09-30 | PRINCE2 | 2021-03-01 | 2021-06-30 |  | 2021-06-30 | 0 | 235544 | 2021-07-01 |  | 2022-12-20 | 2023-09-30 | 1708056 |  | Amber | Green | Green | Green | Green | Close Out documentation completed and delivered to stakeholders.
Q1 23-24 | Melbourne Health | Melb H | 3159 | Unified Communications – Telephony Upgrade Project | Health | Collaboration ,Communication,Systems Management | This project will upgrade the Melbourne Health telephony system to replace the old existing ISDN / PSTN / analogue PABX and phone infrastructure with digital SIP trunks and VoIP phones that provide unified communication and enhanced collaboration. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-02-01 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 | 2023-12-22 | 4326000 | 4576000 | Green | Amber | Amber | Amber | Amber | The project status remains AMBER due to protracted phone roll-out impact on schedule. Infrastructure build finalisation has progressed to schedule (highly available digital telephony via Cisco Call Manager across two Data Centres).
Q1 23-24 | Melbourne Health | Melb H | 3160 | Office 365 Implementation Project | Health | Collaboration ,Content Management,Systems Management | Extensive technical and change management project to implement the required foundation, application and governance layers for Melbourne Health to deploy and adopt the full collaboration potential of the Microsoft Office 365 suite. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2023-09-01 | PRINCE2 | 2021-01-04 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 | 2023-09-01 | 3532700 |  | Green | Green | Green | Green | Green | Project Closed Office 365 now under operational support.
Q1 23-24 | Department of Government Services | DGS | 3165 | Emergency Management Victoria-VCDI Partnership | Emergencies and Safety | Data Management,Reporting ,Visualisation ,Analyses and Statistics ,Business Intelligence | The primary objective of this partnership is to rapidly and practically enhance EMV (including the State Control Centre) and the emergency management sector’s data and analytics capability in order to help it respond to major and complex emergencies | Closed - Completed | Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2023-09-28 | Agile | 2021-01-11 | 2021-01-22 |  | 2021-01-22 | 0 |  | 2021-01-25 |  | 2022-06-30 | 2023-09-28 | 2300000 |  | Green | Green | Green | Green | Green | VCDI has now delivered EMVs first Data Governance Framework to support future implementation of new technology solutions uplift the workforce skill profile and support best data practice. Support moving forward will be focused on supporting the digital release of the strategy to the EM Sector as part of a separate engagement with EMV.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | This project will deliver a fit-for-purpose case management system for the Post Sentencing Authority. | Initiated |  |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 |  | 150000 | 363395 | [11 empty] | The project has experienced funding delays and delays with an outcome for the preferred platform selection to enable the common platform approach for the project. A common platform has now been selected. Further work is being done on consolidating another business unit into the program of work, increasing the cost but also increasing the value to the department significantly. Project initiation was completed in June 2023, and project delivery is due to commence in December 2023.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 |  | 131615000 |  | Amber | Green | Amber | Amber | Amber | Delivery remains Amber due to a lack of contingency to fully recover from the previous Program Increment impacts. Preparation activities across the remaining Work Packages continues. Agency Portal went live to business on Wednesday 12 July 2023. Driver and Vehicle Sanctions (DVS) Release 1.2 Go-Live was revised to 17 July 2023 due to the Victorian Infringements Enforcement Warrant (VIEW) system release happening at the same time and went live as scheduled.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems to deliver safety and cost benefits. The project will provide access to rehabilitation and reintegration services through in-cell technology. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2024-06-30 | 18868800 | 12145800 | Green | Green | Green | Green | Green | The project is tracking to budget, scope and schedule.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3172 | JKE Upgrade & Linux Migration | Law and Justice | Development and Integration | This project is to transition the Justice Knowledge Exchange (JKE) Enterprise Service Bus from Solaris to Linux platforms and upgrades it to webMethods version 10. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2020-07-01 | 2020-08-31 |  | 2020-08-31 | 26466 |  | 2020-09-01 |  | 2022-02-28 | 2023-12-31 | 1664286 | 2246804 | Amber | Amber | Red | Green | Amber | Additional JKE Project funding was approved in July 2023. The JKE upgrade project has migrated over 95% of integration services to the new environment. In this reporting period there have been a number of issues with development and procurement impacting planned timelines. Planning is now in progress to complete remaining deliverables and engage required vendor services
Q1 23-24 | Melbourne Water | MELB Water | 3180 | Digital Education and Engagement Services | Environment and Water | Communication | Melbourne Water has a Water Act obligation through the Statement of Obligations to educate schools about Water Literacy and our range of services. This 3 year program will focus on encouraging water literacy across the school community. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-25 | 2021-07-01 | 2021-12-02 | 2021-12-20 | 0 |  | 2021-12-20 |  | 2024-05-30 |  | 1804843 |  | Green | Green | Green | Green | Green | New Project Manager onboarded. Digital Learning Gateway Procurement activities with vendor are in progress. Frog Census App: Work in progress to migrate from Vendor hosting to service provider hosting and to establish a support contract.
Q1 23-24 | Department of Government Services | DGS | 3191 | Email Fraud Defence (DMARC) | Government and Economy | Security Management | Implementing DMARC (Domain-based Message Authentication, Reporting and Conformance) will make it significantly harder to send fake emails claiming to be from the Victorian government & will help prevent fraud to the Victorian government & citizens. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-26 | 2021-05-31 |  | 2021-06-04 | 170672 |  | 2021-06-04 |  | 2023-12-29 |  | 5829328 |  | Green | Green | Green | Green | Green | Project tracking well to the approved schedule and budget.
Q1 23-24 | Department of Government Services | DGS | 3199 | Registry System Replacement - RTBA | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 |  | 2022-03-01 |  | 2023-06-30 | 2024-06-28 | 8900000 | 10394000 | Green | Green | Red | Red | Red | Project is tracking Red as the current Release 1 end date of June 2023 has not been achieved. Project re-baseline details are underway however project is more likely to be completed in 2024.
Q1 23-24 | Department of Government Services | DGS | 3200 | Local Jobs First Policy Intelligence Engine | Business and Industry | Analyses and Statistics ,Business Intelligence,Data Management | DJSIR have partnered with DPC to develop a policy intelligence engine to improve the effectiveness of the Local Jobs First policy. The technology solution will support an uplift in capability to improve the delivery of important policy. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2020-12-01 | 2021-02-11 |  | 2021-02-11 | 0 |  | 2021-05-01 |  | 2023-06-30 | 2024-06-30 | 2400000 |  | Green | Green | Green | Green | Green | It has been a successful quarter with the PIE project moving into BAU and now being maintained under a maintenance Service level agreement.
Q1 23-24 | Department of Education | DE | 3203 | Infrastructure Portfolio Management (IPM) | Education | Investment Management,Management of Process | The project is the implementation of a Software as a Service solution that meets the needs of the department & delivers new infrastructure management capability. The project will deliver procurement, project, program & portfolio level information. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-22 | 2021-10-31 | 2021-11-30 | 2021-12-01 | 111310 |  | 2021-12-01 |  | 2022-12-31 | 2024-02-29 | 6738690 | 6543764 | Green | Green | Green | Red | Amber | The project successfully went live with a Release on 11 September 2023 following slippage in July due to delivery issues by the vendor. The issues were resolved as forecast with the next Release anticipated for 9 October 2023. A revised schedule has been approved by the Project Control Board.
Q1 23-24 | Department of Education | DE | 3208 | eduSafe Plus – Phase 2 | Education | Human Capital / Workforce Management | The project will deliver the functionality for managing incidents, OHS and workers’ compensation using a platform-based approach. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-29 | 2021-06-11 |  | 2021-06-11 | 1 | 0 | 2021-06-14 |  | 2022-06-30 | 2023-11-16 | 3192672 | 7337459 | Amber | Amber | Amber | Amber | Amber | The project status is currently Amber. One high risk currently exists on the project which is the vendor contract expiry in October. A resolution is expected prior to contract end date (October 2023). The rollout to schools for OHS and Claims Management has continued as per the project schedule.
Q1 23-24 | CenITex | CenITex | 3212 | DC Exit, Discovery, Re-Architecture and Migration - Stage 1 | Government and Economy | Data Management | To delivery data centre discovery for all Government Shared Platform clients. In addition to the discovery also design a new landing platform and plan for migration of the services. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-04-20 |  | 2021-05-06 | 0 |  | 2021-06-10 |  | 2022-06-30 | 2023-12-29 | 5600000 | 5637863 | Amber | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | CenITex | CenITex | 3213 | Hybrid Cloud Program: Mediation Layer - Stage 1 | Government and Economy | Data Management | Cenitex will work closely with DPC to establish a program that will focus on enabling migration from the existing on-premise data centers to a HICT multi-cloud elastic environment to provide Government with secure and resilient access to the services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-05-25 |  | 2021-06-11 | 0 |  | 2021-06-22 |  | 2022-06-30 | 2024-01-31 | 3650000 | 5900000 | Amber | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Postponed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2022-09-14 | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2024-06-28 | 3174023 |  | Amber | Green | Green | Green | Green | Due to IT Portfolio Prioritisation decision, SRM Project has been placed on HOLD until new FY (FY23/24). Project end date has been extended to end of FY 23/24 to align. The status will be re-reviewed for FY 23/24.
Q1 23-24 | Department of Families, Fairness and Housing | DFFH | 3215 | The Integrated Client and Case Management System (ICCMS) Infrastructure Refresh and Software Upgrade | Community Services | Customer Relationship Management,Systems Management | The project will deliver a refreshed hardware/hosting and software solution to the department's primary client and case management business system to ensure a stable, responsive and reliable platform. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-01 | 2020-11-13 |  | 2020-11-16 | 0 |  | 2021-02-01 |  | 2022-12-31 | 2024-06-30 | 4350000 | 6000000 | Amber | Red | Red | Red | Red | Project is progressing and data warehouse upgrade to Oracle cloud infrastructure continuing. Project is reporting a Red health status pending approval of additional funding.
Q1 23-24 | Department of Transport and Planning | DTP | 3234 | Digital Twin Victoria Program (DTV Program) | Property and Planning | Data Management,Knowledge Management | The DTV Program will recreate Victoria online so that government, industry and the community can collaborate to enhance real-world outcomes through shared data and technology leveraging spatial data, artificial intelligence, sensor data and more. | Delivery | Cost Reduction (Financial), Eco Improvement (Non Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-06-01 | 2020-07-28 |  | 2020-11-15 | 0 |  | 2021-01-01 |  | 2024-06-30 |  | 37431600 | 37431163 | Green | Green | Green | Green | Green | The majority of Program workstreams are on track - no intervention or actions required
Q1 23-24 | Department of Transport and Planning | DTP | 3238 | Digital Planning Reform Program | Property and Planning | Data Management,Management of Process ,Reporting ,Tracking and Workflow,Visualisation | Digital Reform program will deliver a portal for Victoria with easy access to guidance information and services to reduce complexity and to provide greater consistency and certainty to users. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2020-11-01 |  | 2020-11-01 | 0 |  | 2021-03-29 |  | 2024-06-30 |  | 15755000 |  | Green | Green | Green | Green | Green | The program is now reporting an overall status as green. The program is tracking to schedule.
Q1 23-24 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System will be replaced to meet current business operations and reporting requirements and drive best practice in forensic investigations. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-01-07 |  | 2022-01-07 | 0 | 350000 | 2022-01-07 |  | 2023-12-31 | 2024-10-31 | 5650000 |  | Green | Green | Green | Green | Green | Victorian Institute of Forensic Medicine (VIFM) has signed a contract with Supplier to deliver a new case management system using the Microsoft Dynamics 365 platform.
Q1 23-24 | Victorian Institute of Forensic Medicine | VIFM | 3242 | ICT Infrastructure Migration to the Cloud | Law and Justice | Systems Management | ICT Infrastructure Cloud Migration project will reduce the risk associated with aging ICT infrastructure | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 | 2022-01-03 | 2022-01-03 | 0 | 585000 | 2022-01-03 |  | 2024-06-30 |  | 2338000 |  | Green | Green | Green | Green | Green | Phase 1 completed on schedule and on budget. The cloud and on-premise environments are continuing to be reviewed with migrated servers being reconfigured additional servers being migrated to the cloud and on-premise servers decommissioned to maximise the cost effectiveness of the project. Phase 2 is expected to start in 2024 following the Victorian Institute of Forensic Medicine (VIFM) Replace Case Management System project transitioning the existing case management system to a new cloud-based solution.
Q1 23-24 | Office of Public Prosecutions | OPP | 3243 | Digital Innovation Project Prosecution Case Management | Law and Justice | Tracking and Workflow | Project to upgrade case management system and integrate with other core systems | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-07-01 | 2021-12-31 | 2022-10-31 | 2023-01-06 | 300000 | 450000 | 2023-01-09 |  | 2024-08-01 | 2024-01-29 | 3300000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 23-24 | Department of Education | DE | 3246 | Workplace Management System | Education | Human Capital / Workforce Management | This project will explore the procurement and implementation of a new cloud-based service technology platform to facilitate real-time desk booking, space utilisation, workforce planning, and reporting across all department-owned and leased sites | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2021-07-06 | 2022-04-30 |  | 2022-05-02 | 153088 |  | 2022-05-02 |  | 2023-03-31 | 2023-11-01 | 3623757 | 3748865 | Green | Green | Green | Amber | Green | The project is currently in a "Green" status: • Pilot Phase Implementation for CBD sites has been successfully completed. • The Go Live Phase implementation for regional sites began on 11th September 2023h and is progressing as planned, with the last regional site scheduled for completion by 20th October 2023. • Project and Enterprise Project Management (EPM) closure is expected to be finalised by 3rd November 2023.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3248 | VicEmergency Uplift | Emergencies and Safety | Communication | The VicEmergency website & mobile app require upgrades and new apps to ensure alignment with key IGEM and Royal Commission recommendations. | Closed - Completed | Risk Reduction (Non Financial) | 2023-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-13 | 2021-01-02 |  | 2021-03-02 | 700000 | 267000 | 2021-07-01 |  | 2022-06-30 | 2023-09-30 | 2500000 |  | Green | Green | Green | Green | Green | The project is now completed and closed.
Q1 23-24 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2025-06-30 | 16689890 | 18418852 | Green | Green | Amber | Amber | Amber | Project is reporting amber due to dependencies on a number of cyber incident recovery activities. The project is expected to be back on track following completion of recovery activities.
Q1 23-24 | CenITex | CenITex | 3256 | IPS Uplift | Government and Economy | Security Management | To uplift the Intrusion Protection System (IPS) of the Cenitex security services to meet current data throughput and also allow for growth in traffic for coming years. | Delivery | Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2021-07-15 | 2021-12-31 | 2021-07-15 | 2021-07-15 | 0 |  | 2021-07-15 |  | 2021-12-31 | 2023-12-29 | 1478085 | 2208949 | Amber | Amber | Red | Green | Green | Project tracking to plan.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3258 | Distracted Driver Camera Project | Law and Justice | Development and Integration | Procurement and implementation of new road safety cameras capable of automatically detecting mobile phone and seatbelt offences. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-05-23 | 2022-05-23 | 2000000 | 1966138 | 2022-05-23 | 2022-05-31 | 2023-06-30 | 2023-12-31 | 8987738 | 8990232 | Amber | Amber | Amber | Green | Green | The project is tracking well against scope and budget. The project achieved the Go-live for commencement of enforcement and issuance of infringements for offences on 1 July 2023 following a three-month Advisory Letter period (between April and June 2023). The project is currently working on a Transition to Business-as-Usual Plan and is on schedule to achieve the next major milestone project completion and closure by 31 December 2023.
Q1 23-24 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Delivery of a Health Information Exchange (HIE) for the secure sharing of clinical information at the Point of Care. Note change of name from LISConnect Project - Pathology Health Information Exchange (HIE) to Health Information Exchange (HIE) | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 |  | 0 | 24000000 | Amber | Amber | Amber | Green | Amber | The project is tracking to budget and scope however is experiencing some delays due to technical issues. The team is working to resolve the issues and is reviewing the schedule.
Q1 23-24 | Southern Metropolitan Cemeteries Trust | SMCT | 3266 | Next Gen Business System Program | Health | Customer Relationship Management,Financial Management | The Next Gen Business System Program will replace existing legacy systems with modern CRM and ERP platforms to fully integrate business processes and data across the enterprise, customers, and partners. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-07-26 | 2022-02-28 | 2022-04-30 | 2022-04-30 | 0 | 1500000 | 2022-08-01 |  | 2023-11-24 | 2024-02-29 | 7700000 |  | Green | Green | Green | Green | Green | User Acceptance Testing (UAT) was completed as planned as was production confirmation. Training materials were finalised and train-the-trainer training was delivered. Preparation for data migration UAT was completed and detailed operational and technical cutover planning commenced for a functional go live on 4 December 2023. Overall quarterly status of the project is green.
Q1 23-24 | South East Water | SE Water | 3267 | OpenText Content Server Upgrade | Environment and Water | Content Management | The content server produce, opentext, requires an upgrade to a current version to ensure it is within support parameters. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2020-07-13 | 2021-08-02 |  | 2021-08-04 | 60000 |  | 2021-08-04 |  | 2022-04-22 | 2023-11-24 | 1163487 | 1780000 | Green | Amber | Red | Green | Amber | Data migration has caused a cost and time impact to the project. Remediation is occurring with good results.
Q1 23-24 | Ambulance Victoria | AVS | 3269 | Infrastructure Cloud & Financial Analytics (ICFA) | Health | Analyses and Statistics ,Business Intelligence,Financial Management,Knowledge Discovery ,Reporting | Transition AV Financial Reporting and Analytics system to Cloud service enabling AV to mitigate the current technology risks associated with operating an out of support system while also providing additional functionality for financial reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-07-01 | 2021-12-31 |  | 2021-12-31 | 213850 | 68606 | 2022-01-01 |  | 2022-12-31 | 2023-10-13 | 2174650 | 2569894 | Amber | Amber | Green | Green | Amber | The project is reporting as Amber due to a delay in approval of the Autonomous Data Warehouse (ADW) Proof of Concept (POC) approval.
Q1 23-24 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 | 2024-05-02 | 2424764 |  | Amber | Green | Amber | Green | Green | Final cost report to be completed once all asset numbers have been updated in the database. Expected completion for Phase 1 activities is end Oct 23. Remaining scope for phase 2 & 3 will be prioritised along with other projects in the IT Portfolio.
Q1 23-24 | Melbourne Water | MELB Water | 3274 | Portal New Services | Environment and Water | Communication,Content Management,Customer Relationship Management | Portal went live in 2019 as a minimal viable product (MVP). In line with the Strategy and Pricing Submission 2021 (Water Plan 5) a roadmap of key enhancements will be delivered to improve customers digital experience. | Postponed | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2022-09-14 | PMBoK | 2021-07-01 | 2021-10-29 |  | 2021-12-22 | 0 |  | 2022-01-10 |  | 2023-06-30 | 2024-06-28 | 2975826 |  | Amber | Green | Green | Green | Green | As a part of the IT Capital Prioritisation process a review of all FY22/23 projects across the IT portfolio was conducted. Work on the Portal New Services project will be paused from October and for the remainder of this financial year. Schedule has been extended to reflect the decision to delay this project until 23/24FY. Currently on-hold.
Q1 23-24 | Melbourne Water | MELB Water | 3275 | Website New Services | Environment and Water | Communication,Content Management,Customer Preferences,Customer Relationship Management | The Melbourne Water Website went live in October 2017 as a minimal viable product (MVP). In line with Strategy and Pricing Submission 2021 (Water Plan 5), a roadmap of key enhancements will be delivered to improve customers digital experience. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-10-29 |  | 2021-12-22 | 0 |  | 2022-02-10 |  | 2022-06-30 | 2023-10-16 | 1243560 |  | Amber | Amber | Green | Green | Green | Funding was reduced in prioritisation decision. Project running with 'keep the lights on' until confirmation can be received from the business to close the project.
Q1 23-24 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 |  | 6428267 | [5 empty] | Green | Project Delivery phase has commenced and Design workshops are 30% completed. Workshops are scheduled for completion December 2023.
Q1 23-24 | Dental Health Services Victoria | DHSV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2024-12-20 | 9490000 |  | Green | Green | Green | Green | Green | The EoHR Project progressed onto testing and software validation of the product while undertaking concurrent change management and training activities. The Steering Committee has endorsed an amended go-live and and schedule
Q1 23-24 | Victorian Building Authority | VBA | 3296 | Practitioner Registration Program (PRP) | Property and Planning | Customer Relationship Management | Our strategic objective is making licensing & registration systems more efficient, simpler & transparent, we plan to create a Practitioner Registration Platform providing online web forms & internal workflows & data integrations | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-05 | 2021-03-24 |  | 2021-03-24 | 0 |  | 2021-03-24 |  | 2022-01-31 | 2023-10-31 | 2030000 | 1630000 | Green | Green | Green | Green | Green | The project is live as of 31st July and will be closed at the end of Oct
Q1 23-24 | Department of Health | DH | 3301 | Disaster Recovery as a Service (DRaaS) | Health | Development and Integration | Enable Victorian public health services to have a fit-for-purpose ICT disaster recovery capability for critical applications in the event of a significant disruption. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-09-01 | 2021-07-30 | 2021-05-28 | 2021-05-28 | 1432000 |  | 2021-07-26 |  | 2023-06-30 | 2023-12-22 | 3883000 | 17463449 | Amber | Amber | Green | Green | Red | The project has experienced delays due to competing priorities for key technical resources. The project is reviewing the resource priorities to mitigate the risk of further delays
Q1 23-24 | Department of Transport and Planning | DTP | 3306 | One Digital Workplace: Identity and Access Join | Transport and Vehicles | Development and Integration ,Systems Management | Enable an integrated and secure Department of Transport (DoT) through ensuring any DoT user from anywhere using a DoT issued device can access data systems and resources across the department. | Delivery | Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2022-03-25 | 2024-04-30 | 5870000 | 9570000 | Amber | Amber | Green | Green | Green | Overall status is green. Project is tracking to the schedule.
Q1 23-24 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | Objective of this project is to prepare an options analysis brief outlining best of breed solutions for Timetabling and Journey planning. The analysis will inform a recommended solution to build and implement. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2024-06-30 | 4739268 |  | Amber | Amber | Amber | Amber | Green | Overall project status is green. Business testing and data load of timetables are currently in progress.
Q1 23-24 | Department of Transport and Planning | DTP | 3313 | Public Transport Real-time Vehicle Location | Transport and Vehicles | Business Intelligence,Data Management,Development and Integration | Objective of this project is to modify A,B & C-Class tram Thoreb units to enable transfer of data to Transnet & trial Traffic Light Prioritisation. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2023-09-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-20 | 2022-02-28 | 2022-02-28 | 0 |  | 2022-02-28 |  | 2022-06-30 | 2023-09-29 | 2011672 |  | Amber | Amber | Amber | Amber | Green | Project completed.
Q1 23-24 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3315 | Business Transformation Program - Horizon 1 | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Management of Process ,Tracking and Workflow | The program will uplift capabilities across key business functions, including customer service, data, asset and workforce management, and financial management to enable improved customer service and efficiency.​ | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2023-09-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-11 | 2021-04-27 |  | 2021-04-27 | 115137 |  | 2021-07-01 |  | 2023-06-30 | 2023-08-31 | 5200000 | 6213256 | Green | Green | Amber | Amber | Green | Horizon 1 is now completed and has delivered the foundational work for Finance / CRM / Billing systems and finalised future state of business processes in order to deliver Tranche 1 of the program.
Q1 23-24 | South West Alliance of Rural Health | SWARH | 3317 | SWARH Modern Workplace Migration and Adoption | Health | Collaboration ,Communication,Content Management,Customer Initiated Assistance,Customer Preferences,Document Management ,Forms Management,Human Capital / Workforce Management ,Knowledge Discovery ,Knowledge Management ,Management of Process ,Organisational Management ,Records Management ,Search ,Security Management ,Tracking and Workflow | To migrate all SWARH-supported Health Services to modern workplace cloud services, and promote the adoption of these services. This will drive improved communication, collaboration and productivity, across and within each of these Health Services. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PMBoK | 2021-12-03 | 2022-05-16 | 2022-08-31 | 2022-08-31 | 224344 | 288344 | 2022-10-03 |  | 2023-06-30 | 2024-03-22 | 2809441 |  |  | Amber | Amber | Green | Green | 5500 mailboxes migrated across 8 Health Services. South West Health (SWH) migration was a significant milestone. Feedback from SWH in relation to the migration was extremely positive.
Q1 23-24 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 |  | 32018000 | [5 empty] | Amber | Project over all status is amber due to project schedule issue. Development work is ongoing.
Q1 23-24 | Fire Rescue Victoria | FRV | 3320 | Response Monitoring and Move-Up Monitoring | Emergencies and Safety | Business Intelligence | • Improve emergency response benchmarks, predicative deployment analysis and aid decision making to improve operational response utilising historical response data. • Efficient resource planning and use based on real time data to inform operation | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV PMF | 2021-06-01 | 2021-10-01 |  | 2021-10-01 | 1 | 0 | 2021-12-01 |  | 2023-06-30 |  | 3000000 |  | Amber | Amber | Amber | Amber | Amber | The project is reporting amber as there have been delays relating to execution of the contract. A variation to schedule will be completed upon contract execution.
Q1 23-24 | Fire Rescue Victoria | FRV | 3325 | HRIS | Emergencies and Safety | Human Resources | HRIS Project is in the initiation stage, with the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 |  | 22392000 | [5 empty] | Amber | A variation has been approved to recommence the project in Q2 2023-24. Project is currently reporting amber whilst resource pipeline constraints are being mitigated.
Q1 23-24 | Transport Accident Commission | TAC | 3329 | Financial Management & Procurement System | Transport and Vehicles | Financial Management | The project will replace the existing Finance and Procurement management systems in order to ensure compliance requirements are met, mitigate the risk of fraud and corruption and move processes towards industry practice. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-16 |  | 2021-12-16 | 270115 |  | 2021-12-16 | 2021-12-16 | 2023-02-06 | 2023-11-30 | 2412927 | 2708084 | Amber | Green | Green | Green | Green | On Track.
Q1 23-24 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 |  | 23495000 |  | Green | Green | Green | Green | Amber | Delays in finalising Statement of Work have impacted vendor activities. Statement of Work is in final draft and tabled for approval at the Steering Committee and PCB mid-October.
Q1 23-24 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Postponed |  | 2023-08-09 | PMBoK | 2021-10-08 | 2022-09-22 | 2024-09-12 |  | 0 | [5 empty] | 0 | [6 empty] | Due to dependencies on a number of projects being successfully implemented during FY23/24 including Document Management System Upgrade and Digital Asset Storage Remediation Program, a decision has been made to pause the ECM project, with an aim to recommence delivery in 24/25.
Q1 23-24 | Austin Health | AH | 3341 | EMR Documentation and Infusions Project | Health | Communication,Document Management ,Forms Management,Tracking and Workflow | The project will implement electronic clinical documentation and the administration of fluid medication and nutrition infusions, reducing the risks associated with paper-based document management and improving patient safety. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2021-10-04 | 2021-11-02 |  | 2021-11-08 | 0 |  | 2022-01-24 |  | 2024-01-24 |  | 5381664 |  | Green | Green | Green | Green | Green | Documentation: Successfully implemented all key deliverables Infusions: Final report endorsed and project completed
Q1 23-24 | Victorian Building Authority | VBA | 3357 | Online interactive forms for builder registrations | Property and Planning | Customer Relationship Management | This proposal will create online interactive forms with a simple online payment function, making the application process faster and easier for builders. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-03 | 2022-01-31 |  | 2022-01-31 | 0 |  | 2022-01-31 |  | 2023-01-31 | 2023-08-21 | 1700000 | 2194510 | Green | Green | Green | Green | Green | This project is live and will be closed by the end of Oct
Q1 23-24 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated enterprise wide Electronic Document and Records Management Solution and an Enterprise Service Management platform. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-03-31 | 8559000 | 9059000 | Amber | Amber | Amber | Amber | Amber | The EDRMS project is rated Amber, due to ongoing resourcing delays and risks regarding budget and procurement schedule. These impacts are being managed and the project is expected to deliver its outcomes. The project remains on track for completion by 31 March 2025.
Q1 23-24 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Technology enablement of Finance and Procurement, including the implementation of Oracle Cloud. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Green | Amber | Red | Red | Red | The procurement process to select and engage an implementation partner has re-commenced. This process was previously paused to enable more time to be spent defining the scope of the Fusion Cloud platform, and to ensure that solution is aligned to strategic objectives. Whilst the procurement process has re-commenced, the pause has resulted in a program delay, and the costs/benefits will need to be reviewed and updated.
Q1 23-24 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | Establishment of a single enterprise wide fit for purpose rostering and timesheet solution for Victoria Police. The solution will support rostering and timesheet management across all sworn and VPS staff and will be on approved mobile devices. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 27438000 | Amber | Amber | Amber | Amber | Amber | The Enterprise Rostering project is rated AMBER, trending to GREEN. The project remains on track for completion by 30 September 2025.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3361 | ACCS Arbitration Neo Module | Government and Economy | Customer Relationship Management | A new arbitration function will allow ACCS to make binding determinations for worker's compensation disputes not resolved through the existing conciliation process. The model provides a low-cost, timely and effective alternative to the court process. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-17 | 2022-04-14 | 2024-05-31 |  | 0 | 1877768 | [11 empty] | WorkSafe/WIC/ITSS have made the decision to "test the market" to determine if there was an appropriate off the shelf SaaS solution that support both conciliation and arbitration case management. An RFI (Request for Information) was issued in August 2023 with short-listed potentially suitable respondents invited to participate in vendor showcases. An Evaluation Report is currently being drafted by the Evaluation team. This report will provide detail on all RFI vendors based on the Evaluation criteria assessment, including recommendations on shortlisted vendors to be invited to RFT.
Q1 23-24 | Fire Rescue Victoria | FRV | 3364 | Fire Station Switches | Emergencies and Safety | Assets/Materials Management | Replacement of all end of life (EOL) fire station switches supporting the FRV network to ensure a safe secure and reliable ICT environment | Delivery | Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2023-06-30 | 2024-06-30 | 1575000 | 2048379 | Amber | Amber | Amber | Amber | Amber | Due to a recent cyber incident the project has been impacted by resourcing constraints and delays to the project schedule. A variation is being drafted to recommence the project in Q2 2023-24. Upon approval the project schedule and budget will be updated and the project appropriately resourced.
Q1 23-24 | Fire Rescue Victoria | FRV | 3365 | ICS Equipment Refresh - ICT Infrastructure Equipment at End of Life | Emergencies and Safety | Assets/Materials Management | Procure ICT infrastructure equipment to replace existing assets that have reached end of life to ensure ongoing reliability of FRV's ICT infrastructure. | Delivery | Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2020-11-30 |  | 2020-11-30 | 0 |  | 2022-02-14 |  | 2024-06-30 |  | 2100000 | 1532272 | Amber | Amber | Amber | Amber | Amber | Due to a recent cyber incident the project has been impacted by resourcing constraints and delays to the project schedule. A variation is pending approval to recommence the project in Q1 2023-24. Upon approval the project schedule and budget will be updated and the project appropriately resourced.
Q1 23-24 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2024-12-31 | 138595535 | 138595535 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 23-24 | Department of Transport and Planning | DTP | 3370 | One Digital Workplace: O365 Tenancy Consolidation | Transport and Vehicles | Collaboration | Objective of the office 365 Tenancy Consolidation project is to deliver a single Microsoft Office instance across DoT to allow for cross entity collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2022-04-28 | 2022-07-29 | 2022-07-29 | 0 |  | 2022-07-29 |  | 2023-01-31 | 2023-12-29 | 7750000 |  | Amber | Amber | Green | Amber | Amber | The overall status is amber. Transport user migrations in stage 1, 2 and 3 completed. Project end date to be re-baselined for final cleanup work left from Stage 3 and new work commenced in Stage 4 Roads email conversions
Q1 23-24 | Department of Health | DH | 3373 | Meeting Room Technology Upgrade | Community Services | Collaboration ,Communication | This project will seek to equip meeting rooms with Microsoft Teams enabled technology and devices to ensure streamlined meetings for staff working in the office, remotely and from hub locations. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-06-25 | 2021-11-30 |  | 2021-12-15 | 0 |  | 2022-03-01 |  | 2023-06-30 | 2024-01-31 | 6000000 |  | Green | Green | Green | Green | Green | Project is progressing to cost and revised schedule.
Q1 23-24 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | TBC | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The digital marketplace is meeting agreed timelines for releasing functionality into the production version of Digital marketplace which aligns with the expected benefit delivery throughout the 23/24FY
Q1 23-24 | Monash Health | Monash H | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | Delivery of a Shared Pathology Information System supporting the Department of Health Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 |  | 25000000 |  |  |  | Green | Amber | Amber | The impact to the project scope and timelines for the new service provider transition is still under investigation.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3379 | AppLift Project (Sycle Replacement) | Government and Economy | Reporting ,Tracking and Workflow,Visualisation ,Business Intelligence,Organisational Management | The AppLift project will deliver a Strategic Planning, Project Portfolio Management and Performance Reporting Solution that will replace Sycle and enable enriched and efficient reporting. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-05-02 | 2022-10-24 | 2022-12-14 | 2022-12-14 | 0 |  | 2022-12-14 |  | 2023-12-19 |  | 2842792 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and planned activities. The solution is in the final stages of testing. The project focus now turns to solution, service and business readiness activities in preparation for go-live and transition to operations.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3389 | Prison Industries Enhancement Phase 3 Project (PIE3) | Law and Justice | Management of Process | PIE3 will continue to be a key support of Prison Industries’ strategy to transition operations to standard systems. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Project Management Excellence | 2021-10-26 | 2022-03-05 |  | 2022-03-05 | 0 |  | 2022-09-05 | 2022-04-25 | 2024-06-30 | 2024-07-29 | 1959548 | 2932750 | Green | Green | Green | Green | Green | The project is tracking to budget, scope and schedule.
Q1 23-24 | Department of Government Services | DGS | 3390 | WOVG Common Corporate Platforms | Government and Economy | Human Capital / Workforce Management | Implementation of a whole of government cloud based single instance to modernise Human Resources, Finance and Procurement platforms to deliver consistent corporate services across the Victorian Public Service to improve process efficiency. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-28 | 2020-09-29 |  | 2020-09-29 | 808026 |  | 2020-09-30 |  | 2026-09-30 |  | 111630410 | 140000000 | Amber | Amber | Amber | Amber | Amber | The Department of Transport and Planning is the first department to be onboarded to the WOVG HR and Payroll platform, which went live on 22 May 2023. The CCP program is currently in the process of scoping requirements for the next phase of the program.
Q1 23-24 | Department of Education | DE | 3391 | Arc Learning (FUSE Replacement) | Education | Development and Integration | A repository of high-quality, curriculum-aligned learning resources and objects for classroom use and on-demand professional learning content. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-04-01 | 2022-06-30 |  | 2022-06-30 | 235628 |  | 2022-07-01 |  | 2023-06-30 | 2023-11-27 | 1667084 | 2257620 | Green | Green | Amber | Green | Red | The project status is currently reporting Red pending final approval of the project change request to re-baseline the project schedule and budget based on the confirmation of scope and prioritised requirements. The Project Control Board has pre-approved rescheduling the 'Go-live' date to soft launch at the end of November and hard launch for Term 1 2024.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3392 | Identity and Access Management (IDAM) PHASE 2 | Employment and Workplace | Systems Management | Close gaps in the management of the identities that have access to DJCS data by implementing automated workflows. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-10-18 | 2022-03-18 |  | 2022-03-18 | 113451 |  | 2022-03-21 |  | 2022-07-31 | 2024-01-30 | 937060 | 1291510 | Green | Green | Green | Green | Green | The project is tracking to budget scope and schedule. Three project workstreams out of five have been completed. The remaining workstreams are progressing as expected.
Q1 23-24 | Melbourne Water | MELB Water | 3397 | Project Management Transformation | Environment and Water | Collaboration | Melbourne Water uses an enterprise Project Management tool for managing the capital program. Key issues are; - System functionality, - Performance, - End user experience - Technology that won't reach end-of-support | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2022-04-01 | 2022-07-12 | 2022-10-04 | 2022-10-04 | 0 |  | 2022-10-04 |  | 2023-09-30 | 2024-03-29 | 1293120 |  |  | Green | Amber | Amber | Red | Final workshops for discovery are completed and were focused on the following: 1. Writing and validating user stories/requirements and sending them over to the Vendor for more accurate build estimates. 2. Setting up the environment ready for software deployment. 3. Continuing with Proof of Concept builds and playbacks which help inform the requirements generation. 4. Understanding costs and timeline options for the rest of the project and documenting the extra funding requirement to make sure the rest of the project can be delivered.
Q1 23-24 | Western Health | WH | 3398 | Western Health - Bacchus Marsh-Melton Amalgamation - Network Switch and Clinical Grade Network Uplift | Health | Systems Management | Uplift of the Bacchus Marsh and Melton network switch and clinical grade network infrastructure to facilite health service amalgamation with Western Health | Closed - Completed | Efficiency/Productivity (Non Financial) | 2023-09-29 | PRINCE2 | 2021-07-01 | 2021-09-30 |  | 2021-12-21 | 0 |  | 2022-01-03 |  | 2022-12-30 | 2023-08-31 | 4500000 | 7400000 | Green | Green | Green | Amber | Green | Project Deliverables complete. Project now closed.
Q1 23-24 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 |  | 22637000 | [5 empty] | Green | Overall project status is green. Project is tracking to its schedule.
Q1 23-24 | Dental Health Services Victoria | DHSV | 3400 | Smile Squad Network infrastructure | Health | Systems Management | Provision of network infrastructure to smile squad service program | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-07-12 | 2022-01-28 |  | 2022-01-28 | 100000 |  | 2022-01-31 |  | 2023-08-04 | 2023-12-20 | 1964978 |  | Green | Green | Amber | Green | Green | Project is progressing against rebaselined schedule. Installation of network equipment in dental vans is almost complete.
Q1 23-24 | South East Water | SE Water | 3445 | CRUX | Environment and Water | Financial Management | Delivery of new ERP solution including Finance, Procurement & Project Management functions | Delivery | Cost Reduction (Financial) |  | PMBoK | 2022-02-28 | 2022-07-29 |  | 2022-07-29 | 150000 |  | 2022-08-01 |  | 2023-08-04 | 2023-11-30 | 6547711 | 12205891 | Green | Amber | Red | Amber | Amber | UAT has completed and end user training is underway. Data migration for production has commenced. Go live is tracking well towards mid October. While no active issues are reported, risks for data migration keep the project in amber status.
Q1 23-24 | CenITex | CenITex | 3449 | Windows Server 2012 Refresh | Government and Economy | Assets/Materials Management | Uplift Windows servers in scope to more up-to-date version where possible. For servers unable to be upgraded migrate them to Azure where MS extended security update (ESUs) will be available for 3 more years. Decommission redundant Windows servers. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-11-30 | 2022-06-02 |  | 2022-06-02 | 49000 | 49000 | 2022-06-14 |  | 2023-10-31 |  | 1991466 |  | Green | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | CenITex | CenITex | 3450 | Cenitex Windows and Unix Server Patching – One Month Patching Cycle | Government and Economy | Data Management | Automate the following categories for Windows and Unix monthly patching - Pre patching automation workflows - During Patching automation workflows - Post patching automation workflows and -Application health check Automation | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-22 | 2020-11-05 |  | 2020-11-05 | 0 |  | 2020-11-18 |  | 2023-04-28 | 2023-10-27 | 1050177 | 1100177 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 |  | 2024-12-01 | 2025-06-30 | 56681000 |  | Amber | Amber | Amber | Red | Red | Phase 1: Release 1 planned go live date is late November 2023, subject to meeting the go-live criteria including user acceptance testing. An indicative date for a small build (for deferred, non-critical functionality) is to be scheduled. The Program is reviewing requirements and processes for other Lists to identify opportunities for process streamlining and reusing already-developed features and functionality. Future state processes, user research and journeys, requirements, and business rules for the Residential Tenancies List Phase 2 are in development. A rolling pre-discovery has commenced to incorporate all remaining Tribunal Lists, seeking to establish consistency of processes across the Tribunal.
Q1 23-24 | CenITex | CenITex | 3452 | Legacy Hardware Refresh | Government and Economy | Assets/Materials Management | The project will refresh the core network infrastructure in the data centres, ensuring the infrastructure platform is supported and robust to meet the demands of Cenitex customers. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-11-15 | 2022-05-05 |  | 2022-05-05 | 0 |  | 2022-05-05 |  | 2023-06-30 | 2024-09-30 | 4049735 | 4894833 | Amber | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Peninsula Health | PEN Health | 3455 | Peninsula Health Digital Application Oncology/Haematology Management System | Health | Management of Process | Deploy a fit for purpose Oncology & Haematology management system to achieve contemporary efficient & effective chemotherapy prescribing & treatment scheduling. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-04-05 | 2023-01-02 | 2022-07-01 | 2022-07-01 | 70000 | 95000 | 2023-02-17 |  | 2024-03-29 |  | 1450000 |  |  |  | Green | Green | Green | Project is on track.
Q1 23-24 | Box Hill Institute Group | BHIG | 3456 | Cloud Service Migration | Employment and Workplace | Management of Process | Migration of core on-premise business systems to cloud hosting and implementation of new business system capabilities onto a common ERP cloud hosted platform. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2022-04-01 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-09-01 |  | 2024-04-30 |  | 4557503 |  | Green | Green | Green | Green | Green | Implementation Phase for the first two (of five) project workstreams tracking well with focus on functional integration and data migration testing. Go-live preparations for first migration in early Q2 2023/24 completed including training and post go-live support arrangements. Preparations for second migration at end Q2 2023/24 on schedule. Two other project workstreams remain in the detailed Planning/Design phase with time added to schedule to complete phase. This was due to departure of two key project resources and extra time to validate business process changes required to align with native system capabilities. This phase will be completed in mid Q2 2023/24.
Q1 23-24 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Initiated |  |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-08-15 |  | 0 | 0 | [11 empty] | Tender evaluation completed with prospective vendor identified. Contract negotiation with prospective vendor in progress.
Q1 23-24 | Goulburn-Murray Rural Water Corporation | GMR Water | 3460 | Primary Data Centre On-Premise Refresh | Environment and Water | Systems Management | Refresh Goulburn-Murray Water's IT Infrastructure assets - Servers, Network and Storage as per the asset lifecycle. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2021-11-01 | 2021-11-26 |  | 2021-11-26 | 10000 |  | 2022-07-01 |  | 2023-06-30 | 2023-12-31 | 1231487 | 1302225 | Green | Green | Green | Green | Green | Project is tracking well on time cost and quality. Migration of production workloads have been completed. Decommissioning of old IT Infrastructure in the final stages. All project risks are being actively monitored and under control.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3461 | Infrastructure Migration to Amazon Web Services (AWS) - Foundation Build and Migration Planning | Government and Economy | Systems Management | A key initiative within the IT enablement plan to migrate approximately 80% of business applications to the AWS platform in line with target enterprise architecture. This phase will deliver the foundation build and migration planning activities. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-31 |  | 2022-08-04 | 0 |  | 2022-09-01 |  | 2024-03-31 |  | 4084380 |  | Green | Green | Green | Green | Red | The project is currently reporting as red. The Plan phase is complete and has delivered the AWS Foundation Infrastructure and a Proof of Performance has been conducted. Upon completion of the plan phase it was determined that the migration costs would be significantly more than anticipated. Alternate options will be proposed based on costs, benefits and risks. This could result in either re-scoping or stopping the project. A recommendation will be prepared for the relevant governance committees for endorsement.
Q1 23-24 | State Revenue Office | SRO | 3462 | Windfall Gains Tax | Government and Economy | Development and Integration | From 1 July 2023, a windfall gains tax applies to land that is subject to a government rezoning resulting in a value uplift to the land of more than $100,000. This initiative implements the systems needed to support administration of this tax. | Delivery | Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2022-07-01 | 2022-12-31 | 2023-02-23 | 2023-02-24 | 0 | 3708718 | 2023-02-24 |  | 2024-06-30 |  | 14100000 |  |  |  | Red | Red | Amber | The project has been replanned with a second phase (2A) delivering liability calculations residential land exemptions Valuer General integration.
Q1 23-24 | V/Line Corporation | V/Line | 3464 | eTicketing | Transport and Vehicles | Customer Preferences,Management of Process | The eTicketing project will implement a system to generate eTicket via electronic means such as email, mobile, improving customer experience by making V/Line long-distance and coach tickets accessible to customers in their preferred format. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-01-27 | 2023-06-30 | 2023-06-30 | 150000 | 216084 | 2023-07-03 |  | 2024-03-29 |  | 2024792 | [5 empty] | Amber | Vendor Development Block 1 of 4 completed with Block 2 of 4 in progress along with V/Line Development work in progress. Once the change in scope is approved, status can be changed to green in next reporting period.
Q1 23-24 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2023-12-15 |  | 0 | 500000 | [11 empty] | Stakeholder identification and process inventory for employee time and attendance underway. T&A requirement documentation and analysis on payroll reporting to commence.
Q1 23-24 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 |  | 19500000 |  |  |  | Green | Green | Green | Project proceeding to stakeholder expectations
Q1 23-24 | Department of Education | DE | 3468 | School Bus Management System (Uplift to platform) | Education | Systems Management | This project will re-platform School Bus Management System (SBMS) from its existing system onto the Salesforce platform where it can be delivered and supported on an Enterprise platform with stronger foundations and an improved and robust design. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2023-09-12 | Agile | 2022-06-27 | 2022-06-27 |  | 2022-07-29 | 0 |  | 2022-07-31 |  | 2022-12-01 | 2023-09-12 | 1428995 |  | Green | Amber | Amber | Amber | Green | The project has completed. Project went to the production environment on 12 September 2023 (a solution implementation issue resulted in slight schedule delays). Followed by that, the project went into hypercare (warranty) phase for the subsequent three weeks.
Q1 23-24 | Department of Health | DH | 3469 | My Health Record (MHR) Expansion 2022-2024 | Health | Data Management,Development and Integration | Connection of Public Sector Residential Aged Care Services (PSRACS) and Registered Community Health Services (RCHS) for viewing, upload RCHS Event Summary, Outpatient Specialist Letter, and improve clinical document uploads to MHR at point of care. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2022-06-01 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 |  | 1770000 |  | Green | Green | Green | Green | Green | Project is on schedule.
Q1 23-24 | Suburban Rail Loop Authority | SRLA | 3471 | Contract Management System - SRLA | Transport and Vehicles | Management of Process ,Records Management ,Reporting | The project will deliver a modernised contract management system for SRLA to integrate multiple platforms, improving workflow efficiencies and data quality across functions | Closed - Completed | Efficiency/Productivity (Non Financial) | 2023-09-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-03-02 | 2022-09-14 |  | 2022-09-30 | 483200 |  | 2022-10-03 |  | 2023-06-14 | 2023-09-28 | 4025000 | 4373645 |  | Green | Green | Green | Green | Project deliverables have been met and Unifier application has successfully been implemented.
Q1 23-24 | Energy Safe Victoria | ESV | 3476 | ESV Transformation - Digital Component - Tranche 1 | Environment and Water | Business Intelligence,Content Management,Customer Relationship Management,Data Management,Development and Integration ,Financial Management,Knowledge Management ,Management of Process ,Reporting ,Routing and Scheduling,Security Management ,Tracking and Workflow,Visualisation | Digital foundations enabling ESV to become a safety first, data driven customer centric regulator. Digital foundations include: - Customer Engage Platform - Field Services Platform - Data Hub - Website replacement - Finance Platform. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial) | 2023-07-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-11-30 |  | 2022-12-07 | 1048699 |  | 2022-12-08 |  | 2023-07-31 |  | 5644825 |  |  |  | Green | Green | Green | Transformation program Tranche 1 has completed against the project plan and schedules.
Q1 23-24 | Barwon Region Water Corporation | BR Water | 3483 | C1408 - Data for a High Performing Business | Environment and Water | Business Intelligence,Data Management | Taking a phased approach, this project will establish foundational technology, establish data management practices and build data capabilities across the business. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2021-08-20 | 2022-05-26 |  | 2022-05-27 | 141200 |  | 2022-07-01 |  | 2023-06-30 | 2023-12-31 | 2203795 | 1485800 | Amber | Red | Red | Red | Red | Project had been delayed due to several implementation issues such as achieving Cloud Security Infrastructure acceptance criteria data transformation issues related to unstructured data from FOCUS3 and data ingestion & replication issues. Additional scope for Customer data has been added to the project. ACTION TO GREEN: Project has raised a change request PCR003 to seek additional time and budget to complete the remaining scope of the project and also include the new scope for Customer Data. Once PCR003 is approved the project will be re-baselined.
Q1 23-24 | Grampians Rural Health Alliance | GRHA | 3484 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 1 & 2 | Health | Development and Integration | Ballarat Base Hospital Redevelopment - ICT Program - Stage 1/2 ICT systems to support the project works, improving patient and staff systems & support. | Delivery | Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-03 | 2022-11-04 | 2022-11-01 | 2022-11-01 | 0 |  | 2023-03-01 |  | 2024-10-25 |  | 2458647 | [5 empty] | Green | Project on track
Q1 23-24 | Yarra Valley Water | YV Water | 3485 | Enterprise Analytics Platform - Phase 1 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational datastore and business intelligence reporting technologies with a modern, scalable data and analytics platform. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-06-01 | 2022-09-30 | 2022-10-25 | 2022-10-26 | 120000 |  | 2022-10-26 |  | 2024-06-30 | 2023-11-30 | 1703700 | 3150200 |  | Green | Green | Green | Green | Incorrect delivery costs previously reported (excluded FY24 approval). Project build and technical release of foundational component completed. Staged implementation of remaining scope items developed and undergoing testing and UAT for completion in Nov release. Business case endorsed for commenced of second phase of capability development and rollout.
Q1 23-24 | Environment Protection Authority | EPA | 3486 | MAJ105-SDOKR2-1 Enviro Manager | Environment and Water | Business Intelligence,Data Management | Implementation of Enviro Manager system. The purpose of the Enviro Manager project is to have a modern stable environmental data management system that provides value to EPA by having streamlined processes and improved data quality and management. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Agile and Waterfall | 2022-07-25 | 2022-09-09 |  | 2022-10-27 | 28884 |  | 2022-11-03 |  | 2023-06-30 | 2023-11-15 | 2002427 | 2901242 |  | Amber | Red | Green | Amber | Risks associated with the delivery schedule of the current phase and resourcing has moved the project to "On Watch" status.
Q1 23-24 | South East Water | SE Water | 3487 | Acumen Phase 1 | Environment and Water | Data Management | Delivery of the platform designed in phase 0 to ingest all 8 source systems and deliver on the 3 use cases. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2022-08-31 |  | 2022-09-01 | 100000 |  | 2022-09-05 |  | 2023-06-01 | 2023-11-24 | 4832820 | 5705936 | Green | Green | Green | Amber | Red | Delays to the schedule and cost impacts have been caused by data migration complexity when preparing data for production.
Q1 23-24 | South East Water | SE Water | 3488 | Pricing Reform 23 System Changes | Environment and Water | Financial Management | The upcoming pricing period 5 has resulted in a need to create major tariff reform in our billing system. | Closed - Completed | Compliance (Non Financial) | 2023-07-31 | PMBoK | 2022-07-04 | 2022-10-28 |  | 2022-11-02 | 189196 |  | 2022-11-07 |  | 2023-07-28 |  | 1636586 |  |  | Green | Green | Green | Green | Production go live occurred in July. Hypercare occurred in July. The project has been closed end of July
Q1 23-24 | Environment Protection Authority | EPA | 3489 | MAJ101-Permissions Digital Build Improvement Program | Environment and Water | Business Intelligence,Development and Integration ,Document Management ,Management of Process ,Tracking and Workflow | Delivery of a suite of priority digital enhancements to Dynamics and Portal to realise efficiency improvements for internal and external stakeholders. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-10-13 |  | 2022-10-26 | 78363 |  | 2022-11-07 |  | 2023-12-31 | 2025-02-06 | 2732021 | 2196377 |  | Green | Green | Green | Green | 95% of Phase 1 requirements have been completed, and requirements for the Development Advisory are ready for approval by the November PCG. 198 enhancements are now in production, supported by Organisational Change Management activities.
Q1 23-24 | Austin Health | AH | 3494 | Austin Health HR Information Systems | Health | Human Resources | Replacement of legacy HR Systems for Payroll, Recruitment and On-boarding. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-07-31 | 2023-02-01 |  | 2023-02-01 | 0 |  | 2023-02-01 |  | 2024-06-30 |  | 7800000 |  |  |  | Green | Green | Amber | Project on track. Finalised Design Phase Completed iterations of playback Commenced Systems Integration Testing Legacy data issues putting pressure on the schedule.
Q1 23-24 | Victorian Building Authority | VBA | 3495 | Building Practitioner System | Property and Planning | Customer Relationship Management | The Building Practitioner System functional scope is positioned within the CRM roadmap to build upon the foundational work in the scope of the existing PRP project while ensuring that the functions built, and sequencing of work is aligned to succes | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-12-01 | 2022-06-15 |  | 2022-06-16 | 328000 |  | 2022-06-16 |  | 2023-05-26 | 2023-10-31 | 2500000 | 4622000 | Amber | Amber | Green | Green | Green | This project is now live and will be closed by the end of Oct
Q1 23-24 | Peter MacCallum Cancer Centre | Peter MAC | 3496 | Parkville Laboratory Information System Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. Stgae 1: LIS planning and procurement Stage 2 (delivery): LIS implementation | Initiated |  |  | PRINCE2 | 2022-03-01 | 2023-12-31 |  |  | 8000000 | [12 empty] | LIS Tender in progress.
Q1 23-24 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2026-12-31 | 5135000 | 21744926 |  |  | Green | Amber | Amber | Overall project status is amber. Majority of the project deliverables are on track. Horizon 3 planning is ongoing.
Q1 23-24 | Department of Transport and Planning | DTP | 3500 | CCTV Multi-casting Project | Transport and Vehicles | Business Intelligence,Communication,Visualisation | The objective of this project is to implement a multicast solution to address the physical firewall limitation and support the increasing number of CCTV cameras in the network. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-01-31 | 2023-12-18 |  | 0 | [12 empty] | Project initiation and procurement activities are ongoing.
Q1 23-24 | Department of Transport and Planning | DTP | 3501 | CCTV Federation and Third Party CCTV camera access | Transport and Vehicles | Business Intelligence,Communication,Visualisation | The objective of this project is to enable CCTV federation access with external CCTV systems of Melbourne Metro Trains and Southern Cross Station and develop an integrated platform for 3rd Party CCTV camera access. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-01-31 | 2023-12-18 |  | 0 | [12 empty] | Project initiation and procurement activities are ongoing.
Q1 23-24 | Department of Transport and Planning | DTP | 3502 | Speed Change Management Tool Project | Transport and Vehicles | Communication,Content Management,Data Management | The objective of this project is to streamline the speed zone and speed sign change processes. This will be achieved through an integrated Speed Change Management Tool (SCMT). | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2023-01-31 | 2023-04-28 | 2023-05-08 | 0 |  | 2023-06-19 |  | 2024-07-31 |  | 1029000 |  |  |  |  | Green | Amber | Overall project status is amber due to delay in production deployment delay. Solution development and testing is in progress.
Q1 23-24 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 |  | 1512000 |  | Green | Green | Green | Amber | Green | A variation has been approved to recommence the project in Q2 2023-24.
Q1 23-24 | Fire Rescue Victoria | FRV | 3516 | Network Systems Equipment End of Life | Emergencies and Safety | Assets/Materials Management | Identify and replace network system equipment that are approaching end of life. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-12-15 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2024-06-30 |  | 3179371 | [5 empty] | Amber | A variation has been approved to recommence the project in Q2 2023-24. Project is currently reporting amber whilst resource pipeline constraints are being mitigated.
Q1 23-24 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3518 | Project Synergy | Employment and Workplace | Development and Integration | Consolidation of applications | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-12 | 2022-12-09 |  | 2022-12-09 | 628000 |  | 2023-02-06 |  | 2024-02-06 | 2024-02-16 | 2036760 |  |  |  | Green | Green | Green | Overall Status is green project is tracking to plan. Phase 1 (SAS) was delivered on time and budget. Phase 2 (SRGO) development is underway.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3520 | Provision of a Claim Management Solution (CMS) | Emergencies and Safety | Development and Integration | Replacement of the Victorian Disaster Recovery Funding Arrangements (DRFA) Claims Management Solution, the key platform for local councils to lodge claims seeking reimbursement for eligible expenditure incurred following natural disaster events. | Closed - Completed | Customer Satisfaction (Non Financial) | 2023-08-04 | Agile | 2021-09-21 | 2022-02-01 |  | 2022-02-01 | 247510 | 284279 | 2022-09-20 |  | 2023-03-30 | 2023-08-04 | 904328 | 1465286 | Green | Green | Amber | Green | Green | This project is now closed. This has now moved to production and successfully implemented at the end of August 2023.
Q1 23-24 | CenITex | CenITex | 3521 | Cenitex Long Term Tape Modernisation | Government and Economy | Data Management | Switch long-term data retention from physical media (tapes) to cloud storage enabling Cenitex to offer improved Service Level Agreements for data restoral. Reduce risk of data loss arising from technological obsolescence and media deterioration. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-12-16 | 2022-10-20 |  | 2022-10-20 | 49000 |  | 2022-10-25 |  | 2023-11-30 |  | 1534208 | 1541000 |  | Green | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Peninsula Health | PEN Health | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Initiated |  |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2023-12-14 |  | 0 | 26576 | [11 empty] | The project remains in the Initiation Stange
Q1 23-24 | Grampians Rural Health Alliance | GRHA | 3523 | AD Domain Migration | Health | Systems Management | The AD domain migration project aims to consolidate four separate Grampians Health environments(Ballarat, Edenhope, Horsham and Stawell) into one cloud instance. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2022-11-21 | 2022-12-05 |  | 2022-12-05 | 0 |  | 2022-12-05 |  | 2023-11-30 |  | 2529763 |  |  | Green | Green | Green | Green | The project is on track
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3527 | PeopleCentral Project - Payroll Integrations & Strategic Workforce Experience Portal | Government and Economy | Human Resources | Deliver new functionality in the SuccessFactors platform, including a transition from Aurion to PeopleCentral for people management & payroll processing, system authentication & integrations, as well as succession & people analytics modules. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-10-06 |  | 2022-10-10 | 0 |  | 2022-10-11 |  | 2023-06-30 | 2024-03-31 | 2400000 | 2753702 |  | Green | Amber | Green | Amber | Project is tracking Amber. Delays encountered due to implementation partner resource capacity challenges. Replanning is underway.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3532 | Delivery Enablement | Government and Economy | Customer Relationship Management | Facilitate the continued delivery of products and services onto the CRM during the transition period into ITSS. The licencing/Advisory, Inspections/Investigations and Claims & Recovery projects are all dependent on the enablement stream for delivery | Closed - Completed | Cost Avoidance (Financial) | 2023-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-08-31 |  | 2022-09-01 | 0 |  | 2022-10-03 |  | 2023-06-30 | 2023-07-31 | 4613798 |  |  | Green | Green | Green | Green | All scope delivered successfully. Project closed.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3540 | Recovery Service Model Technology and Implementation. | Government and Economy | Customer Relationship Management | Delivery of case management capability using Saleforce platform and solution to enable improved recovery management and planning tools as well as core claims management capability rolled out to WorkSafe internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-08-23 |  | 2022-08-24 | 0 |  | 2022-10-03 |  | 2024-11-30 |  | 39266624 |  |  | Amber | Amber | Green | Amber | Supplier for data migration solution has not been selected as planned. Revisions to the solution is required together with replanning of functional delivery to align with data availability completed and revised phase 1 delivery to Q3 2024.
Q1 23-24 | Transport Accident Commission | TAC | 3541 | Infrastructure Migration to Amazon Web Services (AWS) - Foundation Build and Migration Planning | Transport and Vehicles | Systems Management | A key initiative within the IT enablement plan to migrate approximately 80% of business applications to the AWS platform in line with target enterprise architecture. This phase will deliver the foundation build and migration planning activities. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-07-01 | 2022-08-31 |  | 2022-09-15 | 0 |  | 2022-09-15 |  | 2024-03-31 |  | 2722920 |  |  | Green | Green | Green | Red | The project is currently reporting as red. The Plan phase is complete and has delivered the AWS Foundation Infrastructure and Proof of Performance has been conducted. Upon completion of the plan phase it was determined that migration costs would be significantly more than anticipated. Alternate options will be proposed based on costs benefits/risks. Further options to be considered in this phase for the migration of on-premise data workloads to the cloud with more cost-effective approaches to achieve that outcome are being currently considered for recommendation to management for the project. Recommendations will be prepared for relevant governance committees for endorsement.
Q1 23-24 | Ambulance Victoria | AVS | 3542 | Cybersecurity Program | Health | Security Management | This program is the implementation of the 32 security controls issued by the Dept of Health over a 3-year phased approach. Phase 1 will deliver the key Australian Cyber Security Centre (ACSC) Essential 8 security controls at maturity level 1. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-01-31 |  | 2023-01-31 | 0 | 283240 | 2023-02-01 |  | 2023-11-24 | 2024-06-30 | 5379745 | 5396050 |  |  | Green | Green | Green | The project is reporting as green and delivery is progressing as planned.
Q1 23-24 | Ambulance Victoria | AVS | 3544 | Health Safety & Claims Management System (HSCS) | Health | Human Capital / Workforce Management | AV’s current HSCS is being improved to assist in identifying and managing safety incidents and improving general OHS practices. It will also assist in managing WorkCover claims and supporting injured staff through the return to work process. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 | 2023-11-17 |  | 0 | 200000 | [11 empty] | The project remains on track in the Initiate stage.
Q1 23-24 | Ambulance Victoria | AVS | 3546 | Digital Employee Experience Platform (DEEP) Project | Health | Communication,Content Management | Introduce a new intranet solution to replace the end-of-life SharePoint Server and provide a platform that supports improved online productivity and engagement for all staff. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-02-28 | 2023-07-21 | 2023-07-21 | 0 | 126134 | 2023-07-24 |  | 2024-06-30 |  | 2429914 | [5 empty] | Green | The project is on track with the vendor onboarded in July 2023.
Q1 23-24 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will address the closure of both Ambulance Victoria’s Data Centres and the end-of-life of Data Centre assets through migrating workloads to Cloud. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 894921 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 |  |  | Amber | Green | Green | The project is reporting as green and delivery is progressing as planned.
Q1 23-24 | Ambulance Victoria | AVS | 3548 | Enterprise Data Warehouse | Health | Business Intelligence,Development and Integration | Following closure of the Predictive Analytics Program, the EDW Project has been created to focus on establishing a modern cloud-based data and analytics platform that will provide real-time information and decision support to our operations teams. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-01-31 | 2023-02-12 | 2023-02-12 | 75267 | 165788 | 2023-03-13 |  | 2024-03-31 | 2024-04-05 | 7791544 |  |  |  | Green | Green | Green | The project is reporting as green and delivery is progressing as planned.
Q1 23-24 | Geelong Performing Arts Centre | GPAC | 3549 | Geelong Arts Centre Digital Transformation: Implementation of core applications | Culture, Sport and Recreation | Customer Relationship Management,Financial Management,Reporting | Business Applications implementation project-Phase 1 Implementation of core applications: Design & implementation of ERP comprising Microsoft Dynamics Business Central, Payroll, Budgeting process and Asset management. Design & implementation of CRM | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2022-12-12 |  | 2022-12-12 | 58000 | 58000 | 2023-01-09 |  | 2023-12-31 | 2024-06-30 | 1242000 |  |  |  | Green | Green | Green | The project is tracking well to approved plan.
Q1 23-24 | Hume Rural Health Alliance | HRHA | 3550 | Hume Regional Patient Administration System (PAS) | Health | Financial Management,Records Management ,Tracking and Workflow | This project will delivery a regional patient administration system to support patient administration workflows and reporting. The project addresses critical operational and clinical risks to support patient care | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-04-28 |  | 2023-05-01 | 0 | 300000 | 2023-05-01 |  | 2024-12-31 |  | 7700000 |  |  |  |  | Green | Green | Project is running to plan. Comprehensive regional governance has been established
Q1 23-24 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Initiated |  |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2023-08-31 |  | 0 | [12 empty] | Preferred vendor has been selected. Awaiting final budget approval to move project into delivery phase.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3552 | FY 2022-23 Common Platforms Program | Government and Economy | Systems Management | Establish the three priority common technology platforms for use by all Groups. The collaboration, cloud and infrastructure and integration common technology platforms. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial) | 2023-09-14 | Waterfall | 2022-11-01 | 2022-12-09 |  | 2022-12-09 | 160000 |  | 2022-12-12 |  | 2023-06-30 | 2023-07-31 | 973000 |  |  | Amber | Amber | Amber | Green | The program for FY22-23 was completed within the agreed time and budget. The end program report is completed and in the process of obtaining the formal signoff.
Q1 23-24 | Transport Accident Commission | TAC | 3553 | Voice Recording | Transport and Vehicles | Communication | Voice recording enables TAC to perform call coaching; for the ongoing improvement of our clients interactions with the TAC as well as supporting our staff’s wellbeing when managing challenging phone calls and behaviours of concern. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2022-10-20 | 2022-10-20 |  | 2022-10-20 | 0 |  | 2022-10-20 | 2022-11-28 | 2023-08-31 | 2023-10-31 | 1481639 |  |  | Green | Green | Green | Green | On Track.
Q1 23-24 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Initiated |  |  | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 |  | 0 | [12 empty] | Business Case is being drafted.
Q1 23-24 | Melbourne Water | MELB Water | 3559 | Network Architecture Improvements SDWAN | Environment and Water | Security Management | Network Architecture improvement to SD WAN / Zero trust Model | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-08-26 | 2023-01-16 |  | 2023-01-25 | 0 |  | 2023-01-26 |  | 2023-10-10 | 2024-04-04 | 1189517 | 2895116 |  |  | Amber | Amber | Amber | Project preparing for a change request to include the scope from tranche 2 & 3 rather than commence a new project, overall health will remain Amber until approvals are completed. Preparations in progress to complete Pilots at site Test Lab in mid October and pumping Station in mid November. Schedule impacted by delays in solution development and hardware procurement.
Q1 23-24 | Melbourne Water | MELB Water | 3560 | Network Hardware Refresh 22/23 | Environment and Water | Security Management | Melbourne Water is ensuring continued investment in our IT network through ongoing refresh of IT Hardware as it approaches end of life rather than extending support, reducing risk of unplanned network outages. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2023-01-02 | 2023-03-06 | 2023-08-15 | 2023-08-15 | 0 |  | 2023-08-15 |  | 2024-04-04 |  | 3158890 | [5 empty] | Amber | Completed design and implementation of network reporting and alerting. Several items progressing through approval stages; Microwave link upgrade, router deployments & terminal server hand over. RFQ responses for switches have been received for assessment. SoW’s for preferred Data Centre option and replacement of Load Balancers have been reviewed. Hardware upgrade cutover attempt was backed out due to a Controller failover issue, this has been resolved and rescheduled. This has caused a delay of 5 weeks and Amber schedule health with a Project Change Request pending to return to green.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2024-06-30 |  | 70000 | 600000 | [11 empty] | An implementation planning study for electronic patient record foundations and clinicals for three health services is underway.
Q1 23-24 | Emergency Services Telecommunications Authority | ESTA | 3564 | Alternate CAD | Emergencies and Safety | Systems Management | Build an additional platform as a backup/redundancy to support Computer Aided Dispatch platform during planned and unplanned outages. | Delivery | Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-02-15 | 2023-12-31 | 2023-02-02 | 2023-02-02 | 0 | 600000 | 2023-08-01 |  | 2024-02-29 |  | 5371545 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q1 23-24 | Peter MacCallum Cancer Centre | Peter MAC | 3567 | Wireless Network Refresh | Health | Collaboration ,Communication | Upgrade the Wireless Network Infrastructure at the VCCC to replace legacy hardware. | Initiated |  |  | PRINCE2 | 2022-10-20 | 2023-07-31 | 2023-10-30 |  | 0 | [12 empty] | Implementation Planning Study in progress. Design Signed off and PID is drafted to be signed off.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3568 | Unified Communications Infrastructure | Health | Communication | Replace end of life PABX with new Unified Communications infrastructure for Mildura Base Public Hospital (MBPH) | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2021-06-23 | 2023-02-15 | 2023-06-02 | 2023-06-02 | 0 |  | 2023-06-05 |  | 2024-03-22 |  | 1207979 |  |  |  |  | Green | Green | Project is on track
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3569 | Nurse Call System Replacement | Health | Communication | Replace end of life nurse call system at Mildura Base Public Hospital (MBPH) | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-06-23 | 2023-03-31 |  | 2023-03-31 | 0 |  | 2023-04-01 |  | 2024-03-22 |  | 1024735 |  |  |  |  | Green | Green | Project on track
Q1 23-24 | Alfred Health | ALFRED | 3571 | EMR Oncology Implementation Project | Health | Records Management | Digitalisation of scheduling and transition of all documentation relating to a patient’s treatment, including chemotherapy prescribing and administration, to be electronic within the EMR. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-04-01 | 2022-12-31 |  | 2022-12-31 | 649302 |  | 2023-01-01 |  | 2025-03-31 |  | 5031638 |  |  |  | Green | Green | Green | On track
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3572 | Bedside Medical Device Integration (BMDI) Upgrade | Health | Tracking and Workflow | Upgrading patient monitoring systems in the Bendigo Hospital | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2021-03-01 | 2021-09-30 |  | 2021-09-30 | 0 |  | 2022-06-30 |  | 2023-06-30 | 2024-02-29 | 1290202 |  |  | Green | Green | Green | Amber | Implementation and training for the introduction of bedside monitoring in additional wards has been rescheduled due to conflicting priorities with another ICT project.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3573 | Bendigo Day Rehabilitation Centre ICT Upgrade | Health | Assets/Materials Management | Procurement and installation of network hardware to support new Bendigo Day Rehabilitation Centre | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2022-01-03 | 2022-05-23 |  | 2022-05-23 | 0 |  | 2022-05-23 |  | 2023-05-31 | 2023-12-22 | 1203000 |  |  | Green | Green | Green | Green | Project on track
Q1 23-24 | Department of Health | DH | 3574 | Teams Telephony and Genesys Implementation | Employment and Workplace | Collaboration ,Communication | This project will replace existing telephony systems at all department of Health and department of Families, Fairness and Housing locations with Teams Telephony and Genesys systems that will support improved services. | Closed - Completed | Cost Reduction (Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2023-08-31 | PRINCE2 | 2022-05-01 | 2023-01-31 |  | 2023-01-31 | 195010 |  | 2023-02-01 |  | 2023-06-30 | 2023-08-31 | 1233791 | 1013000 |  |  | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 |  | 0 | [12 empty] | Project intitiation document and requirements were tabled at the September PAS Governance Meeting and endorsed to commence implementation.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3576 | Automated Dispensing Project | Health | Management of Process ,Tracking and Workflow | Implement medication cabinets throughout the Emergency and inpatient departments at Bendigo Hospital | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-01-24 | 2019-09-04 |  | 2019-09-04 | 0 |  | 2020-03-19 |  | 2023-12-31 |  | 2600000 |  |  | Green | Green | Green | Green | The project is on track.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3577 | Expanding Victoria's Waste Data Systems | Environment and Water | Data Management | Investment in a circular economy must be underpinned by reliable and useful data. To support this, the Victorian Government will develop new Victorian Circular Economy metrics and expand the waste data system to cover the entire Victorian economy. | Delivery | Compliance (Non Financial) |  | Governance by Sustainability Fund reporting and review | 2020-10-06 | 2021-07-01 |  | 2021-07-01 | 4668000 | 0 | 2021-07-01 |  | 2024-06-30 |  | 2438000 | 7106000 |  |  | Green | Amber | Amber | Project is amber due to delays in mandatory data regulations and migration of data and change to the scheduled due date for the annual CE Market Report.
Q1 23-24 | Department of Health | DH | 3579 | Identity and Access Management Implementation - Phase 2 | Employment and Workplace | Systems Management | Enhance the existing Department User Onboarding Portal (DUOP) to enable self service and a centralised governance capability enabling improved management of business partner access. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-09-30 |  | 2022-10-24 | 311065 |  | 2022-10-24 |  | 2023-06-30 | 2024-01-31 | 2516489 | 2467097 |  | Green | Green | Green | Green | Project is progressing to cost and revised schedule.
Q1 23-24 | Peter MacCallum Cancer Centre | Peter MAC | 3582 | Core Infrastructure Refresh - Package 1 & 3 | Health | Assets/Materials Management,Systems Management | The Core Infrastructure refresh is a program of works to Refresh Operational Compute & Storage, Refresh, Backup Infrastructure and On-premise Research Compute Infrastructure. It is split into 4 packages to be delivered in a phased approach. | Initiated |  |  | PRINCE2 | 2022-10-17 | 2023-07-31 | 2023-09-30 |  | 0 | [12 empty] | Implementation Planning Study Kicked off. Design Signed off and PID is drafted to be signed off.
Q1 23-24 | Department of Transport and Planning | DTP | 3584 | Heavy Vehicle - Structural Assessment and Permit System (HV-SAPS) | Transport and Vehicles | Customer Initiated Assistance,Management of Process ,Tracking and Workflow | The objective of this project is to automate assessment part of the process of issuing permits for Class 1 vehicles to the heavy vehicle industry. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-11 | 2023-03-31 | 2023-12-18 |  | 0 | [12 empty] | Project initiation and procurement activities are ongoing.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3585 | Regional Community Care Coordination Platform | Health | Records Management ,Tracking and Workflow | Delivery of a digital medical record for all the Community Services provided by members of the Loddon Mallee Rural Health Alliance | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-04-01 |  | 2019-04-10 | 0 |  | 2019-04-11 |  | 2021-03-31 | 2024-08-31 | 1330000 | 4528817 |  | Amber | Red | Amber | Amber | The project team has experienced delays caused by vendor scheduling/quality and continuing resourcing constraints at the participating health services.
Q1 23-24 | Eastern Health | EH | 3587 | NEPN Pathology Reform Program LISConnect Project | Health | Development and Integration | Delivery of shared and integrated laboratory information system for North East Pathology Network which consists of Eastern, Austin and Northern Health Pathology Services. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-02-01 | 2024-03-31 |  |  | 2000000 | [12 empty] | Initial project planning is in progress. The project is on track to exit Initiation stage by the due date March 2024, independent assurance has commenced.
Q1 23-24 | Greater Western Water Corporation | GW Water | 3592 | Corporate Systems Communication | Environment and Water | Document Management ,Financial Management,Human Resources,Management of Process ,Records Management ,Reporting | This project aims to standardise consolidate provide consistency and uplift working practices & corporate platforms in the new GWW environments (ex WW & CWW) | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-08-05 |  | 2022-08-05 | 60097 |  | 2022-08-05 |  | 2023-06-30 | 2023-11-10 | 2039903 | 2182159 |  |  | Green | Green | Green | Project delivered remaining timesheeting component with hypercare being run through to November. Project will be completed in Q2
Q1 23-24 | CenITex | CenITex | 3596 | Enterprise platforms renewal program | Government and Economy | Customer Relationship Management | Upgrade existing Dynamics 365 platform and implement a system that integrates & meets stakeholder requirements for Customer Engagement Project Services and Finance. Also, mitigate support issues due to end of life of the current platform. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-01-04 | 2023-01-12 |  | 2023-01-12 | 0 |  | 2023-02-03 |  | 2024-06-28 |  | 1652000 |  |  |  | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3598 | Agriculture Victoria Services Portal - Release 1 | Business and Industry | Management of Process ,Organisational Management | Establishment of the Agriculture Victoria Services Portal and automation within that portal of agricultural chemical user permitting. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Agile | 2022-07-14 | 2022-12-13 |  | 2022-12-14 | 30000 |  | 2022-12-19 |  | 2023-10-31 |  | 1600000 |  |  |  | Green | Green | Green | On track to complete development by October 2023 in readiness to ‘Go Live’.
Q1 23-24 | Department of Health | DH | 3599 | Mental health and wellbeing website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3600 | Advanced Scheduling and Capability Uplift | Health | Human Capital / Workforce Management | Develop smart rostering and uplift LMRHA member organisational capability to use the core functions of the time and attendance and basic scheduling solution. | Delivery | Cost Reduction (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2022-10-31 |  | 2022-11-18 | 0 |  | 2022-11-21 |  | 2023-12-31 | 2024-04-28 | 1055163 |  |  |  | Green | Green | Green | The Steering Committee has approved an extention of the project to end April 2024. As a result of this and the planned Go Live of 2 health services the status remains green.
Q1 23-24 | Barwon Region Water Corporation | BR Water | 3601 | C1400 - M365 Phase 3 | Environment and Water | Collaboration | Barwon Water currently runs the Microsoft Office Suite on all laptops and utilises this as a key corporate business tool. In line with Microsoft’s roadmap we are upgrading our Microsoft Suite to Microsoft M365. [O365, OneDrive, Teams & SharePoint.] | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2021-07-01 | 2022-01-31 |  | 2022-02-01 | 88158 |  | 2022-02-01 |  | 2023-06-30 |  | 1297936 | 2679081 |  |  | Amber | Red | Red | Enterprise deployment of SharePoint Teams Sites successfully completed. The change has been received positively. Key challenge for the project is to finalise SharePoint Foundation Sites design. Schedule will be revised upon governance approval, anticipated in Q2. RETURN TO GREEN Seek external provider guidance for SharePoint Foundation sites design. This guidance will be core input into project change request 003 which will contain a significant schedule and budget revision.
Q1 23-24 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Initiated |  |  | Agile | 2023-02-24 | 2023-10-27 | 2023-11-05 |  | 1084000 | [12 empty] | System Implementation partner selected for IPS and phase 1 implementation. IPS to commence 23rd October.
Q1 23-24 | Suburban Rail Loop Authority | SRLA | 3603 | Common Data Environment (CDE) | Transport and Vehicles | Assets/Materials Management,Data Management,Document Management ,Management of Process ,Reporting | SRLA Common Data Environment (CDE) aims to enhance the existing Information Exchange System and set up new subsystems to support efficient and effective document control and collaboration between packages and contractors with ISO 19650 compliance. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-04-17 | 2023-02-27 | 2023-02-27 | 787129 | 369676 | 2023-02-28 |  | 2024-06-28 |  | 7541906 | 8004784 |  |  |  | Amber | Green | All required commercial and procurement activities are on track. Project is on track to deliver significant enhancements to the CDE as per planned schedule.
Q1 23-24 | Suburban Rail Loop Authority | SRLA | 3604 | Enterprise Data and Analytics Platform (eDAR) | Transport and Vehicles | Analyses and Statistics ,Data Management,Reporting ,Visualisation | Delivery of a Data, Analytics and Reporting Platform, integration of core transactional systems, creation of required data models and provision of reporting in a streamlined and efficient manner. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-02 | 2023-06-30 | 2023-07-31 | 2023-07-31 | 0 | 506211 | 2023-08-01 |  | 2024-10-31 |  | 4008009 | [5 empty] | Green | Project critical path activities tracking to schedule
Q1 23-24 | Monash Health | Monash H | 3605 | SAPPHire - SAP | Health | Financial Management,Human Resources | As part of the overall South Eastern Metro Health Service Partnership strategy, Monash Health are implementing SAP Payroll and a Human Resources Information System. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-03-01 | 2022-05-20 |  | 2022-06-02 | 50000 |  | 2022-09-01 |  | 2024-06-30 |  | 6600000 |  |  |  | Green | Green | Amber | Several integrations and data migration activities are currently running behind schedule. They are actively being managed, and as of now, they have not had any impact on the overall project cost or the scheduled go-live date.
Q1 23-24 | Office of the Chief Parliamentary Counsel | OCPC | 3608 | Workflow Management System | Law and Justice | Development and Integration | WMS project will provide workflow for managing legal projects to improve management of the projects as per the OCPC standards and timely and accurate reporting to internal and external users to ensure timely publishing on the legislation website. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2021-06-18 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2023-02-24 |  | 2024-07-13 |  | 2500000 |  |  |  | Green | Green | Green | Release 1 comprised eight sprints and focused primarily on the portal part of the WMS project to create an interface with the Parliament and instructors from external Vic Government departments.
Q1 23-24 | Department of Education | DE | 3610 | VISIT 3-0 | Education | Customer Relationship Management,Financial Management,Management of Process ,Reporting | VISIT 3.0 project will optimise the user experience improve ISP processing and administrative functions strengthen compliance and risk related functions; and enhance application and data security of VISIT. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2023-01-31 |  | 2023-01-31 | 263000 |  | 2023-02-01 |  | 2023-12-29 |  | 2692544 |  |  |  | Green | Green | Green | Release 3 of the VISIT 3.0 project was successfully implemented on 27 September 2023 which included a number of significant features, with the remaining scope to be delivered in December.
Q1 23-24 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | Upgrade the existing platform(s) due to impending end of support timeline with a contemporary integrated solution. | Initiated |  |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 |  | 0 | [12 empty] | Tender response reviews conducted and Agreement executed Sept 28th
Q1 23-24 | CenITex | CenITex | 3613 | Metro and regional Site refresh | Government and Economy | Assets/Materials Management | Consolidate and replace end of life networking hardware located at customer office locations including routers switches and wireless access points to maintain performance and availability of network service. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2022-12-16 | 2022-12-23 |  | 2022-12-23 | 0 |  | 2023-01-20 |  | 2023-06-30 | 2024-06-30 | 6598602 |  |  |  | Green | Green | Green | Project is tracking to plan.
Q1 23-24 | Melbourne Water | MELB Water | 3614 | Physical Servers Upgrade | Environment and Water | Assets/Materials Management | This project will upgrade infrastructure, including end of support blades, and upcoming end of support network connection equipment. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-01-03 | 2023-04-04 |  | 2023-04-04 | 0 |  | 2023-04-05 |  | 2024-01-23 |  | 1089616 | 1223060 |  |  |  | Green | Green | New virtual machine hosts patched to the latest version and added to two existing server clusters. Storage setup and network tested and host monitoring in place. Failover testing carried out and a test virtual machine created and tested across all new hosts, with non-production virtual machines migrated to the new hosts.
Q1 23-24 | Department of Health | DH | 3615 | OurService Extensions | Health | Forms Management,Tracking and Workflow | Deliver multiple enhancements to ServiceNow platform, including migration of additional new services and integration with other major corporate systems, that further improves the consistency and customer experience of service. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2022-10-03 | 2023-05-26 |  | 2023-05-26 | 302604 |  | 2023-05-26 |  | 2024-06-30 |  | 2365565 |  |  |  |  | Green | Green | Project is progressing to cost and schedule.
Q1 23-24 | Westernport Region Water Corporation | WPR Water | 3617 | Civica Authority v7.1 Upgrade | Environment and Water | Customer Relationship Management | As part of Year Two of the Technology Roadmap, Westernport Water is upgrading our existing finance and utility billing platform to ensure that it continues to meet stakeholder expectations. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2023-07-30 | Agile | 2021-07-01 | 2022-02-15 |  | 2022-02-15 | 216187 |  | 2022-11-21 |  | 2023-07-30 |  | 983813 |  |  |  | Green | Green | Green | Project completed.
Q1 23-24 | Department of Government Services | DGS | 3619 | Digital Records & Information Management Shared Services (DRIMSS) | Government and Economy | Content Management,Records Management ,Systems Management,Document Management | The project will implement an improved records and information management system to automate the records and information management process and comply with public records management requirements for the Department | Delivery | Compliance (Non Financial), Cost Reduction (Financial) |  | Agile | 2020-11-15 | 2021-06-25 |  | 2022-09-15 | 0 |  | 2022-12-05 |  | 2024-05-10 |  | 2099521 |  |  |  | Green | Green | Green | Project is progressing. Approvals on physical records migration strategy achieved. Continue planning and solution prototyping activities. Resource constraints risks. Consideration to expand scope of project under discussion for the inclusion of DTF and DGS.
Q1 23-24 | Department of Health | DH | 3621 | Wifi Audit and Ways of Working Remediation | Health | Systems Management | The project will deliver uplifted WiFi capability in all Department of Families, Fairness and Housing, and Department of Health offices, providing more effective internet connectivity throughout all location environments. | Delivery | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-07-01 | 2022-12-22 |  | 2022-12-22 | 0 |  | 2023-02-15 |  | 2024-06-30 |  | 2835288 | 2778965 |  |  | Green | Green | Green | Project is progressing to cost and schedule.
Q1 23-24 | State Revenue Office | SRO | 3624 | Smartforms Replatforming | Government and Economy | Development and Integration | Migrate 50+ digital customer forms to a new platform so that the SRO can accurately calculate taxes, levies and duties and issue the right exemptions and concessions. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Agile | 2022-08-01 | 2023-01-02 |  | 2023-01-02 | 100000 |  | 2023-01-02 |  | 2024-06-30 |  | 2100000 |  |  |  | Green | Green | Amber | The project is still tracking well to deliver a new platformed solution by 30 June 2024 however displays as amber due to uncertainty around a number of key resources being available.
Q1 23-24 | Yarra Valley Water | YV Water | 3626 | 3G to 4G/5G Telecommunications Infrastructure Upgrades | Environment and Water | Communication | Upgrade of obsolete 3G telecommunications infrastructure to 4G/5G | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-07 | 2021-07-16 |  | 2021-07-16 | 71049 |  | 2021-07-16 |  | 2023-10-31 | 2023-12-31 | 2552948 |  |  |  | Green | Green | Green | Progressing well overall. Project near completion, slight delay but not significant
Q1 23-24 | Department of Health | DH | 3627 | Hearing Management System (HeMS) for Mental Health Tribunal | Health | Customer Relationship Management | Deliver a new Hearing Management System for the Mental Health Tribunal body that can meet its current and emerging legislative requirements for case and hearing management. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2023-08-31 | Agile | 2022-10-03 | 2023-03-01 |  | 2023-03-01 | 0 |  | 2023-03-13 |  | 2023-08-31 |  | 1575236 |  |  |  | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q1 23-24 | CenITex | CenITex | 3631 | Next Generation SDWAN | Government and Economy | Organisational Management | Cenitex is developing a Next Generation SD-WAN product to deliver secure, robust, and scalable network connectivity. This project will build baseline infrastructure dir the Cenitex fully managed SD-WAN product and conduct pilot testing to mitigate a | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2021-12-13 | 2022-04-26 |  | 2022-04-26 | 49000 |  | 2022-04-28 |  | 2023-09-30 | 2023-10-31 | 998073 |  |  |  |  | Green | Green | Project is tracking to plan.
Q1 23-24 | Hume Rural Health Alliance | HRHA | 3632 | Emergency Department Information System (EDIS) Upgrade | Health | Records Management ,Tracking and Workflow | Upgrade of the Albury Wodonga Health emergency department patient management systems which are end of life. | Delivery | Compliance (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-01 | 2023-05-15 |  | 2023-05-16 | 123629 |  | 2023-05-16 |  | 2024-12-01 |  | 1501292 |  |  |  |  | Green | Green | Project on schedule for Phase 1 Go Live in the current Albury Campus Emergency Department on 29 November 2023.
Q1 23-24 | Hume Rural Health Alliance | HRHA | 3633 | Clinical Information System Upgrade | Health | Records Management | Delivery of an upgraded, supported version of the Clinical Information System at Northeast Health Wangaratta (NHW) to minimise risk of legacy IT infrastructure and reinstate support for this critical system. | Delivery | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-06-22 |  | 2023-06-23 | 80000 |  | 2023-06-26 |  | 2024-08-05 | 2024-11-01 | 2720000 | [5 empty] | Green | Development is progressing well. Overall the Project is tracking to schedule and to budget. Risks are being monitored and mitigation plans are in place.
Q1 23-24 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3635 | Website Replatform | Education | Communication | Holmesglen's current website is hosted on-premise and some software will be deprecated by 31 December 2023. This poses an unacceptable risk to Holmesglen. This project is about migration and redesign of the current website to a new cloud platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | hybrid - waterfall/agile | 2023-01-09 | 2023-02-06 |  | 2023-02-15 | 0 |  | 2023-04-03 |  | 2023-11-24 |  | 1511813 |  |  |  |  | Green | Green | Project is on time; within budget and within scope
Q1 23-24 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 |  | 10148335 | 10592143 |  |  |  | Green | Green | Enable Program is well established with a full project team and the People Journey Project and Rostering Projects are running to plan.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3641 | Online Claim Initiative | Government and Economy | Customer Relationship Management | • To expand the use of the electronic claim form making it available to all employers, injured workers and Agents. • Delivery of a plan to expand use of the digital form to all employers, for use by Injured workers, Employers and Agents. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2022-11-30 |  | 2022-12-01 | 0 |  | 2022-12-07 |  | 2023-12-22 |  | 3836646 |  |  |  |  | Green | Green | On Track
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Government and Economy | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 |  | 4316783 |  |  |  |  | Green | Amber | Project has been rebaselined allowing for a two step procurement phase to mitigate possible risks around Vendor Selection. A Project Change Request has been raised and on approval the project will return to green.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3643 | AWS Integration Platform Replacement | Government and Economy | Systems Management | The Integration and Orchestration platform (IOP) enables interaction from the CRM Inspections and Licensing Applications with internal and external systems. To migrate and services on the current IOP from private cloud to an Open-source platform. | Postponed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2023-09-29 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-05-02 | 2022-06-30 |  | 2022-07-07 | 0 |  | 2022-08-01 |  | 2023-11-03 | 2023-08-31 | 1100124 |  |  |  |  | Amber | Red | The project has stood up the Integration Platform and implemented the security monitoring. Due to a Firewall issue preventing further progress the project has been put on hold for ~6 months. During this period work will be undertaken separately to resolve the firewall issue. In order to reduce run costs while the project is on hold the platforms that have been stood up in the Cloud have been archived and will be reinstated upon project resumption.
Q1 23-24 | Monash Health | Monash H | 3644 | Security Card Technology Upgrade | Health | Security Management | Replacement of access control card readers and associated hardware across all sites to ensure access control security remains at an appropriate level and can integrate with current and future system requirements. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2022-04-15 | 2023-02-23 |  | 2023-02-23 | 0 |  | 2023-05-03 |  | 2024-05-31 |  | 2263923 | 2332000 |  |  |  | Amber | Amber | The project scope and schedule have been successfully resolved. However, there is still a cost risk associated with a change in delivery requirements that may result in additional costs.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides servers & network infrastructure integration of clinical equipment and provision of mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 |  | 5158000 |  |  |  |  | Green | Green | Project is on track
Q1 23-24 | Monash Health | Monash H | 3646 | EOL Switch Replacement (Tranche One) | Health | Systems Management | Network edge switch replacement project across Monash Medical Centre, Moorabbin Hosptial, Dandenong Hospital and the Kingston Centre. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2021-11-01 | 2022-01-17 |  | 2022-05-16 | 0 |  | 2023-01-02 |  | 2024-04-01 |  | 4200000 |  |  |  |  | Green | Green | The project is currently on track.
Q1 23-24 | Monash Health | Monash H | 3647 | EOL Switch Replacement (Tranche Two) | Health | Systems Management | Network edge switch replacement project for Monash Childrens Hospital and Monash Health Translation Precinct. Replacement of 226 end of life network switches. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2022-10-03 | 2022-11-21 |  | 2022-11-21 | 0 |  | 2023-02-01 |  | 2024-04-01 |  | 1653431 |  |  |  |  | Green | Green | Planning on track.
Q1 23-24 | Emergency Services Telecommunications Authority | ESTA | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 |  |  | 0 | [12 empty] | Project is in initiation phase. ESTA has established the official project governance framework. ESTA has engaged a strategic delivery partner, who will support ESTA in project delivery. Selection of the strategic delivery partner was done collaboratively with operational and technical experts.
Q1 23-24 | Department of Jobs, Skills, Industry and Regions | DJSIR | 3652 | Online Core Skills Assessment Tool (OCSAT) | Education | Analyses and Statistics ,Data Management,Development and Integration ,Forms Management,Knowledge Discovery ,Reporting | The project will provide an online standardised tool for the assessment of literacy, numeracy, and digital skills for people seeking to participate in government subsidised training at TAFEs and Learn Local Organisations. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2023-02-28 |  | 2023-02-28 | 609978 |  | 2023-03-01 |  | 2023-12-31 |  | 2537775 | 2705528 |  |  |  | Red | Amber | The project reported an Amber status due to slow uptake from pilot participants to enable validation of the tool. The project team is actively working to resolve this issue through an extension of the pilot and close engagement with participating providers.
Q1 23-24 | Department of Education | DE | 3653 | VRQA Regulatory Field Services CRM | Education | Customer Relationship Management | The development of a case management solution for Regulatory Field Service (RFS) team using Salesforce Customer Relationship Management (CRM) as a platform. This will allow RFS team to use Salesforce CRM as their case management platform. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2023-01-16 | 2023-02-28 |  | 2023-03-31 | 0 |  | 2023-04-03 |  | 2023-12-05 |  | 1164508 |  |  |  |  | Amber | Green | Current status of the project is Green. The project is on track for the delivery and the solution is scheduled to go live in the end of November 2023.
Q1 23-24 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Initiated |  |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-02-29 |  | 200000 | 300000 | [11 empty] | initial project staff recruitment is underway with project team members planned to be on in November. Project Office and equipment implemented. Individual agency business cases are in draft, planning for signoff in early 2024.
Q1 23-24 | Department of Education | DE | 3657 | Securing Connected Learners (SCL) Program | Education | Development and Integration ,Security Management ,Systems Management | A 5-year program creating enhanced security capabilities for schools & transitioning schools to platforms. In 2023 the program will jointly prioritise addressing child safety risks in primary schools & security & privacy risks in secondary schools. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid-Waterfall, Agile | 2022-10-18 | 2023-03-30 |  | 2023-03-30 | 661179 |  | 2023-04-03 |  | 2025-06-30 |  | 16638821 |  |  |  |  | Amber | Amber | The overall health remains ’Amber’ however trending towards ‘Green’ following the re-phasing of key delivery targets and positive progress made on several key program risk and issues.
Q1 23-24 | Department of Families, Fairness and Housing | DFFH | 3658 | Integrated supervised contact and access solution | Community Services | Customer Relationship Management | Integrate existing case management and support systems (Contact & Access Transport System) for supervised contact and access to eliminate duplicate processes and better support planning and decision making for children in out of home care. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2022-10-13 | 0 |  | 2023-02-01 |  | 2024-06-30 |  | 1217500 |  |  |  |  | Green | Green | Project is progressing to cost and schedule.
Q1 23-24 | Department of Education | DE | 3660 | QARD Case Management System (Assessment and Rating Module) | Education | Business Intelligence,Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Reporting | A Case Management System for Quality Assessment and Regulation Division (QARD) to manage assessment and rating process for Early Childhood Service and Provider entities . | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2021-01-04 | 2021-03-11 |  | 2021-05-11 | 0 |  | 2021-09-08 |  | 2023-10-31 |  | 3035022 |  |  |  |  | Amber | Amber | The overall status of the project is Amber due to slippage in the project schedule. The revised project delivery date is 31 October 2023.
Q1 23-24 | Department of Families, Fairness and Housing | DFFH | 3661 | Decoupling of Housing Integrated Information Program (HiiP) and BTM Databases - Stage 2 | Community Services | Systems Management | This project is stage two of the work to decouple the connections between the SQL server databases to enable both to be upgraded independently to supported versions providing improved security and performance. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-04-20 | 2023-06-23 |  | 2023-06-23 | 0 |  | 2023-06-23 |  | 2024-06-30 |  | 1305000 |  |  |  |  | Green | Green | Project is progressing to cost and schedule.
Q1 23-24 | Department of Health | DH | 3662 | Orygen ICT Transition Project | Health | Development and Integration ,Financial Management,Human Capital / Workforce Management ,Human Resources,Organisational Management ,Records Management ,Supply Chain Management ,Systems Management | Implementation of electronic medical record systems, financial, human resource and clinical rostering platforms to enable transition to a designated mental health service under the new Mental Health and Wellbeing Act 2022. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2022-10-01 | 2023-05-04 |  | 2023-05-04 | 0 |  | 2023-08-01 |  | 2024-04-30 |  | 6437760 | [5 empty] | Green | Delivery activities are on track.
Q1 23-24 | Northern Health | NH | 3665 | Northern Imaging Victoria | Health | Reporting | Moving radiology/imaging services in-house to Northern Health | Delivery | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-02-01 | 2022-04-28 |  | 2022-04-28 | 600000 |  | 2022-12-20 |  | 2023-11-30 |  | 3955883 |  |  |  |  | Green | Green | This project is currently on track
Q1 23-24 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2024-11-15 | 3450000 |  |  |  |  | Amber | Amber | The new PM has joined the Northern Health team and is focusing efforts on the resourcing issue to bring it back to green.
Q1 23-24 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 |  | 225000 | 232500 | [11 empty] | Significant process made during FY2324 Q1 - The main highlights during this period were completing our RFI and RFQ tender processes.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3668 | EMD (Emergency Management Day) PHASE 2 | Law and Justice | Development and Integration | This project supports management of EMD data for remanded prisoners to avoid unlawful detention or release and reduce legal risk. The objective is to provide a system for SCWA to manage sentences prisoner discharges and documentation for CV. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial) |  | Agile | 2022-05-02 | 2023-03-31 |  | 2023-06-16 | 0 |  | 2023-03-31 | 2023-06-17 | 2024-06-30 |  | 1466100 | [5 empty] | Amber | Funding was secured in June 2023 to enable this Project to commence. The project is in the process of ramping up resources to commence project delivery. Development commenced in early August 2023. Note: Initiation work was completed as a BAU activity by BAU resources no defined budget was allocated for this component of the activity.
Q1 23-24 | Victorian Managed Insurance Authority | VMIA | 3671 | Corporate Operations Systems Implementation | Government and Economy | Financial Management,Human Resources | Implementation of: •An integrated platform for Finance and Human Capital Management •Enhancing user experience with seamless integration •Transforming our existing processes to align with the new platform | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2023-02-07 | 2023-05-05 |  | 2023-05-12 | 0 |  | 2023-06-05 |  | 2024-03-15 |  | 4602226 |  |  |  |  | Green | Amber | The project status is AMBER noting budget, scope and benefits are on track and schedule is tracking an Amber risk due to integration design and change requests to be approved to recover.
Q1 23-24 | Department of Government Services | DGS | 3682 | Get a birth certificate proof of concept | Community Services | Customer Relationship Management | Develop a proof-of-concept pilot for delivering front-end Births, Deaths and Marriages services as a function of Service Victoria. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid | 2022-05-03 | 2022-05-03 |  | 2022-05-03 | 0 |  | 2023-07-01 |  | 2024-12-31 |  | 2400000 | [5 empty] | Green | Project tracking well to deliver MVP (phase #1) of the POC form by March 2024
Q1 23-24 | Melbourne Health | Melb H | 3683 | CMI Data Access Project | Health | Data Management,Records Management ,Reporting | The CMI Data Access Project will deliver the disaggregation of data contained in the Mental Health Client Management Interface (CMI). There will be four data repositories created to enable mental health program reporting for NH, WH, RMH and Orygen. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-11-17 | 2023-09-04 | 2023-09-04 | 147800 | 80000 | 2023-09-04 |  | 2024-06-30 | 2024-09-30 | 1122200 | 1190000 |  |  |  |  | Green | Progressing to schedule.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3685 | FY 2023-24 DEECA Cyber Security Program | Government and Economy | Security Management | FY 20233-24 Cyber Security program will deliver a set of controls processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Initiated |  |  | Waterfall | 2023-07-03 | 2023-11-30 |  |  | 388000 | [12 empty] | The FY23-24 Cyber Security Program is in the Plan phase. The Program is tracking to schedule as well as planed initiation cost.
Q1 23-24 | Department of Energy, Environment and Climate Action | DEECA | 3686 | FY 2023-24 Common Technology Platform program | Government and Economy | Systems Management | FY 2023-24 Common Technology Platform program will continue the build of standardised technology services that will be accessible for use across all DEECA Groups in order to derive better value from our enterprise technology platforms. | Initiated |  |  | Waterfall | 2023-07-03 | 2023-11-30 |  |  | 234000 | [12 empty] | The FY23-24 Common Technology Platforms Program is in the Plan phase. The Program is tracking to schedule as well as planed initiation cost.
Q1 23-24 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Initiated |  |  | PMBoK | 2022-01-03 | 2025-12-01 |  |  | 0 | [12 empty] | On track
Q1 23-24 | Department of Education | DE | 3689 | Master of Inclusive Education and Graduate Certificate Initiative Reporting and Tracking Tool | Education | Analyses and Statistics ,Management of Process ,Records Management ,Tracking and Workflow | ​Develop and deploy a technology solution that will enable the Inclusive Education Scholarships Unit (IESU) to manage the administration, data collection, reporting functions and accurate acquittal of funding, for the initiative. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2023-02-27 | 2023-04-24 |  | 2023-04-24 | 0 | 0 | 2023-07-03 |  | 2024-02-09 |  | 1097640 | 1156086 |  |  |  |  | Green | The project is currently reporting Green and is on track to deliver the MIE/GCE solution by 9 February 2024. Development of the Master of Inclusive Education and Graduate Certificate Education Application for Inclusive Education Scholarships Unit users has been completed in the last quarter.
Q1 23-24 | Transport Accident Commission | TAC | 3691 | Continuous Delivery 24 | Transport and Vehicles | Systems Management | Continuous Delivery project is aimed at maturing the TAC Technology delivery model with planned releases to support the system changes and initiatives required in the areas of Business Improvement Scheme Performance and System Stabilisation. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2023-05-18 | 2023-07-01 | 2023-05-18 | 2023-05-18 | 0 |  | 2023-07-01 |  | 2024-06-30 |  | 2763390 | [5 empty] | Green | On Track.
Q1 23-24 | Transport Accident Commission | TAC | 3693 | Strategic Analytics Program | Transport and Vehicles | Business Intelligence | The TAC will be provided with a trusted accessible and well governed platform that contains the single source of truth for delivering TAC's data analysis needs. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2024-06-30 | 2023-07-01 | 2024-06-30 |  | 4300000 | [5 empty] | Green | Program is tracking to budget and benefits as planned. Risks are being managed in the register and regularly reviewed with nothing significant to highlight at present. However with the addition of the transition work to the scope following the review is a ‘watch item’ as the delivery of use cases into production will be restricted until the transition is complete. The program is monitoring this risk and will know more as the plan to complete the transition firms up with the onboarding of supplier and ITSS resources.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | Kyabram District Health Service ICT transition from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  |  | 100000 | [12 empty] | Project Manager recruitment in progress
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | Maryborough District Health Service ICT transition from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 |  |  | 0 | [12 empty] | Project Working Group established. Key project governance documents, including project management plan framework, commenced.
Q1 23-24 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  |  | 65000 | [12 empty] | A business case for the regional implementation of a HRIS is in development, and will be presented at the December 2023 Board meeting for a decision
Q1 23-24 | Energy Safe Victoria | ESV | 3697 | ESV Transformation - Digital Component - Tranche 2 | Environment and Water | Business Intelligence,Content Management,Customer Relationship Management,Data Management,Development and Integration ,Financial Management,Knowledge Management ,Management of Process ,Reporting ,Routing and Scheduling,Security Management ,Tracking and Workflow,Visualisation | Digital delivery enabling ESV to become a safety first data driven customer centric regulator. Tranche 2 includes relocating digital infrastructure and assets to new office, developing customer platform and enhancing Data Hub and Finance Platform. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-11-30 |  | 2022-12-07 | 0 |  | 2023-08-01 |  | 2024-06-30 |  | 5129000 | [5 empty] | Green | Transformation program is tracking green against the project plan and schedules
Q1 23-24 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 |  | 4316783 | [5 empty] | Amber | Project has been rebaselined allowing for a two step procurement phase to migitate possible risks around Vendor Selection. A Project Change Request has been raised and on approval the project will return to green.
Q1 23-24 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 |  |  | 900000 | [12 empty] | Project initiated. Business Analysis activities commenced and in progress
Q1 23-24 | Emergency Services Telecommunications Authority | ESTA | 3700 | Emergency Sector Integration Platform | Emergencies and Safety | Systems Management | Provide a new single, vendor agnostic integration platform to interface into multiple ESTA data sources that provides reliability and meet current and future anticipated requirements. | Initiated |  |  | Project Management Excellence | 2021-08-09 | 2021-12-28 | 2023-10-31 |  | 570406 | 1300000 | [11 empty] | The Emergency Sector Integration Platform is selecting a preferred vendor, and is expected finalise a vendor in October 2023. Emergency Service Organisations continue to be briefed on the progress of the project.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3702 | MyWorkSafe Portal CRM | Government and Economy | Customer Relationship Management | The myWorkSafe Portal provides access to WorkSafe products for external users so that they can ‘self-service’. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-01 |  | 2023-06-01 | 0 |  | 2023-07-03 |  | 2024-06-30 |  | 4489897 | [5 empty] | Green | On-Track
Q1 23-24 | Royal Women’s Hospital | RWH | 3703 | Rostering, Time and Attendance Project | Health | Human Capital / Workforce Management | The Project will upgrade the current RosterOn system (vendor RLDatix, formerly Allocate Software) to the new and enhanced RLDatix rostering system – Optima. This project is part of an overarching People Systems Improvement Program with RMH and WH. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-03 | 2023-09-01 |  | 2023-09-01 | 31980 |  | 2023-09-03 |  | 2024-12-31 |  | 1140573 | [5 empty] | Green | Project progressing to schedule.
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3704 | Licensing CRM | Government and Economy | Customer Relationship Management | Transitioning the Licensing value stream from legacy applications to our CRM platform centralises the data relating to license holders (and their journey with WSV) | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-01 |  | 2023-06-01 | 0 |  | 2023-07-03 |  | 2024-06-30 |  | 4473503 | [5 empty] | Green | On-Track
Q1 23-24 | WorkSafe Victoria | WorkSafe | 3705 | Inspections CRM | Government and Economy | Customer Relationship Management | The Inspections & Investigations Product project continues to enhance notifications and inspectorate functionality including the asbestos removal, incident, construction excavation, fireworks discharge and OHS essentials notification forms. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-01 |  | 2023-06-01 | 0 |  | 2023-07-03 |  | 2024-06-30 |  | 4474030 | [5 empty] | Green | On-Track
Q1 23-24 | Melbourne Water | MELB Water | 3708 | Document Management System Upgrade 2023 | Environment and Water | Records Management | Upgrade on-prem document management system and refresh 'as-is' integrations with security improvements so that they work effectively with the new version. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-07-01 | 2023-07-18 |  | 2023-07-18 | 0 |  | 2023-07-18 |  | 2024-03-12 |  | 1296183 | [5 empty] | Green | The project is progressing with Technical Design underway with productive collaboration between all vendors. Infrastructure work has also commenced with the decommissioning of the existing DEV infrastructure and build of the new DEV infrastructure.
Q1 23-24 | Melbourne Health | Melb H | 3709 | RMH Human Resource Information System (HRIS) Project | Health | Human Capital / Workforce Management ,Human Resources | To deliver a HRIS that will replace HR onboard and end of life eRecruit and address the following operational issues: -Lack of integration -Poor employee manager and candidate experience -Manual and duplicative processes -Strategic planning | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-08-18 |  | 2023-08-21 | 30000 |  | 2023-08-21 |  | 2024-09-30 |  | 4277958 | [5 empty] | Green | Progressing to schedule
Q1 23-24 | Yarra Valley Water | YV Water | 3711 | Primequest/Exadata Replacement | Environment and Water | Data Management | Remediate risk of end of life infrastructure by migrating it to new infrastructure (Primequest/Exadata), or where suitable, migrate it to cloud | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-11-04 | 2023-06-30 |  | 2023-06-30 | 366930 |  | 2023-07-01 |  | 2024-06-30 |  | 5893910 | [5 empty] | Green | Received Oracle and majority of Fujitsu kit that we purchased. To date, we have successfully migrated 65 services to our cloud environment. To date, we have successfully migrated 40 databases to our new Oracle environment.
Q1 23-24 | Royal Women’s Hospital | RWH | 3714 | RWH Human Resource Information System (HRIS) Project | Health | Human Capital / Workforce Management ,Human Resources | Project to replace the existing eRecruit (eQuifax) system that becomes end of life in June 2024. New system, SAP SuccessFactors will deliver recruitment, onboarding, employee central and aspects of performance / goals functionality. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-10 | 2023-09-04 | 2023-11-03 |  | 30000 | 50000 | [11 empty] | Procurement process near completion.
Q1 23-24 | Royal Women’s Hospital | RWH | 3719 | Business Intelligence & Analytics Replacement System (BIARS) | Health | Business Intelligence | Business Intelligence (BI) and analytics upgrade for infrastructure and software by partnering with external provider. Decommission current BI system (RISE) and provide better system capability for operational reporting requirements. | Initiated |  |  | PRINCE2 | 2023-07-03 | 2023-11-03 |  |  | 100000 | [12 empty] | Market tendering process for selection of external vendor is near completion.
Q1 23-24 | Austin Health | AH | 3721 | Austin Health Financial Management Information System | Health | Financial Management | The replacement of Austin Health's legacy Financial Management Information System | Initiated |  |  | PRINCE2 | 2023-04-03 | 2024-02-28 |  |  | 0 | [12 empty] | Commenced procurement process for Systems Integrator Procurement process on track
Q1 23-24 | Peter MacCallum Cancer Centre | Peter MAC | 3722 | Mosaiq Migration to Cloud and Upgrade | Health | Systems Management | The project is being implemented in 2 phases: Phase I: Migration Mosaiq application from On premises infrastructure to Elekta Azure Cloud Infrastructure. Phase II: Post Migration application will be upgraded to the latest version of Mosaiq. | Initiated |  |  | PRINCE2 | 2022-03-01 | 2023-12-22 |  |  | 20475 | [12 empty] | The procurement phase of the project has commenced. Implementation Planning Study in progress.
Q1 23-24 | Western Health | WH | 3723 | Bachus Marsh Melton (BMM) EMR Transition - Devices | Health | Systems Management | Provision and integration of Electronic Medical Record (EMR) IT Devices at BMM s at Western Health (WH) | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-20 | 2023-08-08 |  | 2023-08-14 | 0 |  | 2023-08-28 |  | 2024-01-16 |  | 1549000 | [5 empty] | Green | Project has just commenced.
Q1 23-24 | Department of Health | DH | 3731 | Managed Service Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Applications and Services (AS) business unit within the Digital Health branch of the Commissioning and System Improvement division. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 |  | 1412500 | [5 empty] | Amber | Project is tracking to budget and scope, however has some delays to the schedule due to resource availability. The team is working to resolve this and is reviewing the schedule.
Q1 23-24 | Essential Services Commission | ESC | 3732 | Victorian Energy Upgrades (VEU) IT System Upgrade | Environment and Water | Analyses and Statistics ,Customer Relationship Management,Development and Integration | The project will deliver a replacement to the existing VEU registry system to improve information access, process management and consumer engagement, meeting new legislative and regulatory requirements. | Initiated |  |  | Agile | 2023-08-01 | 2024-08-30 |  |  | 500000 | [12 empty] | ESC is currently in the tender period. As we will be conducting a selective, the project team organised briefing meetings with selected solution providers and gauged their interest in participating in the VEU Tender. ESC will go to market in mid-November and the products will be evaluated in January/February 2024.
Q1 23-24 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 |  |  | 0 | [12 empty] | Initiation activities are on schedule
Q1 23-24 | Melbourne Water | MELB Water | 3734 | Finance System Cloud Transition | Environment and Water | Financial Management | Due to a vendor decision to move all on-premise customers to SaaS by 2024 this project is required to upgrade Melbourne Waters finance system and move to the cloud. | Initiated |  |  | PRINCE2 | 2023-07-03 | 2024-01-24 |  |  | 0 | [12 empty] | Project team is working through Discovery phase assessing the current state of the on-prem environment including business processes, integrations and configurations. Technical assessment is being conducted by an external vendor with Stakeholder Engagement sessions scheduled during week of Oct 9th.
Q1 23-24 | Department of Transport and Planning | DTP | 3743 | OneView Permits and Permits Portal Phase 2 | Transport and Vehicles | Business Intelligence,Collaboration ,Communication,Tracking and Workflow | Key objectives of this project is to enhance the Permits Portal to support the modernisation of business processes and reduce processing times and provide disruption information to motorists. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-09-18 | 2023-08-01 | 2023-09-18 | 0 |  | 2024-06-30 | 2023-09-18 | 2024-06-30 |  | 4500000 | [5 empty] | Green | Overall project status is green. Project is tracking to its schedule.
Q1 23-24 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Business Transformation Program (BTP) - Tranche 1 | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 |  |  | 899582 | [12 empty] | Initiation activities are on track
Q1 23-24 | Greater Western Water Corporation | GW Water | 3750 | Satellite 1 - Asset | Environment and Water | Organisational Management ,Systems Management | Satellite #1 will identify and uplift the required Asset satellite application changes to support the successful Billing and Collections program Go-Live. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-21 | 2023-09-07 |  | 2023-09-07 | 164588 |  | 2023-09-07 |  | 2024-06-30 |  | 3227489 | [5 empty] | Green | Project progressing with planned deliverables. Land Development spatial systems and asset integration on track for Q3 completion
Q1 23-24 | Greater Western Water Corporation | GW Water | 3751 | Satellite 2 - Customer | Environment and Water | Organisational Management ,Systems Management | Satellite #2 will identify and uplift the required Customer satellite application changes to support the Billing and Collections program Go-Live. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-21 | 2023-04-06 |  | 2023-04-06 | 499457 |  | 2024-04-06 | 2023-04-06 | 2024-06-30 |  | 4352349 | [5 empty] | Green | Project progressing with planned deliverables.IVR website and outage notificatons design and system build completed. System integration testing support and operational readiness on track for Q3
Q1 23-24 | Greater Western Water Corporation | GW Water | 3755 | Satellite 3 - Digital | Environment and Water | Management of Process ,Organisational Management ,Systems Management | identify & provide the GWW digital systems uplift required support the B&C billing system Including developing new capability for customer Change of Ownership on our platform. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-21 | 2023-04-21 |  | 2023-04-21 | 146900 |  | 2023-04-21 |  | 2024-06-30 |  | 1528896 | [5 empty] | Green | Project progressing with planned deliverables. Design and system build completed. System integration testing & support and operational readiness on track for Q3
Q1 23-24 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 |  | 14429000 | [5 empty] | Green | Project is progressing to cost and schedule.
Q1 23-24 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 |  | 7490000 | [5 empty] | Amber | Overall project status is amber due to strategic project scope discussion. Project team is working with the steering committee to resolve the issues.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3759 | Enterprise Data & Insights Environment - EDIE | Law and Justice | Business Intelligence | The project will ingest priority distributed data sets to a centralised Enterprise and Data and Insights Environment within Amazon Web Services (AWS), enabling secure user access, data analytics and insights. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2022-10-26 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 0 |  | 2022-11-01 | 2022-11-02 | 2023-11-03 | 2024-01-10 | 2408777 | [5 empty] | Green | The project is tracking well against budget, scope and schedule
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3760 | GSP File Services Migration | Law and Justice | Business Intelligence | Migration of all DJCS files residing on the legacy DOJVIC network drive infrastructure to the GSP network or SharePoint. | Initiated |  |  | Project Management Excellence | 2022-11-20 | 2024-03-31 |  |  | 485000 | [12 empty] | The project is seeking an implementation partner. Budget and schedule are to be re-baselined following engagement of an implementation partner and replanning of delivery stage.
Q1 23-24 | Department of Justice and Community Safety | DJCS | 3761 | Marine Search and Rescue Radio Replacement | Emergencies and Safety | Communication | The project will connect Marine Search and Rescue units to the Victorian Radio Network and provide 24 base radios, 74 mobile radios and 90 portable radios. | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2023-01-01 | 2023-01-10 |  | 2023-01-10 | 0 |  | 2023-03-01 |  | 2024-12-01 | 2024-05-01 | 1377000 | [5 empty] | Amber | The project is experiencing delays due to cost estimation issues. The overall number of devices will be reduced to meet increasing asset costs and remain within the budget constraints.
Q1 23-24 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Initiated |  |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  |  | 0 | [12 empty] | Phase 2 commencing next quarter. Business case established
Q1 23-24 | State Revenue Office | SRO | 3763 | Land tax Reform | Government and Economy | Development and Integration | To implement the 2023 Victorian Budget Land Tax changes, including the operational enhancements required to efficiently cater for a broader customer base. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-15 | 2023-06-29 |  | 2023-06-29 | 0 |  | 2023-07-03 |  | 2024-12-31 |  | 2826000 | [5 empty] | Green | Overall the project is tracking to achieve its key milestones as planned.
Q1 23-24 | State Revenue Office | SRO | 3765 | Payroll tax Reform | Government and Economy | Development and Integration | This project implements the system changes necessary to allow for administration of Payroll tax changes introduced as part of the 2023 Victorian Budget (temporary Covid Surcharge, remove exemption for private schools, sliding scale). | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-23 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-03 |  | 2025-06-30 |  | 4772200 | [5 empty] | Green | The project is tracking well to meet benefits, schedule and budget.
Q1 23-24 | State Revenue Office | SRO | 3766 | Revenue Management Systems Modernisation -Proof of Concepts | Government and Economy | Development and Integration | The State Revenue Office is modernising its Revenue Management Systems. This stage of the program is designed to test business processes on the Oracle technology platform to assess if it enables a better customer and employee experience. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-05 | 2023-06-30 |  | 2023-06-30 | 163154 |  | 2023-07-03 |  | 2024-01-31 |  | 6751800 | [5 empty] | Green | Overall the project is on track to achieve its outcomes
Q1 23-24 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  |  | 400000 | [12 empty] | A SMS Functional and Business requirements collection framework and a SMS Project Management Plan both completed by 30/9/23. The development of SMS Functional and Business requirements and performance obligations are both underway and will be finalised during Q2 2023/2024
Q1 23-24 | Department of Transport and Planning | DTP | 3768 | MOG 2023- Finance and Procurement System Stream | Transport and Vehicles | Collaboration ,Customer Relationship Management,Financial Management,Investment Management,Management of Process ,Organisational Management ,Tracking and Workflow | Purpose of this project is to make necessary changes to DTPs Finance and procurement system to facilitate the Machinery of Government changes announced in December 2022 | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  |  | 0 | [12 empty] | Project initiation activities are ongoing.
Q1 23-24 | Department of Transport and Planning | DTP | 3769 | MOG 2023- Collaboration Tools | Transport and Vehicles | Collaboration ,Content Management,Data Management,Knowledge Discovery ,Knowledge Management ,Records Management | Purpose of this project is to make necessary changes in DTP Records Management System to facilitate Machinery of Government changes announced in 2022. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  |  | 0 | [12 empty] | Project initiation activities are ongoing
Q1 23-24 | Department of Transport and Planning | DTP | 3770 | MOG 2023- Core IT System Stream | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Purpose of this project is to make necessary changes in DTP's Core IT System to facilitate Machinery of Government changes announced in 2022 | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-11-30 |  |  | 0 | [12 empty] | Project initiation activities are ongoing.
Q1 23-24 | Department of Transport and Planning | DTP | 3772 | Customer Facing Transport Website | Transport and Vehicles | Communication,Content Management,Data Management,Document Management ,Search | Objective of this project is to develop a brand new platform to transfer all non-Registration and Licencing content and experiences to into a new customer facing transport website. | Delivery | Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-01 | 2023-09-28 |  | 2023-09-28 | 0 |  | 2023-09-28 |  | 2024-08-30 |  | 5133448 | [5 empty] | Amber | Project overall status is amber due to schedule issue. Project team is working with the stakeholders and project control board to mitigate the issues.
Q1 23-24 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2023-11-30 |  |  | 0 | [12 empty] | Project initiation activities are on-going.
Q1 23-24 | Environment Protection Authority | EPA | 3775 | MAJ126 - Tasking and Coordination Digital Solution | Environment and Water | Human Capital / Workforce Management | Deliver a digital rostering solution with an enhanced Incident Command System (ICS) that consolidates all Incident Command into a single system and integrates directly into EPA HR system to enable payment of EBA allowances. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - Agile and Waterfall | 2023-06-02 | 2023-06-20 |  | 2023-06-20 | 0 |  | 2023-06-20 |  | 2024-05-17 |  | 1535155 | [5 empty] | Red | A number of scope changes have necessitated budget and timeline re-planning
Q1 23-24 | Environment Protection Authority | EPA | 3776 | MAJ127 - Replacing Existing Document Solution | Environment and Water | Records Management | The project will deliver a robust and cost-effective document generation and distribution solution, with availability of operational support based on Australian business hours followed by a quick response and resolution time. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - Agile and Waterfall | 2023-05-23 | 2023-07-28 |  | 2023-07-31 | 0 |  | 2023-07-31 |  | 2024-05-31 |  | 1080000 | [5 empty] | Green | The project is on track however running under budget due to resourcing.
Q1 23-24 | Environment Protection Authority | EPA | 3777 | MAJ129 - Implement a zero-trust approach to security | Environment and Water | Security Management | Implement a zero-trust approach to security | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-03-10 | 2023-06-01 |  | 2023-06-01 | 0 |  | 2023-07-01 |  | 2024-06-28 |  | 1313100 | [5 empty] | Green | Roadmap workshops are on schedule and nearing completion. Once completed an exercise will be held to confirm prioritisation of activity.
Q1 23-24 | Environment Protection Authority | EPA | 3778 | MAJ131 - Migrate Airwatch to the Cloud | Environment and Water | Development and Integration | Migrating the aging on-premise system to cloud infrastructure, and supporting device connectivity | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-07-03 | 2023-09-08 |  | 2023-09-11 | 0 |  | 2023-09-11 |  | 2024-06-28 |  | 1055000 | [5 empty] | Green | The project is on schedule and within budget.
Q1 23-24 | Environment Protection Authority | EPA | 3781 | MAJ128 - Website and intranet refresh | Environment and Water | Collaboration ,Communication,Content Management | Improving EPA’s internal and external channels (website, intranet and reporting tools) to improve user experience and awareness | Initiated |  |  | Hybrid - Agile and Waterfall | 2023-05-11 | 2023-12-31 |  |  | 0 | [12 empty] | Procurement activities are underway.
Q1 23-24 | Department of Health | DH | 3783 | FoodTrader Oscar Solution | Business and Industry | Data Management | Deliver an online registration portal for Victorian food businesses for registration of temporary and mobile and fixed food and other businesses registration functionality to allow these businesses to continue to register and comply. | Delivery | Compliance (Non Financial) |  | Agile | 2023-01-03 | 2023-03-15 |  | 2023-03-15 | 108232 |  | 2023-03-16 |  | 2024-06-30 |  | 6703768 | [5 empty] | Green | Project progressing to cost and schedule. Internal funding source to be confirmed.