## ProjectData
CollectionPeriod | ProjectID | AgencyName | AgencyShortName | ProjectTitle | GovernmentDomain | Description | StartDate | PMMethod | PMOther | Stage | PreImpEndDate | PreImpCost | PlanndedImpEndDate | PlannedImpCost | RevisedImpEndDate | RevisedImpCost | ImpStatus | Previous Status 3mth | Previous Status 6mth | Previous Status 9mth | Previous Status 12mth | Comments | DataCurrencyDate
Q1-2016-17 | 8A05D8AC-5DF3-45DA-BFFA-FAFC3C4356B7 | South West Alliance of Rural Health | SWARH | Barwon Health Data Warehouse Refresh | Health | Barwon Health is undertaking a project to rebuild their current data warehouse to enable us to move from reporting off individual transactional systems to a federated repository of all data required for reporting. | 2013-08-01 | PRINCE2 |  | In progress - implementation | 2016-06-01 | 0 | 2016-06-30 | 1760000 | 2017-11-30 |  | Green | Amber | Amber | Amber | Amber | Project on track to meet revised implementation date of 30 November 2017. Project remains on budget. | 2016-10-18
Q1-2016-17 | 1A1D78FE-A909-464F-81B7-27ECED47AC97 | South West Alliance of Rural Health | SWARH | SWARH Accelerated adoption of a Regional E.H.R | Health | The 13 SWARH agencies that utilize the SWARH EHR do not have dedicated change management agents to facilitate functionality uptake. The project aims to improve functionality to directly capture information in the Patient Administration System, eMedication Management, Clinical, Emergency, Theatre, appointment scheduling and community workflows. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2015-09-20 | 0 | 2017-09-21 | 3045000 |  |  | Green | Green | Green | Green | Green | Project is progressing to schedule. | 2016-10-26
Q1-2016-17 | 6F51921B-0BE8-43F9-A56E-7AFB03E8F2D8 | Alfred Health | ALFRED | Upgrade Alfred Health PABX Telephony, switchboard, computer core network, cabling and wireless services | Health | Implement Alfred Health ICT Strategy including managing critical ICT infrastructure risks to carry out technology refresh and replace out-of-support systems (PABX Telephony, switchboard, computer core network, cabling and wireless) to support safe and high quality care to patients. | 2014-09-23 | PRINCE2 |  | In progress - implementation | 2014-10-10 | 0 | 2016-11-30 | 3700233 |  |  | Green | Green | Green | Green | Green | Project is ON TRACK. | 2016-10-18
Q1-2016-17 | BDF32C2A-6A20-4FB5-AD21-871F569D346B | Alfred Health | ALFRED | Alfred Emergency and Trauma Centre Redevelopment - ICT Component and Emergency Department Information System (EDIS) | Health | Expand and refurbish the Alfred Emergency & Trauma Centre facility staged to ensure operational continuity during the indicative 18 months of building works - ICT Component and EDIS. | 2015-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project is ON TRACK. | 2016-10-20
Q1-2016-17 | EB80B721-ED14-40F9-84D5-C160E1399621 | Alfred Health | ALFRED | Implement eTQC Phase One program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Development and Implementation of Phase One of the electronic-Timely Quality Care (eTQC) project that will significantly improve clinical real-time data capture, management and patient care service delivery, to progress towards a fully electronic medical record across Alfred Health. | 2016-04-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project is ON TRACK. | 2016-10-20
Q1-2016-17 | 43042989-DA36-498B-B806-059CC6769E4B | Alfred Health | ALFRED | Upgrade of Alfred Health analogue telephone with digital phones and wireless network to remove black spots | Health | Replacement of remaining Alfred Health analogue telephone handsets with digital phones, decommissioning of Nortel PABX system and remediate wireless network black spots | 2016-09-15 | PRINCE2 |  | Initiated | [11 empty] | Project is ON TRACK. | 2016-10-18
Q1-2016-17 | CD035DCD-9DDD-44F9-8587-392E51AA223E | Ambulance Victoria | AV | Improving 000 Triage | Health | To work with ESTA to develop a full Business Case for consideration by the government, in accordance with the Department of Treasury and Finance (DTF) guidelines that makes an evidenced based recommendation on a solution that best meets AV’s need to Improve Triage. | 2016-01-01 | Other – please specify | AV Project Management Framework (PRINCE2 based) | In progress - pre-implementation | [11 empty] | The Gateway Review 1 for the Preliminary Business Case took place in August as scheduled. Preparation on the full business case commenced | 2016-10-24
Q1-2016-17 | 5EE27FC9-5491-4667-9009-804C43CF940A | Ambulance Victoria | AV | VACIS 3 | Health | Upgrade electronic Patient Care Record software (VACIS 2 to VACIS 3), and deployment of mobile devices for mobile office. | 2016-02-08 | Other – please specify | AV Project Management Framework (PRINCE2 based) | In progress - pre-implementation | [11 empty] | Pilot sites commenced on 20th October 2016. No major issues to report as of 27th October. Monitoring will continue until Pilot completion on 17th of November 2016. | 2016-10-27
Q1-2016-17 | 82DC1100-ECE9-4799-93B5-41F8ABEE8C0B | Austin Health | AH | Laboratory Information System | Health | Implementation of a common Laboratory Information System as an externally hosted fully managed service in collaboration with two other state public health services. It will replace an existing internally hosted Pathology Laboratory System . | 2014-07-21 | Other – please specify | Overarching PRINCE2 approach with AGILE management of agency configuration and build. | In progress - implementation | 2015-06-04 | 50000 | 2017-01-31 | 1366875 | 2017-06-30 | 1486087 | Green | Green | Red | Red | Green | Project progressing to schedule. | 2016-09-30
Q1-2016-17 | FE15A512-0A86-454E-B368-753337768B4B | Austin Health | AH | Clinical Research Data Warehouse | Health | The objective is to implement a Data Warehouse to support clinical research. This entails developing the technical platform to extract and store data from a number of systems; and provide the foundation for clinical analytics. | 2015-07-01 | PRINCE2 | Vendor specific framework - based on Prince 2 | In progress - pre-implementation | [11 empty] | Project establishment phase completed. Design has commenced. Testing timelines have been reset to match the Oncology project testing timelines. | 2016-09-30
Q1-2016-17 | 5AC945FC-3674-4D21-844B-10637572BA48 | Austin Health | AH | Oncology Information System (OIS) | Health | The objective of the OIS is to improve the coordination of patient care and cancer treatments through ordering, scheduling and documenting cancer protocols within the EMR (Electronic Medical Record). The goal is to capture patient information electronically to populate the Data Warehouse to facilitate cancer research. | 2015-09-22 | Other – please specify | Vendor specific framework, based on Prince 2 | In progress - implementation | 2015-12-14 | 966042 | 2016-10-14 | 3400000 | 2017-06-30 | 3552000 | Green | Amber | Green | Amber |  | Project scope signed off and timeline revised to match agreed scope. Project is progressing to revised schedule. | 2016-09-30
Q1-2016-17 | CCCA63CF-018C-40E7-A31D-47DA7D152911 | Austin Health | AH | Theatre Management System | Health | The objective of Theatre Management System, is to improve the ordering and scheduling of procedures for both elective and emergency patients; to improve documentation of the preadmission process and ensure patients are ready for care; and to improve the flow of patients through the perioperative area. | 2015-09-22 | Other – please specify | Vendor specific framework - based on Prince 2 | In progress - implementation | 2015-12-14 | 617185 | 2016-10-14 | 3600000 | 2016-12-31 |  | Green | Green | Amber | Green |  | User acceptance testing completed and have commenced Conversion Phase. User Go live scheduled for 7th November 2016. | 2016-09-30
Q1-2016-17 | B4AA2A5D-8DB1-47B7-BB04-7E54A94C1930 | Bendigo Kangan Institute | BKI | Student Management System Implementation | Education | Implementation of new Student Management System across the integrated Bendigo Kangan Institute | 2013-02-01 | PRINCE2 |  | In progress - implementation | 2014-04-01 | 82723 | 2016-12-31 | 9800000 | 2017-03-31 | 12300000 | Amber | Amber | Green | Amber | Green | Since the implementation in December 2015 of the Student Management System Phases One and Two, the project has expended significant effort in post go-live support of the business in particular with AVETMISS reporting and defect resolution. In parallel, Phase 4A (ASMS) and 4B (Moodle two way interface) and some tranches of Phase 5 have been completed. A review of cost to complete the project has resulted in an increase of $2.5m to the budget. The project continues to undergo a review of business functions and product functionality to re-validate scope for the remainder of the implementation. | 2016-09-30
Q1-2016-17 | 12173148-2781-4F08-9A8F-8B5751C5C4AB | Bendigo Kangan Institute | BKI | Human Resources and Payroll Information System Implementation | Education | Implementation of new Human Resource and Payroll Information System across the integrated Bendigo Kangan Institute | 2015-01-27 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The contract negotiation with vendors was finalised in late October | 2016-09-30
Q1-2016-17 | 18C8670A-54B5-49A6-8807-DA93761CFDC2 | CenITex | CTX | Operating System Upgrade Across Windows Fleet | Government and economy | To upgrade fully managed servers in the shared environment to a supported server operating system | 2015-06-01 | PRINCE2 |  | In progress - implementation | 2015-06-01 | 15000 | 2017-06-30 | 2295214 |  |  | Green | Green | Green | Green | Green | Upgrades continue as planned. Activity has commenced to build a secure network enclave for unsupported Windows 2003 servers that cannot not be upgraded due to customer business constraints | 2016-10-20
Q1-2016-17 | 9F6B93E7-4787-44D2-AA55-43B016AB8D05 | CenITex | CTX | Shared Storage & Backup Refresh | Government and economy | To consolidate the existing Storage and Backup environment to meet growth requirements, mitigate email related operational risks and accommodate customers migrating to the shared storage platform. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2015-07-01 | 15000 | 2016-06-30 | 6995450 | 2016-12-30 | 7295450 | Green | Amber | Green | Green | Green | Migrations and decommissions continue as per updated schedule and will complete as planned | 2016-10-20
Q1-2016-17 | 2CD0BFF9-07A8-454C-BABE-D43FA107C182 | CenITex | CTX | Network Access Switch Refresh | Law and justice | To refresh the oldest network equipment at a large CBD customer site. | 2015-07-20 | PRINCE2 |  | Completed | 2015-07-20 | 15000 | 2016-05-22 | 1436180 | 2016-09-30 | 1036180 | Green | Green | Green | Green | Amber | Project completed | 2016-10-20
Q1-2016-17 | E95CD7A0-7AE2-4E02-80D0-EECE6ED01B5D | CenITex | CTX | Operating System Upgrade Across Windows Fleet | Health | To upgrade servers in the customer environment to a supported server operating system | 2016-02-08 | PRINCE2 |  | In progress - implementation | 2016-02-08 | 15000 | 2018-06-30 | 3570000 |  |  | Green | N/A | N/A | N/A | N/A | Target state platform established Approximately 40% of migrations completed or in flight | 2016-10-20
Q1-2016-17 | 9F535AA9-B719-4257-AAA1-5AFDDBC8AB98 | CenITex | CTX | Office365 Establishment & Migration | Government and economy | To implement Office 365 and make it available as a service for Victorian Government | 2016-05-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 200000 | 2017-06-30 | 4194583 |  |  | Green | Green |  |  |  | Design and build near completion. Migration planning and change management communication activities commenced. | 2016-10-20
Q1-2016-17 | 1C538086-D306-4A51-BED5-7047BADB4AE5 | CenITex | CTX | Hosting Storage Refresh/Consolidation | Government and economy | Refresh and consolidate shared storage infrastructure that supports Victorian government shared server hosting environment | 2016-05-01 | PRINCE2 |  | In progress - implementation | 2016-06-08 | 15000 | 2017-06-30 | 1997000 |  |  | Green | Green | N/A | N/A | N/A | Project on track and is completing data migrations as planned | 2016-10-20
Q1-2016-17 | 272863AD-C71E-47A8-8104-BAFAD910BBC4 | CenITex | CTX | Firewall Refresh for Victorian Government Shared Platform | Government and economy | Refresh firewalls at both primary and secondary Data Centres for Victorian government shared platform | 2016-06-03 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-procurement activities underway | 2016-10-20
Q1-2016-17 | D27645D5-6B7A-46FB-BE31-1BEF20CE3E49 | CenITex | CTX | Corporate ERP SaaS Solution | Government and economy | Implement SaaS based ERP - CRM, PPM and Finance subsystems | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Procurement underway | 2016-10-20
Q1-2016-17 | 117D1335-B270-4416-A731-2C0C76E56A00 | Country Fire Authority | CFA | CFA Resource Tracking System (RTS) | Emergencies and safety | Provide a Resource Tracking System for all CFA resources using CFA mobile radios to collect and transmit location data. This will allow Incident Controllers to have a near real time view of where all resources are located at major incidents enhancing firefighter safety. | 2010-10-01 | PRINCE2 |  | In progress - implementation | 2013-06-30 | 126034 | 2017-06-30 | 2500000 | 2017-06-30 |  | Amber | Amber | Amber | Amber | Amber | CFA is engaged in consultation with firefighter representative bodies. Consultation is becoming protracted but is not currently impacting the end date. | 2016-09-30
Q1-2016-17 | 47F5810F-784E-458D-8506-7C85B73C9B5F | Country Fire Authority | CFA | CFA Short Status Messaging (SSM) | Emergencies and safety | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | 2010-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | This short messaging system project is an element of the larger RDS project and due to delayed in the rollout of the RDS project, this element is running four years behind schedule. The short messaging system is partnered project between ESTA and CFA, who are now engaged in consultations with a third party supplier. | 2016-09-30
Q1-2016-17 | 88A07A25-CB11-477A-83AD-EBE8A7D72186 | Country Fire Authority | CFA | Regional Radio Command Service | Emergencies and safety | Establish new command and control level voice communication service on the Regional Mobile Radio network. Establish interconnectivity between Regional Radio Command Service, Incident Control Centres and operational facilities | 2014-07-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 8000000 | 2017-06-30 | 5000000 |  |  | Amber | Green | Green | Green | Green | The project is currently on hold pending funding from EMV for CFA Outer Metro dispatch. | 2016-10-13
Q1-2016-17 | B7F9C2EA-37D7-4DB8-B611-B29D43452097 | Chisholm Institute | Chisholm TAFE | Customer Relationship Management Implementation | Education | To provide an improved service to existing and potential students to maximise the take-up of educational services | 2016-06-01 | Other – please specify | Currently in Business Case development | Initiated | [11 empty] | Business Case developed; commenced 1 June 2016 and is still in progress. | 2016-09-30
Q1-2016-17 | 5D524B9A-1598-4E8C-92ED-80CCDBDD0371 | City West Water Corporation | CWW | Arrow Program | Business and industry | The Arrow program is a business transformation program to phase in the upgrade of most the business systems to an enterprise platform. | 2011-09-05 | Other – please specify | Oracle AIM | In progress - implementation | 2011-09-30 | 4109900 | 2022-06-30 | 104119621 | 2019-06-30 | 114200000 | Amber | N/A | N/A | N/A | N/A | Arrow program has three releases: Release 1 (Foundation module) - completed in May 2014 Release 2 (Asset management and Field Mobility module) is in progress: - Release 2.1 - Enterprise Asset Management - completed in June 2016 - Release 2.2 - Field Mobility - project timeline has been revised due to a change in system integrator and product selection Release 3 (Customer billing module) is yet to commence, pending on additional funding approval. The implementation cost has been revised to exclude the additional funding for Release 3 as it is yet to be approved. The planned implementation end date has also been corrected due to a data error in the previous report. | 2016-10-25
Q1-2016-17 | 6C1D62AD-9BAD-4613-88D5-87E0CD1355F4 | City West Water Corporation | CWW | Customer Experience Platform - Contact Centre Uplift | Environment and water | Augment new deployed Enterprise Telephony technology to contact centre | 2014-07-02 | PRINCE2 |  | In progress - implementation | 2014-07-02 | 179000 | 2016-03-30 | 1435000 | 2016-11-30 | 1569931.28 | Amber | N/A | N/A | N/A | N/A | Execution for Stage 3 has started. On track for the Nov 2106 implementation. | 2016-10-10
Q1-2016-17 | E80F599B-A91F-46C8-87A9-BD4D7B916132 | City West Water Corporation | CWW | IAPU Arrow Technology Upgrade | Business and industry | Oracle system upgrade initiative is to address the operational risk with CWW's Oracle EBS entering extended support in December 2016. | 2015-08-01 | Other – please specify | Gates Process, Benefit Realisation Model | Completed | 2015-09-01 | 10000 | 2016-02-15 | 2494000 | 2016-06-30 | 2494000 | Green | N/A | N/A | N/A | N/A | Upgraded system went live on 12 May 2016. Upgrade took longer than expected due mainly to issues encountered during implementation as such project was officially closed in Q1, 2016-17. | 2016-10-25
Q1-2016-17 | F04697A0-69A5-4BE3-998D-4FAA3AD7FF52 | Court Services Victoria | CSV | eLodgement Project - Tranche 2 | Community services | Implementation of eLodgement capability in an additional 3 lists within the following Jurisdictions; County Court, Magistrates' Court and VCAT | 2015-08-01 | PRINCE2 |  | Completed | 2015-11-16 | 0 | 2016-06-30 | 1652000 | 2016-08-30 | 1652000 | Green | Green | Green | Green |  | Finalising last part of this 2nd tranche of the project which enables electronic lodgement of documents in an additional list. | 2016-09-30
Q1-2016-17 | C610A140-8B8B-46D4-82AD-AC71AA647C3B | Department of Economic Development, Jobs, Transport & Resources | DEDJTR | Laboratory Information Management Strategy Implementation | Government and economy | This project will implement an enterprise web-based Laboratory Information Management System (LIMS) platform that will consolidate and centralise the existing veterinary diagnostics, plant diagnostics and chemistry Laboratory Information Management Systems to an agreed departmental standard (LabWare WebLIMS). This project is co-sponsored by Greg Harper and German Spangenberg | 2013-04-01 | PRINCE2 |  | In progress - implementation | 2014-12-22 | 0 | 2016-12-30 | 2062000 | 2017-06-30 | 2202000 | Green | Green | N/A | N/A | N/A | The project is currently on track to complete delivery of LIMS by June 2017 | 2016-09-30
Q1-2016-17 | 856FC387-1720-40E8-BEF1-E8BF59874DCA | Department of Economic Development, Jobs, Transport & Resources | DEDJTR | DEDJTR ICT Transition Program | Government and economy | The new DEDJTR Department created the ICT Transition program in early January 2015 to handle all ICT MOG related projects and activity. The main focus for the ICT Transition Program is to design and implement an agreed transition approach and plan to establish consolidated technology services for DEDJTR. | 2015-03-01 | PRINCE2 |  | In progress - implementation | 2015-09-30 | 0 | 2016-09-30 | 9496352 | 2016-11-30 | 9496352 | Green | Green | N/A | N/A | N/A | In this period the project has begun the migration of 5000 users to the new Desktop and Shared Drive structures. The project is currently half way through these migrations. | 2016-09-30
Q1-2016-17 | 5FF8E95C-6029-43F1-A725-B025B25CF43D | Department of Environment, Land, Water and Planning | DELWP | Enterprise Content Management System | Environment and water | Deliver an enterprise content management system | 2012-01-01 | PRINCE2 |  | In progress - implementation | 2012-06-01 | 0 | 2016-04-30 | 6011100 | 2016-11-30 | 6326100 | Green | Green | Green | Amber | Amber | The project slightly delayed due to closure activities. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2016-10-18
Q1-2016-17 | 8C478395-B494-4ACB-92B8-281698823E39 | Department of Environment, Land, Water and Planning | DELWP | Departmental Resourcing and Capability Project (DRaC) | Emergencies and safety | To develop consistent business processes, rules and supporting systems for the identification, management and deployment of resources for emergency management, surge operations and related business continuity issues in DELWP and Regulation and Compliance groups in other departments. | 2014-08-01 | PRINCE2 |  | In progress - implementation | 2015-05-29 | 418012 | 2016-12-31 | 3475758 | 2016-12-31 | 3475758 | Amber | Amber | Green | Green | Green | The project is likely to be extended until March 2017, due to resource availability during bushfire season 2015/2016.No budget impact. Project is currently on budget and is on track to meet its objectives. The controls are in place to manage any risks and issues as they arise. | 2016-10-17
Q1-2016-17 | C9C85060-4F47-423C-B1FA-0F0438299C85 | Department of Environment, Land, Water and Planning | DELWP | Native Vegetation Information Management System (NVIM) | Environment and water | NVIM supports a platform to obtain information on Victoria's native vegetation and biodiversity assets and access to a range of tools. These tools are designed to assist the implementation of government reforms to Victoria's native vegetation permitted clearing regulations, estimating habitat compensation and land security obligations under the Melbourne Strategic Assessment | 2014-09-01 | Agile |  | In progress - implementation | 2015-12-21 | 150551 | 2016-06-30 | 1439441 | 2016-10-31 | 1439441 | Green | Green | Green | N/A | N/A | The project is currently on schedule. There was an approved change request to add one month to the completion date. Project is currently on budget. The project is currently on track to meet its objectives. Mitigation strategies have been implemented for risks and issues. | 2016-10-18
Q1-2016-17 | B703BCE9-F1B3-495E-B4EC-4F8D76B8DF51 | Department of Environment, Land, Water and Planning | DELWP | DELWP Website Transformation | Community services | Deliver a DELWP web presence that supports the delivery of our community charter and facilitates effective interaction with our community and customers online, enabling rapid response to community and customer needs as well as providing a feedback loop. | 2015-07-23 | Other – please specify | Combination of PRINCE2 Project Management and Agile development and delivery | In progress - implementation | 2016-03-15 | 334468 | 2017-04-01 | 1866175 |  | 0 | Green | Green | Green | N/A | N/A | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2016-10-18
Q1-2016-17 | 0695877D-2DF9-40F2-9753-477ADE5A3934 | Department of Environment, Land, Water and Planning | DELWP | Regional WIFI | Employment and workplace | Implementation of WIFI Infrastructure in DELWP regional locations to increase collaboration and efficiency by providing secure network access for 20 priority DELWP regional sites. | 2016-07-14 | PRINCE2 |  | In progress - implementation | 2016-07-30 | 146745 | 2017-08-31 | 1191684 |  |  | Green | N/A | N/A | N/A | N/A | The project is currently on schedule. Project is currently on budget. The project is currently on track to meet its objectives. The controls are in place to manage the risks and issues as they arise. | 2016-10-19
Q1-2016-17 | 73F151E7-D2F3-4CF8-A7A8-FC629476ECC4 | Department of Education and Training | DET | Student Transport Management System | Education | The project will upgrade the Student Conveyance Allowance System, used to manage claims and conveyance allowance payments in the order of $30m per year. The project will incorporate student transport functionality, used to support administration of special school bus contracts worth $72m per annum. | 2010-07-01 | PRINCE2 |  | In progress - implementation | 2015-06-29 | 1221835 | 2016-05-09 | 1316079 | 2017-01-28 | 2154658 | Green | Green | Green | Green | Green | The extended pre-implementation phase is due to the project having been on-hold for an extended period pending DET decisions. In April 2015 the project engaged a vendor to upgrade the Department’s Student Conveyance Allowance System (SCAS) from CRM version 4 to CRM version 2015 and enhance the upgraded SCAS. This upgraded system is then being modified to incorporate the student transport functions. This will result in a single system for DET to manage all student transport and conveyance functionality. The upgraded SCAS with enhancements was successfully released to all Victorian schools in May 2016. During the development of the STMS Functional Design, additional functions were identified and a Project Change Request was approved to include the delivery of these new requirements in the project scope and the project re-baselined accordingly. | 2016-09-30
Q1-2016-17 | BA167DCC-D9C4-433A-90B0-7B19679C66E2 | Department of Education and Training | DET | FUSE SharePoint 2013 Upgrade | Education | FUSE (Find Use Share Education) is an online curriculum and resource portal for teachers and students. This project will upgrade the platform from SharePoint 2007 to SharePoint 2013 with some additional enhancements to improve usability and align resources to the new Victorian Curriculum | 2012-05-21 | PRINCE2 |  | In progress - implementation | 2015-03-06 | 283815 | 2015-11-11 | 1238225 | 2016-10-20 |  | Green | Green | Amber | Amber | Amber | Project activities have progressed to plan. Testing and cutover preparation activities have been completed. FUSE Go Live occurred 26 September. Post cutover activities have commenced in preparation for Project Closure. Project tracking well to agreed cost and schedule. | 2016-09-30
Q1-2016-17 | 891F2445-1AE7-411E-B7DD-CBB33725A606 | Department of Education and Training | DET | Asset Management System Replacement | Education | The AMSR project will identify and implement an Asset (Facilities) Management Software solution for managing information on DET property assets. The system will provide for the end-to-end asset management lifecycle and will replace a number of disparate legacy systems. | 2013-02-28 | PRINCE2 |  | In progress - implementation | 2014-04-30 | 679000 | 2016-07-25 | 5269000 | 2016-11-21 | 5198600 | Amber | Amber | Amber | Green | Amber | The AMSR solution has been implemented for corporate users. Testing of the solution for non-corporate (School-Release) users has been completed. Final testing with ten schools is scheduled to be complete on the 28th October 2016. | 2016-09-30
Q1-2016-17 | AC84992F-C35D-4A5C-891D-3CD6C0956E15 | Department of Education and Training | DET | Exchange Upgrade | Education | The Exchange Upgrade project will upgrade the DET Microsoft Exchange platform from Exchange 2010 to Exchange 2016, including migration of all DET users. The system will provide an enhanced email solution for Government school teachers and corporate staff at DET. | 2013-11-11 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is finalising the procurement activities for the Microsoft Exchange 2016 upgrade. The project is on track to deliver planned benefits, including the provision of an enhanced email solution for Government school teachers and corporate staff at DET. | 2016-09-30
Q1-2016-17 | 6B6471E0-8596-484C-A61C-CFDAAA8ADF6C | Department of Education and Training | DET | International Student Information Management System | Education | This project will identify, procure and customise an existing (Off the Shelf) International Student Information Management System to address existing shortfalls and meet current business needs for the International Education Division. | 2014-01-02 | PRINCE2 |  | In progress - implementation | 2016-05-31 | 201000 | 2017-07-31 | 905000 |  |  | Green | Green | N/A | N/A | N/A | Following the completion of a successful tender process and the appointment of a suitable vendor, the Project has commenced and is progressing towards completion of the system design phase. | 2016-09-30
Q1-2016-17 | A173558D-57C2-442B-83CE-9C5D19ECE124 | Department of Education and Training | DET | eduHub | Education | The eduHub project will develop an integration platform that enables secure and reliable exchange of school administration data with 3rd party vendors. The first phase which supports central delivery of the data to schools has been completed. | 2014-03-24 | PRINCE2 |  | In progress - implementation | 2015-11-13 | 100472 | 2016-12-31 | 1449528 |  |  | Green | Green | Green | N/A | N/A | Business Requirements for the second phase have been endorsed. Design phase is continuing. On track for go live in December. | 2016-09-30
Q1-2016-17 | 831C988E-83C3-44A5-8C6D-E7DFCE78BA41 | Department of Education and Training | DET | Antivirus for eduMail and eduGate | Education | The Antivirus for eduMail and eduGate project will implement a solution for DET's email platform and websites in order to protect against SPAM and malware threats. | 2014-07-23 | PRINCE2 |  | Completed | 2015-10-31 | 271000 | 2015-12-31 | 1229000 | 2016-07-29 | 1520000 | Green | Green | Green | Green | Green | The antivirus and spam protection solution have been successfully deployed. Email protection has been successfully deployed. The project scope has delivered protection of the Department's email and websites against virus and SPAM threats. Project is commencing close out activities. | 2016-09-30
Q1-2016-17 | 9300696A-14B5-4D65-8325-83871F2A1687 | Department of Education and Training | DET | eduPass Phase 3 Staff Provisioning | Education | The eduPass Phase 3 Staff Provisioning project will provide a system to manage the identity (username and password) and access controls for over 100,000 users in the Department of Education and Training. | 2014-11-07 | PRINCE2 |  | In progress - implementation | 2015-02-28 | 580968 | 2016-03-31 | 2019032 | 2016-12-30 | 3419032 | Green | Amber | Amber | Amber | Amber | System testing and required commissioning activities are on track for a go live in December. | 2016-09-30
Q1-2016-17 | 8B759B25-3C35-4848-9F65-B6D9CCE2F81D | Department of Education and Training | DET | CASES Technology Refresh | Education | The CASES Technology Refresh project will perform the 4 year refresh of Government schools' technology environment to support administration and financial management functions. The scope encompasses a server, workstations, switch, UPS, printer and backup service. | 2014-12-19 | PRINCE2 |  | In progress - implementation | 2016-07-20 | 692729 | 2017-02-28 | 14707271 |  |  | Green | N/A |  |  |  | Procurement is underway for the required ICT hardware. Project is on track to complete the installation of refreshed equipment at schools during the first 2017 school term. | 2016-09-30
Q1-2016-17 | AC434B54-18F9-494A-83BE-33714A2FFEE8 | Department of Education and Training | DET | Insight Part A Migration | Education | Migration of all existing DET paper and online assessments that exist in disparate systems onto the Insight Platform to provide teachers with the opportunity to understand student progress and develop targeted learning plans to increase student achievement. | 2015-02-01 | PRINCE2 |  | Completed | 2015-06-30 | 150000 | 2016-09-30 | 2500000 |  |  | Green | Green | Green | Green | Green | The migration "Part A" instruments (everything other than on-demand instruments) has been completed and will be deployed to production. | 2016-09-30
Q1-2016-17 | F39DA9A5-0659-4E84-BD7F-314615493E2E | Department of Education and Training | DET | HCM and Local Payroll - Schools Local Payroll (SLP) | Education | The project will migrate the School Council payroll from the schools’ local administration system (CASES21) to DET’s central payroll system (eduPay) through extension of DET's PeopleSoft based eduPay shared services arrangement; delivering a single payroll system for all Department and School Council staff. | 2015-02-19 | PRINCE2 |  | In progress - implementation | 2015-12-31 | 837899 | 2017-06-30 | 2092053 |  |  | Green | Green | Green | Green | Green | The application is now in production use with schools gradually being migrated across from CASES21 to eduPay. The migration will be completed by 30 June 2017. The project is on track to deliver planned benefits, including enabling DET to strengthen its financial controls and compliance measures for the payment of School Council staff; the ability to connect with, and directly communicate information to all staff; a single system view of the workforce so as to provide improved visibility and functionality for workforce management and planning; and improved productivity of school and corporate administration. | 2016-09-30
Q1-2016-17 | 375103CE-0C1B-4288-B786-63EE697E55F3 | Department of Education and Training | DET | HCM and Local Payroll - Performance (PDP) and Learning Management (LMS) | Education | A fully integrated payroll, performance, career and learning management capability for DET and its shared service customers through extension and utilisation of DET's PeopleSoft based eduPay shared services arrangement. To deliver an integrated solution for VPS and teaching staff and a systemic, evidence-based response to aid strategic decision making. | 2015-02-19 | PRINCE2 |  | In progress - implementation | 2016-03-30 | 398000 | 2017-06-30 | 3712048 |  |  | Green | Green | Green | N/A | N/A | The project has completed an updated business case for the LMS component and the overall communication strategy/plan. The detailed design continues for Learning Management. A supporting roadmap and configuration document has been completed. Release of the LMS is subject to formal release of all funding. The pilot for Performance and Development for VPS in 2015/16 is complete. The performance and Development general release for all VPS and Executive Officers for the 2016/17 period is complete. Subject to formal release of all funding, additional development for Teaching Service staff performance and development will commence during October through December 2016 with a planned release during 2017 envisaged. The project is on track to deliver planned benefits by enabling support for improved compliance in terms of financial, performance and learning management; provision of an entire workforce view and facilitating capability, career and succession planning; and more timely and accurate reporting. | 2016-09-30
Q1-2016-17 | F432CE02-811D-4103-AFC6-488E9555038A | Department of Education and Training | DET | HESG IT Business System Replacement | Education | This project is to replace the Skills Victoria Training System (SVTS). | 2015-02-23 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project working with preferred vendor to finalise plan for the Implementation Phase. | 2016-09-30
Q1-2016-17 | B7586CF1-6B49-4C1F-991B-2A6BB18AEDD2 | Department of Education and Training | DET | ICT fit-out for Public Private Partnership schools | Education | This project will procure and provision ICT equipment for fit-out of 15 new schools being constructed via the Victorian School Building Authority's New Schools Public Private Partnership (PPP) Project. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project brief was developed and achieved endorsement. Technical resourcing and Technical delivery phasing in development. Infrastructure and device procurements progressing. | 2016-09-30
Q1-2016-17 | 277079FA-D426-4367-8577-31A6E82F4294 | Department of Health and Human Services | DHHS | Health & Hospital Funding Regional ICT cancer Multidisciplinary Meeting Management Project | Health | To deliver a software solution to support multidisciplinary team meetings within and across regional integrated cancer services. | 2012-12-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 3E31DAAA-7C0F-4E9B-A887-1D2CB2CB48AC | Department of Health and Human Services | DHHS | Organisation Design and Visualisation | Community Services | Changes to the Human Resources system to move from a people based to a 'position' based structure, improve functionality and provide a better organisational design and change capabilities. | 2013-05-13 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2014-05-29 | 0 | 2014-09-23 | 934468 | 2016-10-18 | 2086236 | Amber | Amber | Green | Amber | Red | Project schedule delayed due to third party vendor negotiations. A revised project schedule will be presented to the Project Steering Committee for acceptance in October. The key project deliverable has been successfully been implemented into a production environment. | 2016-09-30
Q1-2016-17 | 423EF30E-2193-43FE-A033-B594A2008F76 | Department of Health and Human Services | DHHS | Bendigo Hospital - Group 2 & 3 ICT infrastructure and support systems | Health | Delivery of state-of-the art high availability network, technologies and modern support systems that compliment the new Bendigo Hospital. | 2013-05-28 | PRINCE2 |  | In progress - implementation | 2015-08-01 | 45000000 | 2017-01-23 | 36920000 |  |  | Green | Green | Green | Green | Green | Project progressing to schedule. | 2016-09-30
Q1-2016-17 | 10553C6A-4DBD-4AFE-AF7C-F6A1DC5C854F | Department of Health and Human Services | DHHS | Network user authentication devices upgrade | Community Services | Replace out-of-date infrastructure to provide user authentication and vendor support services. | 2014-03-11 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | EF92AE62-E893-4F6D-A6F4-7700D962211F | Department of Health and Human Services | DHHS | Client Relationship Information System (CRIS) Legislative Changes (Permanency) | Community Services | Significant changes to Integrated Client and Case Management Systems to support child protection permanency reform/legislative changes to the Children, Youth and Families Act 2005, including a better alignment of Children’s Court orders and department case plans and a new range of Children’s Court Orders to support the Permanency Planning Framework | 2014-11-20 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Completed | 2015-05-22 | 284839 | 2016-02-29 | 3800000 | 2016-08-06 | 3814000 | Green | Green | Green | Green | Green | Project successfully completed. | 2016-09-30
Q1-2016-17 | 6C1E7725-6C25-4B52-BC43-20546CE22337 | Department of Health and Human Services | DHHS | Melton Community Based Ambulatory Care Centre (MCBACC) | Health | Implementation of the ICT integration solution between five health providers at the new Melton Community Based Ambulatory Care Centre | 2016-07-07 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 48DF1774-D1D8-4185-9316-96191311523C | Department of Health and Human Services | DHHS | Housing Application Online | Community Services | Enabling potential tenants of Community Service Organisations to submit housing applications online. | 2015-02-20 | Agile |  | Completed | 2016-02-02 | 0 | 2016-07-27 | 1598000 | 2016-09-30 | 1491317 | Green | Amber |  |  |  | Project successfully completed. | 2016-09-30
Q1-2016-17 | 9E946175-99B9-4617-A0E9-9AD24D9F6DE6 | Department of Health and Human Services | DHHS | Housing Infrastructure Capital Refresh | Community Services | Replace ageing and unsupported hardware for the production and disaster recovery environments of the Housing Integrated Information Program (HiiP). | 2015-05-28 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2016-09-30
Q1-2016-17 | F3FF16EB-7A83-44B0-A2DD-9AE829302DB6 | Department of Health and Human Services | DHHS | Budget and Reporting System | Health | The strategic driver in implementing a new budgeting & reporting system is to transform the finance function from a transactional to a value-adding service by providing users with self service capability. The system will replace the current Budget Management System. | 2015-06-01 | PRINCE2 |  | In progress - implementation | 2015-12-31 | 178000 | 2016-10-25 | 2752567 |  |  | Green | Green | Green | Green | Green | Project progressing to schedule. | 2016-09-30
Q1-2016-17 | 041491EE-BCD4-43E1-84F2-EE08A8273A15 | Department of Health and Human Services | DHHS | Corporate Reporting Tool Upgrade | Community Services | Upgrade the Corporate Reporting software and hardware. | 2015-06-25 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2015-11-13 | 0 | 2016-06-30 | 1103846 | 2017-02-28 |  | Amber | Green | Green | Green | Green | Implementation end date has been revised due to resource contention. Project progressing to revised schedule. | 2016-09-30
Q1-2016-17 | E8BD9A4A-9C3D-4F3B-9446-0479C9402ABC | Department of Health and Human Services | DHHS | Victorian eReferral Program | Health | The Program aims to make referral processes more efficient, safe and reliable. The focus of the program, while necessarily including a significant technical component, will also be establishing appropriate governance, standardisation in business processes and information and the change management necessary to deliver the planned benefits and client outcomes. | 2015-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2016-09-30
Q1-2016-17 | AE143C36-2082-406E-9A3C-C0FC04A6CD94 | Department of Health and Human Services | DHHS | Real-time prescription monitoring system | Health | Implement software that transmits pharmacy records in real-time to a centralised database, enabling doctors and pharmacists to make safer clinical decisions prior to prescribing or dispensing medicines at high risk of misuse. | 2015-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2016-09-30
Q1-2016-17 | B58D2FCF-3C95-4FC1-9D58-CD0BB3375A3C | Department of Health and Human Services | DHHS | Victorian Health Incident Management System (VHIMS) | Health | The key objectives are to (1) Simplify and significantly improve VHIMS functionality for health sector users. (2) Ensure that the process for reporting on VHIMS data is made easier and more meaningful and (3) Enable routine analysis of VHIMS data and dissemination of meaningful standardised reports | 2015-07-06 | PMBoK |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2016-09-30
Q1-2016-17 | 8E9ECAF3-7446-4D04-AFD5-F70E6861F814 | Department of Health and Human Services | DHHS | Records Management system upgrade | Community Services | Upgrade the current recordkeeping system software and hardware for all existing users. | 2015-07-12 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | F0A030E2-0262-4E95-AEA4-CCACD742DB1F | Department of Health and Human Services | DHHS | Program Unity | Community Services | Transition DHHS to the Government Shared Platform hosted by CenITex by joining the networks, upgrading infrastructure and moving to a Windows 8.1 desktop. | 2015-07-13 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - implementation | 2016-05-12 | 10795732 | 2016-12-30 | 5182166 | 2017-03-01 |  | Amber | Amber |  |  |  | Project completion date has been revised due to technical problems discovered in the final stages of testing. The technical issues have been resolved and rollout has commenced. The Executive Governance Group has accepted the revised completion date. | 2016-09-30
Q1-2016-17 | 4895BCC7-1650-49DD-9E0A-6A1A5FACFA1B | Department of Health and Human Services | DHHS | Enabled Divisional Area Enhancements (EDAE) | Community services | Address outstanding issues and deliver enhancements to the Housing Integrated Information Program and Integrated Client and Case Management Systems to reflect the organisational restructure from regions to divisions and areas. | 2015-08-10 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 8F362E05-B419-4109-818C-354494E3AFD3 | Department of Health and Human Services | DHHS | Intranet | Community Services | A new combined intranet for the merged former departments. | 2015-08-26 | Agile |  | In progress - implementation | 2016-04-01 | 192105 | 2017-06-30 | 1007895 |  |  | Green | N/A |  |  |  | Project progressing to schedule. | 2016-09-30
Q1-2016-17 | 1037DD45-8510-4EEC-ADC7-9D3F32BF8EFE | Department of Health and Human Services | DHHS | Client Incident Management | Community services | Develop a unified critical incident reporting model to replace the existing client incident management system. | 2015-10-21 | Agile |  | In progress - pre-implementation | [11 empty] | Project is out of scope and will not be reported in the next quarterly update. | 2016-09-30
Q1-2016-17 | 085D4872-3606-493B-98B5-AE35C523B09A | Department of Health and Human Services | DHHS | Bendigo Hospital - Electronic Medical Record | Health | Electronic Medical Records and Digital Medical Records implementation at the new Bendigo Hospital | 2015-12-23 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities in progress. | 2016-09-30
Q1-2016-17 | 188112FA-CA80-49BF-870F-1F92BDE41A69 | Department of Health and Human Services | DHHS | Automation of Family Violence Referral form | Community services | Replace fax transmission of Family Violence Referral forms from Victoria Police to Child Protection, Specialist Family Violence Agencies and other community bodies. | 2016-02-15 | Agile |  | In progress - implementation | 2016-04-27 | 139680 | 2016-11-16 | 2551720 | 2016-12-06 | 2817428 | Amber | Green |  |  |  | Project schedule has been revised due to delays building the interface with Victoria Police. | 2016-09-30
Q1-2016-17 | 50ED1655-7220-4ECC-BD80-C1A25EBFDAC1 | Department of Health and Human Services | DHHS | Health Sector Finance and Materials Information System (FMIS) upgrade | Health | Upgrade of the Finance and Materials Information System (FMIS) for the Victorian Public Health Sector. | 2016-07-01 | PRINCE2 |  | In progress - implementation | 2016-08-10 | 59997 | 2017-09-15 | 2536110 |  |  | Green | N/A |  |  |  | Project progressing to schedule. | 2016-09-30
Q1-2016-17 | DCC9DD56-E088-4568-B3B5-83B16E2DA8ED | Department of Health and Human Services | DHHS | Integration Solution Replacement | Health | Replacement of the integration solution to support Victorian acute public health services with ongoing capability to integrate patient and clinical information within and across health services. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 92E0212C-3F9F-493D-A891-16F27158A066 | Department of Health and Human Services | DHHS | Integrated Client and Case Management Systems (ICCMS) Data Warehouse transition to Corporate Reporting Tool | Community services | Upgrade unsupported data warehouse for integrated client and case management systems. | 2016-09-01 | Other – please specify | Project Management Methodology developed by the former Department of Human Services based on PRINCE2 | Initiated | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 269F2AD8-C692-45A1-AD9F-5FD0A4AB8725 | Department of Health and Human Services | DHHS | Clinical Services Technology Replacement Program | Health | Replacement of clinical services technology assets at Victorian acute public health services. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 9875085D-F469-4DEF-B614-F51EBA1EDEF8 | Department of Health and Human Services | DHHS | Windows Server Remediation Program | Community services | Upgrade, replace or decommission outdated servers and database instances. | 2016-07-01 | Agile |  | In progress - implementation | 2016-07-01 | 0 | 2019-06-30 | 11800000 |  |  | Green | N/A |  |  |  | Project progressing to schedule | 2016-09-30
Q1-2016-17 | 6289B205-46EE-4CFF-AF04-40302D7FF061 | Department of Health and Human Services | DHHS | Parkville Precinct Electronic Medical Record | Health | Implementation of an Electronic Medical Record into Melbourne Health, Peter MacCallum Cancer Centre and The Royal Women's Health Services. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | 1EE7596A-96E9-4CEE-9364-36B3A3F3D033 | Department of Health and Human Services | DHHS | Digital Patient Identification | Health | Implementation of a state-wide Enterprise Master Patient Index (EMPI) to support the objectives of Health 2020, the Clinical Information Exchange (CIE), improved analytic capability and access to My Health Record. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning in progress. | 2016-09-30
Q1-2016-17 | B3F0DDD6-CAC6-4D65-A776-94770FEAA74A | Department of Premier and Cabinet | DPC | ACHRIS Phase 2 Enhancement Project | Culture, sport and recreation | The ACHRIS Phase 2 Enhancement Project will deliver new functionality to AVs online application to support the implementation of the Aboriginal Heritage Amendment Act 21016 and a new infrastructure environment to enable the required flexibility, scalability and operational efficiency to implement these changes. | 2015-01-01 | Agile |  | In progress - implementation | 2015-12-30 | 42900 | 2019-06-30 | 1950000 |  |  | Green | Green | Green |  |  | Development of release 2 (online Payment Gateway) is nearing completion and is scheduled for production release October. Procurement activities for transitioning ACHRIS to the Cloud have been finalised. | 2016-10-01
Q1-2016-17 | 91D2745E-B192-4E8E-BCD6-4022F8F89DAE | Department of Premier and Cabinet | DPC | Single Digital Presence | Government and economy | The Victorian Government will make it easier for Victorians to find, access and understand government information by redesigning and re-platforming Premier & Cabinet websites, including vic.gov.au. This project will also reduce the cost and risk associated with digital services and help us create new services faster. | 2015-09-17 | Agile |  | In progress - implementation | 2016-06-30 | 118800 | 2018-06-30 | 4200000 |  |  | Green | Green | Green |  |  | A RFQ was released on the 17 October 2016. Its objective is to engage a service provider with specific knowledge to recommend the Content Management (CMS) platform that will support the operating model as define within the business case. The RFQ closes on 31 October. The CMS will be recommended by 23 December 2016. | 2016-10-28
Q1-2016-17 | 63FE2940-257B-4616-AEFF-516138AC73E8 | Department of Premier and Cabinet | DPC | Service Victoria | Government and economy | Service Victoria will create a new whole of government service capability to enhance the delivery of government transactions with citizens, enable the delivery of a more effective customer experience and create new distribution channels for simple, high volume transactions. | 2015-07-01 | Other – please specify | Waterfall and agile methodologies used. | In progress - pre-implementation | [11 empty] | Service Victoria has completed planning phase which included working through detailed policy, technology and customer requirements. During 2016-17 Service Victoria will transition to development and testing phase where implementation will draw on the prior planning. | 2016-10-28
Q1-2016-17 | 303A0D99-1A4D-4D45-B607-DF242EF08EF0 | Department of Premier and Cabinet | DPC | TPAMS2025 Project | Government and economy | TPAMS2025 will replace the current Telecommunications Purchasing and Management Strategy (TPAMS) State Purchase Contracts (SPCs) with new SPC arrangements for data, voice, mobile and unified communications services. | 2015-03-31 | PRINCE2 |  | In progress - implementation | 2016-01-21 | 226977 | 2016-11-30 | 2773023 | 2017-01-30 |  | Green | Green | Green |  |  | The approval process for the TPAMS2025 Business Case was completed. External project resources were engaged. Working groups from major customer agencies provide technical input. | 2016-11-03
Q1-2016-17 | 148D3F34-7A2E-4ECA-9814-F61B0D76384A | Department of Premier and Cabinet | DPC | Central Consultation Platform (CCP) Project | Government and economy | This project will deliver a service and platform for use by the Whole of Vic Government (WoVG) to conduct online consultations with the Victorian public. A basic platform will initially be released as a pilot to collect feedback. A fully featured solution will be delivered in subsequent project releases. | 2016-05-01 | Agile |  | In progress - implementation | 2016-05-01 | 42531 | 2017-06-15 | 1158270.3977 |  |  | Green | Green | Green |  |  | Preparation and ongoing review of the full suite of 'go to market' documentation was the primary activity for the period. | 2016-09-30
Q1-2016-17 | A88208B4-C255-4099-B088-0EAB964C0E0F | Eastern Health | EH | Eastern Health - Electronic Medical Record | Health | Build a single Longitudinal Medical Record which ensures that relevant critical information for the provision of patient care is available in the one place at the time of clinical decision making, and ensures presentation in a comprehensive, consistent and contextual manner. | 2015-01-01 | Other – please specify | Cerner Consulting Framework | In progress - implementation | 2015-09-30 | 1027020 | 2017-12-31 | 18852980 |  |  | Green | Green | Green | Green |  | Project progressing to schedule. | 2016-10-01
Q1-2016-17 | B37A3DF7-7887-4027-AFB7-7694396FECAE | Energy Safe Victoria | ESV | 0005 - Gas Online Application | Business and industry | Replacement of manual forms process with automated portal process for Applications for Gas Supply | 2014-10-01 | Agile |  | Completed | 2015-04-15 | 35900 | 2016-06-30 | 604000 | 2016-08-31 | 1087238 | Green | Green | Green | Green | Green | Final project costs now received with an addition $15k spent in this reporting period bring the project to closure. | 2016-10-26
Q1-2016-17 | 2E9F5826-352A-403D-95D4-A449DCA9521A | Energy Safe Victoria | ESV | 0033 - ESV Connect: Licensing and Registration | Business and industry | Replacement of legacy system | 2016-06-01 | Agile |  | In progress - implementation | 2016-08-01 | 395628 | 2017-06-30 | 2000000 |  |  | Green | Green |  |  |  | Project is in-flight and tracking against projected timelines. | 2016-10-26
Q1-2016-17 | B571CFA9-98DC-4EBD-8418-90772E62F356 | Gippsland Health Alliance | GHA | Electronic Medical Record and Community Health (EMRCH) | Health | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | 2016-02-02 | PMBoK |  | In progress - pre-implementation | [11 empty] | Request for Tender closed September 2016. Detailed evaluation in progress | 2016-11-04
Q1-2016-17 | C8B101DA-DB87-4F37-B359-1B033477845D | Goulburn-Murray Rural Water Corporation | Goulburn MW | ECMS Upgrade / Replacement | Environment and water | The existing Records and Document Management System is not meeting the organisation's requirements. The objective of this project is to define the organisation's requirements and to source and implement an Enterprise Content Management System (ECMS) that meets the organisation's current and future requirements for Records, Documents and Information Management. | 2016-01-18 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is in the pre-implementation phase. | 2016-10-21
Q1-2016-17 | B1E7A8CD-2CF3-4255-8A86-C67CACE54298 | Grampians Rural Health Alliance | GRHA | Ballarat Health Services - Rostering & Payroll Interface Project | Health | Implement organisation-wide rostering application and integrate with existing payroll application | 2015-03-16 | Agile |  | In progress - implementation | 2015-06-30 | 465200 | 2017-06-30 | 2252013 |  |  | Green | Amber | Green |  |  | Project is progressing well with uptake across multiple clinical and corporate departments. Schedule and budget are on track. | 2016-10-12
Q1-2016-17 | 4ED08A36-BDB2-47DE-AD26-A594F7262903 | Grampians Rural Health Alliance | GRHA | Regional EMR/HIE Implementation | Health | The development and implementation of shared electronic medical records across the Grampians region | 2015-08-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 1206242 | 2017-03-31 | 1493758 |  |  | Green | Green |  |  |  | Budget is on track from capital funding. Regional participation is fully agreed. Timing and Scope is agreed and on track. | 2016-10-14
Q1-2016-17 | 3675C2AB-2414-4C5C-8EB2-0C83A452C323 | Grampians Wimmera Mallee Water Corporation | GWMWater | Water Treatment Plant PLC Replacements | Environment and water | Renewal of PLCs (Programmable Logic Controllers) at priority Water Treatment Plants to replace redundant technology. | 2014-08-12 | PRINCE2 |  | In progress - implementation | 2016-09-30 | 164327.1 | 2018-06-30 | 1069673 |  |  | Green | N/A |  |  |  | Project tender documentation prepared for priority sites. Works planned to commence after summer in 2017. | 2016-09-30
Q1-2016-17 | 21CF9AAB-F8B6-4130-8688-5519803BFE33 | Health Purchasing Victoria | HPV | Supply Chain Reform Program - Project P058 (Purchasing and Logistics Improvement Project) | Health | Design, source and implement at Melb Health a state-wide purchasing and logistics solution | 2016-05-04 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case development activities are underway | 2016-09-30
Q1-2016-17 | 393F9524-4EF3-41C8-85FE-973B870967A6 | Health Purchasing Victoria | HPV | Supply Chain Reform Program - Project P061 (Information Standards and Master Data Project) | Health | Develop common catalogue data and master data processes for the state | 2016-05-04 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case development activities are underway | 2016-09-30
Q1-2016-17 | 658AB860-05DC-43E9-9A20-6119C3BBA05F | Hume Rural Health Alliance | HRHA | Patient Administration System (PAS) replacement project | Health | A replacement Patient Administration System (PAS) to address problems associated with end of life technology, difficulty harnessing integrated data and difficulty keeping pace with advances in health management technology. The replacement PAS will be adopted by health services within the Hume Region | 2014-02-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning and design is progressing. | 2016-10-27
Q1-2016-17 | 42840EA7-8031-4E89-9342-5D301A102B3D | Hume Rural Health Alliance | HRHA | Goulburn Valley Health Redevelopment | Health | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | 2016-04-20 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Currently in schematic design phase, where ICT input has been requested in order to support this activity. Budget for ICT has been set as part of the project. Scope is still to be defined and has progressed to 2 working groups, will require further consultation post project management team appointment. | 2016-10-18
Q1-2016-17 | A601DB88-0FBF-4450-8710-DADC3B5FCE23 | Melbourne Health | Melb H | Pathology Laboratory Information System Replacement | Health | Implementation of a common laboratory information system as an externally hosted fully managed service in collaboration with two other state public health services. Will replace existing internally hosted pathology laboratory system. | 2014-07-21 | Other – please specify | Overarching Prince 2 approaching with Agile management of agency configuration and build. | In progress - implementation | 2015-06-04 | 50000 | 2017-01-31 | 1826610 | 2017-06-30 | 1826610 | Green | Green | Red | Red | Green | Solution testing progressing. | 2016-10-18
Q1-2016-17 | 6058F428-4889-46F0-9259-7E21AB31AF32 | Melbourne Health | Melb H | Enterprise Billing System | Health | Implementation of an Enterprise Billing System will enable Melbourne Health to achieve a centralised approach for managing patient billing services and improving revenue collection across all clinical areas. | 2016-03-01 | PRINCE2 |  | In progress - implementation | 2016-05-01 | 0 | 2018-08-01 | 4800000 |  |  | Green | Green | Green |  |  | The project is progressing to schedule. | 2016-10-10
Q1-2016-17 | C9492320-23DB-476C-8076-BFFAD623E682 | Melbourne Health | Melb H | Enterprise Content Management System (digitisation of clinical record content) | Health | Implementation of an Enterprise Content Management System to achieve digitised medical record content and automated workflows for Specialist Clinic Referrals Management, Coding and Release of Information | 2015-06-01 | Other – please specify | Overarching Prince 2 approach with Agile management of agency configuration and build. | In progress - implementation | 2015-06-01 | 143000 | 2016-10-07 | 5226000 | 2016-10-07 | 4538653 | Green | Green | Green | Green | Green | Project progressing to completion on 7th October 2016 | 2016-10-26
Q1-2016-17 | 1CE4559D-5CE3-4926-9FBA-687DD9B42E4F | Melbourne Health | Melb H | CAFM Project - Computer Aided Facilities Management | Health | Implementation of an IT software & mobility solution for MH Facilities Management, including: Help desk, Service, Task triage, Resource allocation (staff & contractors), Job management, Contract management (SLA/KPIs), Contractor compliance, Asset management, potential for asset tracking, Maintenance management, scheduler for planned tasks/preventative maintenance, Audits, Property & Estate management including CAD drawings & BAS integration, utilities and metrics that will identify sustainability opportunities. | 2015-11-01 | Other – please specify | DMAIC (Six Sigma) for Stage Gate Processes & PRINCE2 for IT deployment | In progress - pre-implementation | [11 empty] | Pre-implementation phase underway and the Request for Tender (RFT) procurement process is continuing. | 2016-10-26
Q1-2016-17 | 7D017925-2311-4119-B1C6-71F090B94CF4 | Melbourne Health | Melb H | Human Resource Information System (HRIS) | Health | Implementation of a Human Resource Information System that contains the following modules; Employee HR data portal, Recruitment, Onboarding, Learning, performance and Goals, Succession and Career planning. | 2015-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation phase underway. Contract negotiations and Implementation Planning Study (IPS) discussions commenced with preferred vendor . | 2016-10-26
Q1-2016-17 | E524823C-5D64-48B7-98FE-00D4DB28D485 | Melbourne Polytechnic | MelbPoly | Customer Relationship Management Platform and Telephony Upgrade | Education | Implementation of Customer Relationship Management system to increase student enrolment numbers | 2016-04-01 | PRINCE2 |  | Initiated | [11 empty] | Project does not yet have any budget allocated. Working through | 2016-09-30
Q1-2016-17 | 51745FB5-BA96-4FE1-BE14-8B52B81FCE73 | Melbourne Polytechnic | MelbPoly | Centre for Applied Innovation | Education | ICT resources to support the establishment of the Centre for Applied Innovation | 2016-08-29 | Other – please specify | Outsourced to Computer Sciences Corporation | In progress - pre-implementation | [11 empty] | Business case developed | 2016-09-30
Q1-2016-17 | DFE833EE-2DB7-4DCC-A07F-DEC882F6C0CC | Melbourne Water | MW | Q04323 - Developer Funded Works System | Environment and water | The Developer Funded Works System replacement project will migrate the DSCM system and DPW database to an enterprise capability for asset management that is consistent with the Melbourne Water asset information and asset management processes (AMIS). | 2013-09-02 | PRINCE2 |  | In progress - implementation | 2016-01-25 | 0 | 2016-09-30 | 3455000 | 2017-03-31 | 3454000 | Amber | Amber | Green | Amber | Amber | Melbourne Water is delivering the required business functionality in 2 Phases. Phase 1 is due in December. Phase 2 is using an Agile method and is due 31st March 2017. Phased deployment has been necessary to align with changes introduced through core Business Process Improvement. | 2016-10-13
Q1-2016-17 | C5B95B39-CB36-4FBE-B071-B2F89035A4BD | Melbourne Water | MW | Q04322 - Development Services System | Environment and water | (Previous known as "Atlas 4" project). To enhance/replace the Atlas system so as to improve our ability to manage and respond to statutory referrals, development enquiries and works applications. | 2013-09-02 | Agile |  | In progress - implementation | 2016-02-18 | 0 | 2016-12-30 | 4949000 | 2016-11-14 | 4926000 | Amber | Amber | Green | Green | Green | Development of the core DevConnect system is well progressed. This quarter the project absorbed scope change to incorporate integration with the Customer Management System in order to support long term strategic outcomes. The implementation includes further embedding of the new GIS platform. However this transition process has resulted in a number of technical risks coming to fruition which has consumed time and budget contingency. The Project is now progressing to end User Acceptance testing with a number of risks still being managed | 2016-10-13
Q1-2016-17 | 0C4D8B5D-8A4A-45FB-9ECC-B913D2E00211 | Melbourne Water | MW | Q04263 - Field Mobility (Enterprise Mobility Platform) | Environment and water | Selection and introduction of: 1. A ‘best of breed’ enterprise mobility platform 2. A Maximo integrated mobility client for field works management, including: -Work order management, and -Timesheet management Provision of mobile access to Maximo from inside and outside of the MW network, including offline access. | 2014-05-02 | PRINCE2 |  | Completed | 2015-12-23 | 0 | 2016-04-30 | 2578000 | 2016-04-03 | 2556369 | Green | Amber | Amber | Amber | Green | Project practical completion in April. Project now complete and Financial Cost Report approved. | 2016-10-13
Q1-2016-17 | 10E7B7E1-050B-4628-ADD5-193B3CA21926 | Melbourne Water | MW | Q04407 - Enhance Disaster Recovery IT Capability | Environment and water | Provide a fully-managed enterprise-wide Backup & Recovery Cloud Solution | 2014-06-01 | PRINCE2 |  | In progress - implementation | 2015-11-19 | 0 | 2016-03-31 | 1652000 | 2016-10-31 | 1257141 | Amber | Amber | Green | Green | Green | Internal Fusion firewall issues delayed project 15 weeks. Main datacentres and remote sites now cutover. Last Exchange email devices in planning for cutover. BAU handover before end October. | 2016-10-13
Q1-2016-17 | 4CEBC455-29CA-4398-AD50-638CCB707312 | Melbourne Water | MW | Q05292 - ETP PCS Virtualisation | Environment and water | Refresh Technology platform for the Process Control System (PCS) at the Eastern Treatment Plant (ETP) and virtualise the server environment. | 2015-05-14 | PRINCE2 |  | In progress - implementation | 2015-11-26 | 0 | 2016-05-31 | 1100000 | 2016-12-09 | 844536 | Green | Green | Green | Amber | Green | Technology Platform has been upgraded and virtualised. Operations Group is working to upgrade the PCS application to match the new technology platform. PCS application upgrade and progression to fully supported state is scheduled to complete by 09 Dec 2016. | 2016-10-13
Q1-2016-17 | 24B917D1-8FB2-4B5A-A612-39ECFA53990B | Melbourne Water | MW | Q05543 - LIQUID | Environment and water | Replace the Access databases and Excel spread sheets with a single data repository that incorporates backups and DR support. This solution will also support ad-hoc sampling. | 2016-02-25 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2017-01-27 | 1209000 | 2017-02-02 | 1078000 | Green | Green | Green | Green | Green | The implementation status is amber until the decision is made by the senior stakeholders regarding the inclusion of AMIS integration into the scope of the project | 2016-10-13
Q1-2016-17 | 7B151389-ECAD-45C5-9308-825BBD79F563 | Melbourne Water | MW | Q05496 - CRM R1_4 Build Release | Environment and water | CRM Enterprise phase will release new mature iterations for improved benefits and KPI's. This phase will also offer enhanced enterprise support for ALL 9 customer segments | 2015-07-31 | Agile |  | In progress - implementation | 2016-08-01 | 0 | 2016-10-30 | 1404000 | 2016-10-30 | 1384000 | Green | Amber | Green | N/A | N/A | Software enhancements live. Final Task (interaction mapping) to complete by end of October on schedule | 2016-10-13
Q1-2016-17 | 066CD218-AB3F-4856-9CD9-66B6F82668CE | Melbourne Water | MW | Q03317 - Enhanced Headworks Model Development | Environment and water | This project will provide the ability to consider the total water cycle in developing water supply strategies, enabling a method of delivering water supply, waterways and sewage services holistically. | 2015-08-03 | PRINCE2 |  | In progress - implementation | 2016-08-26 | 0 | 2017-09-30 | 1204000 | 2017-09-29 | 891587.42 | Green | Green | Green | Amber | N/A | Final Business Case approved, project in implementation. | 2016-10-13
Q1-2016-17 | 6B13CDE9-97ED-49DC-B160-426D7C8E3304 | Melbourne Water | MW | Q04319 - Risk Management System | Environment and water | To implement an enterprise risk management system that provides a consolidated repository for management of corporate and specialist risks throughout Melbourne Water. | 2013-12-09 | Agile |  | In progress - implementation | 2015-02-19 | 0 | 2015-09-15 | 1110000 | 2016-10-21 | 931096.68 | Green | Green | Green | Green | Green | Risk Workflow scheduled to go-live early / mid October - defect resolution required more effort than expected | 2016-10-13
Q1-2016-17 | CDA562B6-6B54-479A-BB77-DC207EBE2CE5 | Metropolitan Fire and Emergency Services Board | MFESB | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and safety | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | 2013-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2014-07-09 | 60737 | 2017-06-30 | 1200000 |  |  | Green | Green | N/A | N/A | N/A | Implementation has commenced. | 2016-09-30
Q1-2016-17 | 1A41DD56-D037-41FD-B5B2-A7586EB48131 | Metropolitan Fire and Emergency Services Board | MFESB | Replace Legacy Dell Servers | Emergencies and safety | Replacing legacy server hardware. | 2014-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2014-10-01 | 0 | 2018-06-30 | 2180000 |  |  | Green | Green | N/A | N/A | N/A | Hardware Delivered. Services Contract now being developed | 2016-09-30
Q1-2016-17 | 1D1BEC37-2120-4036-8F3B-DBAA2742577A | Metropolitan Fire and Emergency Services Board | MFESB | Legacy SAN Storage Refresh | Emergencies and safety | Replacing legacy and upgrading network storage. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2015-10-01 | 0 | 2017-06-30 | 1500000 | 2017-08-31 | 1230000 | Green | Green | N/A | N/A | N/A | Storage Strategy RFT completed. Finalising contractual arrangements. | 2016-09-30
Q1-2016-17 | 457BDED1-EAE5-45FC-9819-1E1E30095198 | Metropolitan Fire and Emergency Services Board | MFESB | Mobile Data for Vehicles Pilot | Emergencies and safety | Pilot project of mobile data devices installed in fire appliances to receive and display relevant event information. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2016-02-04 | 0 | 2017-06-30 | 1750000 |  |  | Green | Green | N/A | N/A | N/A | Device Procurement in progress. Software development contract completed and end user design in progress. WiFi in Stations being installed. Communications options being assessed. | 2016-09-30
Q1-2016-17 | 12FDE857-12A0-4996-91A4-26F7AB4AE5A2 | Metropolitan Fire and Emergency Services Board | MFESB | End User Device Refresh | Emergencies and safety | Replacement of end user computing devices and consolidation of devices where possible. | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - implementation | 2015-10-01 | 0 | 2018-06-30 | 1343000 |  |  | Green | Green | N/A | N/A | N/A | Progressive delivery, installation and retirement of devices | 2016-09-30
Q1-2016-17 | DFC0F938-9AD5-48E6-9206-C11D6E1C303F | Metropolitan Fire and Emergency Services Board | MFESB | Enterprise Resource Planning solution | Emergencies and safety | Replacement of existing SAP (financial management system) system that has reached end of life. (incl SES) | 2015-07-01 | Other – please specify | MFB Project Management Framework (PME) | In progress - pre-implementation | [11 empty] | Second Tender responses to shortlisted companies are currently being evaluated. | 2016-09-30
Q1-2016-17 | 20D91422-040A-4858-986F-18B73FFB974F | Monash Health | Monash H | Monash Children's Hospital Patient Entertainment System | Health | Implementation of a Patient Entertainment System (PES) for the new Monash Children's Hospital which provides access to services such as the internet, meals ordering , education services, and movie and television channels. | 2015-05-11 | PRINCE2 |  | In progress - implementation | 2016-06-01 | 0 | 2017-03-01 | 1649000 |  |  | Green | Green | Green | Green |  | Project is in progress | 2016-09-30
Q1-2016-17 | 210E4505-9127-40F2-A7E0-9FE7DECB4B21 | Monash Health | Monash H | Medical Grade Network | Health | Implementation of an enterprise wide wired and wireless data network to support the implementation of an Electronic Medical Record (EMR) system. | 2015-10-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning is in progress. | 2016-09-30
Q1-2016-17 | B299B052-58F6-4D7C-9825-07F649025FAB | Monash Health | Monash H | Healthcare Billing System Phase 1 | Health | Implementation of an enterprise billing system for selected services across Monash Health. | 2015-11-16 | PRINCE2 |  | In progress - implementation | 2016-04-01 | 202050 | 2017-02-01 | 1900000 |  |  | Green | Green | Green | Green |  | Project is in Progress | 2016-09-30
Q1-2016-17 | C943D2F6-1C32-49D0-8762-EC1C6FF81A1D | Monash Health | Monash H | Electronic Medical Record | Health | Implementation of an Electronic Medical Record (EMR) system, including clinical documentation, results viewing, and medications management | 2016-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project planning is in progress. | 2016-09-30
Q1-2016-17 | C27D0976-27AF-4844-AC85-13AF88B324C9 | Northern Health | NHS | EMR Project | Health | Implementation of an Electronic Medical Record at Northern Health including all sites | 2016-10-18 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project business case is progressing | 2016-09-30
Q1-2016-17 | 9F62B569-9844-4406-AA03-35C542783FCC | Parks Victoria | PARKSVIC | Customer Relationship Management solution (Pilot and Phase 1) | Environment and water | Implementation of a Customer Relationship Management solution to manage stakeholder data and migration of organisational areas and systems to the new platform. | 2015-07-01 | Agile |  | In progress - implementation | 2016-04-30 | 245033 | 2017-06-30 | 4716000 |  |  | Green | Amber | Green | Green | Green | The Pilot (Stakeholder Relations) was delivered 21st July 2016. This was 3 weeks later than initially planned and the program of work went to at-risk (Amber) whilst further planning was undertaken. Phase 1 discovery and planning was completed by end-August 2016 indicating delivery within acceptable timeframes and at original cost. This allowed the project to return to being on-track (Green). Phase 1 covers four functional areas: Visitor Information Centre, Scientific Research Permits, Volunteer Management and Commercial Agreements. Development of the Visitor Information Centre solution finished on time at end-September 2016 and is due for implementation mid-November 2016. Development and testing of the other three functional areas is presently on-track with implementation scheduled from February to June 2017. | 2016-09-30
Q1-2016-17 | 88EB2212-AC0C-4001-9396-3CFC81EA4523 | Peninsula Health | PenHealth | Rostering Time & Attendance | Health | Enterprise electronic Rostering system | 2015-05-01 | Other – please specify | Adaption of Prince II in conjunction with Vendors PM Planning | In progress - implementation | 2015-12-31 | 566654 | 2017-10-15 | 1847451 |  |  | Green | Amber | Green |  |  | The project is progressing to schedule. | 2016-10-01
Q1-2016-17 | 370BB806-42C5-4180-AAE9-9AD29FDB68F5 | Peninsula Health | PenHealth | Electronic Health Record - Clinical Documentation | Health | Clinical Documentation | 2016-10-01 | Other – please specify | Adaption of Prince II in conjunction with Vendors PM Planning | In progress - pre-implementation | [11 empty] | The project is in pre-implementation. A Purchase Order Contract (POC) has been signed with vendor. | 2016-10-01
Q1-2016-17 | 3F54D2D0-B807-4457-82D2-D5E816F05F1C | Peter MacCallum Cancer Centre | Peter Mac | Picture Archive and Communication System | Health | Implementation of a Radiology Picture Archive and Communication System (PACS) / Vendor Neutral Archive (VNA). | 2014-02-01 | PRINCE2 | Adapted to relevant scope of the project | Completed | 2015-05-20 | 77840 | 2016-07-18 | 1954070 | 2016-07-01 |  | Green | Green | Green | Green | Green | New PACS now live. | 2016-10-28
Q1-2016-17 | 1EFA6AD2-088C-4DC4-A098-741D63C68E65 | Peter MacCallum Cancer Centre | Peter Mac | Laboratory Information System | Health | Implementation of a common Laboratory Information System as an externally hosted fully managed service in collaboration with two other state public health services. | 2014-07-21 | Other – please specify | Overarching PRINCE2 approach with AGILE management of agency configuration and build | In progress - implementation | 2015-06-04 | 132268 | 2017-01-31 | 1669586 | 2017-06-30 | 1998392 | Green | Green | Green | Red | Red | Project progressing towards target delivery date. End date includes post go live support. | 2016-10-28
Q1-2016-17 | 64BF4A07-D43B-4E7C-A725-D5DB05182A4F | Peter MacCallum Cancer Centre | Peter Mac | Relocation Project | Health | As part of the broader Redevelopment program, the objectives of the Building ICT Program are to accept ICT systems and products, transition existing systems from Peter Mac to Parkville, ensure that users are familiar with the new technology, ensure that Peter Mac ICT can support the products in the future | 2014-09-18 | PRINCE2 | Adapted to relevant scope of the project | Completed | 2015-10-31 | 219969 | 2016-07-29 | 941098 | 2016-09-30 | 4003194 | Green | Green | Amber | Amber | Amber | End date includes post move support. | 2016-10-28
Q1-2016-17 | FBD35B2A-E0EE-47EB-A1F9-8076BF0A201C | Peter MacCallum Cancer Centre | Peter Mac | Precinct UR Number | Health | Unique Precinct UR number is required to support patient movement across the Precinct Hospitals at Parkville. | 2015-02-13 | PRINCE2 | Adapted to relevant scope of the project | In progress - implementation | 2015-10-30 | 176826 | 2016-11-18 | 3024816 | 2017-06-30 |  | Amber | Green | Green | Green | Red | Phase 1 and 2 implemented in production. Phase 3 progressing towards implementation. Implementation date revised due to Phase 4 scope being extended to include additional applications. End date includes post go live support. | 2016-10-28
Q1-2016-17 | 10814502-29DB-4E6F-A701-E5578656528B | Peter MacCallum Cancer Centre | Peter Mac | Clinical Viewer | Health | Access to clinical information across the Precinct Hospitals at Parkville is required for the new Clinical Service Operating Model. | 2015-08-24 | PRINCE2 | Adapted to relevant scope of the project | In progress - implementation | 2015-12-18 | 91453 | 2016-10-17 | 1106838 |  |  | Green | Green | Green | Green | Green | Precinct Clinical Viewer now live and post go-live activities underway. | 2016-10-28
Q1-2016-17 | F7F16506-281A-41DD-811F-0BAD6887C081 | Urban Renewal Authority | Places Victoria | PIMS | Property and planning | System that allows for the management of construction projects within a single system | 2014-10-01 | PRINCE2 | Agile | In progress - implementation | 2015-10-15 | 60000 | 2016-10-24 | 2500000 | 2017-01-23 | 2500000 | Green | Green | Green | Green | Green | First phase of implementation has successfully occurred and delivered 11 July. Second phase involves implementation of modules based on project delivery team needs with a staged implementation to Oct. Currently tracking to plan with no major issues. | 2016-09-30
Q1-2016-17 | E3E19E82-6DBC-4C66-9766-04CE45D2DB0C | Port of Melbourne Corporation | PoMC | Vessel Traffic Services Resilience Improvements | Transport and vehicles | Resilience critical replacement of two existing Vessel Traffic Services Radars and Voice Data Recorders. It is expected that the replacements will enhance Port of Melbourne Corporation's capability in delivering Vessel Traffic Services. This project precedes the Vessel Traffic Services Systems Upgrade project. | 2015-02-11 | Other – please specify | PoMC (PMBoK) | In progress - implementation | 2015-10-19 | 60000 | 2016-07-31 | 1700000 | 2016-09-30 | 1700000 | Green | Green | Green | Green | Green | Project remains on schedule and on budget. Installation and integration with the existing system completed and have been functioning satisfactorily. Project close out process now underway with Gate 6 Benefit Realisation to be completed and signed-off. Additionally, some spare parts are being delivered from overseas - expected shortly. | 2016-10-19
Q1-2016-17 | C0981DCE-AC0C-4F97-AB34-E1A5835C8179 | Port of Melbourne Corporation | PoMC | Vessel Traffic Services Systems Upgrade | Transport and vehicles | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | 2015-12-03 | Other – please specify | PoMC (PMBoK) | Initiated | [11 empty] | Project has been initiated and has achieved concept approval. The pre-implementation phase of the project has now commenced - A Project Consultant has been appointed and has now commenced the process of documenting the business and technical requirements for the project. The next major milestone will be the finalisation of the procurement approach. The implementation phase of the project is currently scheduled for commencement late FY2016-17. Planned implementation stage end date is currently scheduled for late FY2017-18. Current project budget is $8.2m. | 2016-10-19
Q1-2016-17 | 212D5A15-2DCB-42A5-BFFB-6038A079B5F0 | Public Record Office Victoria | PROV | Digital Archive Program | Government and economy | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2015-07-01 | 200000 | 2018-06-30 | 4062000 |  |  | Green | Amber | Green | Green | Green | The projects that were commenced last quarter are now completed as planned. Additional elements of the program are now being scoped in readiness for a market approach in 2017. | 2016-10-17
Q1-2016-17 | BF7990AA-E1D3-4AF4-862C-4960C8A9949B | Public Transport Victoria | PTV | Train SCADA (Electrol) Replacement | Transport and vehicles | Replacement of Electrol Train SCADA system - Telemetry Communication Network, and establish a disaster recovery centre and implementation of a new control monitoring system (CMS) for the Melb Underground Rail Loop (MURL). | 2009-02-06 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2010-06-04 | 500000 | 2016-07-30 | 30550000 | 2016-12-30 | 30550000 | Amber | Amber | Amber | Amber |  | Project is currently within budget. There are delays to the program due to interdependencies with external projects and the impacts of infrastructure construction. | 2016-09-30
Q1-2016-17 | 3097600A-919A-482B-89D7-DA90882BF77F | Public Transport Victoria | PTV | Regional Radio Communications Network | Transport and vehicles | The project involves modernisation of the following legacy systems; the train control centre (Centrol) Voice Communications Systems (VCS); the In-cab Communications Equipment (ICE) in the V/Line fleet; and the voice communications network service. | 2012-03-01 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2014-02-27 | 7250000 | 2018-04-03 | 65300000 | 2018-04-03 |  | Amber | Amber | Amber | Amber | Amber | A total of $65.3 million of funding was provided for the project, $43.852 of CAPEX and $21.448 of OPEX. Project is progressing and is currently within budget. Project is on schedule to deliver within the Business Case timeframes (by June 2019). | 2016-09-30
Q1-2016-17 | 0041F85B-F19A-4D4F-9D12-81F36DEF9C2D | Public Transport Victoria | PTV | Operator Payment System Modernisation | Transport and vehicles | Replace the PASS suite of programs (PASS Payments and Bus IT), myriad of spread sheets and manual processes related to operator contract and performance management and operator payments. Decommission of PASS Payments and Bus IT. | 2014-05-14 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-07-16 | 765000 | 2016-03-30 | 10000000 | 2017-03-30 | 5489000 | Amber | Amber | Amber | Amber | Amber | Project delivery is underway but was delayed during the contract execution period. The project has been re-baselined and minor slippage is being managed. This project is stage 1 of 4. | 2016-09-30
Q1-2016-17 | F1A28FC4-80F0-4117-A15F-0E55BB1A4165 | Public Transport Victoria | PTV | Special Event Management System | Transport and vehicles | The project will deliver a web-based cloud-based application designed to interface with data sources including bus, tram and train stops/routes, bus/tram/train timetables via Chronos (middleware), planned occupations from Operators, Base Maps, GIS spatial data from PTV libraries, patronage data from Marketing Access database, Road occupations from VicRoads. | 2014-08-05 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-05-18 | 104000 | 2016-09-23 | 1810000 | 2016-11-16 |  | Amber | Green | Green | Green | Green | The vendor has completed data migration and system testing. PTV testing and documentation updates are underway. The project is expecting a one month delay to accommodate additional changes to user guides and training materials etc. due to system design updates made following user acceptance testing. | 2016-09-30
Q1-2016-17 | 8E2C3A60-3C22-448D-B455-248EF1F86DCC | Public Transport Victoria | PTV | Timer Solution of Tram Fleet | Transport and vehicles | To purchase and install a pilot timer solution across the entire tram fleet (one per class) and to incorporate the use of timers in future tram installations. | 2014-08-27 | Other – please specify | PTV Investment Lifecycle | Postponed | [6 empty] | N/A |  |  |  |  | Project did not progress past value for money assessment and is to be formally closed out. | 2016-09-30
Q1-2016-17 | EEC2C527-849A-4B53-80BD-9D2AC3CDE6F0 | Public Transport Victoria | PTV | Delivering Real Time Train Information - Phase 1 | Transport and vehicles | Deliver real time Metro train information to customers via PTV and operator mobile apps, PIDs and via open access to data. | 2014-11-18 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-11-13 | 0 | 2016-09-19 | 2000000 | 2016-10-07 |  | Green | Green | Green | Green | Green | Project is progressing well against schedule and is currently within budget. All functionality has been delivered. The project is now conducting all required functional, performance and security tests before implementation. There has however been a two week delay in completion of the setup of the "To-be Production" environment. Go-live is now expected in early October 2016. | 2016-09-30
Q1-2016-17 | 900DD93B-437F-4BD7-BD3B-568C6ADB6E77 | Public Transport Victoria | PTV | Data Analytic Platform | Transport and vehicles | Provide PTV wide data access to enable the business to analyse, visualise, share and report data insights. | 2014-11-19 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-05-31 | 100000 | 2016-10-04 | 4780000 | 2017-01-31 |  | Amber | Green | Amber | Green | Amber | Project is currently progressing well against the schedule and the final code drop is on schedule to be received in October 2016. However the implementation end date has been re-forecast to provide for longer system and user acceptance testing and for system training to take place in the new year rather than prior to Christmas. | 2016-09-30
Q1-2016-17 | F9B591DD-3771-4B49-AFD0-BBFDCD2D60C9 | Public Transport Victoria | PTV | Vehicle Passenger Information System (VPIS) A & C Class | Transport and vehicles | Procure and implement a system using commercial-off-the-shelf (COTS) products to provide reliable and dynamic on-tram passenger information. | 2015-05-01 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-02-29 | 0 | 2017-05-30 | 8732000 | 2018-04-12 | 10160000 | Amber | Amber | Green | Green | Green | The project has been delayed due to an expansion of the project scope to include VPIS implementation in C2 class trams. This scope expansion has impacted the timeframes to execute the contract with the vendor. The project has also been provided additional funding based on the expanded scope and experiences of the VPIS rollout on B2 trams. Project delivering on schedule against the revised timelines. | 2016-09-30
Q1-2016-17 | FF2B5DFD-2557-4525-B2E6-3C5DF315690E | Public Transport Victoria | PTV | Time Table on Demand | Transport and vehicles | Establish authoritative information repository for each identified data set. This repository will form the single source of truth for PTV timetabling needs. Uplift to outdated technology (DIVA and EFA), introduction of new technologies to enable standardised information exchange with Operators. | 2015-06-19 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-12-09 | 150000 | 2016-06-29 | 4195000 | 2017-06-30 |  | Red | Amber | Green | Green | Green | The complexities of the system requirements, and interdependencies with other public transport information systems resolved into delivery challenges in October 2016. Concerns were identified about the output results and the main vendor's ability to deliver the necessary automation of the application required in a cloud environment. The project has already incurred delays and PTV is considering alternate delivery and funding options to minimise the risk of further delays or reduced scope delivery. | 2016-09-30
Q1-2016-17 | B04B01FB-75C3-4DC5-BDA3-26728F5808EC | Public Transport Victoria | PTV | Bus Information Improvement Project | Transport and vehicles | Develop common reference data model for Bus Information, improve stop data quality and completeness, empower operators to self-manage bus data and develop and establish a framework for bus performance monitoring. | 2015-07-19 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2015-12-18 | 20000 | 2016-07-29 | 1412000 | 2016-12-23 |  | Amber | Amber | Green | Green | Green | The project has been delayed whilst a Performance Monitoring issue was resolved and to address a missed database adjustment before the system can be fully operational. | 2016-09-30
Q1-2016-17 | 209855D5-316B-4FC8-98C9-0EB3DBF9D212 | Public Transport Victoria | PTV | Rail Industry Only (RIO) - Mobile and Handheld Radio Replacement | Transport and vehicles | Replace 500 existing mobile and handheld radios with new devices and update the supporting infrastructure to address the ACMA regulatory requirements to operate within the Harmonised Rail Industry Only (RIO) spectrum. | 2016-05-20 | Other – please specify | PTV Investment Lifecycle | Postponed | 2016-06-24 | 0 | 2016-12-07 | 1950000 | 2017-02-03 |  | Red | Green | N/A |  |  | Project has been paused pending identifying enough licences in the correct frequency range that can be used by Yarra Trams. This is being managed by Victrack with involvement from the PTV project team. Alternative options are being identified and all parties are working closely to determine the strategy that will be required moving forward. At the time of commencement of the project, the limitation of the licences was unclear. | 2016-09-30
Q1-2016-17 | C8BCC4C4-6590-4258-A4CA-93E6577ED584 | Public Transport Victoria | PTV | Train Control Monitoring System (TCMS) for South Morang and Hurstbridge | Transport and vehicles | To deliver a modern Train Control Monitoring System 'instance' at Epping to replace the standalone WESTCAD and SIGVIEW workstations and to support more efficient train control operations on the South Morang and Hurstbridge lines. | 2016-10-21 | Other – please specify | PTV Investment Lifecycle | Initiated | [11 empty] | Project has Chartered and is in the project development phase. | 2016-09-30
Q1-2016-17 | 00C1F30A-A205-4DF6-9EA1-FB421B3550F2 | Public Transport Victoria | PTV | PTV Intranet Update | Transport and vehicles | Redesign and review/develop/migrate content from PTV's existing intranet to a new cloud-hosted solution in order to enhance capability for collaboration, information and knowledge management. | 2016-10-21 | Other – please specify | PTV Investment Lifecycle | Initiated | [11 empty] | Project has Chartered and is in the early project development phase. | 2016-09-30
Q1-2016-17 | 90506C0B-9234-4580-91BA-0F3FAD7CD487 | Public Transport Victoria | PTV | Digital Train Radio System (DTRS) upgrades - Gateway GPRS Support Node (GGSN) and Lawful Interception Management System (LIMS) | Transport and vehicles | Upgrade, installation and commissioning of GGSN and LIMS at both the primary and back-up data centres. | 2016-06-24 | Other – please specify | PTV Investment Lifecycle | In progress - implementation | 2016-08-08 | 0 | 2016-12-12 | 3164223 |  |  | Green | N/A |  |  |  | Project is progressing to schedule and budget. | 2016-09-30
Q1-2016-17 | 7B9CF170-B52D-43E0-B11C-7D8F80BD0E42 | Public Transport Victoria | PTV | myki and PTV Website Integration and Development | Transport and vehicles | The project will include a complete website redesign focused on user experience, integration of the myki portal and the PTV website, a fully scalable website that renders to mobile devices, accessibility to WCAG 2.0 standards and integration with the PTV knowledge management system. | 2015-12-16 | Other – please specify | PTV Investment Lifecycle | In progress - pre-implementation | [11 empty] | Project is progressing to schedule and budget. | 2016-09-30
Q1-2016-17 | 69E81A8D-D604-414B-8EA9-38983ACAF241 | The Royal Children's Hospital | RCH | Electronic Medical Record Project | Health | Implement an integrated Electronic Medical Record to support the delivery of high quality, safe and sustainable healthcare. | 2012-07-01 | PRINCE2 |  | In progress - implementation | 2014-06-30 | 2306233 | 2016-12-31 | 45747763 | 2016-12-31 | 45747763 | Green | Amber | Green | Green | Green | As scheduled on 30 April 2016, system implemented to all areas of RCH. The project is now in the post go-live phase. Current activities include finalisation of project on schedule for December 2016 completion, transition to on-going support; and commencement of Benefits program. | 2016-09-30
Q1-2016-17 | 9BCE9086-FEFA-4F65-8B3B-134D771F80E4 | The Royal Victorian Eye and Ear Hospital | Eye and Ear | ICT Redevelopment Stage 3 Hardware Tender | Health | Fit-out of new IT infrastructure to support hospital redevelopment objectives | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2014-06-30 | 0 | 2018-12-31 | 1180000 |  |  | Green | Green | Green | Green | Green | Project progressing to schedule | 2016-10-10
Q1-2016-17 | C5C5EA10-5B30-4891-A4B4-DC13F806D5FA | The Royal Victorian Eye and Ear Hospital | Eye and Ear | Electronic Medical Record Project | Health | Implementation of further EMR modules to provide a clinical information system for the hospital. | 2016-08-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project progressing to schedule | 2016-10-10
Q1-2016-17 | 6E9A75AD-6936-4720-9CD3-278979DD766C | Royal Women' s Hospital | RWH | Clinical Viewer Replacement Project | Health | The existing clinical viewer, is being replaced at RWH. RWH objectives are to provide real-time, electronic, point of care imaging, pathology results and acknowledgement to facilitate efficient planning of patient care, enhance access to results for clinicians, minimize clinical risk and maximize clinician time. | 2015-09-22 | PRINCE2 |  | Terminated | 2015-10-14 | 76000 | 2016-07-05 | 1040422 |  | 0 | N/A | N/A | N/A | N/A | N/A | The Clinical Viewer Replacement project has been terminated by RWH due to the replacement solution not being functionally fit for purpose. RWH intend to continue operating with the existing clinical viewer solution until an appropriate replacement is acquired. | 2016-09-30
Q1-2016-17 | 7D730679-870B-4E34-BF28-9830A0EA99E9 | South West Institute of Technical and Further Education | SW TAFE | SWTAFE Smart Classroom - TSAF Funded | Education | To install 15 'smart classrooms' across the Institute Campuses along with a telephony and wifi upgrade. | 2015-09-24 | Other – please specify | SWTAFE | In progress - implementation | 2016-03-07 | 510561 | 2016-12-30 | 1639863 | 2016-12-30 | 2470000 | Green | Amber | Amber | N/A | N/A | Pilot smart classrooms have been tested and a further fixed classroom has been installed. Orientation training material is being developed and will be rolled out commencing 15 August and concluding with the project closeout phase in December 2016. The final 10 rooms will be installed between 8 Sept - 20 Sept. These installations will occur during term break and will enable further orientation to be delivered. | 2016-09-30
Q1-2016-17 | F45605DD-5216-4E6D-A8D6-6F39094645B9 | South East Water | SEW | Trade Waste Information System | Environment and water | The project will deliver a new solution for South East Water to manage our Trade Waste business. This new solution replaces a VB6 application and will enhance customer service by enabling mobility and improved analytical reporting | 2014-09-15 | Agile |  | Postponed | 2015-01-05 | 0 | 2016-12-12 | 1879878 |  |  | Amber | Amber | Amber | Amber | Green | The project will be postponed to review and optimise the business processes. The optimisation is expected to be completed in February 2017. | 2016-10-26
Q1-2016-17 | B1B47682-7C50-49C0-97AD-8E17CD1D7DFF | State Revenue Office | SRO | LPR#2 - Land Ownership and NOA (LOAN) | Government and economy | This project is part of the Better Revenue Management System program to redesign the Land Tax administration business processes to achieve operational efficiencies, improve effectiveness of managing land ownership data (using Notice of Acquisition - NOA information) and to extend the life of SRO's revenue management system. | 2015-09-17 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Pre-implementation activities concluded on 30 September 2016 and the project has moved into the IT delivery. | 2016-10-11
Q1-2016-17 | 6E0B5B53-9A3C-48C7-8EDA-E1CFEF7E14D1 | Transport Accident Commission | TAC | Claims Business Model | Transport and vehicles | The Claims Business Model program of work aims to deliver solutions that enables balance between claims management effort and liability management across the business, and through that, empowering clients , making it easier to work with the TAC, and improving the efficiency of the management of claims. | 2013-11-01 | PRINCE2 |  | In progress - implementation | 2014-06-30 | 704927 | 2018-06-30 | 39290751 |  |  | Amber | Amber | Green | Green | Green | Planning of program through to completion is in progress. The re base lined program will be presented at the December 2016 Board meeting. Completion of technical services tenders was completed in September 2016. The combination of these two processes will result in the status of Amber changing back to Green. Actual project expenditure to 30 September 2016 represented a favourable variance to budget. Current forecast anticipates that total project expenditure will not exceed approved funding of $39.99m. A fundamental component of the project was delivered in May 2016, demonstrating the expectation that the project remains on schedule to be completed by 30 June 2018. | 2016-10-26
Q1-2016-17 | EE466748-D9CB-4827-8D66-FA317634B247 | Transport Accident Commission | TAC | Integration Platform Refresh for TAC | Transport and vehicles | Joint project with WorkSafe to upgrade the Integration Platform to the latest version, which will also enable the consolidation (and decommission) of some of the older Integration Software products in use. | 2014-07-01 | PMBoK |  | Completed | 2015-08-31 | 620089 | 2016-06-30 | 313437.2 | 2016-07-31 | 558404 | Green | Amber | Amber | Amber | Green | The Integration Platform Refresh project had been aligned with the WebSphere Application Platform Refresh project. These projects had significant interdependencies and required a joint schedule for migration. The Integration Platform Refresh Project completed at end of July 2016. | 2016-10-26
Q1-2016-17 | B90383E6-B6EA-4C94-9CE4-3EB46982E6A8 | Transport Accident Commission | TAC | Enterprise Database Rationalisation (Stream2) | Transport and vehicles | This project is to uplift and rationalise the database platforms across both the TAC and WorkSafe. This will deliver improved performance and capacity and allow us to decommission legacy database systems across TAC & WorkSafe. | 2014-12-01 | Other – please specify | Other - Internally Developed framework | Completed | 2016-01-31 | 899904 | 2016-06-30 | 929262 | 2016-07-31 | 928207 | Green | Green | Green | Amber | Green | The project completed the TAC deliverables within the TAC approved budget at end July 2016. | 2016-10-26
Q1-2016-17 | D31393AB-7B6A-40ED-B864-1116ABFF5E25 | The Gordon Institute of Tafe | The Gordon | BlendED Learning - Technology Applications | Education | Creation of blended online learning resources for major courses offered by the Institute. Provision of supporting ICT infrastructure including an upgraded WiFi network at major campuses, improved access for BYODs, new lecture capture enabled classrooms; and providing additional computer resources to support a blended online learning model within the Institute. | 2014-12-01 | Other – please specify | Project Control group oversight. Reporting against Project Plan Phases and Deliverables. | In progress - implementation | 2014-12-01 | 0 | 2017-12-31 | 4658000 |  |  | Green | Green | Green | Green | Green | Project proceeding according to schedule. | 2016-09-30
Q1-2016-17 | E6921E38-5284-4018-9163-A2C934330ECB | Victorian Auditor-General's Office | VAGO | ERP Solution Replacement | Government and economy | Replace aging Components of existing ERP solution and provide additional functionality. | 2016-09-02 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business case development and strategic options analysis | 2016-10-28
Q1-2016-17 | F4FFFA37-46AC-42C5-A70C-A4B83DBCE884 | Victorian Building Authority | VBA | Business Systems Transformation - Phase (1) | Government and economy | The BST program is intended to progressively re-engineer VBA regulatory processes and implement new integrated applications which will replace legacy systems and manual processes, to: mitigate technology risk, enhance risk based regulation, reduce regulatory burden, increase efficiency and reduced cost; and, improve consumer outcomes | 2014-10-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 986248 | 2019-07-01 | 12375133 | 2019-07-01 | 12375133 | Green | Green |  |  |  | Initial business case was approved in April 2015. The revised business case (post market process) and proposed allocation of funding for stage (1) was tabled for VBA Board approval in mid-May. Vendor on boarding and commencement of delivery has commenced as at 1 July 2016 and the project is now in the design phase. | 2016-09-30
Q1-2016-17 | 4F0C9D77-471C-4AC2-A4DD-66053BA0124C | Victorian Ombudsman | VO | ICT Relocation to new premises | Government and economy | Various ICT projects such as infrastructure, desktop hardware, audio/visual, telephony and CenITex services to support and enable the relocation of the Ombudsman's office to Level 2, 570 Bourke St | 2016-02-01 | Other – please specify | Various - from waterfall to agile | In progress - implementation | 2016-02-01 | 0 | 2017-03-30 | 2000000 |  |  | Green | Green |  |  |  | Physical relocation on Monday 27 August, 2016 to new premises was successful. There are still various defect, system integrations and desktop Windows OS uplift that are being finalised. | 2016-10-27
Q1-2016-17 | 831734FC-8A3B-48C3-9421-FD2984BAE38F | Victoria Police | VicPol | Parole System Reform | Law and justice | Undertake system modifications to support the introduction of the Corrections Amendment (Breach of Parole) Act 2013 and the adoption Measure 11 of the Callinan "Review of the Parole System in Victoria" into Victoria Police. | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2014-11-01 | 0 | 2016-03-31 | 2005700 | 2016-12-30 | 2000000 | Amber | Green | Green | Green | Green | Victoria Police (VP) and Corrections Victoria (CV) have jointly resolved the approach to implement Multiple Custody Types. VP is working to upgrade the systems and processes relating to breaches of parole within the shortest timeframe possible. | 2016-09-30
Q1-2016-17 | 5CE0DDC4-65F9-4832-8A3E-258484DF6E2D | Victoria Police | VicPol | PIPP Transformation | Law and justice | To provide police with the ability to access the information they need securely, where and when they need it. This is about delivering benefits to the frontline, freeing up police from time consuming administrative tasks. | 2013-07-01 | PRINCE2 |  | In progress - implementation | 2015-06-30 | 0 | 2017-03-30 | 10919000 |  |  | Green | Amber | Green | Green | Red | The final business case for PIPP Transform is under development for submission in December 2016 and subsequent project closure. | 2016-09-30
Q1-2016-17 | B9D633EA-D960-4138-80DC-279DD4950271 | Victoria Police | VicPol | PIPP Sustain | Law and justice | The PIPP Sustain project will address immediate issues to maintain the performance of LEAP and Interpose Victoria Police information systems to enable the commencement of planning for longer-term reforms to these systems and processes. | 2013-07-01 | Other – please specify | IT PMO Project Management Framework | In progress - implementation | 2013-06-30 | 0 | 2015-12-31 | 12301000 | 2017-06-30 | 12301000 | Green | Red | Amber | Green | Red | Interpose 2.2 upgrade released to production in June 2016. A minor enhancement release is planned to complete this activity and is the cause of the revised implementation date. Delivery remains within budget. | 2016-09-30
Q1-2016-17 | 7B8DCA81-5A8F-4F5B-A85D-98B488D9572D | Victoria Police | VicPol | Timely Warrants | Law and justice | Deliver the technical system changes including the development of: 1.1 - Central Brief Storage System; 1.2 - Updates to LEAP Warrant Management to and from Courts Victoria; 1.3 - Changes to the EWOK system include printing of electronic warrants. | 2014-12-17 | PRINCE2 |  | Completed | 2015-07-30 | 0 | 2015-12-30 | 2167000 | 2016-08-31 | 2167000 | Green | Red | N/A | N/A | N/A | Project Completed Central Brief Storage System (CBSS) successfully implemented and in Production. | 2016-09-30
Q1-2016-17 | CD1CD84B-7B9A-45AC-BF36-80217E2EF216 | Victoria Police | VicPol | BlueConnect - Mobile Technology | Law and justice | Handheld, mobile devices to put critical information into the hands of frontline police and allow them to feed it back into the organisation’s intelligence from the field. | 2015-11-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 73569000 |  |  | Amber | N/A |  |  |  | Two RFTs have been released to the market and response evaluation and vendor selection is underway. Initial capability for a limited number of users is targeted for Q2 2017 with completion of full deployment remaining achievable by June 2019. | 2016-09-30
Q1-2016-17 | 96298933-1BE6-432C-8592-DE0D8059B6EB | Victoria Police | VicPol | BlueConnect - Intelligence Management | Law and justice | A new intelligence capability to bring together Victoria Police’s multiple data sources to deliver quick, easy access to intelligence to better inform police. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 82644000 |  |  | Green | N/A |  |  |  | The RFT has been released to the market and response evaluation and vendor selection is underway. Initial capability is forecast to be delivered to Intelligence Analysts in July 2017. | 2016-09-30
Q1-2016-17 | DC0C1FE8-AEFA-45AB-974C-7F1EA95D950D | Victoria Police | VicPol | Body Worn Camera (BWC) | Law and justice | Victoria Police will procure and deploy BWCs capable of capturing direct and objective audio and video face-to-face interactions, in an operational context between police members and the public, and real-time capture of video evidence of the scene of an incident. | 2015-07-01 | PRINCE2 |  | In progress - implementation | 2016-06-30 | 0 | 2021-06-30 | 42591900 |  |  | Green | N/A |  |  |  | Recruiting project staff, completed Project Management Plan. | 2016-09-30
Q1-2016-17 | 350BE61D-B129-42F0-961C-D858ED208609 | VicRoads | VicRoads | Payment Card Industry (PCI) Program | Business and industry | VicRoads has a program of works to meet the required compliance under the PCI-DSS merchant banking scheme to the 3.1 standard (moving to 3.2 August 1st 2016) | 2014-01-10 | Other – please specify | Waterfall supported by prince2 | In progress - implementation | 2015-12-24 | 600000 | 2016-11-30 | 3000000 | 2017-12-30 | 3000000 | Green | Green | Amber | Amber | Green | The project is on track for delivery in December 2017 as agreed by the Project Authority and Westpac. The Project is currently progressing with the remediation of the various payment channels and the separation of the payment environment from the overall VicRoads network. Opportunities to improve customer service and simplify compliance overheads by providing more transactions online are being implemented. | 2016-09-30
Q1-2016-17 | 66415365-BA83-4FD3-A39F-C819A9411D4D | VicRoads | VicRoads | Connect - Finance and Payroll upgrade | Transport and vehicles | This project is to upgrade VicRoads core finance & payroll system to provide a supported, cost-effective system that aligns VicRoads for future change, provides opportunities for process improvement and reduces risk of system failure. | 2014-10-09 | PRINCE2 |  | In progress - implementation | 2016-02-01 | 192000 | 2017-05-01 | 5511000 | 2017-05-01 | 5398000 | Green | Green | Green | N/A | N/A | The project is on track for delivery. Vendor is working in VicRoads to conduct a software version upgrade from Ellipse version 6.3.2 to Ellipse Version 8.7. Detailed Functional Solution Design docs scheduled for delivery mid Nov 2016. Unit Testing, System Testing, and System Integration Testing planning underway. | 2016-09-30
Q1-2016-17 | DDCE6B02-4DF3-4E93-BE4F-AD4F8B35372C | VicRoads | VicRoads | R&L IT Systems Transformation (Stage 1) | Transport and vehicles | This comprises of two components; critical remediation of current back end systems as a result of the RandL pause and cancellation; and Proof of Concept and planning to transform back end VicRoads IT systems that support registration and licencing services (R&L). | 2015-07-01 | Agile |  | Completed | 2015-11-30 | 0 | 2016-06-30 | 4500000 | 2016-09-30 | 4500000 | Green | Green | Green | Green | Green | Remediation of Critical Legacy systems is complete. Legacy Back-end systems Proof of Concept is complete. R&L IT Systems Transformation (Stage 2) Commenced based on findings of stage 1. | 2016-09-30
Q1-2016-17 | 06764DA4-CAB2-46AF-94D2-AFB343489106 | VicRoads | VicRoads | Asset Maintenance Reporting | Transport and vehicles | Asset Maintenance Reporting is being established to integrate various VicRoads road and asset maintenance related datasets to deliver compliance reporting and analytics that support effective road network and asset planning. | 2015-10-24 | Agile |  | In progress - pre-implementation | [11 empty] | This project will be delivered in five phases, with phase 1 now complete. Phase 2 finalising build phase. Phase 3-5 requirements are complete and about to go into build phase. | 2016-09-30
Q1-2016-17 | 58F9F700-240D-4A11-B898-27BB1B398A3C | VicRoads | VicRoads | Electronic Document Records Management System (EDRMS) Upgrade | Business and industry | A back-end systems upgrade of VicRoads' current Electronic Document Records Management System (EDRMS) to the vendors OpenText (Content Suite). The key objectives are to provide a more robust and supported platform. | 2015-11-26 | PRINCE2 | Waterfall supported by prince2 | In progress - implementation | 2015-11-20 | 115000 | 2016-10-30 | 2150000 | 2016-12-30 | 2150000 | Green | Green | Green | Green | Green | User Acceptance Testing (UAT) is in progress. Issues identified in the UAT is being fixed by the vendor. Additional UAT is been planned for October. End delivery date will be based on outcome of the successful testing and change management activities. | 2016-09-30
Q1-2016-17 | 8E3DBEF4-6A94-4F88-83DE-CE4DE2EEFE39 | VicRoads | VicRoads | ICT/ITS Infrastructure Transformation | Business and industry | This project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support VicRoads current and future ICT and Intelligent Transport System requirements. | 2016-05-09 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Expression of interest has been released to the market on 20 July 2016. The EOI evaluation plan is complete and the collaborative dialogue phase is now in progress. Pre-implementation activity is scheduled to finish by February 2017. | 2016-09-30
Q1-2016-17 | 1CB5876A-3C65-4438-9495-5EC79BD4A7C1 | VicRoads | VicRoads | R&L Digital Services Transformation (Stage 2) | Transport and vehicles | Digital Services Transformation Stage#2 continues to rollout key VicRoads transactions online including Individual and partner transactions, Organisation Portal and refunds/ cancellations | 2016-05-30 | Agile |  | In progress - implementation | 2016-06-30 | 0 | 2017-06-30 | 12523000 |  |  | Green | Green |  |  |  | Design & Build for Organisation Portal commenced. Design for enhanced payments capabilities, registration enhancements and additional Individual and partner transactions is in progress. Rescheduling of some project activities required due to impacts of PCI Compliance . | 2016-09-30
Q1-2016-17 | C5289C03-B1CD-452A-8FA6-77335FB7B9FD | VicRoads | VicRoads | R&L IT Systems Transformation (Stage 2) | Transport and vehicles | R&L IT Systems Transformation Stage#2 comprises initiation activities for the R&L Systems Back-end Transformation which includes Business Case Development for ERSC submission, Project specification and planning activities for the transformed system | 2016-07-01 | Agile |  | Initiated | [11 empty] | Business Case and Project Specification has been developed. Development of target system architecture and associated design documentation is underway. Project estimates are being confirmed against latest project documentation. | 2016-09-30
Q1-2016-17 | C133D9C6-7A58-4AE6-B676-6B66FB6F2B21 | VicRoads | VicRoads | Registration System Upgrades | Transport and vehicles | This initiative comprises of improvements to R&L front end and back end systems to provide improvements to customer service and payments options. | 2016-07-01 | Agile |  | In progress - implementation | 2016-07-31 | 0 | 2017-06-30 | 7350000 |  |  | Green | Green |  |  |  | Design and build activities for improved customer service and payments capabilities have commenced. | 2016-09-30
Q1-2016-17 | DAAE32BD-136F-48C1-BCE8-719A044943E5 | VicRoads | VicRoads | Sydney Coordinated Adaptive Traffic System (SCATS) Connectivity Migration Project | Transport and vehicles | Supply, Install and Manage the communication service for all the Managed Traffic Signal Sites. Supply, Install and provide a communication service for all unmanaged Traffic Signal Sites. | 2016-09-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project progressing on track as per baselined schedule. Market engagement Phase 1 - Expression of Interest (EOI) underway. Phase 2 - Preparation for Request for Tender (RFT) is in progress and is scheduled to be released in November 2016. | 2016-09-30
Q1-2016-17 | 02530175-FEA5-498A-AC9C-506FA050D66B | VicRoads | VicRoads | CityLink Tullamarine Widening (CTW) Section 3 Project | Transport and vehicles | This project includes the upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals). It provides integration, testing, and configuration of ITS devices to communication network and control systems and upgrade of backend systems and infrastructure to support the managed motorway. | 2015-10-01 | PRINCE2 |  | In progress - implementation | 2016-03-01 | 238683 | 2017-12-31 | 12591000 | 2017-12-31 | 12591000 | Green | Amber | Green | Green | Green | The project is on track to be delivered by December 2017. Commenced the review of solution design for STREAMS enhanced Center to Center. Development of STREAMS Enhancement requirements for release 1 is underway. | 2016-09-30
Q1-2016-17 | 15CBBB50-AF2E-42B9-AF08-181D3313D4DA | VicRoads | VicRoads | CityLink Tullamarine Widening (CTW) Section 1 & 2 Project (M80 Upgrade ) | Transport and vehicles | This project includes the integration, testing and configuration of ITS devices to communication network and backend control systems, provide upgrade of STREAMS (core ITS system for monitoring and control of field devices installed other than traffic signals) and infrastructure to support the managed motorway. | 2016-07-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Review of various design packages submitted by civil team is ongoing. Project Initiation Document is being reviewed .Project plan is being developed. | 2016-09-30
Q1-2016-17 | 24DBC2E8-C9E8-4024-84E3-6644EA8507AD | VicRoads | VicRoads | Dynamic Variable Speed Limit (DVSL) Project - Phases 2 & 3 | Transport and vehicles | The development of a new DVSL system integrated with Coordinated Ramp Signal and Lane Use Management System to maximise freeway capacity, minimise flow breakdown and improve traffic safety in congested conditions. | 2016-06-30 | PRINCE2 |  | Initiated | [11 empty] | Awaiting the outcomes of the benefit realisation evaluation from Phase 1 work prior to starting Phases 2-3. | 2016-09-30
Q1-2016-17 | 8F2A88A3-F446-4468-858F-2D9EE0F3A80C | VicRoads | VicRoads | Monash Freeway Upgrade (MFU) Project | Transport and vehicles | The project includes the integration, testing and configuration of ITS devices to backend control systems and communication network, provides new communication network and upgrade of backend systems and infrastructure to support the managed motorway. | 2016-06-30 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Integrated program between Intelligent Transport System (ITS) and civil program is being finalised. Reviewing various management plans and design packages submitted by civil team is in progress. | 2016-09-30
Q1-2016-17 | 53D79719-0C8E-475D-A1FA-CC76B22B27FE | Victorian Rail Track | VicTrack | VicTrack Telecommunications Service Management System (TSMS) Implementation | Transport and vehicles | To implement a new service management system for the Telecommunications group to replace the existing tool that is end of life | 2014-07-01 | Other – please specify | VicTrack Project Management Framework | Postponed | 2015-09-24 | 430000 | 2017-04-12 | 1770000 | 2017-06-28 | 2122303 | Amber | Amber | Green | Green | Green | Project Steering Committee decided to place this project on hold pending a review. An external consultant has been engaged to deliver an options paper and a recommendation on next steps. The delivery Contractor will be interviewed by our consultant to incorporate their feedback before finalising a recommendation report to the VicTrack Steering Committee. | 2016-09-30
Q1-2016-17 | E0A097AE-85FC-4CA3-A69A-D2A00D3DD23C | Victorian Rail Track | VicTrack | Network Transformation - IP/MPLS Reference Design Project | Transport and vehicles | Primary deliverable is a Reference Design that describes a future vision for a single IP/MPLS based network to replace VicTrack’s current seven Telecommunications Networks. | 2016-01-27 | Other – please specify | VicTrack Project Management Framework | In progress - pre-implementation | [11 empty] | Project completed the evaluation of the RFT responses up to the shortlisting stage. Project team plans to complete shortlisting of preferred vendors and make recommendation to award in late October 2016 or early November 2016. | 2016-09-30
Q1-2016-17 | A7965C46-BFF4-4EBC-B7AA-C00516D1330C | Victorian Rail Track | VicTrack | Network Transformation - Analogue Gateway | Transport and vehicles | The project scope is to go through an RFT process to identify an analogue gateway device(s) that is flexible to allow combinations of different analogue interface types on as need basis. | 2016-02-02 | Other – please specify | VicTrack Project Management Framework | In progress - pre-implementation | [11 empty] | The analogue gateway project is tracking to its forecast completion date of 30 November 2016 and is on track to achieve its budget of $1.8M. The project has completed unit testing, and commenced system testing. Project team plans to complete system testing and commence application testing in October 2016 | 2016-09-30
Q1-2016-17 | 9B79AB3D-E162-4537-A2BF-27552C85CFDA | Victoria Legal Aid | VLA | Mobile Workforce (Desktop Replacement) | Law and justice | Replacement of current computer, iPad and PABX with single device | 2015-07-01 | PRINCE2 |  | Completed | 2015-11-30 | 150000 | 2016-08-30 | 1480000 |  |  | Green | Green | Green | Green |  | The project has been completed and closed. | 2016-10-14
Q1-2016-17 | CB1A0B60-3D33-481E-831B-9EFAB2DEFE14 | V/Line pty Ltd | V/Line | V/One Phase 2 | Transport and vehicles | Implementation of HSE, Contract Management and Project Management into V/Line's ERP system | 2014-04-01 | Agile |  | In progress - implementation | 2015-06-30 | 11300000 | 2016-12-30 | 3455000 |  |  | Green | Green | Amber | Green | Green | Currently on time and on budget | 2016-10-25
Q1-2016-17 | 9683AA7B-6F46-4705-A126-D1C60D4E1BE2 | V/Line pty Ltd | V/Line | Budgeting and Forecasting Tool | Transport and vehicles | Implementation of a budgeting and forecasting tool | 2016-04-30 | Agile |  | In progress - implementation | 2016-04-30 | 0 | 2016-06-30 | 1200000 |  |  | Green | Green | Green | N/A | N/A | Currently on time and on budget | 2016-10-25
Q1-2016-17 | 8BED38EF-FE3E-4495-BC7E-F3FA2C3D2C01 | V/Line pty Ltd | V/Line | Rail Information and Operations System | Transport and vehicles | Replacement of some of V/Line's Day of Operations Systems | 2016-06-15 | Agile |  | Initiated | [11 empty] | Currently out to the market with a public EOI | 2016-10-25
Q1-2016-17 | D780935B-FC42-406A-998B-D27F4FECEEED | Victorian Managed Insurance Authority | VMIA | Risk Scorecard Project | Government and economy | Development of a WoVG online Risk Maturity Assessment Tool. The tool will support the Victorian Government Risk Management Framework agencies in conducting an online self-assessment of risk management within their organisations. | 2015-10-15 | Other – please specify | Waterfall | In progress - pre-implementation | [11 empty] | Responses received following an approach to market is that the total cost of the project is under $1 million. As the cost of the project is under $1 million it is out of reporting scope and therefore will be removed from the next quarter report. | 2016-10-31
Q1-2016-17 | 51F0DD75-C48D-4116-BC1B-B746A0B52B18 | Victorian Managed Insurance Authority | VMIA | DBI IT Platform upgrade | Government and economy | Upgrade of VMIA's Domestic Building Insurance claims and policy management system. The upgrade is being undertaken to drive improvements and efficiencies through the delivery of an integrated technology platform for the distribution and management of domestic building insurance. | 2016-04-19 | Agile |  | In progress - pre-implementation | [11 empty] | Responses from a selective request for quotation were received and evaluated. Proof of concept implementation is in progress as at 30 September 2016. | 2016-10-31
Q1-2016-17 | 1E2E4EA4-B729-40AA-874F-FEC6177162EE | Victorian Registration and Qualifications Authority | VRQA | VRQA State Register CRM Upgrade | Education | The State Register system is used by the VRQA for the registration of education and training providers, including schools, Vocational Education and Training, and Overseas Secondary Student Exchange Organisations. The project aims to upgrade the current CRM platform to provide improved functionality to support the VRQA’s ongoing business functions. | 2014-06-16 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Business Process Improvement workshops have been completed and identified opportunities are being considered for inclusion. An agreed timeframe for delivery is being developed based on business process changes to be included in the project | 2016-09-30
Q1-2016-17 | 9E7A0013-0E70-496E-B229-2FA0B18A7599 | Victorian Registration and Qualifications Authority | VRQA | EPSILON | Education | The EPSILON project will replace the existing legacy system "DELTA" to enable VRQA to meet its legislative obligations with respect to apprentices and trainees. | 2014-07-07 | PRINCE2 |  | In progress - implementation | 2016-02-29 | 373000 | 2016-08-22 | 2441656 | 2017-07-17 |  | Amber | Green | Green | Green | Green | System development is nearing completion and testing activities are continuing. A dependency on the Commonwealth’s Australian Apprenticeships Management System (AAMS) project, which has been delayed, will require the EPSILON project to re-schedule its release time frame. The project is currently completing an impact analysis to estimate the cost and schedule impact of the AAMS delay. | 2016-09-30
Q1-2016-17 | 497B1254-6F84-40F4-B994-6F6126E46989 | Wannon Region Water Corporation | Wannon Water | IT Infrastructure Upgrade | Environment and water | To ensure currency and to provide adequate computing capacity and storage platform for WW business systems | 2016-01-01 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | The project is at the option investigation stage. | 2016-10-24
Q1-2016-17 | 78565F2D-B3FE-44E5-8E29-2D3EF03A3A0E | Western Health | WH | Western Health Electronic Medical Record (EMR) Project | Health | Implementation of the Statewide Electronic Medical Record (EMR) Solution to provide a clinical information system for the hospital | 2015-08-19 | PRINCE2 |  | In progress - pre-implementation | [11 empty] | Project pre-implementation and planning activities are progressing to schedule | 2016-10-24
Q1-2016-17 | AF619CB7-77DB-495D-BE54-9B4ED4B62D2D | William Angliss Institute | WAI | Access Angliss | Education | Project is to mature e learning offerings and delivery for the Institute by uplifting the Information Technology infrastructure foundation underpinning the Institute's delivery and administration, and also upgrading e learning tools and staff capacity and capability in utilising these tools | 2015-06-30 | Other – please specify | Streamlined Prince2 | In progress - implementation | 2015-09-30 | 0 | 2016-06-30 | 4955000 | 2016-12-31 | 4955000 | Green | Green | Amber | Amber | Red | Project has been completed with some additional fine tuning to occur. Substantial progress has been made across all subprojects comprising the Project - including completion of upgraded network switching environment, new Storage Area Network, network gateway solution (Palo Alto), servers and Virtual Student Desktops as IT infrastructure foundation work. Near-completion of video capture technology (Echo 360), creation of a multi media centre and training programs in content capture and elearning to be customised. In addition, final project activity will involve an externally facilitated change management program to pilot groups to ensure maximum activation of all staff and teaching staff in particular. | 2016-09-30
Q1-2016-17 | 5F80910B-8B8A-4A46-B3DA-2D2D5D02CFBC | WorkSafe Victoria | WSV | VMware 5 Migration | Government and economy | The VMware 5 project is upgrading the Virtualisation Server Platform (VMware) from a mixture of older non supported software versions to a current vendor supported software version. | 2014-07-01 | PMBoK |  | In progress - implementation | 2015-11-30 | 597295.47 | 2016-09-30 | 884383 | 2017-01-31 | 1098383 | Green | Green | Green | Green | Green | The majority of the systems have been migrated, the remaining systems are being migrated in the October - December 2016 period. Systems and project dependencies and development complexity caused timing and budget impact. | 2016-09-30
Q1-2016-17 | C985DC72-C877-475A-9189-AA80C5D7B729 | WorkSafe Victoria | WSV | Integration Platform Refresh for WorkSafe | Government and economy | The Integration Platform Refresh project will upgrade the platform to the latest vendor-supported versions of the Integration Services Platform. | 2014-07-01 | PMBoK |  | Completed | 2015-08-31 | 620089.13 | 2016-06-30 | 313437.2 | 2016-07-31 | 573999.2 | Green | Amber | Amber | Amber | Green | The project has successfully completed. | 2016-09-30
Q1-2016-17 | DDF6B9FA-8C1A-4FF8-9D9C-45F701F7C75F | WorkSafe Victoria | WSV | Portal & Intranet Services Upgrade Project | Government and economy | The project will upgrade the legacy IBM Portal, Intranet and Web Content Management systems to supported products and platforms. | 2014-07-21 | PMBoK |  | In progress - implementation | 2016-04-30 | 323226 | 2016-12-31 | 728834 |  |  | Green | Green | Green | Green | Green | Implementation/build phase of the project commenced in May 16. Intranet and Portal content development and build completed. Testing and deployment scheduled. | 2016-09-30
Q1-2016-17 | 4CA01AF3-5A25-497D-B379-FF49A9DEFC18 | WorkSafe Victoria | WSV | WebSphere Application Platform Refresh | Government and economy | The upgrade of IBM WebSphere Application Server software platforms to the latest supported version. | 2014-09-01 | PMBoK |  | In progress - implementation | 2015-08-31 | 713847.43 | 2016-10-31 | 792135.51 |  | 1217167 | Amber | Green | Amber | Green | Amber | Project variance caused by dependency impacts. The project is currently tracking to the revised budget. | 2016-09-30
Q1-2016-17 | AC034513-A73B-4CA5-89C8-C0C9F3C4D626 | WorkSafe Victoria | WSV | Agent Contract 2016 (IT Component) | Government and economy | WorkSafe's is renewing the contract with it's Insurance Agents. | 2014-10-01 | PMBoK |  | Completed | 2016-03-31 | 306903.71 | 2016-09-30 | 1325269 |  |  | Green | Green | Green | Amber | Green | The project has successfully completed. | 2016-09-30
Q1-2016-17 | ECE53766-9848-46FA-99E9-DF0BF34EA8FE | WorkSafe Victoria | WSV | Enterprise DB Rationalisation (S2) | Government and economy | The project will upgrade the legacy hardware and software database platforms to current vendor supported platforms. | 2014-12-01 | PMBoK |  | Completed | 2016-01-31 | 902808.1 | 2016-07-30 | 1765203.83 |  |  | Green | Green | Green | Amber | Green | The project has successfully completed. | 2016-09-30
Q1-2016-17 | C3727867-4771-40CB-94A3-D1BFBAA10C87 | WorkSafe Victoria | WSV | TRACCtion (WorkSafe ACCtion Replacement Project) | Government and economy | The feasibility study and high level planning for the possible transition off WorkSafe's Mainframe legacy systems. | 2015-12-01 | PMBoK |  | Completed | 2016-09-29 | 1483736 | 2016-09-30 | 0 |  |  | Green | Green | Green | Green | N/A | The feasibility study work completed in September 2016. | 2016-09-30
Q1-2016-17 | 226212B6-FB10-429D-B510-EEE51B71F2A5 | WorkSafe Victoria | WSV | Digital Claims File | Government and economy | The electronic document management system which is currently used for Invoices and Certificates of Capacity will be expanded to include all other Claims File documents. | 2015-07-01 | PMBoK |  | In progress - implementation | 2016-08-31 | 1246158 | 2017-12-31 | 4753842 |  |  | Green | Green | Green | Green | Green | The project remains on track and development is progressing well. | 2016-09-30
Q1-2016-17 | 5884FC74-66D3-4FCD-B1F0-A6F6DCCB2DDA | Yarra Valley Water | YVW | Project ENGAGE | Environment and water | Implementation of an Integrated Contact Centre Service to provide Yarra Valley Water customers with a choice of contact channels. | 2015-04-24 | PRINCE2 |  | In progress - implementation | 2016-04-01 | 347000 | 2016-09-30 | 1422900 | 2017-03-14 | 1422900 | Green | Green | Amber | N/A | N/A | Release two (2 of 4) was implemented on 20th October as scheduled and has delivered routing services to the business; call recording, workforce optimisation functionality, and self-service to the public. Design and planning for the third release is underway. | 2016-10-15
Q1-2016-17 | A1F0BB0F-0CFD-45DF-9086-6CE531C56C9F | Yarra Valley Water | YVW | Customer Communication & Management (CC&M) Phase 3 | Environment and water | Implement in-house production of bills ready for print to reduce the dependency on external providers. | 2015-06-26 | Agile |  | In progress - implementation | 2016-01-26 | 0 | 2016-06-24 | 1102800 | 2017-02-28 | 1102800 | Green | Green | Green | Green | N/A | Substantial business benefit has been derived from Print Ready Bills, which was delivered June 2016. Print Ready Letters is scheduled for release in November 2016 and Bill Archival and Retrieval is now scheduled Feb 2017. The project is tracking to budget. | 2016-10-15
Q1-2016-17 | A6CE860F-C61C-4EAE-B20D-F57BF53D9CA4 | Yarra Valley Water | YVW | Upgrade Yarra Valley Water Website | Environment and water | Upgrade the YVW Website to resolve technical limitations, meet regulatory requirements, mitigate security risks, adopt a platform that supports responsive design, and improve website functionality. | 2015-07-27 | Agile |  | In progress - implementation | 2016-07-05 | 561000 | 2016-11-01 | 1303000 |  |  | Green | Green | N/A | N/A | N/A | Pre-production site released for staff feedback 17th October 2016. Implementation date on track for weekend of 30 Oct 2016. Scheduled to go live to customers by 1st November 2016 | 2016-10-15
Q1-2016-17 | A6425E12-3672-4792-8E17-EA647A652A0D | Department of Justice & Regulation | DJR | Rostering for Prisons | Law and justice | Procurement and implementation of a rostering system that assists prisons to effectively and efficiently meet their staffing, management and reporting needs. | 2011-11-14 | Other – please specify | Project Management Excellence | In progress - implementation | 2013-02-04 | 0 | 2015-06-30 | 1396882.28 | 2017-09-30 | 1396882.28 | Green | Green | Green | Amber | Red | Implementation activities at prisons are underway. Work is also in progress to address existing Telstra infrastructure constraints to ensure the required level of performance. | 2016-10-13
Q1-2016-17 | 8A47D6A2-0453-49CE-99FE-FDFD9C116C7B | Department of Justice & Regulation | DJR | LaGIS - Liquor and Gambling Information System Project | Law and justice | The Liquor and Gambling Information System (LaGIS) aims to improve the efficiency of the Victorian Commission for Gambling and Liquor Regulation's regulatory processes by delivering an integrated system for licensing and compliance. | 2012-02-22 | Other – please specify | Project Management Excellence | In progress - implementation | 2012-05-31 | 344816.04 | 2015-12-22 | 11820849.01 | 2016-12-02 | 12621773 | Green | Amber | Amber | Red | Red | Commenced User Acceptance Testing and planning for deployment in December. | 2016-10-12
Q1-2016-17 | 06067601-2D18-48E3-8F60-71489A6AA73F | Department of Justice & Regulation | DJR | Mobile Camera Replacement (MCR) Project | Law and justice | MCR Project is the procurement of a replacement mobile camera system for the IMES business unit. The mobile camera system is the key component of the mobile camera service provided to the State by Serco Traffic Camera Services. | 2012-12-03 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-02-19 | 1568992.5 | 2015-12-21 | 0 | 2017-06-30 | 0 | Green | Green | Green | Green | Green | The procurement phase has been extended to include the Pilot Stage, which has commenced. | 2016-10-19
Q1-2016-17 | B65282BF-398B-481C-A821-E4AAAAC6B0BC | Department of Justice & Regulation | DJR | Upgrade project - Electronic Document and Records Management System (eDRMS) Upgrade | Law and justice | TRIM is DJR's electronic document and records management system (eDRMS). It requires an upgrade from v6 [last installed 2008] to v8.2, being compatible with Windows 8.The project is in the development environment stage, close to a pre-production environment with go-live likely this calendar year. | 2013-02-26 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-03-25 | 2020139 | 2016-07-31 | 3470677 | 2017-03-13 | 3470677 | Green | Green | Green | Green | Green | The project is in pre-production stage and testing is underway. The deployment period will be complex and will commence in January 2017. | 2016-10-17
Q1-2016-17 | D4183B03-BEA3-4423-A3BD-D425C03B60F7 | Department of Justice & Regulation | DJR | Win 8 Desktop Upgrade Project | Law and justice | Win 8 Upgrade to replace Win XP DJR desktops | 2013-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2013-12-13 | 2800000 | 2015-12-31 | 5400000 | 2016-11-30 | 4105000 | Green | Amber | Green | Amber | Green | The project is 97% complete and in the final stages of clean up. | 2016-10-18
Q1-2016-17 | CA3494BE-4208-47F0-A8FF-0AB9E0756753 | Department of Justice & Regulation | DJR | ACMA Compliance | Emergencies and safety | This project moves five agencies from their existing radio systems onto shared, multi-agency radio systems, in order for the agencies to comply with new ACMA regulations. The project also includes the procurement of new radio terminals and associated services under a state-based managed services contract. | 2013-07-01 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | Negotiations are continuing with the State's preferred Managed Service Provider. Funding issues are being addressed. | 2016-09-30
Q1-2016-17 | BB8F3133-4BC8-414B-AE5B-25A4ADB96F23 | Department of Justice & Regulation | DJR | Births, Deaths and Marriages (BDM) Core System Replacement Project | Law and justice | The replacement of the BDM core system will provide a scalable and robust design with enhanced functionality and migrated data. | 2013-10-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-06-30 | 1518095.36 | 2017-06-19 | 13925000 | 2017-09-30 | 13925000 | Green | Green | Green | Green | Green | The project is in Delivery Stage and system development is underway. | 2016-10-13
Q1-2016-17 | 11CD0994-A403-493F-AD1B-22520AF00611 | Department of Justice & Regulation | DJR | CV-CATS- APB Case Workflow System - | Law and justice | The provision of an electronic database and case workflow system that aligns to a re-engineered set of business processes to deliver a significantly improved and enhanced user experience | 2014-04-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-11-20 | 996219 | 2016-12-15 | 3811985 | 2018-12-01 | 4400000 | Amber | Green | Green | Green | Green | Phase 1 of the Adult Parole Board (APB) Case Workflow System is in operation. Project will be delivered in stages through to 2018. | 2016-10-11
Q1-2016-17 | 4A60FB2A-9801-4262-AF2C-4E070D46E907 | Department of Justice & Regulation | DJR | E*Justice Strengthened Enforcement | Law and justice | Implement changes to the current IT system and database to ensure compliance with new legislative, policy and practice changes to support the Government's parole reform agenda. | 2014-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-12-23 | 0 | 2016-06-30 | 1028095 | 2017-03-31 | 1872300 | Amber | Amber | Green | Green | Green | Three components have been completed as planned. The fourth component has been delayed. | 2016-10-11
Q1-2016-17 | BFFBD9BE-A506-4455-AF71-75D06FA8B864 | Department of Justice & Regulation | DJR | Emergency Alert Phase 3 - Delivery | Emergencies and safety | Capital works associated with the Emergency Alert carrier contract extensions up to June 2018. 4G implementation and technology uplift. | 2014-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-07-01 | 1405046 | 2016-07-25 | 11533626 | 2016-12-31 | 11533626 | Amber | Green | Green | Green | Amber | 4G upgrade all completed. Final delivery is delayed due to issues arising from the implementation to the new platform. There is no impact on service delivery or budget. | 2016-09-30
Q1-2016-17 | 6C50E709-47D4-41E4-B77D-3FD0C4B0CA9A | Department of Justice & Regulation | DJR | Prisoner Transport Order System (PTOS) | Law and justice | The PTOS Project will deliver an integrated transport order and information management system for implementation across Corrections, Police and DHHS to provide transport orders to the contractor and management information for all prisoner transports. | 2014-11-04 | Other – please specify | Project Management Excellence | In progress - implementation | 2014-12-04 | 180000 | 2016-09-05 | 3761184 | 2017-03-01 | 5061839 | Green | Green | Green | N/A | N/A | Project on track, with budget and schedule re-baselined. Implementation scheduled for the New Year (2107) | 2016-10-11
Q1-2016-17 | 8FD77B53-37C0-4739-BF5B-8F0D38B9E30D | Department of Justice & Regulation | DJR | Asset Refresh | Law and justice | The Asset Refresh program of work is an ongoing, multi-year program that uses infrastructure assets depreciation funds to replace like for like infrastructure to maintain the environment at DJR and promote stability and continuity. | 2015-07-01 | Other – please specify | Project Management Excellence | Completed | 2015-12-30 | 5000 | 2016-06-30 | 2416180 | 2016-08-30 |  | Green | Green | Green | Amber | N/A | Project is complete | 2016-10-18
Q1-2016-17 | 2417684C-75F3-4F2C-B486-2845B2C69F2E | Department of Justice & Regulation | DJR | DJR Information Management Strategy | Law and justice | A program of work to build information management capability within the department and address known issues in relation to the management of information. | 2015-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-09-01 | 83000 | 2018-06-30 | 1375600 |  |  | Green | Green | Green | Green | N/A | Stage One of the IMS (2015-16) is complete. Second of three stages is underway | 2016-10-12
Q1-2016-17 | 34709842-E4CC-4D8B-B697-2B9CBE4A99EF | Department of Justice & Regulation | DJR | Jcare - electronic prescribing | Law and justice | The Jcare - electronic prescribing project will provide additional functionality to the current electronic health record used in Victorian prisons (Jcare) to allow clinicians to prescribe medication within Jcare. | 2015-07-01 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-07-01 | 0 | 2017-01-01 | 1716000 | 2017-07-01 | 1808719 | Green | Green | Green | Green | Green | Full site deployment to be completed in July 2017. No change to delivery timing. | 2016-10-10
Q1-2016-17 | B2C53213-E810-4199-AB05-016E482D260D | Department of Justice & Regulation | DJR | CCS Accommodation Expansion Program | Law and justice | IT fitout for sites being constructed or modified to accommodate additional staff for Community Correctional Services (CCS) and other business units across Victoria. The number of sites potentially requiring IT treatment has recently increased from 29 to 59 sites. | 2015-07-29 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | Four sites successfully deployed in September 2016. Project is on track to deliver four further sites between November and December 2016. | 2016-10-17
Q1-2016-17 | C6CDEC69-2300-4AEF-BD39-EEAA677EEC53 | Department of Justice & Regulation | DJR | Police Digital Radio Upgrade Project ('PDRUP') | Emergencies and safety | Migrate Victoria Police outside of the metro (MMR network) area from the legacy (analogue unencrypted) radio network (StateNet Mobile Radio ('SMR')) to the new (digital and encrypted) network (Regional Mobile Radio ('RMR')) | 2015-09-07 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-01-14 | 0 | 2017-08-07 | 14100000 | 2018-03-01 |  | Red | Amber | Green | Green | Green | Procurement, implementation and business readiness planning are progressing. Funding issues are being addressed. (Note: issue is joint with ACMA Compliance Project) | 2016-10-12
Q1-2016-17 | C8C50184-9D92-4C7B-8D5F-35D8757A878B | Department of Justice & Regulation | DJR | New Infringements ICT System | Law and justice | Reform Program following the successful passage of the Fines Reform Act (2014). The ICT component of the program involves the procurement of an end-to-end COTS system to replace its current legacy infringement management system, VIMS, addressing all changes under the Act. | 2015-10-27 | Other – please specify | Project Management Excellence | In progress - pre-implementation | [11 empty] | The contract has been awarded and works have commenced. | 2016-10-19
Q1-2016-17 | 4714C415-0D0F-4703-B62B-FB2AA0E5CD79 | Department of Justice & Regulation | DJR | Internet Remediation Project | Law and justice | A program of works to remediate and stabilise the Internet used by Courts & DJR. This includes proxy servers, DNS, SMTP, core switches and mobility. | 2015-11-30 | Other – please specify | Project Management Excellence | In progress - implementation | 2015-12-09 | 25 | 2016-12-31 | 4156300 |  |  | Green | Green | Green | Amber | N/A | Stage 1 is 100% complete; Stage 2 is 61% complete; Stage 3 is 87% complete and Stage 3a is 20%. Project is on track. | 2016-10-12
Q1-2016-17 | 46E3F515-0E50-4E2C-9207-302BF866E461 | Department of Justice & Regulation | DJR | Capacity Uplift Project | Law and justice | This project will procure and implement additional capacity into the DJR Data Centres at Burwood and Ballarat. | 2016-03-22 | Other – please specify | Project Management Excellence | In progress - implementation | 2016-07-01 | 0 | 2016-10-31 | 2301476 |  | 2596422 | Green | Green | Green | N/A | N/A | Project is on track. | 2016-10-12
Q1-2016-17 | 64FBAE5B-1C9F-4CCF-8D22-F99DEE02A842 | Department of Justice & Regulation | DJR | Emergency Alert Phase 4 - Delivery | Emergencies and safety | Secure service continuity and delivery of a national telephony based emergency warning system, ensuring a more sustainable EA service: a service that remains up to date and relevant to community use and demand, maintains an acceptable performance standard and incurs minimal capital expenditure and cost surprises. | 2016-05-06 | Other – please specify | Project Management Excellence | Initiated | [11 empty] | A Request for Tender seeking a supplier for the replacement of the EA system was released 28 September 2016. The tender closes 8 December 2016. | 2016-09-30