## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q1 24-25 | Q2 24-25 | Q3 24-25 | Q4 24-25 | Q1 25-26 (Current) | Reporting Comments
Q1 25-26 | Country Fire Authority | CFA | 2151 | CFA Mobile Data Capability and Short Status Messaging (SSM) | Emergencies and Safety | Communication | Development and deployment of the Mobility Data Capability (MDC) platform, incorporating Short Status Messaging, will deliver operational efficiency and safety benefits to members and the community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2027-06-30 | 2850000 |  | Amber | Amber | Amber | Amber | Amber | The project is continuing to experience system integration issues for the Short Status Messaging component, resulting in an amber status. The delivery of this component will be delayed and included in the broader technology upgrade across the emergency sector.
Q1 25-26 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2026-06-30 | 89200000 | 158650000 | Red | Red | Red | Red | Amber | Build of Criminal release was materially finalised last quarter and deployment activities have been in progress including data migration, external interface testing and go-live readiness planning.
Q1 25-26 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 | 2026-12-31 | 9680463 |  | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2026-06-30 | 3443281 | 3883649 | Amber | Amber | Amber | Red | Red | The roll-out to the remainder of the workforce is underway with the next tranche of employees migrating in October 2025. Issue resolution timelines continue to impact the schedule.
Q1 25-26 | Department of Education | DE | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage school land & building assets enabling evidence-based decision making at both DE Corporate & School level & support attestation against Asset Management Accountability Framework. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-08-29 | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2025-08-29 | 12956778 | 25565174 | Amber | Green | Green | Green | Green | The project has delivered the stated outcomes and was closed in Q1 2025-26.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2026-06-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Road Safety Package includes a number of initiatives. The initiatives with ICT deliverables are: • Computerised Maintenance Management System (CMMS) • Network Security - Improvements to security of the Fixed Digital Road Safety Camera network. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-07-23 | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 869178 | 2021-05-24 |  | 2022-04-21 | 2025-07-23 | 6967000 | 13618249 | Green | Green | Green | Green | Green | The CMMS initiative was completed in December 2023. The Network Security initiative was completed June 2025, with the entire Fixed Digital Road Safety Camera (FDRSC) network migrated to a centralised firewall protected environment. The project has transitioned to business as usual and is now closed.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2026-08-17 | 6074206 | 10879302 | Red | Amber | Red | Red | Amber | An updated schedule was approved in September which has moved the project to Amber. The project continues to work with the vendor on planning the Mental Health phase of the project.
Q1 25-26 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | The project aims replace the existing operational applications that operate in silos to create an enterprise Fire Rescue Portal. This will provide a system to support an efficient and effective Operational Response System. | Postponed | Compliance (Non Financial) | 2024-03-31 | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2025-06-30 | 2109000 |  | Amber | Amber | Amber | Red | Red | The Fire Rescue Portal project remains on hold, with formal closure yet to be confirmed by the project sponsor. While no further work is currently underway, future direction will be determined through ongoing strategic planning and review of organisational priorities and funding availability. The project status is red as there are no resources allocated to support continuation of this project.
Q1 25-26 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2026-06-30 | 3760000 | 4349947 | Amber | Amber | Amber | Amber | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-09-16 | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2023-12-30 | 2023-12-30 | 3297000 | 2971000 | 2024-03-01 |  | 2025-06-30 | 2025-08-01 | 18423392 | 14971907 | Amber | Amber | Amber | Amber | Green | The Financial Assistance Scheme (FAS) went live on 18 November 2024, with core functionality delivered. Further systems development due to adjusted and refined requirements was completed in August 2025. Migration of legacy data into the new system has been completed and operational use of the new functionality also commenced in August 2025. Project closure was endorsed on 16 September 2025.
Q1 25-26 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 650000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 10251000 | Amber | Amber | Amber | Amber | Green | The project is rated green due to a key procurement milestones being met.
Q1 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2026-09-30 |  | 75000 | 487457 | [11 empty] | GVW has gone out to market seeking a consultancy to update and revise the Business Case and revisit the Sourcing Strategy for this project which is expected to be presented to The Board by 3rd Quarter FY 25/26.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 | 2023-06-30 | 150000 | 213455 | 2024-03-01 |  | 2025-12-31 | 2026-06-01 | 1878947 | 1893035 |  | Amber | Amber | Green | Green | The project has undergone several iterations to ensure alignment with the overall organisational IT strategy and architecture. Despite being in delivery phase, the project is still undertaking some initiation activities due to variations in scope, and the engagement of new vendors. A revised project plan, incorporating an updated schedule is being finalised.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2026-06-30 | 131615000 | 169961000 | Amber | Amber | Amber | Red | Red | The project has continued its analysis for more efficient, alternative delivery approaches to meet the current timelines. The project is reporting a Red status due to schedule pressure, with the program's delivery velocity trailing forecast outcomes. The program has made some interim delivery approach adjustments, transitioning to shorter delivery cycles to improve throughput while the more detailed analysis continues.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems for safety benefits. Prison management systems will be uplifted, and rehabilitation and reintegration services will be enhanced. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2029-06-30 | 18868800 | 46682876 | Green | Green | Green | Green | Green | The program is tracking well against budget, schedule and scope. The increased delivery cost from the planned $18.86m to the revised $46.68m is due to an increase in scope to roll out the automation technology across multiple sites across the state. The delivery end date has also been revised from June 2025 to June 2029 to accommodate the additional scope.
Q1 25-26 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 | 1178280 | 2022-03-01 |  | 2023-06-30 | 2026-03-31 | 8900000 | 23850720 | Amber | Amber | Amber | Amber | Amber | The project has expanded its scope to include portable bonds scheme (PBS). The revised budget and schedule include additional PBS scope. The project reported Amber as it is currently finalising PBS requirements.
Q1 25-26 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2026-05-28 | 3174023 |  | Green | Green | Green | Green | Green | As at 20250930: RFQ Vendor responses under evaluation. .
Q1 25-26 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System will be replaced to meet current and future business and reporting requirements. The project delivers a contemporary solution to support forensic investigations for Victoria’s justice system. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-08-19 | PRINCE2 | 2021-07-01 | 2022-01-07 |  | 2022-01-07 | 0 | 350000 | 2022-01-07 |  | 2023-12-31 | 2025-08-19 | 5650000 | 6150000 | Green | Green | Green | Green | Green | The project is complete, with the new case management system launched on 19 August 2025.
Q1 25-26 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2026-08-17 | 16689890 | 18418852 | Green | Green | Green | Amber | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2025-12-31 | 27220000 | 24026574 | Amber | Amber | Red | Red | Red | Project is progressing to revised cost but is experiencing technical issues and constraints in accessing required services. Work is continuing to resolve these issues and impact to schedule is currently being assessed.
Q1 25-26 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 | 2025-11-05 | 2424764 |  | Green | Green | Green | Amber | Amber | As at 20250930: RFQ process progressing and confirming scope it is expected a Change Request will be required to realign the schedule end date post RFQ activity.
Q1 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2026-06-30 | 6428267 | 11849537 | Green | Green | Green | Green | Green | System testing is continuing which has identified some missing functionality that was in the original design. It is anticipated these will be built and provided by mid November to allow SIT to be completed by December 2025. A revised budget and timeline has been approved by both Executive and Finance Committee
Q1 25-26 | Oral Health Victoria | OHV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2025-12-19 | 9490000 |  | Amber | Amber | Amber | Amber | Amber | Project resources onboarded for R2 planning and commencement of engagement approach with business and sector. First set of activation sites identified and engaged.
Q1 25-26 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | The objective of the project is to implement public transport timetabling solution for each mode which will improve business process and data accuracy, providing Victorian commuters consistent and timely information when using public transport. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2025-09-18 | 4739268 | 6716680 | Amber | Amber | Green | Amber | Red | The project status is reported as red due to solution implementation issues impacting the project scope and schedule. The project team is working on mitigating these issues to get the project back on track and will inform the revised delivery end date in the next reporting period.
Q1 25-26 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2026-03-30 | 32018000 |  | Amber | Green | Green | Green | Green | The AVMS On Board project has progressed to the on board tram installations of AVMS.
Q1 25-26 | Fire Rescue Victoria | FRV | 3325 | Human Resources Information System (HRIS) | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2026-09-16 | 22392000 |  | Amber | Amber | Green | Amber | Red | Tender evaluation is currently underway and progressing as planned. The funding for the program is being finalised through a business case, resulting in a red cost status until the funding has been resolved. The funding position is posing a significant risk to the schedule, resulting in an red overall status rating.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2027-04-01 | 23495000 |  | Green | Red | Red | Green | Amber | Project delivery is in line with the revised schedule with targeted actions in place to address remaining scope and quality risks.
Q1 25-26 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 | 2025-11-06 |  | 0 | [12 empty] | As at 20250930: Business Case due for submission in November.
Q1 25-26 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-12-31 | 8559000 | 8559000 | Green | Green | Green | Green | Amber | The project status has been changed to ‘Amber’ due to forecast completion of content ingestion exceeding the project end date. The core objective of the Business Case has been achieved and the EDRMS (Records365) has been delivered by 31 March 2025. The project is ongoing until 31 December 2025 in order to deliver and embed supporting products as part of the overall solution suite.
Q1 25-26 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Red | Detailed Design is in progress although tracking behind schedule. The project team is working closely with the Systems Integrator to confirm the approach and detailed plan and to define the new operating model and finalise requirements. Additional project budget is required to complete the Build Test and Deployment activities. A request for additional project budget has been submitted.
Q1 25-26 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Red | Red | Red | Red | Red | Path to Green requires confirmation of project budget then contract signing with the supplier. Schedule can then be re-baselined with confirmed scope and project schedule dates.
Q1 25-26 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2025-12-31 | 138595535 | 136247000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The Digital Marketplace is meeting agreed timelines for releasing functionality into the production version of Digital Marketplace which aligns with the expected benefit delivery
Q1 25-26 | Alfred Health | ALFRED | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-06-30 | 25000000 | 41800000 | Amber | Amber | Red | Red | Amber | This is a complex clinical project delivered across multiple health services and sites. The Project team is actively working with all the health services and vendors to resolve identified defects to meet the expected project timelines.
Q1 25-26 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2026-06-30 | 22637000 |  | Green | Green | Green | Green | Green | The overall status is green, and the project is on track with all implemented systems in the process of being transitioned to operations.
Q1 25-26 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2026-06-30 | 56681000 |  | Amber | Amber | Amber | Amber | Amber | DCMS Program remains rated Amber, with steady progress being made toward modernising VCAT’s case management capability. After the initial release of Rental Dispute Resolution Victoria (RDRV), work continues on the remaining Residential Tenancies (RT) case types which are planned for completion by August 2026 (subject to plans being approved). Development of the Guardianship List (GL) digital solution is progressing, supported by a new approach to order template design ensuring consistency and efficiency across all lists. Once both RT and GL are complete, more than 90 per cent of VCAT’s caseload will be managed on the modern digital platform.
Q1 25-26 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 |  | 2580000 |  | Green | Green | Green | Amber | Amber | Planning the next phase is progressing with the remaining functionality to be implemented including - Learning Performance Engagement Succession Rostering Time and Attendance and Payroll. The project is working through the final procurement steps with the delivery partner. The revised contract is due for board endorsement in the coming months. This will enable the project to be re-baselined and commence next phase. Delivery date will be aimed to be confirmed within the next quarter.
Q1 25-26 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 | 2024-12-09 | 2025-09-30 | 2025-12-23 | 3300000 |  | Green | Amber | Green | Green | Green | In Q1 2025/26, the project team finalised and prepared for release a Request for Information (RFI) process to evaluate best-of-breed time and attendance solutions. The project team is currently progressing the development of a modernised payroll exception reporting solution, which is expected to enhance payroll processing efficiency by the end of Q2
Q1 25-26 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 |  | 19500000 | 20419619 | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q1 25-26 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System (LIS) Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. Stage 1: LIS planning and procurement Stage 2 (delivery): LIS implementation | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 | 31572148 | Green | Green | Amber | Amber | Amber | This quarter focused on strengthening governance and delivery. Oversight transitioned to the Chief Quality Officer with all streams realigned under a new Senior Project Director. Schedule and risk management were streamlined and a budget review identified a shortfall for future planning.
Q1 25-26 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2026-06-30 | 5135000 | 45000518 | Green | Green | Green | Amber | Amber | The program is reporting an amber status as it is experiencing budget pressure on several potential pilots, with replanning occurring to ensure value is obtained from the pilots.
Q1 25-26 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 | 2026-06-30 | 1512000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Peninsula Health | PEN Health | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 | 2025-12-31 | 1222641 | 1423459 | Green | Green | Green | Green | Green | Bluetooth Angle of Arrival (AoA) installation is complete and the final pendant design finalised awaiting testing. 4D Radar cabling is done and sensors are installed in designated rooms environmental sensors and nurse call systems are fully signed off. Patient tablets are fully installed and penetration testing has been performed with all identified issues mitigated.
Q1 25-26 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Green | Green | Green | Red | The project reported a red status due to project budget confirmation in progress. Delivery is progressing well and remains on track in the current financial year. The project will be rebaselined once the budget is confirmed.
Q1 25-26 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2025-01-23 | 2025-01-23 | 0 |  | 2025-01-23 |  | 2025-12-31 | 2026-01-31 | 3368053 |  |  |  | Green | Green | Green | Project is tracking well. Focus for current period is on integration with key systems, ServiceNow and SAP. Successful integration with these solutions is critical to project success. We hope to have the work planned out shortly.
Q1 25-26 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-30 | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 | 2023-12-13 | 0 |  | 2023-12-13 |  | 2024-11-19 | 2025-08-15 | 2722712 | 6892613 | Green | Green | Green | Red | Red | As at 20250930: Project remains postponed to reassess approach to ensure we achieve business benefits.
Q1 25-26 | Melbourne Water | MELB Water | 3559 | Network Architecture Improvements SDWAN | Environment and Water | Security Management | Network Architecture improvement to SD WAN / Zero trust Model | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-08-26 | 2023-01-16 |  | 2023-01-25 | 0 |  | 2023-01-26 |  | 2023-10-10 | 2026-12-09 | 1189517 | 3470123 | Amber | Red | Red | Red | Amber | As at 20250930: Decision was made to close this project after the completion of Phase 1. A new project will commence for Phase 2 using an alternate solution.
Q1 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2026-01-30 |  | 70000 | 600000 | [11 empty] | Work has been progressing on detailed costings and agreed approach. Final costings and agreed approach on target for Q3 2025 - 2026.
Q1 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3567 | Wireless Network Refresh | Health | Collaboration ,Communication,Systems Management | The project will deliver a modernized wireless network infrastructure at the Victorian Comprehensive Cancer Centre (VCCC), replacing outdated hardware with advanced, high-performance equipment. | Closed - Completed | Risk Reduction (Non Financial) | 2025-08-31 | PRINCE2 | 2022-10-20 | 2023-07-31 | 2023-08-14 | 2023-08-14 | 0 | 48807 | 2023-08-15 |  | 2025-01-31 | 2025-08-31 | 1600929 | 1407637 | Green | Green | Green | Green | Green | Project complete
Q1 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 | 2026-04-30 | 4930809 |  | Amber | Amber | Amber | Red | Amber | The project status is AMBER due to additional clinical requirements resulting in a change in scope, impacting on overall timeline. Project will present re-baseline to governance group and return to Green in next reporting cycle.
Q1 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3585 | Regional Community Care Coordination Platform | Health | Records Management ,Tracking and Workflow | Delivery of a digital medical record for all the Community health care provided by members of the Loddon Mallee Rural Health Alliance to support connected patient care across the region (and between health services). | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-04-01 |  | 2019-04-10 | 0 |  | 2019-04-11 |  | 2021-03-31 | 2025-10-03 | 1330000 | 4528817 | Green | Green | Green | Amber | Green | All project deliverables have been completed. Transition to operational support teams currently underway alongside closure activities. Project will formally close in October.
Q1 25-26 | CenITex | CenITex | 3596 | Enterprise platforms renewal program | Government and Economy | Customer Relationship Management | Upgrade existing Dynamics 365 platform and implement a system that integrates & meets stakeholder requirements for Customer Engagement Project Services and Finance. Also, mitigate support issues due to end of life of the current platform. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-01-04 | 2023-01-12 |  | 2023-01-12 | 0 |  | 2023-02-03 |  | 2024-06-28 | 2025-10-31 | 1652000 | 1798319 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q1 25-26 | Department of Health | DH | 3599 | Mental Health and Wellbeing Website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  | Green | Amber | Red | Red | Red | The project continues to rely on the key dependency of the roll out of the Rostering project. The project continues to scope new integrations. System Integration Testing about to commence.
Q1 25-26 | Department of Premier and Cabinet | DPC | 3608 | Workflow Management System for Office of Chief Parliamentary Counsel (OCPC) | Government and Economy | Development and Integration ,Tracking and Workflow | WMS project will provide workflow for managing legal projects to improve management of the projects as per the OCPC standards and timely and accurate reporting to internal and external users to ensure timely publishing on the legislation website. | Postponed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) | 2025-05-09 | Agile | 2021-06-18 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2023-02-24 |  | 2024-07-13 | 2026-11-20 | 2500000 |  | Amber | Green | Red | Red | Red | The project is on hold pending governance decision.
Q1 25-26 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 | 2026-04-17 | 9510000 | 10162829 | Green | Green | Green | Green | Green | The project is tracking in line with stakeholder expectations
Q1 25-26 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 | 2025-12-08 | 10148335 | 10592143 | Green | Green | Green | Green | Green | The Enable Program continues to run to the technical go live plan of both active projects with SuccessFactors already live. The Enable Program remains overall green but noting a slight delay in final go live for the final phase (phase 4) scheduled for late November/early December. Phase 4 is our biggest group involving Nursing & Midwifery.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Employment, Skills and Workplace | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-06-26 | 4316783 | 4224778 | Green | Green | Green | Red | Red | Schedule impacted due to critical infrastructure (servers) not being delivered on time. Path to green involves re-baselining the project, pending approval of a change request.
Q1 25-26 | Monash Health | Monash H | 3644 | Security Card Technology Upgrade | Health | Security Management | Replacement of access control card readers and associated hardware across all sites to ensure access control security remains at an appropriate level and can integrate with current and future system requirements. | Closed - Completed | Risk Reduction (Non Financial) | 2025-09-30 | Waterfall | 2022-04-15 | 2023-02-23 |  | 2023-02-23 | 0 |  | 2023-05-03 |  | 2024-05-31 | 2025-07-31 | 2263923 | 2519211 | Amber | Amber | Green | Green | Green | The project is complete and transitioned to Operations
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 | 2025-12-31 | 5158000 |  | Green | Green | Green | Green | Green | ICT equipment and systems operational in new hospital. Project is on track.
Q1 25-26 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-11-27 | 2024-12-01 | 20588172 |  | 2024-12-02 |  | 2027-06-30 | 2028-06-30 | 233301093 |  |  | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 | 2024-11-22 | 200000 | 2675777 | 2025-03-12 |  | 2025-11-11 |  | 3383375 |  |  |  |  | Green | Green | The EMR Expansion project is tracking well—currently rated Green and actively progressing through the Delivery phase.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 3658 | Integrated supervised contact and access solution | Community Services | Customer Relationship Management | Integrate existing case management and support systems (Contact & Access Transport System) for supervised contact and access to eliminate duplicate processes and better support planning and decision making for children in out of home care. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2022-10-13 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2025-12-14 | 1217500 | 3229852 | Green | Green | Amber | Green | Green | Project is progressing to cost and schedule.
Q1 25-26 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2026-03-31 | 3450000 |  | Amber | Amber | Green | Amber | Green | Following the rebaseline of the project schedule to accommodate an upgrade required for integration with the meal ordering system an item not included in the original scope the project status has been returned to green. Northern is currently awaiting the detailed implementation plan to be presented by the vendor outlining the approach and timelines for the upgrade.
Q1 25-26 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 | 2026-02-27 | 1314347 | 1335472 | Green | Green | Green | Green | Green | Project is tracking as expected.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3668 | EMD (Emergency Management Day) PHASE 2 | Law and Justice | Development and Integration | This project supports management of EMD data for remanded prisoners to avoid unlawful detention or release and reduce legal risk. The objective is to provide a system for SCWA to manage sentences prisoner discharges and documentation for CV. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial) |  | Agile | 2022-05-02 | 2023-03-31 |  | 2023-06-16 | 0 |  | 2023-03-31 | 2023-06-17 | 2024-06-30 | 2025-11-30 | 1466100 | 1466100 | Green | Green | Green | Green | Green | The project has been delayed due to business resource availability. Completion is now expected in November 2025.
Q1 25-26 | Melbourne Health | Melb H | 3683 | CMI Data Access Project | Health | Data Management,Records Management ,Reporting | The CMI Data Access Project will deliver the disaggregation of data contained in the Mental Health Client Management Interface (CMI). There will be four data repositories created to enable mental health program reporting for NH, WH, RMH and Orygen. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-11-17 | 2023-09-04 | 2023-09-04 | 147800 | 80000 | 2023-09-04 |  | 2024-06-30 | 2025-11-28 | 1122200 | 1190000 | Amber | Green | Green | Green | Green | Project is tracking to schedule and budget
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Initiated |  |  | PMBoK | 2022-01-03 | 2025-12-01 | 2026-02-27 |  | 0 | [12 empty] | Project is continuing to scope IT deliverables and technical specifications. Currently in the tender phase for 2 ICT packages.
Q1 25-26 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 | 2026-06-30 | 3463000 |  | Amber | Amber | Amber | Amber | Amber | This quarter several key infrastructure setups have been completed including Clinical Grade Network links, end user devices replacement, data backup, firewall and parallel network. The completed works will enable migration readiness for essential applications. The project is Amber as the Payroll implementation scope/timeline is under review placing schedule under pressure. The project team will propose an alternate approach for governance approval upon review completion.
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2025-04-01 | 2025-04-01 | 0 | 150000 | 2025-04-01 |  | 2026-12-31 |  | 3450000 |  |  |  |  | Green | Green | Key work packages for AD/Email/M365 Unified Communications and ICT support arrangements in progress. Project is on track.
Q1 25-26 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 | 2025-08-28 | 2025-12-20 | 2027-06-30 | 13500000 |  | Amber | Amber | Amber | Amber | Amber | The project status is AMBER due to a delay in kicking off change readiness activities due to a delay in resourcing, impacting on timeline. Timeline will be adjusted to minimise impact on development implementation start date of February 2026.
Q1 25-26 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-06-26 | 4316783 |  | Green | Green | Green | Red | Red | The project status is RED because the schedule was impacted due to critical infrastructure (servers) not being delivered on time. Path to green involves re-baselining the project, pending approval of a change request.
Q1 25-26 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 | 2026-04-24 |  | 900000 | 1476107 | [11 empty] | The project team is evaluating the system and implementation partner options and requires additional time to ensure the correct solution is selected to meet V/Line's needs. The initiation period is expected to be completed in April 2026 with the base project resources recruited to deliver the business case and develop the project delivery plan.
Q1 25-26 | Triple Zero Victoria | TZV | 3700 | Emergency Sector Integration Platform | Emergencies and Safety | Systems Management | Provide a new single, vendor agnostic integration platform to interface into 000VIC data sources that reliably meets current and future anticipated requirements, The platform is vital for the integration of Next Generation CAD to current ESO systems. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-07-14 | Project Management Excellence | 2021-08-09 | 2021-12-28 | 2024-02-28 | 2024-02-29 | 570406 | 1400264 | 2024-02-29 |  | 2024-12-31 | 2025-07-14 | 5070736 | 9016536 | Red | Red | Green | Green | Green | The project is completed, and the Emergency Sector Integration Platform project was transferred to DJCS on 14 July 2025. DJCS will finalise the platform in preparation for use with emergency service organisations.
Q1 25-26 | Royal Women’s Hospital | RWH | 3703 | Rostering, Time and Attendance Project | Health | Human Capital / Workforce Management | The Project will upgrade the current Rostering system, delivering performance improvements and new enhanced functionalities. This project is part of an overarching People Systems Improvement Program with Royal Melbourne Hospital and Western Health | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-03 | 2023-09-01 |  | 2023-09-01 | 31980 |  | 2023-09-03 |  | 2024-12-31 | 2025-10-30 | 1140573 |  | Amber | Green | Green | Amber | Amber | The project is reporting an Amber status due to a budget overrun resulting from the extended timeline. However the delivery schedule remains on track and discussions regarding funding options are progressing.
Q1 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 3722 | Mosaiq Migration to Cloud and Upgrade | Health | Systems Management | The Mosaiq Migration to Cloud and Upgrade project will move the Mosaiq Radiation Therapy Treatment System from on premisses to Azure Cloud and upgrade its version once in cloud, as current software version is becoming end of life. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) | 2025-08-31 | PRINCE2 | 2022-03-01 | 2023-12-22 | 2024-04-30 | 2024-04-30 | 0 | 20475 | 2024-05-01 |  | 2025-08-31 |  | 1720000 | 1393659 | Green | Green | Green | Green | Green | Project complete.
Q1 25-26 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Applications and Services (AS) business unit within the Digital Health branch of the Commissioning and System Improvement division. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 | 2026-05-31 | 1412500 | 1088061 | Amber | Amber | Red | Amber | Amber | Project is amber due to constraints in accessing the required services which is impacting the schedule.
Q1 25-26 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2026-02-01 |  | 0 | 3000000 | [11 empty] | The primary focus of the St Vincent's Hospital Melbourne Electronic Medical Record (EMR) project continues to be on procurement and contracting processes. Organisational readiness tasks continue including a network uplift and the other infrastructure initiatives to prepare the clinical environment.
Q1 25-26 | Melbourne Water | MELB Water | 3734 | Finance System Cloud Transition | Environment and Water | Financial Management | Due to a vendor decision to move all on-premise customers to SaaS by 2024 this project is required to upgrade Melbourne Waters finance system and move to the cloud. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-09-15 | PRINCE2 | 2023-07-03 | 2024-01-24 | 2024-05-02 | 2024-05-02 | 0 |  | 2024-05-02 |  | 2024-12-17 | 2025-09-15 | 1811601 | 3275441 | Amber | Green | Green | Green | Green | As at 20250930: Project went live mid-September. Hypercare period is complete with no outstanding incidents. Project is now closed.
Q1 25-26 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 |  | 12100105 |  | Green | Green | Green | Green | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2025-12-19 | 14429000 |  | Green | Green | Green | Green | Green | Project progressing to cost and schedule.
Q1 25-26 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 | 2025-12-31 | 7490000 | 13618209 | Green | Amber | Amber | Amber | Green | The overall status is green, and the program scope budget and schedule have been rebaselined.
Q1 25-26 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 | 2026-06-30 | 6640340 | 8243140 | Amber | Amber | Amber | Amber | Amber | The project is currently reporting an Amber status due to ongoing and significant schedule delays. As a result, a decision has been made to terminate the contract with the current vendor and initiate a tender process to engage a vendor for the remaining deliverables and some alternative actions. This approach is intended to mitigate further delays and support the successful completion of the project.
Q1 25-26 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment, Skills and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 | 2027-07-30 | 7818000 | 13258270 | Green | Green | Green | Green | Green | Key scope, schedule and budget review conducted. Budget now reflects OTCD Grant and MP internal costs aligned to scope and schedule. Project progressing to revised plan and targets.
Q1 25-26 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 | 2028-12-31 | 543000000 | 680350000 | Green | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q1 25-26 | Box Hill Institute Group | BHIG | 3786 | Campus Network Infrastructure Upgrade | Employment, Skills and Workplace | Systems Management | Replacement of network infrastructure hardware and software assets within data centres and across all campuses that do not meet the minimum operational requirements related to supportability capacity performance reliability and security. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2025-09-30 | Waterfall | 2023-08-01 | 2023-12-22 |  | 2023-12-22 | 129131 |  | 2023-12-22 |  | 2025-02-28 | 2025-09-30 | 6860000 | 6200000 | Red | Green | Amber | Green | Green | Completed all remaining network device deployments across Box Hill Lilydale and City Campuses. Commenced project closure activities including transitioning to operational control.
Q1 25-26 | Victorian Electoral Commission | VEC | 3802 | Roll Managment System (RMS) Technical Upgrade | Government and Economy | Systems Management | The project will replace the legacy RMS application with a new and supported technology platform, reducing VEC's risk of using an unsupported platform and enabling system continuity for roll management | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-04-14 | 2023-11-08 |  | 2023-11-10 | 880742 |  | 2023-11-10 |  | 2025-09-30 | 2025-10-24 | 7841489 | 8456690 | Green | Amber | Amber | Amber | Green | The project has successfully met all Go Live criteria resulting in the new application being implemented as at 25/8. Hypercare support concluded on 30 September, marking the transition to standard operations.
Q1 25-26 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 | 2024-10-22 | 2026-06-22 | 2027-03-19 | 4966804 | 5381182 | Green | Green | Green | Red | Amber | As at 20250930: Identified a change of scope need to provide for additional support requirements, resources and related increase in budget needs.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Employment, Skills and Workplace | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers & the Victorian community. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 | 326274 | 2023-12-11 |  | 2025-12-31 |  | 7321441 | 3867488 | Green | Green | Green | Green | Green | On track
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2026-01-31 |  | 0 | [12 empty] | Grampians Health continues to progress a shared EMR program with another Victorian health service. Procurement is in progress but has taken longer than anticipated and continues to push out program timelines for completion of the initiation phase, with delivery expected to commence in Q3 2025-2026.
Q1 25-26 | Ambulance Victoria | AVS | 3816 | Rostering System Replacement (WMS) | Health | Systems Management | The project will replace the current end-of-life rostering software with a new workforce management solution, minimising software stability and security risks, and improving efficiency in rostering processes to deliver more impact to our community. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-30 |  | 2024-03-31 | 1271134 | 826551 | 2024-04-01 |  | 2025-06-30 | 2025-10-30 | 3846467 | 6370186 | Amber | Amber | Amber | Amber | Red | The project is tracking Red due to resource challenges and delayed implementation activities. The project team will continue to manage closely during Q2 FY26.
Q1 25-26 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2025-10-31 |  | 0 | 0 | [11 empty] | The project encountered minor delays during the formal tender evaluation phase. At the end of August, the project sought governance approval for the contract award and received endorsement to proceed with an initial agreement with the preferred supplier. This includes launching a Blueprinting and pre-contract readiness phase, aiming commencement in November 2025. The purpose of this phase is to refine the implementation schedule, scope, and cost estimates ahead of the formal contract award, which is now targeted for March 2026. Progress tracking and further updates will be provided in the next reporting cycle.
Q1 25-26 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Employment, Skills and Workplace | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 | 2027-12-31 | 8000000 |  | Amber | Amber | Amber | Green | Green | The project is progressing well and remains aligned with approved plans.
Q1 25-26 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | The objective of this program is to implement cyber and information security standards, enhancing information security measures and reducing risks of cyber incidents, by embedding robust and proactive cyber security practices. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2026-06-30 | 6800000 | 17334852 | Green | Green | Green | Amber | Amber | The program status is reported as amber. The status is amber due to the challenges related to project work-streams. The program team is working on mitigating these risks. The program includes thirteen completed project streams with eight others in progress.
Q1 25-26 | Department of Transport and Planning | DTP | 3829 | Public Transport Data program (PTDP) (Formerly known as ITDP) | Transport and Vehicles | Business Intelligence,Communication,Customer Initiated Assistance,Customer Preferences,Data Management,Search | Purpose of this program is to improve the Department’s capability to deliver accurate and consistent real-time information for customers whenever, wherever and however they need it. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-29 | 2023-08-31 | 2023-08-31 | 0 | 0 | 2023-09-01 | 2024-01-01 | 2025-11-30 |  | 16140000 |  |  |  | Amber | Amber | Green | The program status is green and is nearing program closure.
Q1 25-26 | HealthShare Victoria | HealthShare | 3835 | Healthshare Victoria Long Term Warehouse Management System Solution | Health | Supply Chain Management | The implementation of a scalable Warehouse Management System to support Healthshare Victoria's current & future growth plans, enabling a safer, effective and efficient distribution centre operations | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) | 2025-08-31 | PRINCE2 | 2022-12-05 | 2023-09-05 |  | 2023-09-06 | 0 |  | 2023-09-07 |  | 2025-01-31 | 2025-08-31 | 6218693 |  | Amber | Amber | Green | Green | Green | The overall project status is green as WMS was deployed in both DC’s (Derrimut and Dandenong) as per the plan. The project has been handed over to BAU support. All outstanding defects have been transitioned to BAU for ongoing management and resolution. Green
Q1 25-26 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2026-06-30 | 4565000 | 9509070 | Amber | Green | Green | Green | Green | - Deployed Module 1 at Western and Ballarat. Albury scheduled December - Deploying Module 4 at Alfred Health - Module 2 deployments halted due to competing priority. - Module 5 deployment halted due to lower uptake. - RPA POC completed - Moving to phase 2 and early production deployment at RMH
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that supports agricultural research. This project will be delivered in three phases over the next three years. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-31 | 2024-12-31 | 150000 | 399415 | 2025-01-01 |  | 2027-12-18 |  | 3675686 | 5836104 |  |  | Amber | Amber | Green | Phase 1 activities have been successfully completed and Phase 2 requirements definition is underway. Note that the project budget reflects the Phase 1 and 2 budget only and will be incrementally adjusted based on the subsequent phase planned commitment.
Q1 25-26 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 | 2026-08-31 | 1477000 | 2983000 | Red | Green | Green | Green | Amber | The IT/OT separation is behind schedule. This may impact the commencement of the IT segmentation phase..
Q1 25-26 | Barwon Region Water Corporation | BR Water | 3842 | C1443 - Land Development and New Connections Transformation | Environment and Water | Customer Relationship Management | The Land Development and New Connections Transformation project will redesign and configure services delivered by the Land Development and Connections functions increasing innovation, reliability and customer affordability. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-07-31 | Waterfall | 2021-11-01 | 2022-10-31 |  | 2022-10-31 | 75000 |  | 2022-11-07 |  | 2024-09-30 | 2025-07-31 | 1414000 | 1341000 | Amber | Amber | Red | Red | Green | All development work has been completed. Finalisation of the deployment of external facing portal and internal reporting has been handed over to operations for BAU completion.
Q1 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Postponed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-09-24 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 | 2025-12-19 | 2643965 | 2888965 | Amber | Amber | Red | Red | Red | Phase 2 of the HRIS project has been formally paused to allow resolution of outstanding PACCT Enterprise Agreement negotiations and enable a comprehensive review of the system build. The project will recommence following approval of a rescope and change request reflecting revised budget, schedule, and delivery approach.
Q1 25-26 | Department of Health | DH | 3844 | Security Access Modernisation | Health | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 | 2025-12-31 | 1413388 | 1387986 | Green | Green | Amber | Green | Green | Project is progressing to cost and schedule.
Q1 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Postponed | Increased Revenue (Financial) | 2025-06-05 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 | 2025-12-31 | 3157730 | 4311828 | Red | Red | Red | Red | Red | The project has been paused whilst a reset of the work is undertaken. This work was completed end September with options for delivery of the functionality being considered by the BKI Executive and Board.
Q1 25-26 | Department of Health | DH | 3846 | SDWAN activities and production rollout | Health | Systems Management | Delivering a new resilient, secure and internet centric network solution to all Department of Health and Families, Fairness and Housing sites, supporting the departments move towards cloud based IT services. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-12-01 |  | 2023-12-04 | 0 |  | 2024-01-02 |  | 2025-06-30 | 2025-12-31 | 1422000 | 1862867 | Green | Green | Green | Green | Amber | Project is Amber due to instability issues with implemented solution. Resolution is being investigated and any impact to schedule will be assessed.
Q1 25-26 | Western Health | WH | 3851 | Western Health - Mental Health Transition (ICT Infrastructure) | Health | Development and Integration | WH and RMH teams are migrating IT services to WH. Priority is minimal disruption to services, with workarounds in place to maintain service continuity and direct access to the Project team to address any issues potentially impacting patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-10-30 |  | 2023-11-20 | 0 |  | 2024-01-01 |  | 2024-10-30 | 2025-12-12 | 1960000 |  | Green | Green | Amber | Green | Green | ICT infrastructure build completed in August 2025 with service transition activities to be completed by December 2025.
Q1 25-26 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2025-05-28 | 2025-05-28 | 0 | 1900000 | 2025-05-29 |  | 2027-06-30 |  | 12000000 | [5 empty] | Green | The project is progressing well and remains on track across all key dimensions—schedule, budget, and benefits. Procurement activities have been successfully completed, with the vendor contract now signed, providing certainty for delivery and financial planning.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3854 | Impact Assessment Strategic Project | Emergencies and Safety | Data Management | This project will deliver improvements to Impact Assessment processes and systems in Victoria, aiming to provide efficient, timely and appropriate support for communities impacted by an emergency. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2023-08-01 | 2024-01-31 |  | 2024-01-31 | 255242 |  | 2024-02-01 |  | 2025-06-30 | 2025-12-31 | 6800000 |  | Green | Green | Amber | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2028-06-30 | 40229527 | 64701864 | Green | Amber | Red | Red | Red | Project is progressing but is reporting a Red health status primarily due to constraints in accessing required services and procurement delays impacting schedule. The underlying issues are being actively addressed, and schedule replanning is underway.
Q1 25-26 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 | 2026-06-29 |  | 1117000 | [12 empty] | The TCC RSS contract was awarded in FY25 Q4 and now in the delivery phase. The project is tracking well against scope, budget and schedule, including in relation to achievement of programmed delivery milestones with an overall green rating. ​ The project will remain in initiation until TCC - Back Office Systems (BOS) procurement completes in FY26 Q4 to maintain procurement integrity. The TCC RSS and TCC BOS projects are complementary streams of the one project which share a budget. Disclosing the full cost of TCC RSS could potentially enable TCC BOS respondents to derive the BOS budget compromising procurement integrity and competitive positioning. The Revised Initiation End Date reflects this approach.
Q1 25-26 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes in FY26 Q4 to maintain procurement integrity.​ Governance approvals to proceed to the BOS RFP were received. The BOS RFP is in progress and progressing to baseline schedule and within the approved budget.
Q1 25-26 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-07-02 | 2025-07-02 | 0 |  | 2025-07-07 |  | 2026-08-13 |  | 11070000 | [5 empty] | Amber | Due to gaps in business process understanding and concerns with velocity the project has gone into a minor replan which is addressing these concerns with no impact to budget.
Q1 25-26 | Department of Education | DE | 3862 | Victorian Curriculum and Assessment Authority (VCAA) Student Portal | Education | Communication,Customer Initiated Assistance,Reporting ,Tracking and Workflow | The student portal will provide a new digital channel for senior secondary students to access a range of VCAA services including enrolment details examination timetables and academic records, reducing reliance on paper records. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-07-21 | Agile | 2023-07-03 | 2023-11-30 |  | 2023-11-30 | 20000 |  | 2024-02-26 |  | 2025-03-31 | 2025-07-21 | 2405203 | 3117778 | Green | Green | Green | Green | Green | The project has successfully delivered the stated outcomes and was closed in Q1 FY26.
Q1 25-26 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 | 2026-06-30 | 3436310 | 8470976 | Green | Green | Amber | Green | Green | The project continues to build the foundations established in FY25. Horizon 2 has begun and is on tracking focussing on enhancing field service inventory and works management capabilities. Horizon 2 will also decommission the asset works and field management solution which was used by Western Water and is now obsolete.
Q1 25-26 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  | Green | Green | Green | Green | Green | Phase 1 activities (including data data migration and procurement) are continuing through Q1 and remain on track for completion in Q3.
Q1 25-26 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Postponed |  | 2025-06-30 | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [5 empty] | 0 | [6 empty] | Due to resourcing constraints, the project was postponed in June 2025. The project completed the initiation phase in January 2024 and was approved to commence procurement activities for the provision of a safety incident management system. Once resources become available, the project will transition to the delivery phase, commencing with procurement activities.
Q1 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Employment, Skills and Workplace | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 | 2026-07-31 | 1205132 |  | Green | Green | Green | Amber | Amber | Reviewing the project with newly established PMO. Functional and technical requirements are being re-evaluated based on discovery and testing with the student management system. Project timelines will be re-baselined based on PMO findings. Timelines will be confirmed in the next quarter.
Q1 25-26 | Austin Health | AH | 3877 | Anesthetics & Device Integration (AnDI) Project | Health | Development and Integration ,Document Management ,Knowledge Management ,Management of Process | Digitising theatre based documentation and integrating monitoring device data into the Electronic Medical Record, for safer patient outcomes and improved efficiency. | Closed - Completed | Cost Reduction (Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) | 2025-08-29 | Agile | 2024-05-27 | 2024-08-05 |  | 2024-08-05 | 0 |  | 2024-08-05 |  | 2025-08-29 |  | 4585000 |  | Green | Green | Green | Green | Green | Completed Phase 3 Go Live. Completed post go-live optimisations. Completed Project Health Check workshop. Completed handover to BAU . Project Closed
Q1 25-26 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 | 2026-06-30 | 1937205 |  | Green | Green | Green | Green | Green | Phase 2 of project has kicked off with initiation planning and solution design completed. Solution build is in progress with build and system testing to be completed in FY26 Q2. Remaining UAT and training planned for FY26 Q3. On-track as per schedule.
Q1 25-26 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 | 2026-04-30 | 3200000 |  | Green | Green | Green | Amber | Green | Northern has successfully resolved the technical challenges previously encountered with the new Citrix platform. System testing of the new environment is now underway to confirm stability and performance ahead of production rollout. Following a review of migration dependencies and vendor resourcing constraints, the project timeline has been rebaselined.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Employment, Skills and Workplace | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 | 2025-02-24 | 2025-02-24 | 947722 | 758291 | 2025-02-25 |  | 2025-10-31 |  | 4999889 | 4914431 |  |  | Amber | Amber | Red | Status downgraded to Red due to schedule delay. Build activity is in progress and a change request has been raised for initial release in March 2026. Plan to return status to Green is in place.
Q1 25-26 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-13 | 2024-10-25 |  | 2024-11-14 | 0 |  | 2024-11-14 |  | 2026-07-21 |  | 2900000 | 3198501 |  | Green | Green | Green | Amber | As at 20250930: Development work is continuing on multiple streams. A change request is required to address additional cost in line with the new estimates given after further requirements definition.
Q1 25-26 | Victorian Gambling and Casino Control Commission | VGCCC | 3883 | Compass - Gambling License System (GLS) replacement project - Release 1 | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-09-06 | 2024-08-30 | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-08-01 | 2025-10-21 | 1500000 | 1757000 | Green | Green | Green | Green | Green | The project is tracking well. The build phase, system and user acceptance testing, and data migration testing has been completed. Planning for the transition to the new system has commenced. The delivery end date has been revised by 1 month to October 2025 due to data migration complexities.
Q1 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3884 | SEC Retail Customer Billing System | Energy and Resources | Customer Relationship Management | This project is implementing a Customer Billing System that will enable SEC to launch an Energy Retail Business servicing electricity C&I Customers. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-21 | 2024-10-11 | 2024-10-18 | 2024-10-31 | 225000 | 258000 | 2024-10-31 |  | 2025-09-30 |  | 2780120 | 3125120 |  | Green | Green | Green | Green | Project has delivered successfully and handed over to operations
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 3886 | Grampians Health Success Factors Phase 2 | Health | Human Resources | Implementation of SAP SuccessFactors, including Employee Central Payroll, refactoring of Employee Central, Recruitment, Onboarding, and implementation of Performance & Goals. Phase 2 will deliver integration with rostering, finance and IT systems. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-13 | 2023-12-15 |  | 2023-12-15 | 0 |  | 2024-08-14 |  | 2025-09-26 | 2025-11-28 | 2905553 |  |  | Green | Green | Green | Green | 2 rounds of parallel payroll testing have now been successfully completed and the cutover to the production environment has commenced as of the 13th October. The cutover period will take place over a 4 week period in preparation for our go live date of the 3rd November. From the 3rd November, Employee Central Payroll, Employee Central Time off and the upgrades to our existing modules of Employee Central, Recruitment and onboarding will all go live. This will also include integrations to our rostering system Optima.
Q1 25-26 | Greyhound Racing Victoria | GRV | 3887 | Greyhound Whole of Life Tracking (GWOLT) | Business and Industry | Analyses and Statistics ,Business Intelligence,Customer Relationship Management,Management of Process | Digital Whole of Life Greyhound Tracking (DGT) involves the digitised data capture storage and retrieval to automate processes for tracking and recording the location and health of Victorian greyhounds throughout stages of their lives. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-08 | 2025-01-31 | 2025-03-23 | 2025-03-23 | 0 |  | 2025-03-24 |  | 2026-03-31 |  | 2920000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule. Some automation functionality has already been delivered, and is in use with appropriate governance structures.
Q1 25-26 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-06-01 | 2024-06-25 | 0 |  | 2024-07-01 | 2024-07-01 | 2026-06-30 | 2025-12-01 | 25000000 |  |  | Green | Green | Amber | Amber | The project reported amber due to delay in completing data testing activities partially due to the high complexities in integrating multiple systems across three departments. Project remains on track for delivery
Q1 25-26 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 |  | 2947600 |  | Green | Green | Amber | Amber | Amber | Technical build is well progressed however business adoption will take longer than expected. Refocussing on documentation, change management, training materials to ensure business readiness and alignment to benefits
Q1 25-26 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 | 2026-06-30 | 7069087 | 6967773 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  | Green | Green | Green | Green | Green | The project is tracking to plan. The second phase launch is going ahead for Q2 FY26. Post this launch the project will move into warranty.
Q1 25-26 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-01-31 | 2715200 | 2967206 | Amber | Amber | Red | Amber | Amber | Project is amber due to constraints in accessing the required services which is impacting the schedule.
Q1 25-26 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-09-03 | 2025-06-30 | 2025-04-14 | 2025-04-14 | 200000 | 254000 | 2025-04-14 |  | 2026-10-30 |  | 1440000 |  |  |  |  | Green | Green | Project progressing well. Draft Statement of Work received following design workshops. Supporting partner integrations have been scoped and presented to Project Steering Committee.
Q1 25-26 | Peninsula Health | PEN Health | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  | 2024-10-31 | 340000 |  | 2024-11-04 |  | 2025-10-31 | 2026-02-27 | 2620000 | 2621445 |  | Green | Green | Green | Green | The Project Steering Committee has approved rescheduling the Phase 2 go-live to the week beginning 10 November 2025. This milestone adjustment does not materially impact the overall project end date. The revised timeline accommodates additional data migration activities and ensures the availability of key stakeholders from both the project team and MePACS management throughout the go-live and transition period.
Q1 25-26 | Monash Health | Monash H | 3911 | Delphi - Oracle Cloud Fusion | Health | Financial Management | The project will implement Oracle software as a service to uplift management of finance, procurement, enterprise performance, project management, supply chain, and warehouse, enabling more efficient and effective business processes for Monash Health. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-08-07 | 2024-09-13 |  | 2024-09-13 | 50000 |  | 2024-09-16 |  | 2025-12-26 | 2025-12-31 | 17631000 |  | Green | Green | Green | Green | Amber | The project has experienced issues with data migration issues, and finalising the store to fulfill user acceptance testing in the Supply Chain stream which have put pressure on the overall schedule. The risk associated to these issues are being actively managed.
Q1 25-26 | Monash Health | Monash H | 3912 | Maternity Digital Transformation Project | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-10-31 | 2024-04-04 | 2024-04-04 | 0 | 0 | 2024-11-01 |  | 2026-05-27 |  | 11522379 |  |  |  | Amber | Green | Green | Project is on track. The execution phase is progressing well with three sprints currently on track for completion. Key project activities remain on schedule including steady progress in data collection and the commencement of testing activities.
Q1 25-26 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Improve strategic and operational asset management and service delivery through the implementation of Maximo Works Management providing benefits such as, a more financially sustainable business and keeping bills affordable for all. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2025-07-01 | 2025-07-01 | 824310 | 2162000 | 2025-07-01 |  | 2026-12-31 |  | 10208000 | [5 empty] | Green | The Barwon Water Group’s Works and Asset Management (WAM) project commenced Delivery in July 2025 with the objective to transform BWG’s works and asset management processes using IBM Maximo. Key milestones included the successful deployment of Phase 0—upgrading BWG's previous version of Maximo from version 7.6 to 9.1 on 22 September—and the formal commencement of Phase 1 focusing on Barwon Water Solutions (BAS) external work processes. Phase 2 of the project also commenced targeting treatment and network facilities works and asset management within Barwon Water.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-11 |  | 2024-10-11 | 1214790 |  | 2024-10-11 |  | 2026-06-30 |  | 23066733 | 25623840 |  | Green | Red | Red | Red | The program status is red due to delays in finalising remaining procurement activities. The impact to cost and schedule is being assessed, but is not expected to affect the overarching Public Housing Maintenance Modernisation schedule.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 3921 | Automated System Integration of the Victorian Housing Register (online) Application | Community Services | Records Management | Moving the Victorian Housing Register Application to an automated integrated solution, thereby improving the timeliness and capacity to manage an increase in volumes at an office level, improving client experience with faster feedback. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-28 | 2024-06-28 |  | 2024-06-28 | 192450 |  | 2024-07-15 |  | 2025-06-30 | 2025-11-28 | 1614264 | 2554264 | Amber | Red | Green | Red | Green | Project is progressing to revised schedule and cost.
Q1 25-26 | South East Water | SE Water | 3923 | Acumen Phase 2 | Environment and Water | Business Intelligence,Data Management | Phase 2 of Acumen will deliver foundation components, including architecture review and data preparation for ingestion and modelling. This will deliver key foundational elements necessary to support future phases. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2024-02-29 |  | 2024-02-29 | 0 |  | 2024-02-29 |  | 2025-04-30 | 2025-11-30 | 3600000 | 6585000 | Green | Amber | Green | Amber | Amber | The project is reporting AMBER due to delays to key milestones relating to development and ingestion of new system data sources into the Acumen program. Delivery end date revised to end of November 2025.
Q1 25-26 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 | 2026-07-31 | 1859425 |  | Red | Red | Red | Amber | Green | The project has recommenced after key roles on the project have been recruited. Project has returned to GREEN after project re-planned in order to deliver remaining scope.
Q1 25-26 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 | 2026-06-30 | 1161000 |  | Green | Green | Amber | Amber | Green | Project had returned to GREEN. Phase 2 development & testing completed. UAT and implementation to be completed by November 2025. Change request approved to deliver Phase 3 by end of FY26.
Q1 25-26 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 | 2026-06-30 | 1600000 | 1700000 | Amber | Amber | Amber | Amber | Green | The PTM SuccessFactors Project is live at one regional site. Preliminary dates have been agreed and will be presented to governance groups in Early November. Payroll teams have agreed to the planned phased approach and implementation dates. The project control group have endorsed the additional funding of the split go-live, to be approved by the GHA steering committee.
Q1 25-26 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2026-06-30 |  | 11000000 |  | Green | Green | Green | Green | Green | The program is tracking to plan for Q1 FY25/26. Delivery Teams have been working with stakeholders to review and refine Q2 delivery plans.
Q1 25-26 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-02-20 | 2025-07-07 | 2025-07-07 | 0 |  | 2025-07-07 |  | 2026-06-10 |  | 4868275 | [5 empty] | Green | As at 20250930: Integration and testing in progress.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Employment, Skills and Workplace | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-06-30 | 4597071 | 10624421 | Green | Green | Amber | Red | Green | The project is currently reporting a Green status with substantive discussions underway regarding the testing strategy and active engagement from business stakeholders.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 3934 | Licensing CRM (Customer Relationship Management) FY25 | Employment, Skills and Workplace | Customer Relationship Management | Transition of the remaining 5 license journeys from the legacy mainframe. This completes the transition of License Management capability to the CRM, unifying business processes, centralising data, and enhancing both customer and employee experiences. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-03-31 | 4466242 | 6958211 | Green | Green | Red | Green | Amber | The project reported an Amber status due to schedule related risk. Further analysis is required to evaluate the complexity of current requirements, in order to determine potential impacts on solution implementation and change management.
Q1 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3938 | SEC Corporate ERP System | Energy and Resources | Financial Management,Human Resources,Supply Chain Management | The SEC Corporate ERP system implementation project will select and implement an integrated Finance, HR and Procurement system to meet the requirements of SEC. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-12 | 2024-11-30 | 2024-10-30 | 2024-10-30 | 390000 | 210000 | 2024-11-01 |  | 2025-06-30 | 2025-07-25 | 1390000 |  |  | Green | Green | Green | Green | Project successfully delivered and handed over to operations
Q1 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3940 | SEC Energy Markets Projects | Energy and Resources | Financial Management | This ETRM Solution will provide an integrated suite of systems and processes to meet the SEC’s requirements of Deal capture, Settlements validation, Authorised trader/mandate register and Risk management. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-17 | 2024-10-14 |  | 2024-10-18 | 195172 |  | 2024-10-18 |  | 2025-07-16 |  | 3376919 |  |  | Green | Green | Green | Green | Project delivered successfully and has been handed over to operations
Q1 25-26 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 | 2025-01-31 | 2025-01-31 | 0 | 270000 | 2025-02-01 |  | 2026-06-30 |  | 2443584 | 2443584 |  |  | Amber | Amber | Amber | This represents a schedule-related risk only, with no impact to the approved budget, overall project timeline, and scope.
Q1 25-26 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 | 2025-12-31 | 6678000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope and budget, with a minor schedule delay to last milestone due to business reprioritisation. The software platform is live and over 25k meters deployed (Phase 1 goal) with enhanced features to identify customer leaks. Large meters from EDMI with new protocol has been tested in Production.
Q1 25-26 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2025-03-31 | 2025-05-31 | 2025-06-19 | 650000 | 736000 | 2025-06-19 |  | 2026-04-30 |  | 3936260 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule
Q1 25-26 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 | 2026-03-31 |  | 1772100 | 3795600 | [11 empty] | Post RFT submission activity called Co-Design commenced as YVW assesses final details to validate requirement nuances and options. This contributes to final award decision and completion of the delivery business case.
Q1 25-26 | Yarra Valley Water | YV Water | 3947 | MAXIMO 2025 UPGRADE | Environment and Water | Data Management | To upgrade Maximo software version 7.6 to version 9 to ensure continued support, enhance operational efficiency and leverage additional functionalities | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2025-01-15 | 2025-01-08 | 2025-01-08 | 697090 |  | 2025-01-08 |  | 2025-12-31 |  | 1723910 | 2134000 |  |  | Green | Amber | Green | The project remains on track for completion by the planned end date. The new Maximo v9 system was successfully implemented in September and is currently in the hypercare phase. The cost variance reflects the use of additional project resources.
Q1 25-26 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Initiated |  |  | PRINCE2 | 2024-09-30 | 2025-02-06 | 2025-11-06 |  | 0 | [12 empty] | As at 20250630: Business Case to be submitted Q2 FY25/26.
Q1 25-26 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-05-21 | 2024-12-11 | 2024-12-11 | 0 |  | 2024-12-11 |  | 2026-06-30 |  | 4807000 | 5483137 |  | Green | Green | Red | Green | As at 20250930: Project Change Request was approved reverting to green.
Q1 25-26 | Melbourne Water | MELB Water | 3950 | Intranet Renewal | Environment and Water | Communication | Renew or replace current Melbourne Water Intranet, including full investigation of options and user impacts. Re-imagine employee access to internal information. | Initiated |  |  | PMBoK | 2024-08-26 | 2024-12-18 | 2025-12-01 |  | 0 | [12 empty] | As at 20250930: RFP in progress to inform Business Case submission.
Q1 25-26 | Melbourne Water | MELB Water | 3951 | IT Facilities End of Life Hardware Replacement | Environment and Water | Assets/Materials Management | Replacement of critical IT facilities hardware (Air conditioners Uninterrupted Power Supply batteries) that are coming out of warranty or service contracts and due to 24/7 use require replacement. | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2025-07-31 | PMBoK | 2023-12-05 | 2024-09-09 |  | 2024-09-09 | 0 |  | 2024-09-09 |  | 2025-03-31 | 2025-07-31 | 1076437 |  | Green | Green | Green | Green | Green | As at 20250930: Project is complete.
Q1 25-26 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-03-21 | 2024-12-12 | 2024-12-12 | 0 |  | 2024-12-12 |  | 2026-06-30 |  | 2290000 | 3060378 |  | Green | Green | Red | Green | As at 20250930: Scope reduced to focus on most critical areas of delivery and risk reduction.
Q1 25-26 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2025-02-28 | 2025-02-28 | 10000000 | 0 | 2025-03-03 |  | 2026-06-30 |  | 10000000 | 10001234 |  |  | Green | Green | Green | Overall program status is green and is on track.
Q1 25-26 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  | 2024-11-13 | 0 |  | 2024-11-13 |  | 2026-03-12 |  | 1992000 |  |  | Green | Green | Green | Green | As at 20250930: Delivery on track.
Q1 25-26 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 | 2026-11-30 | 2750000 |  | Green | Green | Amber | Amber | Amber | Hardware staging activities completed along with initial device configuration Project reporting Amber due to extended delivery phase caused by a delay in scoping documentation. Scoping documentation expected in Q1 and project will be back on track.
Q1 25-26 | Department of Education | DE | 3956 | Automated Briefing and Correspondence (ABC) Implementation | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 | 2025-10-31 | 2657628 | 3757628 | Green | Green | Amber | Green | Green | The project was re-baselined in June 2025 following analysis of additional requirements, extending delivery to Q2 2025-26. The project team progress towards a target Technical Go-Live in October 2026.
Q1 25-26 | Environment Protection Authority | EPA | 3959 | MAJ140 - Finance System Upgrade | Environment and Water | Financial Management | Migrating from current TechnologyOne FinanceOne Ci solution to TechnologyOne FinanceOne CiA solution to provide extended vendor support and to provide EPA with enhanced Finance and Procurement functionality. The project will alleviate many pain point | Closed - Completed | Cost Reduction (Financial), Workforce Satisfaction (Non Financial) | 2025-08-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2024-10-22 |  | 2024-10-23 | 0 |  | 2024-10-24 |  | 2025-06-30 | 2025-08-30 | 1635000 | 1735000 |  | Amber | Amber | Amber | Green | The project closure report has been approved, and all closure activities have been completed in Project Online.
Q1 25-26 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | SCL is a ‘high profile’ program of work creating enhanced security capabilities for schools initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-03-31 | 3100000 | 6098000 | Amber | Amber | Amber | Amber | Amber | The project is reporting Amber due to complexity related risks and school server readiness. The project is managing the risks and working to mitigate any financial and schedule impact.
Q1 25-26 | Department of Education | DE | 3963 | 50 Early Learning Childcare Centres - Technology Components | Education | Customer Relationship Management | The project will deliver the required technology components in 50 ELC centres to support the Victorian Government initiative in broader early learning, enabling great start for young Victorians. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-15 | 2024-03-15 |  | 2024-03-18 | 0 |  | 2024-03-18 |  | 2032-06-30 |  | 2108035 | 4205068 | Green | Green | Green | Green | Green | The project is tracking to plan. The second phase launch is going ahead for Q1 FY26. Applications integrations are tracking for June 2026.
Q1 25-26 | State Revenue Office | SRO | 3964 | Short Stay Levy | Government and Economy | Development and Integration | A levy on short stay accommodation in Victoria was implemented on 1 January 2025. The short stay levy aims to increase the supply of properties available for long-term accommodation. This project sets up the systems to administer the levy. | Closed - Completed | Social Improvement (Non Financial) | 2025-08-30 | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 81000 | 60000 | 2024-07-01 |  | 2025-06-30 | 2025-08-30 | 3080000 | 3110759 | Green | Amber | Green | Green | Green | Warranty and remediation phases completed full scope has been delivered and project closed.
Q1 25-26 | State Revenue Office | SRO | 3965 | Vacant Residential Land Tax 2 | Government and Economy | Development and Integration | This project will expand the Vacant Residential Land Tax (VRLT) system to collect and administrate VRLT across all Victoria properties from January 2025 and underdeveloped residential land in Greater Melbourne areas from January 2026. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 35000 |  | 2024-07-01 |  | 2026-06-30 |  | 1927652 | 4738171 | Amber | Amber | Amber | Green | Green | The project is on track to deliver the 2026 changes. The budget increase is to reflect the full scope delivery including the 2026 changes.
Q1 25-26 | Department of Transport and Planning | DTP | 3967 | VIDA - Victorian Health Building Authority (VHBA) Integr8 | Transport and Vehicles | Collaboration ,Financial Management,Human Capital / Workforce Management ,Human Resources,Investment Management,Organisational Management | The VHBA Integr8 Program has been established to support VHBA to enact their Machinery of Government changes, with a specific focus on transitioning to the VIDA Information and Technology systems and supporting a smooth transition for VHBA employees. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-09 | 2024-11-11 |  | 2024-11-12 | 250000 |  | 2024-11-12 |  | 2025-11-30 | 2025-09-30 | 8258958 |  |  | Green | Green | Green | Green | Successfully migrated M365 and Identity workstream. This concludes all Business Value Group 1 deliverables.
Q1 25-26 | Alfred Health | ALFRED | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  | 2024-10-21 | 148217 | 69382 | 2024-10-28 |  | 2026-07-01 |  | 1171783 | 1250618 |  | Green | Green | Green | Green | The project is on track.
Q1 25-26 | Greater Western Water Corporation | GW Water | 3971 | Systems Readiness | Environment and Water | Communication,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Forms Management,Management of Process ,Records Management ,Reporting ,Systems Management,Tracking and Workflow | This project was established to focus on uplifting the customer ecosystem with a focus on core billing being operationally sound and to support customer facing processes including stabilising IT infrastructure and new service demands | Closed - Merged | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-04 |  | 2024-07-04 | 1593505 |  | 2024-07-04 |  | 2025-06-30 | 2025-09-30 | 4406495 | 6050397 | Amber | Amber | Amber | Amber | Amber | The organisation has pivoted its approach to remediating the critical scope. This work is now incorporated into an enterprise-wide path out program, which is aligned to the return to service plan and will commence reporting in Q2. This project’s scope will be delivered through this consolidated program to address critical deliverables and meet Return To Service commitments.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3977 | Energy Customer Relationship Management (CRM) Project | Government and Economy | Customer Relationship Management | The Energy CRM Project will deliver a customer management system to enable DEECA's Energy Group to deliver best practice stakeholder engagement and more efficient government processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-12-11 |  | 2024-12-11 | 150000 |  | 2024-12-12 |  | 2025-06-30 | 2025-10-31 | 1277120 |  |  | Green | Amber | Green | Green | The project is tracking well against scope, budget and schedule. Stage 1 has been successfully completed. Planning is underway to incorporate Stage 2 as additional scope, with a re-baseline targeted for the next quarter.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3980 | FireWeb Decommissioning Project | Emergencies and Safety | Management of Process | The FireWeb Decommissioning Project will replace the legacy system FireWeb to improve the accessibility of the information. This infrastructure will be DEECA's primary source for Fire Management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2028-06-30 |  | 5047000 |  |  | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3981 | Emergency Management (EM) Deployment Project | Emergencies and Safety | Management of Process | The EM Deployment project will deliver a modern system to plan and coordinate the commitments and resources for bushfire and other emergency incidents to increase DEECA's capabilities to manage these incidents effectively and in a timely manner. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2026-12-31 | 2026-12-31 | 1223000 |  |  | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule with a planned incremental increase in spend.
Q1 25-26 | Department of Government Services | DGS | 3982 | Service Victoria - Firearms & Private Security Digital Program - Phase 1 | Government and Economy | Customer Initiated Assistance,Management of Process | The project will deliver a minimum viable product to digitise the Firearms licence renewal process, in addition to enabling Firearms licence holders to obtain and securely store their licences in a digital form through Service Victoria app | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2024-03-01 |  | 2024-03-01 | 0 |  | 2024-03-01 |  | 2025-06-30 | 2026-01-30 | 2239255 | 1800000 |  | Green | Green | Green | Green | The project remains on track with respect to the approved scope, budget, and schedule, with pilot delivery having commenced in August 2025.
Q1 25-26 | Greater Western Water Corporation | GW Water | 3983 | Property Information | Environment and Water | Communication,Customer Relationship Management,Data Management,Management of Process ,Systems Management,Analyses and Statistics ,Assets/Materials Management,Content Management,Development and Integration ,Document Management ,Financial Management,Forms Management,Records Management ,Reporting ,Routing and Scheduling,Search ,Tracking and Workflow | This project will focus on remediating critical data and technology components within GWWs customer property and billing systems to meet KPIs, expected service levels, and customer satisfaction objectives | Closed - Merged | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-25 | 2024-07-25 |  | 2024-07-25 | 1 |  | 2024-07-25 |  | 2025-03-31 | 2025-09-30 | 13708801 | 13999999 |  | Amber | Amber | Amber | Amber | The organisation has pivoted its approach to remediating the critical scope. This work is now incorporated into an enterprise-wide path out program, which is aligned to the return to service plan and will commence reporting in Q2. This project’s scope will be delivered through this consolidated program to address critical deliverables and meet Return To Service commitments.
Q1 25-26 | Peninsula Health | PEN Health | 3985 | Peninsula Health Replacement of legacy Citrix virtual desktop environment & virtual server infrastructure | Health | Systems Management | Replacement of legacy Virtual Desktop and Converged Infrastructure at Frankston Hospital providing clinical application access to all sites, increasing usability and access for all staff to applications and data, including Video conference/telehealth | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-03-04 | 2024-10-18 |  | 2024-10-18 | 10000 |  | 2024-10-18 | 2024-10-21 | 2026-02-27 |  | 7329269 | 7982065 |  | Green | Green | Green | Green | Project is tracking to schedule.
Q1 25-26 | Department of Health | DH | 3987 | Donor Conception Register IT System | Health | Customer Relationship Management | Deliver a new IT system to manage Victoria's donor conception registers and allow applicants (donors, donor-conceived persons', parents, and their families) to request information under the legislation. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-01 | Agile | 2024-01-15 | 2024-03-26 |  | 2024-03-26 | 7800 |  | 2024-04-01 |  | 2025-06-30 |  | 1522446 |  |  | Green | Green | Red | Red | Major components of the system have been delivered. The project has confirmed carryover funding to complete the review of business requirements and ensure the current build aligns with recent legislative changes and the transition of functions from VARTA. Delivery will progress under the updated requirements and continue once the revised scope and remaining funding are confirmed.
Q1 25-26 | South East Water | SE Water | 3989 | CRUX - Stabilisation | Environment and Water | Financial Management | Uplift of ERP solution implemented in 2023. Including Finance Procurement & Project Management functions. | Delivery | Cost Reduction (Financial) |  | Waterfall | 2024-07-01 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2025-01-27 |  | 2026-01-30 |  | 3510000 |  |  |  | Green | Green | Amber | Project currently AMBER due to delays in closing out remaining modules due to change in priorities (e.g: Payment Gateway Replacement). As well there has been resource issues impacting delivery.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 3991 | Victorian Water Register (VWR) Evolve Project | Environment and Water | Development and Integration | The VWR Evolve Project will uplift the Victorian Water Register to a supported platform to improve the integrity security and reliability of Victoria's water market and enable future improvements in service delivery and information sharing. | Initiated |  |  | PRINCE2 | 2024-07-01 | 2025-05-31 | 2026-03-31 |  | 0 | 4233990 | [11 empty] | A Proof of Concept was successfully completed during the March 2025 Quarter to assess the feasibility of uplifting the Victorian Water Register to a new supported platform. During the September 2025 quarter, the project commenced a new procurement to secure a suitable Implementation Partner to support project execution.
Q1 25-26 | Melbourne Water | MELB Water | 3992 | Routine Telecommunications Upgrades FY24-26 | Environment and Water | Assets/Materials Management | Upgrade and replacement of degrading IT network cabling and devices - including microwave dishes 4G boosters WAPs and GWIP services. | Initiated |  |  | PMBoK | 2024-10-04 | 2025-02-13 | 2025-12-01 |  | 0 | [12 empty] | As at 20250930: Business case to be finalised.
Q1 25-26 | Eastern Health | EH | 3994 | Eastern Health EMR and Digitisation in the home | Health | Development and Integration | This project implements the EMR workflows across Care@Home services at Eastern Health alongside new integrated electronic logistics and fleet management applications to improve the coordination and delivery of care outside the hospital walls. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 420139 |  | 2024-12-06 |  | 2025-08-31 | 2026-03-31 | 4832935 |  |  | Green | Green | Amber | Amber | Go Live Support period stabilised and concluded. Steering Committee resolved to re-baseline timeline for early 2026 go live of larger service. Vendor engaged in scoping optimisation and improvement phase as part of deploying to larger service.
Q1 25-26 | Eastern Health | EH | 3996 | Eastern Health EMR Mobility and Enterprise Extension (Acute) | Health | Development and Integration | The EMR Mobility and Extension (Acute) Program aims to expand EMR footprint at Angliss and Maroondah Hospitals, simplify clinician workflows and patient information access, and implement EMR Mobility solutions while decommissioning legacy systems. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-02-28 |  | 2025-02-28 | 0 |  | 2025-03-01 |  | 2025-12-15 | 2025-12-31 | 9979000 |  |  |  | Green | Green | Amber | The EMR Mobility and Enterprise Extension changes are successfully live at Box Hill Hospital and Blackburn Public Surgical Centre as planned as of 30th September. In parallel the project steering committee have agreed the Maroondah Hospital go live to continue as planned for 24th November. The Amber status is reflective of the need to work on vendor risks related to defect resolution with mitigation to be confirmed in the next project steering committee meeting.
Q1 25-26 | Eastern Health | EH | 4000 | Advancing Cancer Services through Digital Chemotherapy Project | Health | Development and Integration | This project implements the EMR Oncology modules to all Eastern Health sites where Cancer Services are delivered providing electronic cancer medication prescription and management for more safe and timely care. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2025-02-28 |  | 2025-02-28 | 0 | 511021 | 2025-03-31 |  | 2026-05-31 |  | 3438979 |  |  |  | Green | Green | Green | The project is nearing completion of Design Phase with focus on determining a scheduling and correspondence solution while in parallel building and validating treatment protocols.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4002 | Mature Platform to Target State | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | The Mature Platform work has been defined to complete the implementation of the data pipelines and data objects in the EDH aligned to the approved target state architecture and transform and uplift operational processes aligned to new architecture. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 85310 |  | 2025-01-02 |  | 2025-12-31 |  | 1536799 |  |  |  | Green | Green | Green | On track
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4003 | Return to Work Product Pipeline Implementation | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | Deployment of a production-grade Return to Work (RTW) Dashboard Product to business users including operational support processes user training and change management. As well as automated ingestion of Australian Bureau of Statistics data. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 60290 |  | 2025-01-02 |  | 2025-12-31 | 2026-03-31 | 1318806 |  |  |  | Amber | Green | Amber | The project reported an Amber status due to the materialisation of delivery issues putting the current project end date at risk. A formal Project change request will be raised to address any impacts to the project.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4004 | Oracle Exadata Platform Refresh | Employment, Skills and Workplace | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-05 | 2024-11-29 |  | 2024-11-29 | 240072 |  | 2024-12-01 |  | 2025-10-27 | 2025-11-28 | 2269561 |  |  | Green | Green | Green | Green | On track following approved change request to re-baseline the schedule and include additional scope items.
Q1 25-26 | Department of Health | DH | 4005 | Enterprise Operational Workforce Management System | Community Services | Human Capital / Workforce Management | Replace end-of-life Rostering, Time and Attendance systems for disability residential services, child protection, emergency response and maternal child health divisions across DFFH and DH to enhance workforce management and improve service delivery. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-12-14 | 2024-09-30 |  | 2024-09-30 | 239974 |  | 2024-10-01 |  | 2026-06-30 |  | 3518876 |  |  | Green | Green | Green | Green | Project is progressing to cost and schedule.
Q1 25-26 | CenITex | CenITex | 4008 | AWS and Azure Cloud Landing Zone deployment | Government and Economy | Assets/Materials Management | This project iteratively implements Landing Zone feature enhancements. The focus is security enhancement standards implementation. Landing Zone “Official” security status implementation and delivery of a new cost model for efficient Cloud consumption | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2023-05-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2025-12-15 | 1420000 | 1433831 |  | Green | Green | Green | Green | Project is tracking to plan.
Q1 25-26 | CenITex | CenITex | 4009 | DC Exit Network Establishment – Phase 2 | Government and Economy | Assets/Materials Management | To establish a network extension from Burwood to Equinix ME2 using VicTrack colocation service at Equinix and then execute the base network infrastructure required at the data centre to start migrating Cenitex workloads out of Burwood to Equinix. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-11-01 | 2024-11-30 |  | 2024-11-30 | 0 |  | 2024-12-01 |  | 2025-10-30 | 2026-02-28 | 1993326 | 2786585 |  | Green | Amber | Green | Green | Project is tracking to plan.
Q1 25-26 | Goulburn Valley Region Water Corporation | GVR Water | 4011 | SCADA System Replacement | Environment and Water | Assets/Materials Management,Communication,Data Management,Systems Management | Replacement of the Supervisory Control and Data Acquisition (SCADA) System to ensure GVW's core operational monitoring and automation system remains fit for purpose and reduce business continuity risk. | Initiated |  |  | PMBoK | 2023-05-01 | 2025-04-30 | 2026-04-30 |  | 200000 | 415000 | [11 empty] | GVW has completed an initial engagement with a consultant who has outlined our concept design, validated our estimated cost and outlined a procurement approach involving 2 phases. The first phase of procurement is now complete. The second phase of procurement is underway.
Q1 25-26 | Hume Rural Health Alliance | HRHA | 4012 | Hume Regional EMR Preparation Project | Health | Customer Relationship Management,Records Management | The project will develop and deliver a series of business readiness activities prior to the full implementation of a whole of Hume Rural Health Alliance Electronic Medical Record (EMR), ensuring all IT environments are ready for the roll-out | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-13 | 2025-12-31 | 2025-03-31 | 2025-04-30 | 0 | 200000 | 2025-05-01 |  | 2026-06-30 |  | 4200000 |  |  |  |  | Green | Green | The focus is on planning out the work reestablishing the business case and engaging with experts across the region to prepare for the EMR
Q1 25-26 | Victorian Funds Management Corporation | VFMC | 4013 | Migration to cloud | Business and Industry | Systems Management | This project will transition our investment management system from an on-premises setup to a managed service offering, enhancing support, security and access to new functionality for our core technology platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-05-01 | 2024-05-28 |  | 2024-05-28 | 0 |  | 2024-12-01 |  | 2025-12-31 | 2026-03-31 | 2787000 |  |  | Green | Amber | Amber | Amber | Environments are setup and third-party system integration is underway. Batch management migration is more complex than expected but progressing with completion targeted in the next two sprints. End user testing has started and preparations for go-live will commence next month.
Q1 25-26 | Transport Accident Commission | TAC | 4030 | Oracle Exadata Platform Refresh | Transport and Vehicles | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-11-29 |  | 2024-11-29 | 160048 |  | 2024-12-01 |  | 2025-10-27 |  | 1513041 |  |  | Green | Green | Green | Green | The project is on track following the approval of the change request to rebaseline the schedule and include additional scope items.
Q1 25-26 | Yarra Valley Water | YV Water | 4031 | Digital Metering – Customer Solutions | Environment and Water | Communication,Customer Initiated Assistance,Customer Preferences,Customer Relationship Management,Management of Process ,Reporting ,Visualisation | The project will deliver multi-channel communications and digital meter bill generation, thus providing Yarra Valley Water customers with timely communications, access to water usage information, and leak alerts, improving the end-to-end experience. | Closed - Completed | Cost Avoidance (Financial), Cost Reduction (Financial) | 2025-08-31 | Agile | 2023-09-01 | 2024-03-31 |  | 2024-03-31 | 650000 |  | 2024-04-01 |  | 2025-06-30 | 2025-08-31 | 2636860 |  |  | Amber | Green | Green | Green | Final items and defects completed and project closure tasks underway.
Q1 25-26 | South Gippsland Region Water Corporation | SGR Water | 4033 | ERP Replacement Program | Environment and Water | Assets/Materials Management,Financial Management,Systems Management | The project will migrate three ERP platforms (finance, assets, work management) to cloud to reduce legacy system and security risks, improving workforce efficiency at South Gippsland Water. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Increased Quality (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) | 2025-09-30 | Waterfall | 2024-03-21 | 2024-09-30 |  | 2024-09-30 | 600000 |  | 2024-10-01 |  | 2025-07-01 | 2025-09-30 | 7685000 | 7985000 |  | Green | Amber | Green | Green | The project was closed on 30/9/25 after a successful implementation of the ERP.
Q1 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4037 | Data and Analytics Platform | Energy and Resources | Analyses and Statistics ,Business Intelligence,Data Management | The platform will store data from SEC core systems and provide reporting and analytics capability to SEC business units to maximise value through data based decision making and data modelling. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-16 |  | 2025-01-20 | 240042 |  | 2025-01-20 |  | 2025-07-31 |  | 2734936 |  |  |  | Green | Green | Green | Project was delivered successfully and has been closed.
Q1 25-26 | State Revenue Office | SRO | 4045 | Revenue Management System - Foundation | Government and Economy | Development and Integration | The Revenue Management System (RMS) is the core backend software & technology managing tax-related activities for all customers. This initiative aims to establish the technical foundations to transition all revenue lines to utilise modern technology. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-06-30 |  | 2025-07-01 | 1370114 |  | 2025-07-02 |  | 2026-06-30 |  | 11665000 | [5 empty] | Amber | Onboarding and design activities underway. Reporting as amber due to minor schedule delays. Return to green plan in place.
Q1 25-26 | Peninsula Health | PEN Health | 4046 | Patient Flow Management Solution | Health | Organisational Management | Electronic Patient Flow Management streamlines patient movement, enhances collaboration, optimises access and demand management, reduces length of stay, improves communication, and increases workplace satisfaction and providing bed visibility. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2023-09-08 | 2024-06-10 |  | 2024-08-07 | 50000 |  | 2024-12-20 |  | 2026-01-29 | 2026-04-30 | 2440404 |  |  |  | Green | Green | Green | The integration development process has commenced with the kick-off meeting held on 10th September with representatives from Peninsula Health and the relevant vendors with an aim to deliver the non-production build and complete testing by December 2025. Following this, the Steering Committee has approved the application Go-live for March 2026.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4048 | VicGrid Finance & Procurement - System Establishment | Energy and Resources | Financial Management | The project will deliver the system to manage finances, budgets, and procurement processes for VicGrid, in line with VicGrid's requirements and in compliance with Whole of Victorian Government information security standards. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-18 | 2024-12-17 |  | 2024-12-17 | 0 |  | 2025-02-03 |  | 2025-06-30 | 2025-10-31 | 1490000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Victorian Legal Services Board & Commissioner | VLSBC | 4049 | Regulatory Management System | Law and Justice | Customer Relationship Management | A Regulatory Management System will be delivered. Replacement of legacy systems will improve delivery of service and modernisation of legal regulatory systems will support legal regulation in Victoria. | Postponed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-02-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-10 | 2023-08-22 |  | 2023-08-22 | 330680 |  | 2023-11-27 |  | 2026-05-01 |  | 18400000 |  |  |  | Red | Amber | Amber | Project delivery is currently postponed. The vendor completed a technical release and is no longer contracted to deliver the remaining scope. The business is now validating its requirements and assessing the feasibility with the remaining budget before engaging a new vendor to deliver agree scope. The delivery dates are subject to revision following the assessment.
Q1 25-26 | Liquor Control Victoria | LCV | 4050 | Liquor Control Victoria ICT relocation and support for hardware and software | Law and Justice | Systems Management | The project will relocate on-premises servers to Richmond, decommission legacy hardware, and improve software and hardware support to enable business continuity | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-12-01 | 2025-03-31 | 2025-03-31 | 0 |  | 2025-06-27 |  | 2026-01-31 |  | 4373050 |  |  |  |  | Green | Green | The project is tracking well against budget, schedule and scope. The server relocation was completed in July 2025. Work is underway to enable the transition of systems and support from the Victorian Gambling and Casino Control Commission to LCV.
Q1 25-26 | Liquor Control Victoria | LCV | 4051 | New liquor platform for Liquor Control Victoria (delivered by Service Victoria) | Law and Justice | Customer Initiated Assistance | The project will deliver online licence application forms and a digital proof of age card. Efficiency and data quality will be enhanced, resulting in an improved user experience. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 0 |  | 2022-10-01 | 2023-06-01 | 2026-06-30 |  | 4580000 | 6835000 |  |  | Green | Green | Green | The project is tracking well against budget, schedule and scope. Planning for the next tranche of digital forms is underway.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 4052 | Windows Server Upgrades | Health | Assets/Materials Management | Upgrade of operating systems across SWARH Server environment​. This will provide enhanced performance and scalability of IT infrastructure and simplify management and streamline operations through modern tools and features. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-01-31 | 2025-02-01 |  | 2025-02-01 | 5000 |  | 2025-02-28 |  | 2026-12-20 |  | 2806000 |  |  |  | Green | Green | Green | The project is on schedule with the overall project tracking ahead of Schedule and Budget with 72% of servers upgraded.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 4053 | PACS Replacement | Health | Systems Management | Raplace the existing medial imaging Picture Archiving Communication System (PACS) used by Barwon Health Medical Imaging services. The current system is old and now unsupported with no capacity to upgrade to a new version. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-09-01 | 2025-01-16 |  | 2025-01-16 | 5000 |  | 2025-02-01 |  | 2025-10-30 |  | 2295508 |  |  |  | Green | Green | Red | Successful deployment of the test environment enabled the vendor to test end to end functionality of their migration solution. Storage and migration solutions proposed by the vendor require improvement to meet the project timelines.
Q1 25-26 | Department of Transport and Planning | DTP | 4054 | Energy Digital Transformation | Transport and Vehicles | Organisational Management | The Energy Digital Transformation project aims to enhance the Impact Assessment Unit’s digital capabilities to improve operational efficiency, customer engagement, and overall service delivery. | Closed - Completed | Increased Quality (Non Financial) | 2025-09-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-10 |  | 2025-09-30 |  | 1123594 | 1230577 |  |  | Green | Green | Green | The project has been now closed as the delivery is complete.
Q1 25-26 | Department of Jobs, Skills, Industry and Regions | DJSIR | 4055 | TAFE Customer Relationship Management (CRM) tool phase 2 | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery and the TAFE Network work to improve student experiences and industry outcomes. This phase launches a modern CRM to streamline enrolments at two TAFEs and boost industry engagement across six. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-17 | 2024-11-30 |  | 2025-02-19 | 1 |  | 2025-03-24 |  | 2025-11-30 |  | 4718530 |  |  |  | Green | Green | Amber | The project status is Amber due to recent proposed changes in the planned budget, scope, and timeline. The Student Acquisition Module is scheduled to be completed for 2 TAFEs in November
Q1 25-26 | Department of Transport and Planning | DTP | 4056 | Two-way radio | Transport and Vehicles | Communication | The project will leverage the state emergency radio network to implement two-way radio communication system, enabling enhanced safety of roadside operations through real-time location monitoring, duress alarm capability, and broader coverage. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-01 | 2024-12-31 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2025-12-01 | 2026-04-30 | 1507000 |  |  |  | Amber | Green | Green | The project is tracking well against the project scope, budget, and schedule.
Q1 25-26 | Department of Transport and Planning | DTP | 4057 | OneView Separation | Transport and Vehicles | Systems Management | The project will migrate the Medical Review application to a dedicated instance of Dynamics 365 platform, addressing audit privacy concerns and ensuring stronger compliance with security standards and enhancing the protection of sensitive information | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-09-24 |  | 2024-09-25 | 0 |  | 2024-10-01 |  | 2025-07-22 | 2025-11-07 | 1092420 | 1264000 |  |  | Green | Amber | Green | The domain change and separation changes have been completed successfully, the project is now in the realise phase, we have completed re-testing of the services and are currently reviewing the outcomes, we will then start the project closure process.
Q1 25-26 | Department of Transport and Planning | DTP | 4058 | Transport Victoria website Release 2 and Release 3 | Transport and Vehicles | Development and Integration | The project will consolidate existing digital channels, delivering an enhanced customer experience that integrates all modes of transport, and enables longer term operational efficiencies by simplifying the underlying technical infrastructure. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2025-01-06 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2026-06-30 |  | 8119044 |  |  |  | Amber | Amber | Amber | The project status is amber due to forecast and funding issues. The project is working on resolving these issues to get the project back to green.
Q1 25-26 | Department of Transport and Planning | DTP | 4059 | Pay Portal for Public Transport Ticketing (PTT) | Transport and Vehicles | Development and Integration | The project will roll out a digital pay portal, enabling commuters to interact with the new public transport ticketing (PTT) system, providing faster and easier ticketing transactions for Victorian commuters. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2027-05-13 | 2027-06-30 | 16700000 |  |  |  | Amber | Amber | Amber | The project is amber due to dependencies impacting the project schedule. The project is working on mitigating the risks of delays to get the project back to green.
Q1 25-26 | South West Alliance of Rural Health | SWARH | 4060 | Citrix environment upgrade | Health | Systems Management | Upgrade to the current Long Term Service Release (LTSR) of Citrix to improve platform performance and supportability. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-10-01 | 2024-10-30 |  | 2024-11-30 | 5000 |  | 2025-01-01 |  | 2025-05-31 | 2025-12-01 | 4467000 |  |  |  | Green | Green | Amber | OS upgraded at all sites (approx. 3000 thin clients) The project has been aligned to the existing Windows 11 upgrade project and this has led to a minor delay of the original schedule.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4062 | Claims Systems Modernisation Initiative - Phase 1 | Employment, Skills and Workplace | Customer Relationship Management | The project will deliver a new claim management solution based on the already established CRM platform uplifting both usability & functionality to improve claims management. Phase 1 will roll out the functionality to WorkSafe's internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-24 | 2025-02-24 |  | 2025-02-24 | 0 |  | 2025-02-25 |  | 2025-12-31 |  | 36083436 |  |  |  | Green | Amber | Red | The project reported a Red status due to schedule delays that have been caused by greater than anticipated effort for solution delivery. The project team has completed re-baselining activity for schedule and cost that is pending change request approval.
Q1 25-26 | South East Water | SE Water | 4064 | Asset Management Platform Uplift | Environment and Water | Assets/Materials Management | Upgrade of SEW's Asset Management system from on-premise to cloud including major version uplift. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-07-01 | 2025-03-15 |  | 2025-03-15 | 0 |  | 2025-03-17 |  | 2025-12-19 |  | 1305000 |  |  |  | Green | Amber | Green | Project is reporting GREEN after the successful go-live of the new cloud platform in September. Project currently in hypercare with plan to close out project by mid-December.
Q1 25-26 | South East Water | SE Water | 4065 | Enterprise Telephony Uplift | Environment and Water | Communication | Replacement and uplift of SEW's enterprise telephony solution across the organisation. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2025-01-06 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2025-11-30 |  | 1220000 |  |  |  | Green | Green | Green | Phase 2 of telephony solution roll out underway did initial design work completed. Back-end development in progress with plans in place to roll-out to remaining in scope areas within Q2 FY26.
Q1 25-26 | CenITex | CenITex | 4066 | Software Defined Datacentre (SDDC) Migration | Government and Economy | Assets/Materials Management | To design configure and consume an alternate VMWare based Private Cloud platform, and migrate Cenitex and customer applications from the current platform to the Multicloud solutions including a new IaaS Platform with built-in backup capability. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-02-21 | 2025-04-01 | 2025-02-27 | 2025-02-27 | 0 |  | 2025-11-30 | 2025-03-10 | 2025-11-30 |  | 1431025 | 1427929 |  |  | Green | Green | Green | Project is tracking to plan.
Q1 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4069 | High Performance Compute and Storage infrastructure refresh and upgrade (HPC) | Health | Assets/Materials Management,Systems Management | The project will deliver a refreshed and upgraded High Performance Compute (HPC) and Storage infrastructure for Peter Mac Research, replacing outdated hardware with advanced, high-performance equipment. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-11-28 | 2026-03-30 |  | 0 | [12 empty] | Business case has been drafted and is planned to be presented to the Board to seek funding approval in the next months.
Q1 25-26 | Peter MacCallum Cancer Centre | Peter MAC | 4070 | Network Infrastructure Refresh | Health | Assets/Materials Management,Systems Management | The project will deliver a comprehensive refresh of Peter Mac's network infrastructure, including all physical components and the provision of layer 2 and layer 3 services across the WAN, LAN, and WLAN. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-10-31 | 2026-02-27 |  | 0 | [12 empty] | The business case for Stage 1 of the Network Refresh Program has been approved. The preferred vendor has been selected, and the tender process is being finalized to commence the Implementation Planning Study
Q1 25-26 | State Revenue Office | SRO | 4071 | Inbound Correspondence | Government and Economy | Development and Integration | This Project focuses on inbound communication – phone calls, forms, and emails initially. It aims to enhance data quality, streamline processes, and improve communication channels to deliver a seamless customer experience and boost staff productivity | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 181072 |  | 2025-07-02 |  | 2026-06-30 |  | 5390331 | [5 empty] | Amber | Onboarding and start-up activities underway. Reporting as amber due to minor schedule delays. Return to green plan in place.
Q1 25-26 | State Revenue Office | SRO | 4072 | Enabling Technology | Government and Economy | Development and Integration | This project is establishing enabling technologies and processes to enhance security and uplifting capabilities for future project delivery. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-02-01 | 2025-06-30 |  | 2025-07-01 | 294163 |  | 2025-07-02 |  | 2026-03-27 |  | 1232673 | [5 empty] | Amber | Delivery activities have commenced. Reporting amber while resolving some dependencies which may affect schedule.
Q1 25-26 | Western Health | WH | 4073 | Network Switches Asset Replacement 23/24 | Health | Development and Integration | End of life replacement of network switches at Sunshine Hospital to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2024-02-23 |  | 2024-02-26 | 0 |  | 2024-11-18 |  | 2025-08-26 | 2026-01-15 | 4156643 |  |  |  | Green | Green | Green | Phase 2 of 3 to be completed by 11 November 2025 in accordance with plan. Phase 3 and overall project will be completed by 15 January 2026
Q1 25-26 | Grampians Rural Health Alliance | GRHA | 4074 | Grampians Health Success Factors Phase 3 | Health | Human Resources | The regional adoption of the full Grampians Health instance of SAP Success Factors by GRHA Health Services (Core HR, Recruitment, Onboarding, Payroll, Performance & Goals and Integration Centre). | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-05 | 2025-10-31 |  |  | 78000 | [12 empty] | Phase 3 scoping continuing for the GRHA implementation. RFP tender process completed and awaiting recommendation.
Q1 25-26 | Melbourne Water | MELB Water | 4076 | Mobile Device Management | Environment and Water | Assets/Materials Management | Enhance support for flexible remote working arrangements for staff improving management of corporate devices by implementing a system that effectively addresses the challenges of remote device management and supports Bring your own device policies. | Postponed |  | 2025-09-08 | PMBoK | 2024-08-21 | 2025-05-21 | 2026-09-12 |  | 0 | [5 empty] | 0 | [6 empty] | As at 20250930: A decision has been made to delay commencement of this project until Q1 FY26/27. Project is on hold.
Q1 25-26 | Department of Education | DE | 4078 | Academy Customer Relationship Management_Course Management | Education | Customer Relationship Management,Data Management,Reporting | The project will improve business processes focusing on the Victorian Academy of Teaching and Leadership’s relationship management and enables the effective marketing management delivery and reporting of professional learning to Victorian educators. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-08-16 |  | 2024-08-30 | 0 |  | 2025-01-28 |  | 2026-08-13 |  | 9649702 |  |  |  | Green | Green | Amber | The project reported an Amber status due to additional technical work that has been identified to meet requirements. This poses a risk to the release and Go-Live date. A resolution will be agreed by Q2 2025-26.
Q1 25-26 | Yarra Valley Water | YV Water | 4080 | IT Systems Monitoring & Logging | Environment and Water | Security Management ,Systems Management,Visualisation | Implement a platform which will encompass comprehensive monitoring, logging, synthetic monitoring, and a unified monitoring dashboard to enhance security, improve reliability, and visibility into our IT infrastructure and application performance. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-31 |  | 2025-02-04 | 48000 |  | 2025-02-04 |  | 2027-02-28 |  | 1334300 |  |  |  | Green | Green | Green | Project completed Production environment build. This has enabled logging agents to be rolled out to IT infrastructure in multiple waves. Commenced build of IT infrastructure monitoring dashboard and end-to-end monitoring for pilot application.
Q1 25-26 | Department of Education | DE | 4081 | Service Tracking and Reporting Legacy (STaR) | Education | Communication,Data Management,Forms Management,Reporting ,Tracking and Workflow | The solution will uplift user experience for staff through better controls, efficient case management, robust data visualisations and reporting. Providing actionable insights to influence operational or policy changes for better student outcomes. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-01 | 2024-10-31 |  | 2024-11-20 | 0 |  | 2024-12-01 |  | 2025-06-30 | 2025-10-19 | 3000000 |  |  |  | Amber | Amber | Amber | The project is reporting Amber due to system testing delay. Product development testing completed. The delivery team are finalising pre-production quality assurance and security activities in readiness for product launch scheduled for 27th October 2025.
Q1 25-26 | Department of Education | DE | 4082 | SupportED (formerly Student Support and Intervention) | Education | Analyses and Statistics ,Customer Relationship Management,Data Management,Records Management ,Routing and Scheduling,Tracking and Workflow | This solution streamlines service referrals and case management. Increasing compliance with privacy information security record keeping and other legal obligations ensuring compliance to the departments legislative and regulatory responsibilities. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2024-12-10 |  | 2025-01-10 | 0 |  | 2025-02-19 |  | 2025-06-30 | 2025-11-28 | 3651000 | 4279159 |  |  | Amber | Amber | Amber | The project is reporting an Amber status due to issues with change management resourcing required to support the roll out. To minimise the impact the project will roll out in a phased approach with selected stakeholders and future statewide roll out in 2026.
Q1 25-26 | Victorian Fisheries Authority | VFA | 4088 | Licensing Quota Management System | Business and Industry | Customer Initiated Assistance,Data Management,Management of Process ,Reporting ,Systems Management | The project will digitise the commercial quota management, licencing and permit application process, by delivering a self-service mobile application for commercial fishers and permit holders, improving access to data and support from VFA. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-01 | 2022-11-14 |  | 2024-07-14 | 0 |  | 2025-01-14 |  | 2026-06-30 |  | 1450000 |  |  |  | Green | Green | Green | The project is progressing well and remains on track against key milestones.
Q1 25-26 | Victorian Rail Track | VicTrack | 4090 | Cyber Security Roadmap | Transport and Vehicles | Security Management | To uplift the cyber-security maturity of VicTrack, fulfil our regulatory obligations under VPDSS and the Essential 8, and secure critical assets against cyber threats. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-31 | 2025-03-19 |  | 2025-03-19 | 0 |  | 2025-03-19 |  | 2028-06-30 |  | 12530000 |  |  |  |  | Amber | Green | The program has moved from Amber to Green in the last quarter. The program will continue to monitor progress against the re-baselined schedule, however it's likely some Year 1 projects will carry over to Year 2. There is no cost impact were this to occur.
Q1 25-26 | Victorian Rail Track | VicTrack | 4091 | Project Backup Server & Storage Replacement | Transport and Vehicles | Data Management | Refresh of the current storage and backup solution to improve storage capacity, introduce additional security features, uplift to provide better resilience against modern cyber-attacks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-06 | 2025-06-27 |  | 2025-06-27 | 0 |  | 2025-06-27 |  | 2026-06-30 |  | 1594439 |  |  |  |  | Amber | Green | Project is on track
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4094 | Payroll Technical Upgrade Project | Environment and Water | Human Resources | The project involves the technical upgrade of DEECA's SAP Payroll solution, as the current license and version support are due to expire by the end of 2025. Upgrading to SAP H4S4 is a mandatory requirement to ensure payroll business continuity. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-11-04 | 2024-12-24 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2025-12-19 |  | 3750000 |  |  |  |  | Green | Green | The project is tracking well against approved scope, budget and schedule. Testing activities are completed and deployment preparation progressing well to the target date in October.
Q1 25-26 | Victorian Public Sector Commission | VPSC | 4102 | Cloud Migration and Transformation | Government and Economy | Analyses and Statistics | Modernising VPSC’s analytics by migrating to a secure cloud platform using Microsoft Fabric, Power Platform, and Entra ID to streamline reporting, improve data quality, and enable scalable, AI-driven workforce insights. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-29 | 2024-12-19 |  | 2024-12-19 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1773267 |  |  |  |  | Green | Green | The VPSC Cloud Transformation project is progressing well. This period, the team advanced the core system build, setting up for future data migration and improved digital services. Governance has been strengthened with a dedicated project control group, ensuring oversight and alignment with organisational goals. An external auditor continues to provide independent assurance and support best practice. The team is working closely with users to ensure the solution meets future needs.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4103 | Common Technology Platform (CTP) Program - Phase 3 | Government and Economy | Security Management | The CTP Program was established to deliver the technology strategy via a 3-year phased approach. Phase 3 will uplift the 2 remaining platforms (spatial and digital) and enhance platforms established during previous phases. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-03 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1798000 |  |  |  |  | Green | Green | The project is on track as per the endorsed baseline delivery plan and budget.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4104 | Cyber Security Uplift Program | Government and Economy | Security Management | Cyber Security program will deliver a set of controls, processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-01 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2027-06-30 |  | 6034000 |  |  |  |  | Green | Green | The project is on track as per the endorsed delivery plan and budget.
Q1 25-26 | Hume Rural Health Alliance | HRHA | 4106 | Cyber Security Maturity Uplift implementation | Health | Security Management | The purpose of this project is to ensure a regional uplift in Cybersecurity through reducing risks uplifting governance and risk management practices and alignment to the Department of Health's Cyber Security Assurance Framework. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-02 | 2024-02-12 |  | 2024-02-12 | 0 |  | 2024-07-01 |  | 2027-06-30 |  | 1950000 |  |  |  |  | Green | Green | Project activities remain on track.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4107 | Claims Management System Uplift for Workplace Injury and Rehabilitation Compensation (WIRC) Amendment Act | Employment, Skills and Workplace | Systems Management | This project will operationalise the proposed WIRC Act Amendment Bill (now WIRC Amendment Act 2025) and uplift existing claims management systems to ensure high-quality service and improve support to users of Victoria’s workers compensation scheme. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Waterfall | 2024-11-25 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-03-05 |  | 2026-12-15 |  | 1728437 |  |  |  |  | Amber | Green | WIRC Act Amendment Bill reached Royal Assent on 5 August 2025. Required system changes to support Family Support changes on track.
Q1 25-26 | South East Water | SE Water | 4108 | Service Management System Implementation | Environment and Water | Systems Management | Replacement and transformation of SEW's internal Service Management solution used across multiple business functions. This project will deliver uplift in internal capabilities and deliver efficiencies through streamlining service management processes | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2024-10-01 | 2025-03-28 |  | 2025-04-01 | 0 |  | 2025-04-01 |  | 2026-01-30 |  | 1380500 |  |  |  |  | Green | Amber | Project reporting AMBER due to delays with Phase 1 resulting in the go-live being pushed back to end of October 2025, in order to resolve issues identified. Remaining phases remain on track and within initial project timeline at this stage.
Q1 25-26 | South East Water | SE Water | 4109 | Payment Gateway Replacement | Environment and Water | Financial Management | Replacing current payment gateway solution which is end of life. Project will move all existing payment channels for customers across to a new provider. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-01 | 2025-02-28 |  | 2025-03-10 | 0 |  | 2025-04-01 |  | 2025-11-30 |  | 2120000 |  |  |  |  | Amber | Green | Project reporting GREEN due to a successful deployment and cutover to new payment gateway provider. All existing payment channels successfully migrated with no major issues. Some remaining scope items to be closed out in Q2.
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4111 | Cheques Migration Strategy | Employment, Skills and Workplace | Financial Management | This project will operationalise the Victorian Government directive to cease cheque payments and will implement complex system changes to ensure faster payments for injured workers and providers and reduce administration costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2024-10-08 | 2025-05-27 |  | 2025-05-28 | 0 |  | 2025-05-28 |  | 2027-12-31 |  | 2143701 |  |  |  |  | Green | Green | On track
Q1 25-26 | Department of Transport and Planning | DTP | 4112 | Records Management Uplift - Stage 2b | Transport and Vehicles | Records Management | The project will review and refine the records management environment and consolidate organisational data into Records365, standardising and uplifting the records management solution & practices across the DTP. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-07 | 2025-07-10 | 2025-12-01 |  | 0 | [12 empty] | The project planning is on track, and initiation activities are ongoing.
Q1 25-26 | Melbourne Water | MELB Water | 4117 | Data Lake | Environment and Water | Data Management | Build a data warehouse solution that is scalable, secure and evolves to meet growing business insights and reporting needs of Melbourne Water. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-02-01 | 2024-04-02 |  | 2024-04-02 | 0 |  | 2024-04-02 |  | 2026-05-15 |  | 3301197 |  |  |  |  | Amber | Green | As at 20250930: Progressing with key data migration and reporting enhancements.
Q1 25-26 | CenITex | CenITex | 4118 | Cenitex Office Relocation | Government and Economy | Assets/Materials Management | Make 35C fit for Cenitex purpose to undertake its core role in providing support and technology solutions for customers across WoVG. With a lease end of Jun’25 at 80C, the timeline to undertake this work is tight with a early June relocation target. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2025-03-20 | 2025-03-20 |  | 2025-03-20 | 0 |  | 2025-03-20 |  | 2025-10-31 | 2025-11-30 | 2570677 | 2567674 |  |  |  | Green | Green | Project is tracking to plan.
Q1 25-26 | Victorian Rail Track | VicTrack | 4120 | HCI Replacement Project | Transport and Vehicles | Systems Management | Hyper-converged infrastructure (HCI) utilises physical servers to create a software-defined IT environment that virtualises all components of traditional hardware-based systems. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-05-16 |  | 2025-05-16 | 0 |  | 2025-05-16 |  | 2026-12-31 |  | 9000000 |  |  |  |  | Green | Green | Project is on track to deliver the HCI replacement as required.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 4121 | Replacement Document and Records Management System | Community Services | Records Management | Replace the existing out-of-support records management system (Housing TRIM) with a new, supported record keeping system that uses cloud storage and provides staff with improved business functionality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-29 | 2025-04-09 |  | 2025-04-09 | 351860 |  | 2025-04-09 |  | 2026-03-31 |  | 5898928 | 5642259 |  |  |  | Amber | Amber | Project is progressing but is Amber primarily due to issues identified in system testing. Impact to schedule is currently being assessed.
Q1 25-26 | Melbourne Water | MELB Water | 4127 | Asset Maintenance application upgrade | Environment and Water | Tracking and Workflow | Upgrade of our asset management system to a modern platform that enhances scalability, security, and usability. Ensuring ongoing support beyond 2025, reduces operational risk, and provides advanced features and improved reporting. | Initiated |  |  | Waterfall | 2023-10-09 | 2026-04-09 |  |  | 0 | [12 empty] | 20250930 Ongoing workshops to baseline approach to re-implement/upgrade/resolve issues.
Q1 25-26 | Melbourne Water | MELB Water | 4128 | SCADA For Our Future | Environment and Water | Assets/Materials Management | A next-generation system to enhance real-time monitoring, decision-making, and automation across our water, sewerage, & drainage networks. Providing advance alarm and incident management to meet growing service complexity and performance expectations | Initiated |  |  | Waterfall | 2019-10-25 | 2025-11-25 |  |  | 0 | [12 empty] | As at 20250930: design workshops commenced with preferred supplier working towards Business Case submission before end of 2025.
Q1 25-26 | Melbourne Water | MELB Water | 4129 | Dam Surveillance Information System | Environment and Water | Management of Process | Replacement of an outdated system with a modern, fully supported solution that brings enhanced automation, smarter features, and improved reporting—empowering the Water Control teams to work more efficiently and make better-informed decisions | Delivery | Risk Reduction (Non Financial) |  | Agile | 2023-05-10 | 2024-12-10 |  | 2024-12-10 | 0 |  | 2024-12-10 |  | 2026-10-05 |  | 3340950 |  |  |  |  | Amber | Green | 20250930 On premise solution approved by architecture forums. Vendor chosen via tender process and contract to be completed. Project to re-basline schedule.
Q1 25-26 | Treasury Corporation of Victoria | TCV | 4130 | Infrastructure IT Refresh | Government and Economy | Systems Management | Deployment of a resilient IT infrastructure with cloud-based disaster recovery and secure remote access. It will enhance system uptime, disaster recovery speed and secure remote work capabilities whilst ensuring continuity of TCV’s critical systems. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2025-04-01 | 2025-04-22 |  | 2025-04-22 | 0 |  | 2025-06-20 |  | 2025-11-30 |  | 1476000 | 1536000 |  |  |  | Green | Green | Delivery of the majority of project components completed within this period. Delay in deploying remote access component. Costing still remains within scope.
Q1 25-26 | Western Health | WH | 4132 | Workstation on Wheels (WoW) replacement | Health | Systems Management | This project will replace end-of-life hardware for Workstations on Wheels (WoW) with updated hardware and software, enabling patient record access and update for doctors and nurses to provide quality patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-02-24 | 2025-06-05 |  | 2025-06-06 | 0 |  | 2025-06-23 |  | 2025-11-28 |  | 2400000 |  |  |  |  | Green | Green | Equipment deliveries completed. Implementation commencing
Q1 25-26 | Western Health | WH | 4134 | Network Switches Asset Replacement 24/25 | Health | Systems Management | End of life replacement of network switches across WH sites to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2025-04-23 |  | 2025-04-24 | 0 |  | 2025-08-04 |  | 2026-05-25 | 2026-07-24 | 2353000 | [5 empty] | Green | Detailed project schedule baselined. Equipment orders placed.
Q1 25-26 | Holmesglen Institute of TAFE | Holmesglen TAFE | 4135 | ICT Infrastructure (Servers, LAN, Wifi, Telephony) & Data Centre Refresh | Employment, Skills and Workplace | Systems Management | The project will replace and upgrade the end-of-life ICT infrastructure and data centre with enhanced cyber security protection, minimising security risks and enabling faster, advanced technology access for students and staff at Holmesglen. | Initiated |  |  | Waterfall | 2025-03-26 | 2025-07-28 | 2025-09-30 |  | 0 | [12 empty] | Following formal tender notification, contract negotiations with the selected vendor were successfully completed by the end of Q1, culminating in the signing of the agreement. Hardware required for the infrastructure refresh has been ordered, and a project kickoff meeting is scheduled for early Q2 to initiate implementation planning and stakeholder alignment.
Q1 25-26 | Western Health | WH | 4136 | Automatic Dispensing Cabinets (ADC) | Health | Systems Management | Implementation of automated medication cabinets replacing manual shelving for electronically tracked & secure storage of Imprest medications, enabling timely & safe medication access for staff at new Footscray Hospital delivering quality patient care | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2019-05-14 | 2019-09-04 |  | 2020-01-06 | 0 |  | 2024-03-04 |  | 2026-06-28 |  | 2502072 |  |  |  |  | Green | Green | Project is on track
Q1 25-26 | Southern Metropolitan Cemeteries Trust | SMCT | 4137 | PeoplePro (Human Resources Information System) | Health | Human Capital / Workforce Management ,Human Resources | SMCT's current human resources system is no longer vendor-supported. A replacement system will provide greater efficiencies, employee experience, decision-making and information through more seamless data management and improved processes. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall Agile hybrid | 2022-07-28 | 2024-10-22 |  | 2024-10-22 | 311733 |  | 2024-11-18 |  | 2027-06-30 |  | 1932705 |  |  |  |  | Amber | Green | Project team overcame functional issues previously reported to implement the system on schedule
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4140 | Permissions Application Project | Environment and Water | Collaboration ,Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | The project will deliver a new system to replace the current Wildlife Licence System, which is now at end-of-life. The new system will feature a self-service portal designed to improve user experience, streamline processes, and enhance compliance. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2026-04-01 |  |  | 390151 | [12 empty] | The project is on track with the agreed schedule. The project has commenced procurement activities and is progressing as planned.
Q1 25-26 | Department of Energy, Environment and Climate Action | DEECA | 4142 | Emergency Resource Management System (ERMS) Project | Emergencies and Safety | Customer Initiated Assistance,Human Capital / Workforce Management | The project will deliver a fit-for-purpose ERMS to reduce the impact of bio-security, agriculture, and other emergencies on the Victorian community and environment through timely and effective preparedness, response, relief, and recovery services. | Initiated |  |  | Hybrid - Waterfall and Agile | 2025-07-01 | 2026-01-30 |  |  | 240000 | [12 empty] | Progressing through the procurement process with expectation that the project will engage the vendor in January 2026.
Q1 25-26 | Hume Rural Health Alliance | HRHA | 4144 | Optima Roster System | Health | Human Capital / Workforce Management | Replacement of end-of-life Rostering system (RosterOn) with upgraded version - Optima | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-04-01 | 2022-05-11 |  | 2022-05-11 |  |  | 2022-10-18 |  | 2024-10-31 | 2025-11-28 | 1118495 | 1711000 |  |  |  |  | Green | The project previously experienced schedule impact due to additional system delivery requirements and risks leading to cost increase. Project team placed mitigation in place to minimise risks and the implementation is currently progressing well in stable environment. 5 affiliated health services have been onboarded with the remaining 2 services on target for November 2025
Q1 25-26 | Court Services Victoria | CSV | 4147 | VCAT Long Term Accommodation (LTA ) - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | The objective of the project requires the preparation of the new VCAT Long Term Accommodation site to be a member of the Cenitex GSP INTERNAL Network for use by CSV/VCAT Staff and Customers. | Delivery | Customer Satisfaction (Non Financial) |  | Waterfall and Agile | 2025-05-06 | 2025-05-06 |  | 2025-05-06 | 0 |  | 2025-07-01 |  | 2026-04-30 |  | 1178028 | [5 empty] | Green | Comms links being commissioned, ready for network commissioning.
Q1 25-26 | Barwon Region Water Corporation | BR Water | 4148 | C1419 - Smart Networks Water - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Water Project will procure, implement and monitor Digital Meters in a series of locations within the Barwon region to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-21 |  | 2023-11-21 | 376900 |  | 2024-03-04 |  | 2028-06-30 |  | 9490000 | [5 empty] | Amber | The Smart Networks Sewer project delivery commenced in March 2024. The project has progressed significantly with key deliverables including the Digital Meter procurement process being close to finalisation, the Data and Device Management platform being stood up and trialled and the identification and progressive updating of supporting processes and solutions.
Q1 25-26 | Barwon Region Water Corporation | BR Water | 4149 | C1441 - Smart Networks Sewer - Proof of Value (POV) | Environment and Water | Assets/Materials Management | The Smart Networks Sewer Project will trial, implement and monitor a series of Sewer Sensors and an analytics capability to capture the benefits, costs, resourcing and effort to inform a Mass Rollout Business Case for PS28. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2023-11-23 |  | 2023-11-23 | 251300 |  | 2024-03-04 |  | 2028-06-30 |  | 7170000 | [5 empty] | Green | The Smart Networks Sewer Proof of Value project commenced in March 2024 The project has progressed significantly with the trialling of both sewer sensors in higher risk locations and an analytics capability to support Barwon Water in forming a predictive view of sewer network behaviour. The knowledge captured from these trial phases informs both the deployment and ongoing monitoring of the sewer sensors and the capturing of benefits for the balance of the project.
Q1 25-26 | Transport Accident Commission | TAC | 4151 | Continuous Delivery 2026 | Transport and Vehicles | Systems Management | The project will deliver enhancement to TAC’s Claims Management system to uplift performance, reduce risk, and improve user experience, ensuring sustained business value and responsiveness to priorities | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 5404953 | [5 empty] | Green | The project is tracking well against the approved plan.
Q1 25-26 | Transport Accident Commission | TAC | 4152 | Microsoft Program of Work for Enterprise Readiness (M-POWER) | Transport and Vehicles | Systems Management | This project will establish a dedicated Microsoft tenancy & cloud infrastructure for TAC, streamlining enterprise systems using a modern platform & minimising the risks associated with legacy technologies to enable more efficient services to clients. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2027-12-31 |  | 20000000 | [5 empty] | Green | 1. Scope remains stable and focused on establishing a new Microsoft environment for TAC 2. Budget is on track and within approved parameters 3. Risks mainly relate to legacy system complexity and vendor capacity, with mitigations in place 4. Schedule holding; procurement adjustments not expected to impact milestones
Q1 25-26 | Melbourne Water | MELB Water | 4153 | Web Enhancements | Environment and Water | Content Management | Additional features to be added to MW website to deliver core functions. | Initiated |  |  | Agile | 2025-02-25 | 2026-11-10 |  |  | 0 | [12 empty] | As at 20250930: Business case to be submitted.
Q1 25-26 | Yarra Valley Water | YV Water | 4154 | Finance Transformation | Environment and Water | Financial Management | Implementation of a new Finance system with integrations, including uplift to operating model. Key outcomes being risk reduction achieved by replacing EoL system plus aligning to business priorities of operational efficiencies and UX improvements. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-09-01 | 2026-08-28 |  |  | 1760200 | [12 empty] | Project team identified and established key business drivers, current state analysis, business case for initiation, business requirements document and procurement strategy progressing.
Q1 25-26 | Melbourne Water | MELB Water | 4155 | OS Upgrade | Environment and Water | Systems Management | Upgrading all laptops and PC's to a new operating system. | Delivery | Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2024-10-24 | 2025-07-25 |  | 2025-07-25 | 0 |  | 2025-07-25 |  | 2026-02-27 |  | 1308000 | [5 empty] | Green | As at 20250930: Project is on track.
Q1 25-26 | Yarra Valley Water | YV Water | 4156 | Customised Collections | Environment and Water | Financial Management | This project will deliver a Customised Collections solution in Oracle CC&B, uplifting YVW’s ability to segment customers and tailor debt management. It will reduce bad debt and improve outcomes for customers and the organisation. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2020-08-01 | 2025-09-17 |  | 2025-09-18 | 888100 |  | 2025-09-18 |  | 2026-05-18 |  | 1119197 | [5 empty] | Green | Delivery Business case is now approved. Commenced detailed discovery workshops with Business for the next level of Business requirements. Recruitment is in progress for the open roles due for later in the project and onboarding immediate new team members.
Q1 25-26 | Yarra Valley Water | YV Water | 4157 | Digital Metering – Customer Solutions for New Segments | Environment and Water | Communication,Content Management,Customer Relationship Management,Development and Integration | The project will enable the implementation of the more complex customer journeys inclusive of the process uplifts required to facilitate the installation of digital meter to more complex and larger scale customer types. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-01 | 2025-08-31 |  | 2025-09-01 | 270000 |  | 2025-09-01 |  | 2026-06-30 |  | 2169620 | [5 empty] | Green | Design requirements defined. Project progressing well
Q1 25-26 | WorkSafe Victoria | WorkSafe | 4158 | Safety CRM (Customer Relationship Management) | Employment, Skills and Workplace | Customer Relationship Management | This project will modernise safety inspection and notification systems to improve frontline efficiency and stakeholder experience. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-14 | 2025-05-28 |  | 2025-05-28 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 4863898 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q1 25-26 | Department of Government Services | DGS | 4159 | Children's Digital Program | Government and Economy | Development and Integration | Developing an end-to-end digital experience from birth to school that provides parents with a digital family organiser to manage key information about their child. | Delivery | Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-03 | 2025-06-24 |  | 2025-06-24 | 0 |  | 2025-06-25 |  | 2026-09-30 |  | 17003000 | [5 empty] | Amber | The program status is Amber due to technical design complexities. Expected to return to Green with Phase 1 to be delivered by due date.
Q1 25-26 | Department of Health | DH | 4160 | Data Loss Prevention Phase 1 | Health | Security Management | Conduct detailed current state analysis of DH and DFFH Data Loss Protection (DLP) capability for emails classified as 'Protected' and 'Cabinet-in-Confidence' and implement improved DLP controls to emails, reducing risk of accidental data loss. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-10-27 |  |  | 74200 | [12 empty] | Planning and mobilisation activities are in progress.
Q1 25-26 | V/Line Corporation | V/Line | 4161 | TrackR Stabilisation | Transport and Vehicles | Systems Management | The objective of the project is to stabilise V/Line’s critical train and fleet operations system (TrackR). Stabilisation of TrackR will result in increase in reliability and performance of the system’s key workflows, and improve service delivery. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-09-30 |  |  | 57000 | [12 empty] | Program is tracking to plan with no risks or issues impacting progress. The Program Management Plan (PMP) has been drafted and circulated to stakeholders for approval. Planning and sizing of the stabilisation work has commenced. Recruitment is underway for 3 identified roles to augment the development team.
Q1 25-26 | Goulburn-Murray Rural Water Corporation | GMR Water | 4162 | PC/Laptop Replacement | Environment and Water | Assets/Materials Management | This project will deliver 550 new PCs and laptops, enhancing Goulburn Murray Water’s IT capability by improving performance and reliability, enabling a more productive, digitally enabled workforce for better service delivery. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-03-25 | 2025-09-02 |  | 2025-09-02 | 0 |  | 2025-09-02 |  | 2028-06-30 |  | 1300000 | [5 empty] | Green | The project has commenced with planning and procurement activities now underway. Initial assessments of staff requirements have been completed and deployment scheduling and coordination with relevant departments are in progress.
Q1 25-26 | Melbourne Health | Melb H | 4165 | E-referral for outpatient specialist clinics | Health | Development and Integration | Implementing an Electronic Medical Record integrated e-Referral system across the 4 Parkville Precinct hospitals, which enhances management of external GP/Specialists referrals to outpatient specialist clinics and improves patient data quality | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-03-03 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-09-01 |  | 2026-08-31 |  | 1180854 | [5 empty] | Green | Project initiation and establishing project governance.
Q1 25-26 | CenITex | CenITex | 4166 | DOH Modern Desktop Implementation | Government and Economy | Assets/Materials Management | The project will support DoH and DFFH to modernise workforce desktop environment, streamlining service provision and enabling workforce efficiency and productivity through modern technology. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2025-07-24 | 2025-07-24 |  | 2025-07-24 | 0 |  | 2025-07-31 |  | 2026-06-30 |  | 1949180 | [5 empty] | Green | Project is tracking to plan.
Q1 25-26 | Barwon Region Water Corporation | BR Water | 4167 | C1073 - Information & Records Management (IRM) | Environment and Water | Content Management | This initiative aims to enhance Barwon Water Group's Information Records Management (IRM) capability through a phased maturity uplift. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-09-08 |  | 2025-09-08 | 537000 |  | 2025-09-08 |  | 2026-10-31 | 2026-12-31 | 580000 | [5 empty] | Green | With the approval of the business case the system integrator has now been engaged. Detailed design and implementation of Gov365 can now proceed.
Q1 25-26 | Bendigo Kangan Institute of TAFE | BKI TAFE | 4168 | Artificial Intelligence for Recognition of Prior Learning | Employment, Skills and Workplace | Development and Integration | On behalf of the Victorian TAFE Network, BKI will pilot an artificial intelligence (AI) solution to uplift the assessment capability in the Recognition of Prior Learning (RPL), enabling a more efficient processing time for assessors and applicants. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-08-28 | 2025-12-31 |  |  | 180000 | [12 empty] | The Common Funding Agreement has been executed between Bendigo Kangan Institute and the Department of Jobs, Skills, Industry and Regions, marking the first of eight project milestones and the initial funding milestone under the AI-enabled Recognition of Prior Learning (RPL) pilot. A Project Control Group (PCG) has been established to oversee implementation, with its inaugural meeting to be held in October 2025. Members are expected to endorse the project’s governance framework and confirm Gippsland TAFE and Chisholm Institute as key delivery collaborators.
Q1 25-26 | South East Water | SE Water | 4170 | Acumen Phase 3 | Environment and Water | Business Intelligence | Acumen Phase 3 will deliver remaining data sources into new Acumen platform. A subset of Data Modelling will be undertaken to support the report development required to decommission the legacy data warehouse and reporting environment. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2025-05-01 | 2025-07-28 |  | 2025-07-30 | 0 |  | 2025-07-30 |  | 2026-12-18 |  | 8220471 | [5 empty] | Green | Project reporting GREEN, with development commenced for high priority data sources. Project on track as per baselined schedule.
Q1 25-26 | Victorian Gambling and Casino Control Commission | VGCCC | 4172 | Compass - Gambling License System (GLS) replacement project - Release 2 | Law and Justice | Customer Relationship Management | Release 2 will deliver the remaining components of the new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure improving ICT capabilities. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-14 | 2025-09-12 |  | 2025-09-12 | 120000 |  | 2025-09-15 |  | 2026-03-23 |  | 2541000 | [5 empty] | Green | This project will replace the remaining components of the legacy licensing system with Salesforce. The build phase is progressing as planned, and the project is tracking well against budget, schedule and scope.
Q1 25-26 | Department of Health | DH | 4173 | Maternal and Child Health IT System | Health | Customer Relationship Management | Deliver a new statewide IT system to support the delivery of Maternal Child Health services, providing additional functions as well as accommodating future growth in service delivery and customer base. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2025-03-03 | 2025-05-02 |  | 2025-05-02 | 163733 |  | 2025-05-02 |  | 2027-06-30 |  | 12286267 | [5 empty] | Green | Project is progressing to cost and schedule.
Q1 25-26 | Ambulance Victoria | AVS | 4174 | Mobile Data Network Rural (MDNR) | Health | Communication | The project will upgrade and expand communication services for emergency responders in rural Victoria, improving real-time data access to enable dispatch efficiency, enhancing paramedic safety and better patient care. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-08 | 2022-10-21 |  | 2022-10-21 | 24043 |  | 2024-11-14 |  | 2027-05-30 |  | 24971040 | [5 empty] | Green | Delivery in progress and on track.
Q1 25-26 | South East Water | SE Water | 4175 | Portfolio & Project Management Uplift | Environment and Water | Financial Management | South East Water is uplifting its ERP environment to enable enterprise-wide project and portfolio management. This project will enhance planning execution reporting and data integration across capital and operational projects. | Initiated |  |  | Waterfall | 2025-07-01 | 2026-02-28 |  |  | 1388000 | [12 empty] | Project has commenced working with key stakeholders and vendor to elicit detailed requirements and develop architecture and design artefacts to support the preparation of the business case for implementation.
Q1 25-26 | Emergency Services and Superannuation Fund | ESS SUPER | 4177 | NetSuite General Ledger Implementation | Business and Industry | Financial Management | Replace SunGL (current general ledger system) with Oracle NetSuite to improve efficiency and reduce risk. NetSuite offers a secure scalable cloud-based platform aligned with ESSSuper’s future needs. | Initiated |  |  | PRINCE2 | 2025-07-01 | 2025-10-31 |  |  | 50000 | [12 empty] | Business case is being finalised and approval is being sought in Q2 2025-26.
Q1 25-26 | State Revenue Office | SRO | 4178 | Emergency Services Volunteers Fund | Government and Economy | Development and Integration | From 1 July 2025 the Fire Services Property Levy (FSPL) has been replaced with the Emergency Services and Volunteers Fund (ESVF). From 1 July 202, a new property classification will be introduced for residential PPR and a non-residential fixed charge | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2025-04-02 | 2025-06-30 |  | 2025-06-30 | 208928 |  | 2025-07-01 |  | 2026-06-30 |  | 2208201 | [5 empty] | Green | Project is tracking according to planned activities
Q1 25-26 | State Revenue Office | SRO | 4179 | Enterprise Service Management | Government and Economy | Development and Integration | The State Revenue Office is procuring a modern Enterprise Service Management tool to provide better business outcomes with automation and self-service capabilities. This initiative procures and integrates the tool and implements the required workflow | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2025-03-05 | 2025-06-30 |  | 2025-06-30 | 29739 |  | 2025-07-01 |  | 2027-06-30 |  | 3643630 | [5 empty] | Green | Project start-up activities commenced.
Q1 25-26 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4180 | One-stop shop project | Energy and Resources | Customer Initiated Assistance | Deliver a one-stop shop digital platform to enable Victorian households to be supported by information and access to SEC endorsed installers manage home electrification. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-07-31 |  | 2025-07-31 | 248955 |  | 2025-08-01 |  | 2026-06-30 |  | 7417752 | [5 empty] | Green | Project is tracking to plan.
Q1 25-26 | State Revenue Office | SRO | 4181 | Data Lakehouse Utilisation | Government and Economy | Development and Integration | The establishment of a cloud-based Data Lakehouse is a key element of the SRO's data and analytics strategy to uplift the organisation's data and analytics capacity, capability operational efficiency and reporting. This project includes 2 use cases. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Agile | 2025-02-03 | 2025-06-30 |  | 2025-06-30 | 429284 |  | 2025-07-01 |  | 2026-06-30 |  | 2327800 | [5 empty] | Green | Project tracking according to plan
Q1 25-26 | Department of Health | DH | 4183 | Victorian Patient Transport Assistance Scheme (VPTAS) System Replacement | Health | Customer Initiated Assistance | Implement a new VPTAS claims system that leverages the DFFH-DH Enterprise Payments Platform, enabling digitising of the current paper based claimant forms, providing greater efficiencies in the response to and management of claims. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-31 |  | 2025-07-31 | 89154 |  | 2025-08-01 |  | 2026-04-30 |  | 1710846 | [5 empty] | Amber | Project is progressing but is reporting an Amber status due to refining of requirements. Project is expected to return to Green and is on track to deliver in next reporting period.
Q1 25-26 | Environment Protection Authority | EPA | 4184 | MAJ143 - Land Renewal | Environment and Water | Tracking and Workflow | The project will deliver a digital solution - customer portal, self-triage tools and a web page to improve access to EPA information and advice for land development, enabling environmentally safe outcomes aligned with the Victorian Housing Statement | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2025-05-01 | 2025-05-20 |  | 2025-06-18 | 0 |  | 2025-07-01 |  | 2026-07-31 |  | 1540840 | [5 empty] | Green | The project is on track, delivery delays and risks are being actively managed as well as the key milestones, and Land Development Portal engagement are progressing as planned.
Q1 25-26 | Department of Families, Fairness and Housing | DFFH | 4185 | L17 Family Violence Portal phased upgrade | Community Services | Development and Integration | Upgrade the L17 Family Violence Portal, including software and infrastructure, to the latest supported version, further increasing security and ensuring continuity of service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-05-16 |  | 2025-05-21 | 0 |  | 2025-06-02 |  | 2026-02-13 |  | 1273000 | [5 empty] | Amber | Project is progressing but is experiencing a development issue impacting schedule.
Q1 25-26 | East Gippsland Regional Water Corporation | EGR Water | 4187 | Enterprise Asset Management | Environment and Water | Assets/Materials Management | It is a modern solution for managing the entire asset lifecycle supporting functions such as commissioning maintenance optimization planning reporting and analytics. The system aims to deliver operational cost savings and efficiency improvements. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-10-29 | 2025-01-31 |  | 2025-01-31 | 0 |  | 2025-05-01 |  | 2026-06-30 |  | 1993000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule. Initial build work has been completed, UAT has been successful. Phases one functionally rollout within the next reporting period.
Q1 25-26 | Department of Education | DE | 4190 | Cove (formerly School Compliance) | Education | Tracking and Workflow | The project will re-platform the current assessment and standards management system, improving time to response with evidence attribution and enabling a scalable workforce. | Delivery | Compliance (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-06-30 | 2025-08-15 |  | 2025-08-15 | 0 |  | 2025-08-18 |  | 2026-01-30 |  | 1400000 | [5 empty] | Green | The project is reporting Green and tracking in line with scope and budget.
Q1 25-26 | Department of Education | DE | 4191 | Student Travel System | Education | Management of Process | The project will digitise Student Travelling applications and centralise information, reducing administrative effort and improving accuracy and timeliness of school bus program. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-03-21 |  | 2025-09-08 | 0 |  | 2025-09-08 |  | 2026-03-20 |  | 4242287 | [5 empty] | Amber | The project is reporting Amber due to complexity in engaging geospatial services. The project team are working with procurement to remediate this issue and will revise project timelines when services are secured.
Q1 25-26 | Department of Education | DE | 4192 | School Sport Victoria Website Redevelopment | Education | Management of Process | The project will deliver a modern, secure website to centralise all school sports program information, delivering a comprehensive school sport program information portal to primary and secondary students across Victoria | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-21 | 2025-09-15 |  | 2025-09-15 | 0 |  | 2025-09-30 |  | 2026-04-24 |  | 1200000 | [5 empty] | Green | The project is on track with design complete. Implementation commenced 29th September, 2025.
Q1 25-26 | Department of Education | DE | 4193 | Legacy System Migration Program | Education | Development and Integration ,Security Management ,Systems Management | This program will transition services and systems from outdated infrastructure to modern, scalable and secure infrastructure, minimising security risk and support cost. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | 0 |  | 2025-07-01 |  | 2026-06-30 |  | 7451000 | [5 empty] | Green | The project is on track to deliver the required upgrades within the financial year.