## table
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q4 17-18 | Q1 18-19 | Q2 18-19 | Q3 18-19 | Q4 18-19 (Current) | Reporting Comments
Q4 18-19 | Country Fire Authority | CFA | 2151 | CFA Short Status Messaging (SSM) | Emergencies and Safety | Communication | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | Initiated |  | PRINCE2 | 2010-10-01 | 2018-05-31 | 2019-03-29 |  | 0 | [12 empty] | Key elements of project delivery have been moved from the Multi-Agency Gateway Program (MACG) (led by the Emergency Services Telecommunications Authority) to the Metropolitan Mobile Radio Extension Project (MMR-EP). Delivery of CFA requirements has been reprioritised below other agency deliverables. As a result, the delivery start date is expected in Q1 2019-20.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2152 | Regional Radio Command Service | Emergencies and Safety | Communication | Establish new command and control level voice communication service on the Regional Mobile Radio network. Establish interconnectivity between Regional Radio Command Service, Incident Control Centres and operational facilities | Postponed | 2017-06-30 | Project Management Excellence | 2014-07-01 | 2016-06-30 |  | 2016-06-30 | 8000000 |  | 2016-06-30 |  | 2017-06-30 | 2018-06-30 | 5000000 | [6 empty] | The project has been placed on hold. EMV is exploring possible funding options.
Q4 18-19 | Chisholm Institute of TAFE | Chisholm TAFE | 2153 | Customer Relationship Management Implementation | Education | Customer Relationship Management | To provide an improved service to existing and potential students to maximise the take-up of educational services | Delivery |  | Chisholm PMF (Prince 2 Based) | 2016-06-01 | 2017-05-07 |  | 2017-05-07 | 418304 |  | 2017-05-07 | 2017-05-07 | 2018-03-31 | 2019-12-31 | 3083074 | 3733696 | Amber | Amber | Amber | Amber | Amber | CRM functional for the Enrolment 2018/2019 period and good progress made on enrolment numbers and free TAFE. Project costs are currently being reviewed to determine whether additional funding will be required.
Q4 18-19 | Department of Health and Human Services | DHHS | 2166 | Melton Community Based Ambulatory Care Centre (MCBACC) | Health | Organisational Management | Implementation of the ICT integration solution between five health providers at the new Melton Community Based Ambulatory Care Centre | Delivery |  | PRINCE2 | 2016-07-07 | 2017-11-30 |  | 2017-11-30 | 223020 |  | 2018-01-01 | 2018-01-01 | 2018-12-17 | 2019-09-27 | 1187640 | 1410661 | Green | Green | Amber | Green | Green | The project is progressing to schedule.
Q4 18-19 | Department of Education and Training | DET | 2168 | Exchange Upgrade | Education | Collaboration | The Exchange Upgrade project will upgrade the DET Microsoft Exchange platform from Exchange 2010 to Exchange 2016 (initial plan was to upgrade to Exchange 2013), including migration of all DET users. The system will provide an enhanced email solution for Government school teachers and corporate staff at DET. | Closed - Completed | 2019-06-20 | PRINCE2 | 2013-11-11 | 2015-05-14 |  | 2015-05-14 | 214280 |  | 2015-05-14 | 2015-05-14 | 2017-09-22 | 2019-06-20 | 1045087 | 2644042 | Amber | Amber | Amber | Green | Green | Mail migration and decommissioning of the old platform has been completed. The project is complete and will be closed before the next reporting cycle.
Q4 18-19 | Department of Education and Training | DET | 2169 | International Student Information Management System | Education | Management of Process | This new portal will enable staff at International Education Division (IED) and at schools to manage applications received from international students wanting to study at the Victorian State Government Schools. | Delivery |  | Agile | 2014-01-02 | 2016-05-31 |  | 2016-05-31 | 201000 |  | 2016-05-31 | 2016-05-31 | 2017-12-08 | 2020-01-15 | 905000 | 1742375 | Red | Red | Red | Amber | Amber | Overall status is amber, due to some additional time and funding required to complete the development of the solution. This amber status also reflects current issues relating to a loss of key project team members, which needs to be addressed to minimise associated time and cost impacts to the project. The project is on track in terms of deliverables and plans are underway to return the status to green.
Q4 18-19 | Department of Education and Training | DET | 2173 | CASES Technology Refresh | Education | Systems Management | The CASES Technology Refresh project will perform the 4 year refresh of Government schools' technology environment to support administration and financial management functions. The scope encompasses a server, workstations, switch, UPS, printer and backup service. | Closed - Completed | 2019-06-28 | PRINCE2 | 2014-12-19 | 2016-07-20 |  | 2016-07-20 | 692729 |  | 2016-07-20 | 2016-07-20 | 2017-02-28 | 2019-05-28 | 14707271 | 14950000 | Green | Green | Green | Green | Green | Installation of all IT equipment at schools (network switches, servers, desktops, and printers) is complete. Project outputs have now all been delivered and accepted. Delivery is complete and project is closed.
Q4 18-19 | Department of Health and Human Services | DHHS | 2179 | Health & Hospital Funding Regional ICT cancer Multidisciplinary Meeting Management Project | Health | Customer Preferences | To deliver a software solution to support multidisciplinary team meetings within and across regional integrated cancer services. | Closed - Completed | 2019-05-17 | PRINCE2 | 2012-12-01 | 2017-11-14 |  | 2014-05-19 | 500000 |  | 2018-01-03 | 2018-01-03 | 2019-03-29 | 2019-04-30 | 2000000 |  | Green | Green | Green | Green | Green | Delivery of the software solution was completed on 17 May 2019, this solution is now available for use across regional Victoria. The solution is also available to metropolitan health services. All funding for this project has been expended.
Q4 18-19 | Department of Health and Human Services | DHHS | 2184 | Real-time prescription monitoring system | Health | Data Management | Implement software that transmits pharmacy records in real-time to a centralised database, enabling doctors and pharmacists to make safer clinical decisions prior to prescribing or dispensing medicines at high risk of misuse. | Delivery |  | PRINCE2 | 2016-01-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-07-01 |  | 2020-06-30 |  | 21227000 | 11285526 | Green | Green | Green | Green | Green | Project is progressing to schedule. SafeScript implemention statewide occurred as planned on 1 April 2019 and a mobile version was introduced in May 2019.
Q4 18-19 | Department of Premier and Cabinet | DPC | 2190 | ACHRIS Phase 2 Enhancement Project | Culture, Sport and Recreation | Systems Management | The ACHRIS Phase 2 Enhancement Project will deliver new functionality to AVs online application to support the implementation of the Aboriginal Heritage Amendment Act 21016 and a new infrastructure environment to enable the required flexibility, scalability and operational efficiency to implement these changes. | Closed - Completed | 2019-06-30 | Agile | 2015-01-01 | 2015-12-30 |  | 2015-12-30 | 42900 |  | 2015-12-30 |  | 2019-06-30 |  | 1950000 |  | Green | Green | Green | Green | Green | The ACHRIS Phase 2 Enhancement project was successfully completed on time and within budget with the release of ACHRISv3 on 19 June 2019.
Q4 18-19 | Department of Health and Human Services | DHHS | 2197 | Bendigo Hospital - Electronic Medical Record | Health | Records Management | Electronic Medical Records and Digital Medical Records implementation at the new Bendigo Hospital | Delivery |  | PRINCE2 | 2015-12-23 | 2016-10-05 |  | 2016-10-05 | 11343000 |  | 2016-10-05 | 2016-10-05 | 2018-03-31 | 2020-04-27 | 14987000 |  | Amber | Amber | Amber | Amber | Amber | Due to ongoing negotiations with the vendor the project will work closely with the vendor to ensure the project continues to progress with its final configuration activities.
Q4 18-19 | Department of Health and Human Services | DHHS | 2200 | Replace Integration Solution for Patient and Clinical Information | Health | Development and Integration | Replacement of the integration solution to support Victorian acute public health services with ongoing capability to integrate patient and clinical information within and across health services. | Delivery |  | PRINCE2 | 2016-07-01 | 2016-11-30 |  | 2016-11-30 | 0 |  | 2016-12-01 | 2016-12-01 | 2020-06-30 | 2021-12-30 | 16000000 |  | Green | Amber | Amber | Amber | Green | The program has been re-baselined and endorsed by the Assurance Committee to accommodate Health Service competing local priorities. Program delivery tracking to schedule.
Q4 18-19 | Department of Health and Human Services | DHHS | 2203 | Windows Server Remediation Program | Community Services | Systems Management | Upgrade, replace or decommission outdated servers and database instances. | Closed - Completed | 2019-06-30 | Agile | 2016-06-01 | 2016-06-29 |  | 2016-06-30 | 53000 |  | 2016-06-30 |  | 2019-06-30 |  | 11800000 | 3235305 | Green | Green | Green | Green | Green | Project has delivered its intended result and closeout activities are underway.
Q4 18-19 | Department of Premier and Cabinet | DPC | 2204 | Single Digital Presence | Government and Economy | Content Management | The Victorian Government will make it easier for Victorians to find, access and understand government information by redesigning and re-platforming Premier & Cabinet websites, including vic.gov.au. This project will also reduce the cost and risk associated with digital services and help us create new services faster. | Delivery |  | Agile | 2015-09-17 | 2016-06-30 |  | 2016-06-30 | 118800 |  | 2016-06-30 | 2016-06-30 | 2018-06-30 | 2020-02-28 | 4200000 | 4942000 | Green | Green | Green | Green | Green | In Q4 2018-19 the Single Digital Presence (SDP) continued to consolidate websites onto vic.gov.au and the platform. This included Fire Services Public Sector Innovation Victorian State Budget and DataVic. A template that supports the HTML publication of long form documents to support the digital first approach and move away from PDF’s is now available across the platform. Automation within the platform was increased with the ability to stand up new website instances and regression testing the focus. An accessibility review of the design system was undertaken and remediations adopted.
Q4 18-19 | Department of Health and Human Services | DHHS | 2205 | Unique Patient Identifier | Health | Development and Integration | Implementation of a state-wide Enterprise Master Patient Index (EMPI) to support the objectives of Health 2020, the Clinical Information Exchange (CIE), improved analytic capability and access to My Health Record. | Delivery |  | PRINCE2 | 2016-07-01 | 2016-12-10 |  | 2016-12-10 | 0 |  | 2017-02-01 |  | 2020-06-30 |  | 17100000 |  | Red | Green | Green | Amber | Amber | Awaiting health service acceptance of department's recommended legal and privacy position, prior to progressing.
Q4 18-19 | Gippsland Health Alliance | GHA | 2209 | Electronic Medical Record and Community Health (EMRCH) | Health | Customer Relationship Management | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | Delivery |  | PMBoK | 2016-02-02 | 2017-10-30 |  | 2017-11-01 | 554038 |  | 2018-01-09 | 2018-01-09 | 2019-12-31 | 2020-04-30 | 7419045 |  | Green | Green | Green | Green | Amber | Phase 2 of the project has been revised and endorsed by the steering committee. It has been agreed a go-live date in early February 2020 for Inpatient units and early April 2020 for Mental Health and Theatre to better manage go live change management and support.
Q4 18-19 | Hume Rural Health Alliance | HRHA | 2210 | Goulburn Valley Health Redevelopment | Health | Systems Management | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | Delivery |  | PRINCE2 | 2016-04-20 | 2019-05-31 | 2018-08-01 | 2018-08-01 | 400000 |  | 2018-10-31 |  | 2020-05-29 |  | 4600000 |  |  | Green | Green | Green | Green | Project is on schedule
Q4 18-19 | Goulburn-Murray Rural Water Corporation | GMR Water | 2215 | ECMS Upgrade / Replacement | Environment and Water | Document Management | The existing Records and Document Management System is not meeting the organisation's requirements. The objective of this project is to define the organisation's requirements and to source and implement an Enterprise Content Management System (ECMS) that meets the organisation's current and future requirements for Records, Documents and Information Management. | Closed - Completed | 2019-06-30 | PRINCE2 | 2016-01-18 | 2017-02-28 |  | 2017-02-28 | 37238 |  | 2017-02-28 | 2017-02-28 | 2018-09-06 | 2019-06-30 | 1557208 | 1957275 | Green | Green | Green | Green | Green | Post delivery of the new ECM system, the Knowledge management and Operations team continue to support staff in the usage of the system. Decommissioning activities for the old system have been completed and the project has been closed.
Q4 18-19 | Melbourne Health | Melb H | 2224 | Enterprise Billing System | Health | Financial Management | Implementation of an Enterprise Billing System will enable Melbourne Health to achieve a centralised approach for managing patient billing services and improving revenue collection across all clinical areas. | Closed - Completed | 2019-06-30 | PRINCE2 | 2016-03-01 | 2016-05-01 |  | 2016-05-01 | 0 |  | 2016-05-01 |  | 2018-08-01 | 2018-11-07 | 4800000 | 4854146 | Amber | Amber | Amber | Amber | Green | Phase 1 of project successfully completed. Maintenance and support for phase 1 established. Phase 2 will not progress due to a requirement to meet EMR integration requirements. Project Closed.
Q4 18-19 | Melbourne Health | Melb H | 2226 | CAFM Project - Computer Aided Facilities Management | Health | Assets/Materials Management | Implementation of an electronic Computer Aided Facilities Management system that will provide functionality for: Help desk; Task triage; Resource allocation; Job Management; Maintenance & Scheduled Management; Contract Management; Asset & Life Cycle Management; Property and Estate Management; Facility Condition Assessment and Maintenance management. | Delivery |  | Hybrid - Agile and PRINCE2 | 2015-11-01 | 2015-11-01 |  | 2018-11-27 | 100000 |  | 2019-02-05 | 2019-02-18 |  | 2020-09-01 | 0 | 3900000 |  |  | Green | Green | Green | Project is on track.
Q4 18-19 | Metropolitan Fire and Emergency Services Board | MFESB | 2241 | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and Safety | Content Management | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | Delivery |  | MFB Project Management Framework (PME) | 2013-07-01 | 2014-07-09 |  | 2014-07-09 | 60737 |  | 2014-07-09 | 2014-07-09 | 2017-06-30 | 2020-04-30 | 1200000 | 2327490 | Green | Red | Amber | Red | Green | The MFB Board approved a revised MFBDocs strategy on 29 April 2019. The revised strategy ensures organisational needs of each MFB department are met. The new completion date for the migration of data and production release is 30 April 2020. New data migration activities are on track.
Q4 18-19 | Metropolitan Fire and Emergency Services Board | MFESB | 2243 | Legacy SAN Storage Refresh | Emergencies and Safety | Systems Management | Replacing legacy and upgrading network storage. | Delivery |  | MFB Project Management Framework (PME) | 2015-07-01 | 2015-10-01 |  | 2015-10-01 | 0 |  | 2015-10-01 | 2015-10-01 | 2017-06-30 | 2019-12-31 | 1500000 | 1730000 | Amber | Green | Green | Green | Green | Contract negotiations nearing completion. It is expected that the procurement will be completed in July 2019 with implementation by December 2019.
Q4 18-19 | Metropolitan Fire and Emergency Services Board | MFESB | 2244 | Mobile Data for Vehicles Pilot | Emergencies and Safety | Communication | Pilot project of mobile data devices installed in fire appliances to receive and display relevant event information. | Delivery |  | MFB Project Management Framework (PME) | 2015-07-01 | 2016-02-04 |  | 2016-02-04 | 0 |  | 2016-02-04 | 2016-02-04 | 2017-06-30 | 2020-06-30 | 1750000 | 2486153 | Amber | Amber | Amber | Amber | Amber | MD4V product expected to be ready for pilot on 31 July 2019. Support processes planned for mid-august with the pilot commencing at end of August 2019. Q4 status is amber due to existing resourcing issues that may have impact on the schedule and ICT ability to support the pilot. Recruitment of resource has commenced to resolve this issue.
Q4 18-19 | Monash Health | Monash H | 2247 | Electronic Medical Record | Health | Records Management | Implementation of an Electronic Medical Record (EMR) system, including clinical documentation, results viewing, and medications management | Delivery |  | PRINCE2 | 2016-01-01 | 2016-01-01 |  | 2016-01-01 | 0 |  | 2017-08-01 |  | 2019-12-31 |  | 57700000 |  | Green | Green | Green | Amber | Green | The project is tracking to schedule
Q4 18-19 | Victorian Ports Corporation Melbourne | VPCM | 2262 | Vessel Traffic Services Systems Upgrade | Transport and Vehicles | Communication | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | Delivery |  | VPCM (PMBoK) | 2015-12-03 | 2018-09-28 | 2018-11-30 | 2018-12-10 | 0 | 0 | 2019-01-10 | 2019-01-10 |  | 2020-12-18 | 0 | 9078548 |  |  |  | Green | Green | Preliminary design phase is underway
Q4 18-19 | Public Record Office Victoria | PROV | 2263 | Digital Archive Program | Government and Economy | Content Management | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | Delivery |  | Hybrid - Agile and PRINCE2 | 2015-07-01 | 2015-07-01 |  | 2015-07-01 | 200000 | 0 | 2015-07-01 | 2015-07-01 | 2018-06-30 | 2020-02-16 | 4062000 | 5500000 | Green | Green | Green | Green | Amber | Currently on track to meet revised implementation date of February 2020. Delays have been incurred due to resource shortages in the Technical Services team to assist implementation and effectively manage new and existing vendors.
Q4 18-19 | Victoria Police | VicPol | 2265 | BlueConnect - Mobile Technology | Law and Justice | Collaboration ,Data Management | Handheld, mobile devices to put critical information into the hands of frontline police and allow them to feed it back into the organisation’s intelligence from the field. | Delivery |  | PRINCE2 | 2015-11-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 | 2016-06-30 | 2021-06-30 | 2019-09-30 | 95185400 | 117757400 | Amber | Amber | Amber | Amber | Amber | Overall project health is AMBER primarily due to schedule risks for Release 5.2. Whilst all Release 4 (CAD) activities have concluded delays from Release 4 have had a consequent impact on the Release 5 schedule. Release 5.1 (Crime and Event Reporting) has been delivered. Release 5.2 is forecasted for delivery by 30 September 2019 as per the plan approved by the June 2019 Steering Committee..
Q4 18-19 | Public Transport Victoria | PTV | 2275 | Train Control Monitoring System (TCMS) for South Morang and Hurstbridge | Transport and Vehicles | Systems Management | To deliver a modern Train Control Monitoring System 'instance' at Epping to replace the standalone WESTCAD and SIGVIEW workstations and to support more efficient train control operations on the South Morang and Hurstbridge lines. | Postponed | 2019-04-30 | PTV Investment Lifecycle | 2016-10-21 | 2016-10-21 |  |  | 50000 | [12 empty] | The project is currently on hold. DoT is reviewing scope for delivery.
Q4 18-19 | Public Transport Victoria | PTV | 2278 | myki and PTV Website Integration and Development | Transport and Vehicles | Development and Integration | The project will include a complete website redesign focused on user experience and integration of the myki portal and the PTV website. | Delivery |  | PTV Investment Lifecycle | 2015-12-16 | 2016-10-21 |  | 2016-10-21 | 200499 |  | 2016-10-21 | 2016-10-21 | 2017-11-08 | 2019-06-27 | 3634100 | 7649101 | Green | Green | Green | Amber | Amber | Project is reporting as amber as myki integration timelines have been impacted by work to prepare back-end systems for Next Gen App delivery.
Q4 18-19 | Victoria Police | VicPol | 2279 | BlueConnect - Intelligence Management | Law and Justice | Content Management,Data Management,Knowledge Management | A new intelligence capability to bring together Victoria Police’s multiple data sources to deliver quick, easy access to intelligence to better inform police. | Delivery |  | PRINCE2 | 2015-07-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 | 2016-06-30 | 2021-06-30 | 2019-09-30 | 103304700 |  | Amber | Amber | Amber | Red | Amber | The overall health has improved to Amber due to the decision to extend the project end date in order to upgrade the technical solution. However, the project has experienced delays in the integration of data sources and inclusion of new functionality.
Q4 18-19 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2280 | ICT Redevelopment Stage 3 Hardware Tender | Health | Systems Management | Fit-out of new IT infrastructure to support hospital redevelopment objectives | Delivery |  | PRINCE2 | 2013-07-01 | 2014-06-30 |  | 2014-06-30 | 0 |  | 2014-06-30 | 2014-06-30 | 2018-12-31 | 2020-03-31 | 1180000 |  | Green | Green | Green | Green | Green | Project progressing to schedule
Q4 18-19 | Victoria Police | VicPol | 2283 | Body Worn Camera (BWC) | Law and Justice | Collaboration ,Development and Integration | Victoria Police will procure and deploy BWCs capable of capturing direct and objective audio and video face-to-face interactions. This project includes Equipment Tracking & Management System (ETMS). | Delivery |  | PRINCE2 | 2015-07-01 | 2016-06-30 |  | 2016-06-30 | 0 |  | 2016-06-30 |  | 2021-06-30 | 2020-06-30 | 42643000 |  | Amber | Green | Green | Green | Green | The overall status of the project is Green. As at 30 June 2019 4481 Body Worn Cameras have been deployed.
Q4 18-19 | South East Water | SE Water | 2284 | Trade Waste Information System | Environment and Water | Assets/Materials Management | The project will deliver a new solution for South East Water to manage our Trade Waste business. This new solution replaces a VB6 application and will enhance customer service by enabling mobility and improved analytical reporting | Delivery |  | Agile | 2014-09-15 | 2018-03-20 | 2018-05-30 | 2018-03-30 | 0 | 800000 | 2018-04-02 | 2018-05-31 | 2018-12-18 | 2020-12-28 | 0 | 4000000 | Green | Green | Green | Green | Green | A detailed design has been completed and build estimates has been provided to project governance committee. Solution and delivery options are now being scored against the MVP. Solution recommendations will be provided to project governance committee in September.
Q4 18-19 | VicRoads | VicRoads | 2291 | ICT/ITS Infrastructure Transformation Program (Switch Program) | Transport and Vehicles | Systems Management,Security Management | This project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support VicRoads current and future ICT and Intelligent Transport System requirements. | Delivery |  | PRINCE2 | 2016-05-09 | 2017-08-17 |  | 2017-08-17 | 1250634 |  | 2017-08-17 |  | 2020-02-28 |  | 7649366 | 16609366 | Green | Green | Green | Amber | Amber | The project status is Amber due to schedule slippage; however the overall project is still tracking to be completed by February 2020. 80% of the project is completed. Some components of the project are experiencing delays - additional resources and governance has been put in place to manage this with no impact to the overall budget or schedule. Delays have been escalated to vendor Executive Management and have agreed and implemented Program and Project Management level changes. Revised delivery cost is due to merger of other initiatives (ICT workplace productivity stream Remote access upgrade project) in Q4 17-18 and inclusion of additional scope items (Firewall upgrade).
Q4 18-19 | Public Transport Victoria | PTV | 2308 | Regional Radio Communications Network | Transport and Vehicles | Assets/Materials Management | The project involves modernisation of the following legacy systems; the train control centre (Centrol) Voice Communications Systems (VCS); the In-cab Communications Equipment (ICE) in the V/Line fleet; and the voice communications network service. | Delivery |  | PTV Investment Lifecycle | 2012-03-01 | 2014-02-27 |  | 2014-02-27 | 7250000 |  | 2014-02-27 | 2014-02-27 | 2018-04-03 | 2020-12-31 | 47104000 | 56003000 | Green | Green | Green | Green | Amber | The overall status of the project is now trending amber which can be largely attributed to delays caused by availability of resources at the vendor to finalise the System Description Work Orders (SDWO). Work is underway with the vendor to secure the required resources.
Q4 18-19 | VicRoads | VicRoads | 2312 | Dynamic Variable Speed Limit (DVSL) Project - Phases 2 & 3 | Transport and Vehicles | Development and Integration | The development of a new DVSL system integrated with Coordinated Ramp Signal and Lane Use Management System to maximise freeway capacity, minimise flow breakdown and improve traffic safety in congested conditions. | Postponed | 2018-09-10 | PRINCE2 | 2016-06-30 | 2018-07-01 |  | 2018-07-01 | 0 |  | 2018-07-09 | [6 empty] | Green | Green | Green | Green | ICT component of the project is put on hold.
Q4 18-19 | Victorian Registration and Qualifications Authority | VRQA | 2323 | EPSILON | Education | Customer Relationship Management | The EPSILON project will replace the existing legacy system "DELTA" to enable VRQA to meet its legislative obligations with respect to apprentices and trainees. | Delivery |  | PRINCE2 | 2014-07-07 | 2016-02-29 |  | 2016-02-29 | 373000 |  | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2019-09-09 | 2310749 | 6012057 | Green | Green | Green | Amber | Red | The implementation status of the project is Red due to the number of issues encountered with data migration, which negatively impacted the execution of User Acceptance Testing (UAT) and development work on the integration with external systems. The significant data migration issues have been rectified, enabling more effective UAT to be undertaken and integration with the external systems to be finalised. The full impact of the delays on the Go-Live date are being assessed by the project. Additional quality checks on deliverables received from the main supplier have increased confidence in their ability to deliver. The current schedule is being assessed in detail and being managed closely with the supplier. This approach will reduce risk and progress the project towards “Green” status.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2340 | Mobile Camera Replacement (MCR) Project | Law and Justice | Assets/Materials Management | Mobile cameras are a key component of the State's Road Safety Camera Program. The Mobile Camera Replacement (MCR) Project is tasked with procuring and deploying new mobile camera systems to replace the current cameras used in Victoria. | Delivery |  | Project Management Excellence | 2012-12-03 | 2014-02-19 |  | 2014-02-19 | 1568992.5 | 1568992 | 2014-02-19 | 2014-02-19 | 2015-12-21 | 2019-10-30 | 2826500 | 15531008 | Amber | Amber | Green | Green | Green | The procurement phase of the MCR Project was finalised in July 2018 with the appointment of Sensys Gatso Australia to supply new Gatso T-Series mobile cameras. The project timeframe was re-baselined from that time and aligns with the tender process underway for the Traffic Camera Services Agreement. A limited number of new camera systems are currently being tested and the project aims to complete the roll-out of new camera systems by the end of 2019. An additional 70 cameras have been procured to complete the fleet.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2343 | Australian Communications and Media Authority (ACMA) Compliance | Emergencies and Safety | Communication | This project moves five agencies from their existing radio systems onto shared, multi-agency radio systems, in order for the agencies to comply with new ACMA regulations. The project also includes the procurement of new radio terminals and associated services under a state-based managed services contract. | Closed - Completed | 2019-06-30 | Project Management Excellence | 2013-07-01 | 2017-06-30 |  | 2017-06-30 | 4604445 |  | 2017-06-30 | 2017-06-30 | 2019-05-19 | 2019-06-30 | 20486000 | 45992130 | Amber | Green | Green | Green | Green | The ACMA compliance project reached practical completion in Q4 2018-19, with the move to a new shared, multi-agency radio system that complies with the new ACMA regulations now finalised.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2344 | Births, Deaths and Marriages (BDM) Core System Replacement Project | Law and Justice | Systems Management | The replacement of the BDM core system will provide a scalable and robust design with enhanced functionality and migrated data. | Closed - Completed | 2019-05-31 | Project Management Excellence | 2013-10-01 | 2014-06-30 |  | 2014-06-30 | 1518095.36 |  | 2014-06-30 | 2014-06-30 | 2017-06-19 | 2018-09-30 | 13925000 | 20598000 | Amber | Amber | Amber | Green | Green | Go-Live was achieved successfully on the 19th of February 2019 and handover to the business has successfully completed. The Project was officially closed on the 31st May 2019.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2348 | Prisoner Transport Order System (PTOS) | Law and Justice | Customer Relationship Management | The PTOS Project will deliver an integrated transport order and information management system for implementation across Corrections, Police and DHHS to provide transport orders to the contractor and management information for all prisoner transports. | Closed - Completed | 2019-04-30 | Project Management Excellence | 2014-11-04 | 2014-12-04 |  | 2014-12-04 | 180000 |  | 2014-12-04 | 2014-12-04 | 2016-09-05 | 2019-04-30 | 3761184 | 7540249 | Amber | Green | Green | Green | Green | The Prisoner Transport Order System (PTOS) implementation was completed on 14 November 2017 across Corrections Police Youth Justice and transport contractor (G4S). The reporting component PTOS-BI (Business Intelligence) is now complete. The PTOS-BI component is not part of the operational prisoner transport system but provides a tool to analyse data on prisoner transports being conducted by Victoria Police Corrections Victoria and the contractor G4S. Corrections staff are now using the PTOS-BI application and Victoria Police are able to access the system once they activate their users.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2352 | Community Correctional Services (CCS) Accommodation Expansion Program | Law and Justice | Knowledge Management | IT fitout for sites being constructed or modified to accommodate additional staff for Community Correctional Services (CCS) and other business units across Victoria. The number of sites requiring IT treatment has been confirmed as 49 sites. | Delivery |  | Project Management Excellence | 2015-07-29 | 2016-01-18 |  | 2016-01-18 | 88043 |  | 2016-01-18 | 2016-01-18 | 2016-12-30 | 2021-06-30 | 2610975 | 6254914 | Green | Green | Green | Green | Green | 32 sites successfully delivered to date. The project is planned to deliver a further 6 sites by December 2019. The delivery end date has been extended to June 2021 due to delays in securing and constructing properties. ICT works are on track to deliver according to planned construction timelines.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2354 | New Infringements ICT System | Law and Justice | Management of Process | The ICT component of the program involves the procurement of an end-to-end commercial off-the-shelf (COTS) system to replace its current legacy infringement management system, VIMS, addressing all changes under the Fines Reform Act (2014). | Delivery |  | Project Management Excellence | 2015-10-27 | 2017-12-31 | 2016-08-30 | 2016-08-31 | 0 |  | 2016-08-31 | 2016-08-31 | 2017-12-31 | 2019-03-09 | 43054000 | 59177000 | Amber | Green | Red | Red | Red | Project delivery has been significantly delayed and while delivery of remaining business functionality is continuing, the vendor's performance has not met the State's expectations. DJCS is working with the vendor to improve system functionality to achieve a better result and is engaging in commercial-in-confidence discussions. An agreed revised end date is yet to be determined at this time.
Q4 18-19 | Department of Health and Human Services | DHHS | 2355 | Parkville Precinct Electronic Medical Record | Health | Development and Integration | Implementation of an Electronic Medical Record into Melbourne Health, Peter MaCallum Cancer Centre and The Royal Women's Health Services. | Delivery |  | PRINCE2 | 2016-07-01 | 2018-06-01 |  | 2018-06-01 | 0 |  | 2018-07-02 |  | 2020-10-30 |  | 140432313 |  |  | Green | Green | Green | Green | RMH Emergency Department had a successful Stage 1 go live on 30 June 2019. Stage 2 progressing to schedule.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2357 | Emergency Alert Phase 4 - Delivery | Emergencies and Safety | Communication | Secure service continuity and delivery of a national telephony based emergency warning system, ensuring a more sustainable EA service: a service that remains up to date and relevant to community use and demand, maintains an acceptable performance standard and incurs minimal capital expenditure and cost surprises. | Initiated |  | Project Management Excellence | 2016-05-06 | 2019-01-31 | 2019-09-30 |  | 0 | 1061998 | [11 empty] | Three RFQs and one RFT are required to procure all the necessary service components. The project will move to delivery once these contracts have been awarded.
Q4 18-19 | Barwon Region Water Corporation | BR Water | 2363 | Customer Relationship Management System | Environment and Water | Customer Relationship Management | Current customer systems are disparate and no longer meet business needs and expectations. This project's objective is to implement a CRM Solution to replace a suite of existing solutions, enabling improved levels of service, greater efficiency in service provision and deliver digital customer transformation. | Closed - Merged | 2019-06-30 | PMBoK | 2016-11-01 | 2017-04-30 | 2018-09-30 | 2016-11-01 | 0 | [12 empty] | The project has been merged and is now part of project Sherwin. As project Sherwin is under $1m it won’t be reported on the Dashboard.
Q4 18-19 | Chisholm Institute of TAFE | Chisholm TAFE | 2364 | Network Refresh | Education | Assets/Materials Management | To refresh and improve the network infrastructure to improve functionality, availability and security | Delivery |  | Chisholm PMF (Prince 2 Based) | 2016-11-01 | 2016-11-01 |  | 2017-12-31 | 300000 |  | 2018-03-01 |  | 2019-12-31 |  | 9700000 | 7842838 | Green | Green | Green | Green | Green | Project is over 90% complete. Remaining tasks are focused on validating deliverables and preparing for handover to Operational Support.
Q4 18-19 | Chisholm Institute of TAFE | Chisholm TAFE | 2365 | Systems Integration | Education | Development and Integration | To improve productivity, data integrity, functionality and reduction in operating costs | Delivery |  | Chisholm PMF (Prince 2 Based) | 2016-11-01 | 2017-07-31 |  | 2017-07-31 | 45000 |  | 2017-07-31 | 2017-07-31 | 2018-12-31 | 2019-12-31 | 1155000 |  | Green | Green | Green | Green | Green | Due to the complexity further investigation was required to establish business requirements.
Q4 18-19 | Chisholm Institute of TAFE | Chisholm TAFE | 2366 | Migration to Cloud | Education | Security Management | To migrate the on-site server environment to cloud services to improve availability, improve security, reduce risk and reduce operating costs. | Delivery |  | Chisholm PMF (Prince 2 Based) | 2016-11-01 | 2017-06-30 |  | 2017-06-30 | 119428 |  | 2017-06-30 | 2017-06-30 | 2018-12-31 | 2019-12-31 | 1080572 | 1580572 | Green | Green | Green | Amber | Amber | Estimate we are currently 70% complete. The delay is a deliberate decision to minimise risk and does not impact on the benefits realisation.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2367 | Business Support Systems Review (BSSR) - HCM | Employment and Workplace | Customer Relationship Management | Replatform of existing HCM/Payroll solution to a cloud based system for DELWP to align with WoVG strategy. | Closed - Merged | 2019-06-28 | PRINCE2 | 2016-11-03 | 2016-11-03 | 2017-02-28 | 2017-12-19 | 1450000 |  | 2018-02-01 | 2018-02-01 | 2019-02-28 | 2019-06-30 | 8861300 | 7125000 | Amber | Amber | Green | Amber | Amber | The project was delivered in January 2019 and the project has been supporting stabilization activities. This project is merging with 'Business Support Systems Review (BSSR) - Finance' project in order to present an overall program view of the BSSR Program.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2369 | Smart Planning - Planning Portal | Property and Planning | Content Management | The Planning Portal Project will provide an easily identifiable web-based entry point for the community and government to access a comprehensive and integrated set of planning policies, legislation, planning scheme information, guidelines and services. Introduced as part of the 2016-17 Victorian Budget | Closed - Completed | 2019-05-31 | PRINCE2 | 2016-07-01 | 2017-09-25 |  | 2017-09-25 | 396430 | 454174 | 2017-09-25 | 2017-10-23 | 2018-06-30 | 2019-05-08 | 1475609 | 1375203 | Amber | Green | Green | Green | Green | Policy and Initiatives was deployed into production.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2371 | Smart Planning Online Permits | Property and Planning | Management of Process | Pilot the online lodgement of Planning Permit applications. This includes refreshing the Greenlight applicant and register interface and integrating the Departments WestPac payment gateway for online payments. Introduced as part of the 2016-17 Victorian Budget | Delivery |  | Hybrid - Agile and PRINCE2 | 2016-07-01 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 566687 | 1105996 | 2017-09-11 | 2017-12-06 | 2018-06-30 | 2019-12-23 | 3591152 | 6149022 | Amber | Amber | Amber | Amber | Green | After options analysis EES was descoped by PCB. Platform architecture was developed and features for Heritage solution confirmed.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2378 | Hosting Services Project | Law and Justice | Content Management | SecureWorx currently provides a number of hosting services for DJR. The provision of hosting services is an ongoing requirement for a number of key applications within Corrections Victoria (CV). The project will manage the procurement and transition of hosting, monitoring, disaster recovery, penetration testing and performance testing services for CV. | Delivery |  | Project Management Excellence | 2016-06-15 | 2017-01-31 | 2018-01-31 | 2018-02-01 | 0 | 941800 | 2018-02-02 | 2018-02-02 | 2018-10-31 | 2019-06-30 | 4250000 |  | Green | Amber | Amber | Green | Amber | Eight of the nine applications have been successfully migrated to the new hosting services platform. The final remaining CV application (CVIMS) is expected be migrated by 30 September 2019. Application architecture issues with CVIMS have delayed the final migration. The issues have now been resolved awaiting deployment into production. The project team will also transition all support functions to operational support teams during this period.
Q4 18-19 | Goulburn Valley Region Water Corporation | GVR Water | 2382 | Financial Management Information System | Environment and Water | Financial Management | Upgrade of Goulburn Valley Water's existing and aging financial management information system | Postponed | 2018-06-29 | Internal GVW Project Management Methodology | 2016-03-01 | 2017-03-31 |  | 2017-03-31 | 105567 |  | 2017-03-31 | 2017-03-31 | 2018-03-31 | 2020-02-28 | 1382285 | 2866433 | Amber | Amber | Amber | Amber | Amber | The D365 project is continuing to progress via negotiation and consideration of various legal matters. Project management planning for a project restart has been completed; following confirmation of commercial arrangements the project will have resumed in full.
Q4 18-19 | Parks Victoria | PARKSVIC | 2387 | IT Infrastructure Refresh Program | Environment and Water | Systems Management | Technology Infrastructure replacement and modernisation program updating core IT infrastructure and associated services, network infrastructure, and end user devices. | Delivery |  | PRINCE2 | 2016-10-21 | 2018-06-29 |  | 2018-06-29 | 0 | 0 | 2018-07-02 |  | 2019-12-19 |  | 0 | 7969931 |  | Green | Green | Amber | Amber | Overall Program schedule is at moderate risk of not meeting the end date with an assessment to confirm potential impacts (if any) by next quarter. Core Infrastructure Refresh project will be delivered on time in July 2019. Network Refresh project has commenced with planning activities occurring. PC/Laptop project has commenced with the order of devices and the build of the new SOE occurring now into next quarter.
Q4 18-19 | State Revenue Office | SRO | 2391 | LPR #2&3 - Land Ownership, NOAs and Land Usage Vicroads. | Government and Economy | Financial Management | This project is part of the Better Revenue Management System program to redesign the Land Tax administration business processes to achieve operational efficiencies, improve effectiveness of managing land ownership data (using Notice of Acquisition (NOA Data and Vicroads Data) and to extend the life of SRO's revenue management system. | Delivery |  | PRINCE2 | 2015-09-17 | 2016-09-30 |  | 2016-09-30 | 1505896 |  | 2016-09-30 | 2016-09-30 | 2018-04-13 | 2019-11-25 | 3881729 | 4158204 | Green | Green | Amber | Amber | Green | An additional release was approved to deliver enhancements to Valuation Objections Plan of Sub-division Quality Checking and Municipal Data Veracity functionality by 25 November 2019. The project budget was increased to fund the additional release and forecast project costs are tracking to the revised budget. Work has commenced on the Valuation Objections enhancements and is progressing as planned for delivery in August 2019.
Q4 18-19 | Emergency Services Telecommunications Authority | ESTA | 2395 | Multi-Agency Communications Gateway | Emergencies and Safety | Management of Process | Delivery of a common interface with ESTA's Computer Aided Dispatch (CAD) system to improve operational dispatch data flow between ESTA and the Emergency Services Organisations, particularly to facilitate mobile devices in the field. | Closed - Completed | 2019-06-30 | ESTA Project Management Methodology | 2016-05-01 | 2017-04-07 |  | 2017-04-07 | 600000 | 0 | 2017-04-07 | 2017-04-07 | 2018-12-30 | 2019-05-06 | 5000000 | 6594453 | Amber | Amber | Green | Green | Green | Project closed in June 2019, completed deployment to around 10,000 VicPol IRIS devices on 6 May 2019.
Q4 18-19 | CenITex | CenITex | 2396 | Operating System Upgrade Across Windows Fleet | Health | Assets/Materials Management | To upgrade servers in the customer environment to a supported server operating system | Delivery |  | PRINCE2 | 2016-02-08 | 2016-02-22 |  | 2016-02-23 | 0 |  | 2016-02-24 | 2016-02-24 | 2018-06-30 | 2019-08-30 | 3570000 | 3258334 | Amber | Green | Green | Green | Green | Windows 2003 and 2008 workloads continue to be decommissioned as per DHHS requests. New Citrix environment has been set up in UAT and DR and currently finishing up Production setup. DHHS priorities have been modified for several systems which will result in some systems needing to retain the current OS beyond June. DHHS accept the risks associated with this.
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2401 | Resource Rights Allocation and Management (RRAM) Enhancement Project | Government and Economy | Data Management,Management of Process | RRAM is used by the earth resources regulator (ERR) and the industry to administer and regulate mining and petroleum tenement activities in Victoria. The project aims to deliver enhancements to RRAM's functionality and application by the regulator and industry. | Delivery |  | PRINCE2 | 2017-01-01 | 2018-09-30 | 2017-01-17 | 2017-01-17 | 0 | 435000 | 2017-03-01 | 2017-03-01 | 2019-06-30 | 2019-09-30 | 2391290 |  |  |  | Amber | Amber | Amber | 425 enhancements completed were well received by Industry, as evidenced by the ERR survey completed May 2019. The Project continues to manage challenges with architecture, fluid policy, design requirements and access to subject matter experts..
Q4 18-19 | Department of Education and Training | DET | 2402 | Youth Engagement System | Education | Management of Process | An integrated IT solution which will capture data on disengaged students and students in out-of-home care. It will provide a more comprehensive picture of these key cohorts to ensure they receive the support they need to achieve educational success. | Closed - Terminated | 2019-05-22 | PRINCE2 | 2016-10-03 | 2017-06-29 |  | 2018-06-29 | 0 | 353857 | 2018-06-29 | 2018-06-29 | 2018-12-01 | 2019-05-22 | 1787139 | 1433543 | Amber | Red | Red | Red | Red | As no CAPEX funding is available to complete the YES project and considerable progress made on the alternative steps to support the business during this period, Project Board decided to cancel the project and terminate the contract with supplier. In view of the CAPEX issue, following activities are initiated by Wellbeing, Health and Engagement Division (WHED) to address immediate business needs: ·IMTD has moved the out of home care interim database onto DET network which will enable Regional staff to securely access the database as a short term solution ·a project has been initiated to convert the current MS Access solution to a secured application to align it with DET approved architecture and to provide secure access to all LOOKOUT staff ·CASES21 team is working to link DHHS student identifier to DET student data for correct identification of out of home care students ·the platform to be implemented for the Kindergarten Information Management System will be reviewed against requirements for YES following the completion of KIMS. The technology requirements are similar and this approach will better align to WoVG and the Department's IT strategies. The project will be closed before the next reporting period.
Q4 18-19 | Department of Treasury and Finance | DTF | 2404 | ERP - Financial System | Government and Economy | Financial Management | DTF are replacing its legacy Finance and procurement systems | Delivery |  | PRINCE2 | 2017-01-01 | 2018-01-31 | 2017-12-20 | 2017-12-20 | 550000 |  | 2018-01-01 | 2018-01-01 | 2018-10-08 | 2019-07-01 | 5250000 | 8000000 | Amber | Amber | Amber | Green | Green | Project on track for go live on 1 July 2019.
Q4 18-19 | Eastern Health | EH | 2405 | Eastern Health - PCMS Project | Health | Customer Relationship Management | Replacement of five (5) existing Patient Administration Systems with the Patient and Client Management System (PCMS) solution. | Delivery |  | HTS PCMS Implementation Methodology | 2016-08-22 | 2017-06-30 |  | 2017-06-30 | 634225 |  | 2017-06-30 | 2017-06-30 | 2018-12-31 | 2019-12-31 | 12038173 | 18165517 | Red | Red | Red | Amber | Amber | The complexity of retesting and reintegration of the Electronic Medical Record with the Patient and Client Management System has been realised. Options to resolve these activities have been approved and have recommenced in accordance with the project plan.
Q4 18-19 | Eastern Health | EH | 2406 | Eastern Health - Angliss and Maroondah Hospitals Emergency Department IS Replacement | Health | Customer Relationship Management | Emergency Department information system replacement at Angliss and Maroondah Hospitals. | Closed - Completed | 2019-06-30 | Cerner Consulting Framework | 2016-10-10 | 2017-03-30 |  | 2017-03-30 | 366750 |  | 2017-03-30 | 2017-03-30 | 2018-06-30 | 2019-06-30 | 1725550 |  | Amber | Amber | Green | Green | Green | The Project was completed successfully. Post Implementation Review (including Feedback Survey) completed and statutory reporting submitted to 30/6/19.
Q4 18-19 | Northern Health | NH | 2411 | EMR Project-EMR Readiness phase | Health | Analyses and Statistics ,Collaboration ,Communication,Organisational Management ,Records Management | Implementation of an Electronic Medical Record at Northern Health including all sites | Initiated |  | PRINCE2 | 2016-10-18 | 2019-05-06 | 2020-05-05 |  | 0 | 4130000 | [11 empty] | EMR readiness continues with the EMR team working with NH key stakeholders to build capability in the informatics space. There is a number of key activities planned to prepare Northern for a future EMR in the next 8-12 months.
Q4 18-19 | VicRoads | VicRoads | 2413 | Fines Reform Project | Transport and Vehicles | Development and Integration | Fines Reform is a mandatory legislative project driven by the Department of Justice and Regulation’s Infringement Management Enforcement Services. VicRoads must implement a range of system and business process changes in order to meet its legislative obligations. | Closed - Completed | 2019-06-28 | PRINCE2 | 2017-01-09 | 2017-06-15 |  | 2016-12-12 | 200000 |  | 2017-01-09 | 2017-01-09 | 2018-03-30 | 2019-06-28 | 4102616 | 3400000 | Amber | Amber | Red | Red | Green | Decision has been made by Executive Director Customer & Technology to Close the project and discontinue all support activities for Phase 1 until such time the Department of Justice and Community Safety (DJCS) confirms a revised implementation schedule and Phase 2 remobilisation can commence..
Q4 18-19 | Yarra Valley Water | YV Water | 2416 | Trade Waste Management system | Environment and Water | Assets/Materials Management | Create a new system for managing sewer quality and trade waste agreements | Closed - Completed | 2019-06-30 | Agile | 2016-05-04 | 2016-11-30 |  | 2016-11-30 | 404714 |  | 2016-11-30 | 2016-11-30 | 2018-07-18 | 2019-06-30 | 2006304 | 3947534 | Green | Green | Green | Green | Green | Project has been deployed to production 30/6/2019. This project can be closed.
Q4 18-19 | CenITex | CenITex | 2418 | Data Centre Network Design and Infrastructure Establishment | Government and Economy | Assets/Materials Management | Design and establish software defined networking (SDN) capabilities at government shared platform data centres | Closed - Completed | 2019-06-30 | PRINCE2 | 2017-05-01 | 2017-07-31 |  | 2017-08-01 | 0 |  | 2017-10-24 | 2017-10-24 | 2018-06-30 | 2019-06-30 | 2780216 | 2800216 | Green | Green | Green | Green | Green | Stage 1 - Finalisation of the design for the Cisco existing environment and build has now been completed, to enable Stage 2 to commence. Preproduction LAB available & being used for testing migration plan for move to new platform. A variation was applied in May for an additional $20k to address additional work activity that was done for the SDN JOIN workshops for planning workload migrations. Project complete as scheduled.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2421 | Crown Land Information Improvement Project (CLIIP) | Environment and Water | Data Management | The Crown Land Information Improvement Project (CLIIP) will deliver a modern web based IT solution for the management of Crown land information and associated business processes. The new solution will replace a number of legacy systems and provide a range of Web and Mobile capabilities. | Delivery |  | Hybrid - Agile and PRINCE2 | 2016-09-01 | 2017-07-02 |  | 2017-07-02 | 30000 |  | 2017-07-02 | 2017-07-02 | 2019-07-30 | 2020-03-27 | 3619688 | 3900000 | Green | Green | Green | Green | Green | Project is on Schedule and Budget, on track to meet its objectives. The controls are in place to manage the risks and issues as they arise.
Q4 18-19 | Department of Education and Training | DET | 2422 | eduPass Parent, Carer, Guardian (PCG) | Education | Security Management | eduPass Parent, Carer and Guardian (PCG) will provide near real-time provisioning capability of identities and managed access for Parents, Carers and Guardians as well as enabling self-service registration and account management. The decommissioning of the legacy iDaptive toolset will also be undertaken. | Closed - Completed | 2019-05-31 | Hybrid - Agile and PRINCE2 | 2014-10-16 | 2017-04-01 |  | 2017-04-01 | 299254 |  | 2017-04-01 | 2017-04-01 | 2018-03-17 | 2019-05-31 | 1688005 | 1398097 | Green | Green | Green | Green | Green | The project has deployed the fixes to the production environment and has been verified by the system testers as successful. Project is being closed after the successful complete delivery.
Q4 18-19 | Department of Education and Training | DET | 2423 | eduSafe Plus | Education | Human Capital / Workforce Management | The eduSafe project will deliver one consolidated IT system to replace the separate OHS, Workers Compensation and Workplace incident management systems currently in use at DET. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-01-09 | 2017-01-09 | 2018-09-28 | 2018-10-23 | 0 | 921774 | 2018-10-24 |  | 2020-02-07 |  | 0 | 5320363 |  |  | Green | Green | Amber | Solution development is underway. Project status is amber due to schedule delays caused by project resource constraints. Plans are in progress for a staged implementation approach that should bring the status back to green.
Q4 18-19 | Department of Education and Training | DET | 2424 | CASE and Matter Management | Education | Customer Relationship Management | Case management solution to support the consolidated requirements for Legal Division, Employee Conduct Branch and Integrity and Assurance Division. | Delivery |  | Agile | 2016-11-07 | 2018-02-28 | 2018-06-29 | 2018-06-29 | 0 | 542792 | 2018-07-02 | 2018-07-02 | 2019-09-02 | 2019-09-30 | 3741304 |  |  | Green | Green | Green | Green | Case and Matter Management System development has been completed. The project is currently in the implementation phase with planned go-live in Q3 2019 calendar year. Overall project activities are on track and the status is green.
Q4 18-19 | Monash Health | Monash H | 2434 | PABX Upgrade Stage 1 - Clayton & Dandenong | Health | Systems Management | PABX systems have reached end of life and need to be replaced with latest technology. | Delivery |  | PRINCE2 | 2017-09-01 | 2018-02-28 |  | 2018-02-28 | 1 |  | 2018-07-02 |  | 2019-08-01 |  | 3660000 |  | Green | Green | Green | Green | Green | The Project is tracking to schedule. Deployment of telephony equipment is underway.
Q4 18-19 | Public Transport Victoria | PTV | 2437 | Bus Passenger Information Displays (PIDs) Implementation Program | Transport and Vehicles | Assets/Materials Management | Rebuild PID solution architecture and supply, install and commission PIDs with real time metro train and bus information across regional and metro locations. | Delivery |  | PTV Investment Lifecycle | 2017-06-21 | 2017-06-27 | 2017-06-21 | 2017-06-21 | 0 |  | 2017-10-30 | 2017-10-30 | 2018-04-05 | 2019-07-31 | 1089462 | 1189462 | Green | Green | Green | Green | Green | Project scope has been delivered.
Q4 18-19 | Public Transport Victoria | PTV | 2438 | Operator Payment System Modernisation - Releases 2 to 4 | Transport and Vehicles | Systems Management | Replace the PASS suite of programs (PASS Payments and Bus IT), myriad of spread sheets and manual processes related to operator contract and performance management and operator payments. Decommission of PASS Payments and Bus IT. Releases 2 to 4 and roll out of the Operator Portal. | Delivery |  | PTV Investment Lifecycle | 2017-03-31 | 2017-03-31 |  | 2017-03-31 | 0 |  | 2017-03-31 | 2017-03-31 | 2018-09-30 | 2019-05-30 | 7169100 | 16768100 | Amber | Green | Green | Amber | Amber | Overall status is Amber as the decommissioning of legacy environments is not yet complete.
Q4 18-19 | VicRoads | VicRoads | 2442 | Customer Management & Productivity Platform (One View) | Transport and Vehicles | Customer Relationship Management | This Initiative will deliver foundational aspects of enterprise wide Customer Relationship Management (CRM) platform that enables proactive , responsive and personalised customer service across multiple channels | Closed - Completed | 2019-06-28 | Agile | 2017-05-30 | 2017-06-30 |  | 2017-06-30 | 0 |  | 2017-07-03 | 2017-07-03 |  | 2019-06-30 | 4230000 | 9338055 | Green | Red | Red | Green | Green | Project recommendations have been delivered. The Project Sponsor has accepted the recommendations of the project review report conducted by Ernest & Young. The project has now been closed and a new Project (Dynamics 365) has been initiated to implement E&Y recommendations.
Q4 18-19 | VicRoads | VicRoads | 2444 | Digital Learners Kit | Transport and Vehicles | Customer Initiated Assistance | This initiative will enhance the learning to drive process and strengthen the Graduate Licencing System (GLS ) and is aligned with the Towards Zero Strategy. Delivered via a suite of online and mobile tools to streamline capture of 120 hours driving data, with improved accuracy, data quality and user experience. | Closed - Completed | 2019-04-12 | Agile | 2017-05-30 | 2017-07-12 |  | 2017-07-12 | 0 |  | 2017-11-08 | 2017-11-08 | 2018-09-01 | 2019-04-12 | 7540000 | 8346000 | Amber | Green | Green | Green | Green | Project completed. Total of 77K registered members are using this application as at the end of June 30th.
Q4 18-19 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | A new case management system for the Magistrates’ Court and the Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information. | Delivery |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2021-06-30 |  | 89200000 |  | Green | Green | Green | Green | Green | The Procurement Phase of the project is nearing completion. Following completion of the DTF HVHR Gateway 4 Review, which provided a favourable assessment of the project and confidence to proceed, the contract award approvals process is underway and is expected to be completed by July 2019.
Q4 18-19 | Court Services Victoria | CSV | 2453 | Supreme Court Digital Strategy | Law and Justice | Organisational Management | The Digital Strategy project is laying the foundation for the Court's technology infrastructure and delivering efficiencies and access through system, network and associated process improvements. | Closed - Completed | 2019-06-30 | PMBoK | 2016-01-01 | 2016-06-30 |  | 2016-07-01 | 0 |  | 2016-09-01 | 2016-09-01 | 2018-06-30 | 2019-06-30 | 6424000 | 9896000 | Green | Green | Green | Green | Green | Project was completed within scope
Q4 18-19 | Department of Transport | DOT | 2454 | Transport Information Management System (TIMS) | Government and Economy | Data Management,Development and Integration ,Management of Process | The project will replace the legacy Marine Safety System (MSS), Transport Safety Audit, Accreditation and Reporting System (TSAARS) and Vessel Survey and Marine Qualifications System (VSMQS) with a new cloud-based Salesforce CRM system. | Delivery |  | PRINCE2 | 2017-05-09 | 2017-06-30 | 2017-05-11 | 2017-05-11 | 0 |  | 2017-06-30 | 2018-02-28 | 2018-06-30 | 2019-08-31 | 1554471 | 2015904 | Green | Amber | Amber | Green | Green | Scope and schedule variation for Phase 1.3 to include additional enhancements and organizational change management activities to support external stakeholders' adoption of TIMS. Additional budget granted by the ICT PCB and Project Sponsor.
Q4 18-19 | Department of Health and Human Services | DHHS | 2458 | Our Briefings | Government and Economy | Document Management | The objective of the CBS project is to provide a single, integrated document tracking solution to manage all departmental, Ministerial and Cabinet briefings and executive correspondence processes, including the management of drafting authored versions and approval workflows. | Delivery |  | PRINCE2 | 2017-09-21 | 2018-01-31 |  | 2018-01-31 | 147840 |  | 2018-02-08 | 2018-02-08 | 2018-08-31 | 2019-09-30 | 1813120 | 2736151 | Amber | Red | Amber | Amber | Amber | Project is progressing but has had schedule delays. Project is expected to be fully implemented by Q1 2019/20.
Q4 18-19 | Department of Health and Human Services | DHHS | 2460 | VAHI Information Management Environment (VIME) and Portal | Health | Data Management | Development of a next generation information management approach, leveraging where feasible existing infrastructure, data sources and systems to enable the Agency to create and (along with the data rich website and portal initiative) report accurate, reliable and actionable performance information for health service boards, executives, clinical leaders and the public. | Initiated |  | Agile | 2017-04-26 | 2019-06-30 | 2019-08-30 |  | 130000 | 699168 | [11 empty] | Business case approval in progress. In parallel with finalising the business case some approved delivery work has commenced.
Q4 18-19 | Department of Health and Human Services | DHHS | 2461 | Electronic Document Records Management System | Community Services | Records Management | An implementation project to rollout an Electronic Document Records Management System to all staff in the department. | Delivery |  | PRINCE2 | 2017-04-25 | 2017-09-29 |  | 2017-09-30 | 0 |  | 2017-10-02 | 2017-10-02 | 2019-06-29 | 2020-06-30 | 3000000 | 3737753 | Green | Green | Green | Green | Amber | Project is progressing but is experiencing budget and schedule delays which are currently being addressed.
Q4 18-19 | Department of Health and Human Services | DHHS | 2462 | Family Safety Victoria Central Information Point | Community Services | Data Management,Knowledge Management ,Records Management | The Central Information Point (CIP) is a key reform which includes the establishment of a co-located team of data custodians from Victorian Police, Corrections Victoria, DHHS and Courts. This project will develop the IT systems used to create and deliver CIP reports in line with legislative requirements. | Delivery |  | Agile | 2017-03-13 | 2018-01-29 | 2017-06-30 | 2017-07-03 | 0 |  | 2017-07-04 | 2017-07-04 | 2019-06-30 | 2020-06-30 | 7199594 | 78500000 | Green | Green | Green | Green | Green | Project is progressing to schedule. Stages One and Two successfully delivered. Planned delivery costs now include all stages of the project (Stages One to Four). Planned project delivery costs originally published only included work to complete the first two stages. The updated amount acurately reflects all four stages of the project that were approved in the business case.
Q4 18-19 | Department of Health and Human Services | DHHS | 2463 | Family Safety Victoria Hub Client Relationship Management | Community Services | Customer Relationship Management | This project will deliver a base CRM to support the initial roll out of FSV hubs and with incremental enhancements to continue throughout the lifecycle of the project. | Delivery |  | Agile | 2017-04-17 | 2018-01-29 | 2017-07-07 | 2017-07-10 | 0 |  | 2017-07-11 |  | 2021-06-30 |  | 6840000 | 28240000 | Green | Green | Green | Green | Green | Project is progressing to schedule. Stages One and Two successfully delivered. Planned delivery costs now include all stages of the project (Stages One to Five). Planned project delivery costs originally published only included work to complete the first two stages. The updated amount accurately reflects all five stages of the project.
Q4 18-19 | Department of Health and Human Services | DHHS | 2466 | Office 365 | Community Services | Collaboration | The department is implementing Office 365 as a part of its ICT Workplace modernisation program. O365 is a cloud hosted productivity tool suite allowing staff anywhere access to core office applications e.g. email, word, excel, and a series of advanced applications to support collaboration, document storage/sharing, data analysis, teamwork and planning. | Closed - Completed | 2019-06-29 | Hybrid - Agile and PRINCE2 | 2016-12-08 | 2017-09-15 |  | 2017-09-18 | 0 | 100029 | 2017-09-19 |  | 2019-06-29 |  | 4899971 | 10414707 | Green | Green | Green | Green | Green | The project has delivered its intended result and closeout activities are underway.
Q4 18-19 | Department of Health and Human Services | DHHS | 2471 | Webseal Upgrade | Community Services | Security Management | The department uses security technology Webseal to allow users to access corporate applications. The newer version will enhance functionality to improve secure authenticated access to corporate and web enabled systems. The new authentication technology includes the ability to federate user authentication, improving access/usability for end users by reducing multiple login requirements. | Delivery |  | PRINCE2 | 2015-03-02 | 2016-07-01 |  | 2016-07-04 | 362250 |  | 2016-07-04 | 2016-07-04 | 2018-11-04 | 2019-12-20 | 627750 | 1083255 | Amber | Green | Amber | Amber | Green | Project is progressing to revised agreed schedule.
Q4 18-19 | Emergency Services Telecommunications Authority | ESTA | 2473 | Computer Aided Despatch (CAD) Upgrade | Emergencies and Safety | Systems Management | ESTA’s Computer Aided Dispatch (CAD) system requires upgrading to the latest version to take advantage of features required to meet future emergency services needs. | Delivery |  | ESTA Project Management Methodology | 2017-09-18 | 2019-06-30 | 2019-03-31 | 2019-04-01 | 0 | 610000 | 2019-04-01 |  | 2019-07-31 |  | 2875000 | [5 empty] | Amber | In December 2018, ESTA revised the scope and approach to focus on upgrading and sustaining the existing CAD platform to reduce technology risk. The project has engaged with an external advisory and is developing the business case and gap analysis to support this.
Q4 18-19 | Environment Protection Authority | EPA | 2474 | EDISON (Environment Data Information System Online ) | Environment and Water | Analyses and Statistics ,Business Intelligence | Enable EPA to effectively manage more data from more sources more often, now and into the future. Collect, store, curate and share environment data (air, water, land, waste). | Delivery |  | Agile | 2017-01-21 | 2018-03-30 | 2017-12-19 | 2018-01-31 | 230000 | 255000 | 2018-02-26 | 2018-02-26 | 2018-11-30 | 2019-07-31 | 745000 | 1688000 | Amber | Green | Green | Green | Green | The EDISON product has been in Production throughout the period and has proven to be reliable and robust, with data being ingested and displayed on AirWatch. Only 1 bug was identified, reported and fixed, while 5 minor additional changes (as requested by the business) were also addressed and released successfully. The Phase 2 scope of work has been underway during the period and is close to a successful conclusion. This includes the delivery of an administrative user interface to support incident and emergency response deployments and demobilisations, a data warehouse containing the entire history of air quality monitoring data accessible through a variety of reporting tools, and several additional features designed to make the EDISON system more robust for the organisation. EDISON Phase 2 is due to go-live on 31/07/2019. The Delivery end date was extended to 31/07/19 to allow for handover, additional support and refactoring.
Q4 18-19 | Health Purchasing Victoria | HPV | 2476 | Victorian Health Sector -Common Catalogue (Project 076) | Health | Data Management | Develop common catalogue data and master data processes for the state | Delivery |  | PRINCE2 | 2017-07-01 | 2017-12-31 |  | 2017-12-31 | 404188 |  | 2018-01-01 | 2018-01-01 | 2018-12-31 | 2019-05-31 | 1395812 | 1725480 | Amber | Amber | Amber | Red | Green | The pilot was delivered successfully on schedule and within the approved timelines and budget.
Q4 18-19 | North East Region Water Corporation | NE Water | 2481 | Customer Billing System | Environment and Water | Customer Relationship Management,Knowledge Management ,Management of Process | Procure a new Software solution for billing customers | Initiated |  | Vic Govt PM Framework | 2017-07-01 | 2017-12-31 | 2019-06-30 |  | 0 | [12 empty] | The project has been restarted in June 2019. We are currently reviewing our business requirements.
Q4 18-19 | Parks Victoria | PARKSVIC | 2482 | Asset Management Information System | Environment and Water | Assets/Materials Management | Implementation of an Assets Management technology solution for Built Infrastructure Assets in order to support Parks Victoria compliance with the Victorian Asset Management Accountability Framework. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-07-01 | 2018-09-14 | 2018-08-15 | 2018-08-15 | 0 | 612145 | 2018-08-15 |  | 2019-12-30 |  | 3696855 |  |  | Green | Green | Amber | Amber | With a change in project management personnel and an assessment soon to be completed, a revised approach and plan will be established and executed in the next period.
Q4 18-19 | Parks Victoria | PARKSVIC | 2483 | Digital Customer Engagement | Environment and Water | Content Management | The Digital Customer Engagement project aims to transform Parks Victoria’s approach to engaging customers through the use of digital channels. | Closed - Completed | 2019-06-28 | Agile | 2017-07-01 | 2017-11-16 |  | 2017-11-16 | 199673 | 1987000 | 2017-11-20 |  | 2019-06-28 |  | 4293327 | 2672728 | Amber | Amber | Amber | Amber | Green | Completed all sitecore and VEF data infrastructure base development to move forward from with new website. Waiting ministerial approval for website go-live announcement.
Q4 18-19 | South West Alliance of Rural Health | SWARH | 2485 | Barwon Health Emergency Department Information System (EDIS) Project | Health | Data Management,Document Management ,Knowledge Management ,Reporting ,Tracking and Workflow | Barwon Health is undertaking a project to replace its existing Emergency Department Clinical Information System due to withdrawal of support in the Australian market by the vendor | Delivery |  | Vendor specific methodology | 2016-03-01 | 2017-08-29 |  | 2017-08-29 | 120000 | 1 | 2017-08-30 |  | 2019-08-26 |  | 6580000 | 7082299 | Green | Amber | Amber | Green | Green | Project is completed and in closure.
Q4 18-19 | V/Line Corporation | V/Line | 2489 | New Training Platform | Transport and Vehicles | Development and Integration | Staff Training LMS to improve quality and quantity | Postponed | 2019-01-07 | Hybrid - Agile and PRINCE2 | 2017-09-01 | 2018-05-31 |  |  | 500000 | 678383 | [11 empty] | Project status On Hold awaiting rescope due to Employees Vote NO to Changing EA as an option to facilitate the introduction of A New Vision for Training at V/Line
Q4 18-19 | V/Line Corporation | V/Line | 2490 | Electronic Rostering - Workforce management | Transport and Vehicles | Human Capital / Workforce Management | Electronic Rostering System & Workforce management | Initiated |  | Agile | 2018-01-18 | 2019-06-28 | 2020-05-29 |  | 250000 | 2916067 | [11 empty] | Market analysis completed. High level requirement and business requirements documented, including lessons learnt, market capability, market and vendor risks. The project team is focused on the completion of the key artefacts (Project Brief, High Level Functional Map, Technical Requirements and Client Site Reference Visits report and presentations). Cost to date is $834k, additional budget provided for FY1920 incorporated into Project Initiation Cost. Recruitment delays are translating into delays on delivering to plan, and burn rate risks becoming burn rate issues.
Q4 18-19 | V/Line Corporation | V/Line | 2491 | TRACKR Development | Transport and Vehicles | Systems Management | Replacement of train scheduling, train rostering and day of operation system | Delivery |  | Agile | 2016-06-15 | 2017-01-31 |  | 2018-04-03 | 247150 |  | 2018-04-03 | 2018-04-03 | 2018-12-31 | 2020-06-30 | 1415790 | 4020423 | Amber | Amber | Green | Green | Green | Project is in planning and analysis stage of Phase 2 - LACRS replacement. Four minor releases completed following go-live of TrackR v2 application with features and bug fixes
Q4 18-19 | VicRoads | VicRoads | 2492 | Australian Disability Parking Solution | Transport and Vehicles | Management of Process | Purpose of this project is to streamline and standardise the Disability Parking Application, Assessment and Management processes. | Delivery |  | Agile | 2017-07-01 | 2018-12-21 | 2018-07-02 | 2018-07-09 | 0 |  | 2018-07-23 |  | 2019-09-30 |  | 7905300 |  |  | Green | Green | Amber | Amber | Project is on amber status due to legislative delays have resulted in extension of council on-boarding activities out to the end of June 2020. Working with project authorities to resolve the issues.
Q4 18-19 | Victoria Police | VicPol | 2496 | Police Assistance Line and Online Reporting | Law and Justice | Customer Initiated Assistance | Two new channels for the public to report non-urgent events: Police Assistance Line (PAL) & Online Reporting (OLR). This project includes internet/intranet and cyber security. | Delivery |  | PRINCE2 | 2016-07-01 | 2017-06-30 |  | 2017-06-30 | 0 |  | 2017-06-30 |  | 2021-06-30 | 2020-12-31 | 212200000 |  | Green | Green | Green | Green | Green | The project is on schedule to achieve full capability by 2020.
Q4 18-19 | Victorian Electoral Commission | VEC | 2497 | EMS2 | Government and Economy | Development and Integration | Re-write of Election Management System | Delivery |  | Agile | 2017-03-01 | 2017-05-01 |  | 2017-05-01 | 50000 |  | 2017-05-01 | 2017-05-01 | 2018-06-30 | 2021-06-30 | 2000000 |  | Green | Green | Green | Green | Green | Project has had a slower than antipated start to the quarter with robust discussion on the detailed requirments and project schedule. The decommissioning strategy has also featured as a topic of significant discussion and influencer over the strategic direction of the project.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2499 | End User Computing - Implementation of Enabling Technologies | Government and Economy | Communication | Implementation of Exchange online, MS Office 365, Skype for Business, Windows 10 | Closed - Completed | 2019-05-23 | PMBoK | 2017-07-01 | 2017-07-01 |  | 2017-07-01 | 0 |  | 2017-07-01 | 2017-07-01 | 2018-06-30 | 2019-05-23 | 3981297 |  | Green | Green | Green | Green | Green | Project tracked to plan and is now closed.
Q4 18-19 | Yarra Valley Water | YV Water | 2501 | Corporate Procurement and Contract Management System | Environment and Water | Supply Chain Management | Implement a new corporate procurement governance and contract management system | Delivery |  | PRINCE2 | 2016-10-20 | 2016-10-20 |  | 2017-11-22 | 244000 |  | 2018-01-08 | 2018-01-08 | 2018-08-09 | 2019-09-30 | 2115800 | 2594353 | Green | Green | Green | Green | Green | Change Request completed to extend duration and cost to ensure functionality aligns with new Government procurement regulations.
Q4 18-19 | Yarra Valley Water | YV Water | 2502 | Enterprise Hosting Platform Replacement | Environment and Water | Systems Management | Replacement of Enterprise application hosting platform | Delivery |  | PRINCE2 | 2016-08-03 | 2017-06-09 |  | 2017-06-09 | 209121 |  | 2017-06-09 | 2017-06-09 | 2018-06-30 | 2019-07-31 | 3937879 | 7194879 | Amber | Green | Green | Green | Green | Tracking to plan for completion next quarter.
Q4 18-19 | Melbourne Health | Melb H | 2514 | Network Infrastructure Upgrade Project | Health | Communication | Upgrade of Network IT Infrastructure to provide robust, reliable network communication capability, including comprehensive WiFi network coverage across Melbourne Health agency campuses in readiness for EMR. Including Parkville Precinct Interconnect. | Delivery |  | PRINCE2 | 2017-07-03 | 2017-12-22 |  | 2018-01-01 | 0 |  | 2018-01-01 |  | 2019-12-20 |  | 11105000 |  | Green | Green | Green | Green | Green | The project is progressing to schedule.
Q4 18-19 | Department of Health and Human Services | DHHS | 2517 | Health Care Home ICT Enablement | Health | Development and Integration | ICT activities to support the Department's Health Care Home initiative; allowing health services to upload discharge summaries pathology results and radiology results to My Health Record and to view My Health Record data. | Delivery |  | PRINCE2 | 2017-09-01 | 2017-12-22 |  | 2017-12-22 | 0 |  | 2018-01-02 | 2018-01-02 | 2018-06-30 | 2020-06-30 | 4445000 | 8360000 | Green | Green | Amber | Amber | Green | Project completed its initial phase for connectivity to My Health Record. The secondary phase has been initiated and the activities for eReferrals is progressing to schedule.
Q4 18-19 | CenITex | CenITex | 2518 | Corporate Remedy Fix the Foundations | Government and Economy | Management of Process | BMC suite toolset uplift and functionality review linked to strategic objectives | Closed - Completed | 2019-06-30 | PRINCE2 | 2017-10-02 | 2017-10-25 |  | 2017-10-26 | 0 |  | 2017-10-27 | 2017-10-27 | 2018-06-30 | 2019-06-30 | 1720355 | 1520131 | Green | Amber | Amber | Red | Green | Further variation to extend the project to end of June as well as request additional funding was approved during the quarter, however project experienced further delays with vendor attempting to resolve technical issues with the product. Project has completed all UAT deliverables and is now reporting as closed.
Q4 18-19 | Northern Health | NH | 2519 | Infrastructure and Network refresh | Health | Development and Integration ,Visualisation | To design and implement a highly reliable and highly available infrastructure and network across NH sites to underpin the future EMR | Delivery |  | PRINCE2 | 2017-12-10 | 2018-02-05 |  | 2018-02-05 | 0 |  | 2018-03-26 | 2018-03-26 | 2019-09-10 | 2020-04-30 | 5000000 |  | Green | Green | Green | Green | Green | The project has been re baselined and endorsed by the Steering Committee, and is currently tracking to the revised schedule.
Q4 18-19 | Royal Women's Hospital | RWH | 2521 | EMR Network and Site Infrastructure Upgrade | Health | Organisational Management ,Security Management | To replace and upgrade legacy network, security and wireless infrastructure so that an appropriately secure, reliable and performing infrastructure can be in place to support clinicians and patient access to electronic medical record information. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-09-01 | 2017-10-19 |  | 2017-10-19 | 0 |  | 2017-11-14 |  | 2019-11-01 |  | 4976044 |  | Green | Green | Green | Green | Green | Project tracking to schedule.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2522 | Fuel Management System (FMS) | Emergencies and Safety | Data Management,Development and Integration ,Management of Process ,Reporting | Fuel Management System is single, intuitive and flexible platform for delivering the multi-agency fuel management program in Victoria. This systems is a component of the Emergency Management Information System developed by DELWP for FFMVic and CFA. | Delivery |  | Hybrid - Agile and PRINCE2 | 2015-05-11 | 2015-05-12 |  | 2015-05-12 | 67500 |  | 2015-07-01 | 2015-07-01 | 2018-12-31 | 2020-06-30 | 1900000 | 2223873 | Amber | Amber | Green | Green | Green | FMS Phase 1 (minimum viable product) will be delivered on 1 July 2019 for Forest Fire Management Vic (FFMVic) and Country Fire Authority(CFA) staff operational use.
Q4 18-19 | Goulburn Valley Region Water Corporation | GVR Water | 2524 | Asset Management Information System Replacement Project | Environment and Water | Assets/Materials Management | Carry out the collection and validation of asset data Undertake an AMIS Process Review Implement a software solution that meets the requirements of the organisation | Delivery |  | Internal GVW Project Management Methodology | 2016-11-23 | 2017-12-08 |  | 2017-12-08 | 50000 |  | 2018-01-02 |  | 2021-03-31 |  | 2405000 |  | Green | Green | Amber | Amber | Amber | Refresh of AMIS and GIS specifications and development of procurement/resource strategy.
Q4 18-19 | Goulburn Valley Region Water Corporation | GVR Water | 2525 | Intelligent Metering | Environment and Water | Assets/Materials Management | Installation of intelligent meters in four towns to provide data to target peak demand reduction, leading to: 1 . A permanent reduction in peak day water usage through leakage reduction. 2. Deferral of water network capacity upgrade projects | Delivery |  | GVW Internal Project Management Methodology | 2017-07-01 | 2018-03-02 |  | 2018-03-02 | 10000 |  | 2018-07-31 |  | 2021-06-30 |  | 1790000 |  | Green | Green | Green | Green | Green | Technical review draft has been submitted. Work on reviewing and updating business processes has commenced. A meter audit has begun.
Q4 18-19 | Independent Broad-based Anti-corruption Commission | IBAC | 2526 | Case Management System | Law and Justice | Tracking and Workflow | A system that provides for comprehensive case management, from the receipt of a complaint to the conclusion of an investigation. | Delivery |  | Agile | 2015-07-14 | 2016-05-02 |  | 2016-05-02 | 74518 |  | 2017-12-21 | 2017-12-21 | 2018-12-31 | 2019-12-31 | 1300000 | 1708000 | Green | Green | Green | Green | Green | Phase II deployed successfully, along with the upgrade to HPRM.
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2527 | Future Workplace Program (FWP) | Government and Economy | Collaboration ,Document Management ,Records Management ,Development and Integration ,Systems Management | The program is a coordinated set of projects that will deploy integrated technology platforms and enable business efficiency through information sharing, collaboration solutions and flexible online access to data, forms, and document workflows. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-07-03 | 2018-02-28 |  | 2018-03-22 | 2000000 |  | 2018-03-22 | 2018-03-22 | 2019-06-30 | 2019-09-30 | 10000000 | 15002808 | Amber | Green | Green | Green | Green | The Future Workplace Program is now in closing. The Automated Briefings and Correspondence (e- briefings) project will be delivered in Quarter 2.
Q4 18-19 | Department of Treasury and Finance | DTF | 2528 | SRIMS Infrastructure Refresh and Feasibility Assessment | Government and Economy | Financial Management | SRIMS is the State Resource Information Management System. This project will conduct a feasibility assessment of SRIMS 2025 and deliver upgraded infrastructure to deliver current projected capacity demands. | Delivery |  | PRINCE2 | 2017-10-02 | 2018-03-30 | 2017-12-01 | 2018-01-10 | 250000 |  | 2018-01-10 | 2018-01-10 | 2018-06-30 | 2019-12-31 | 0 | 3500000 | Amber | Amber | Amber | Amber | Amber | Stage 2 remains on hold. All efforts are focused on finalising the tender process and selecting the new strategic support partner.
Q4 18-19 | Royal Children's Hospital | RCH | 2530 | Rostering, Time & Attendance Project | Health | Human Capital / Workforce Management | Implement an enterprise electronic rostering, time and attendance solution. The system will cover rostering, hours worked and time capture to deliver a full 'work to pay' solution. | Delivery |  | PRINCE2 | 2018-01-01 | 2018-12-31 | 2019-03-29 | 2019-04-09 | 330000 | 620000 | 2019-04-15 | 2019-04-15 |  | 2020-02-28 | 0 | 1139709 |  |  |  |  | Green | Overall deployment of rostering is on-track. Additional parallel runs for payroll have created some delays but have no impact on overall project status.
Q4 18-19 | Melbourne Water | MELB Water | 2533 | Inflo CS16 Upgrade | Environment and Water | Content Management,Document Management | Upgrade content management system to current version | Closed - Completed | 2019-06-28 | Agile | 2017-01-25 | 2017-06-30 |  | 2017-11-23 | 0 |  | 2017-11-24 | 2017-11-24 | 2018-10-26 | 2019-06-28 | 1645120 | 1564461 | Green | Amber | Amber | Amber | Green | Project successfully delivered and has now closed.
Q4 18-19 | Department of Health and Human Services | DHHS | 2536 | Technology Modernisation | Property and Planning | Systems Management | The department seeks to modernise technology to enable staff flexibility in how they work and collaborate, through a technology replacement approach. To support the Workplace of the Future. | Closed - Completed | 2019-06-30 | Hybrid - Agile and PRINCE2 | 2017-04-10 | 2017-12-31 | 2017-07-10 | 2017-07-11 | 298000 |  | 2017-07-12 |  | 2019-06-30 |  | 6900000 | 7400000 | Green | Green | Green | Green | Green | The project solution has been delivered, closure administrative activities are underway.
Q4 18-19 | VicRoads | VicRoads | 2537 | National Driver Licence Facial Recognition System (NDLFRS) | Transport and Vehicles | Development and Integration | The National Driver Licence Facial Recognition System (NDLFRS) is an initiative led by Attorney-General's Department (AGD) under the auspices of the National Identity Security Strategy. The NDLFRS will form a component of the overarching National Facial Biometric Matching Capability (NFBMC), which is intended to provide biometric capabilities across a network of government data sources. Matching services involving the Department of Immigration and Department of Border Protection have already become operational within the framework. | Delivery |  | PRINCE2 | 2017-08-01 | 2017-10-30 |  | 2017-10-30 | 0 |  | 2017-11-01 | 2017-11-01 |  | 2019-12-31 | 2960000 | 4490000 | Green | Amber | Amber | Amber | Red | Project status is red due to delays in receiving approval for data transfer policy. VicRoads testing of platform is progressing and operational readiness preparations are underway.
Q4 18-19 | Court Services Victoria | CSV | 2538 | In-Court Technology | Law and Justice | Communication | The eCourts project is to fully upgrade in court technology - including cabling and infrastructure to the Supreme Court's courtrooms and mediation rooms. | Delivery |  | PMBoK | 2017-01-01 | 2017-06-30 |  | 2017-07-01 | 0 |  | 2017-09-01 |  | 2021-06-30 |  | 11748000 | 10911000 | Green | Green | Green | Green | Green | Project is on-track and within scope.
Q4 18-19 | Department of Education and Training | DET | 2540 | Premiers Reading Challenge | Education | Customer Relationship Management | The build of a replacement application and a new Mobile App for the annual Premiers’ Reading Challenge that supports children’s engagement with reading – the foundation for all education and development. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-02-15 | 2018-07-25 |  | 2018-07-25 | 509393 |  | 2018-07-26 | 2018-07-26 | 2019-06-04 | 2019-07-17 | 2568551 | 2696551 |  | Green | Amber | Red | Green | The project has returned to green. The new application is in production and commences a pilot phase from the commencement of Term 3 for the remainder of the 2019 Challenge.
Q4 18-19 | Department of Health and Human Services | DHHS | 2544 | Clinical Information Sharing | Health | Development and Integration | ICT activities to support the implementation of a Clinical Information Sharing Platform to facilities sharing of information between health services. | Delivery |  | PRINCE2 | 2017-10-01 | 2018-01-31 |  | 2018-01-31 | 0 |  | 2018-02-01 |  | 2020-12-31 |  | 18180000 |  | Green | Green | Green | Amber | Amber | Initiate review of Clinical Information Legislative changes required to progress this initiative.
Q4 18-19 | CenITex | CenITex | 2545 | Software Defined DC Hosting Services | Government and Economy | Assets/Materials Management | Transform the current hosting services into a modern, software defined data centre | Closed - Completed | 2019-06-30 | PRINCE2 | 2018-01-03 | 2018-01-16 |  | 2018-01-17 | 0 |  | 2018-02-19 |  | 2019-06-30 |  | 2197700 |  | Green | Green | Green | Green | Green | Stage 1 scope: Design & build then commence migration of services completed. ~1300 services migrated successfully without incident. Project now complete as per scope & schedule. Separate Stage 2 project will complete additional migrations before December 2019 subject to customer endorsement of migration schedule.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2546 | IBM Transformation | Government and Economy | Systems Management | Transition to new supplier, transformation, data centre migration and implementation of Service Now. | Closed - Completed | 2019-06-30 | PMBoK | 2017-11-20 | 2017-11-20 |  | 2017-11-20 | 0 |  | 2017-11-20 | 2017-11-20 | 2018-12-10 | 2019-06-30 | 2436940 | 3810940 | Amber | Amber | Amber | Green | Green | Project tracked to plan and is now closed.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2547 | Business Support Systems Review (BSSR) - Finance | Employment and Workplace | Customer Relationship Management | Implementation of core financial and budgeting solution for DELWP. The project will be implementing cloud-based solutions with integration into existing solutions within the DELWP environment | Closed - Merged | 2019-06-28 | PRINCE2 | 2018-02-01 | 2018-12-31 |  | 2018-12-31 | 851000 |  | 2019-01-01 | 2019-07-01 | 2019-08-15 | 2019-12-31 | 9035669 | 9266000 |  |  | Green | Amber | Red | The project is re-planning to create a new baseline. This project is merging with 'Business Support Systems Review (BSSR) - HCM' project in order to present an overall program view of the BSSR Program.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2548 | Workplace 2020 - Application Refresh | Employment and Workplace | Communication | Reduce email platform hosting, storage and maintenance costs​ and supporting a flexible and mobile workforce​, by providing a consistent and integrated user experience leveraging Office 365​ | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-02-05 | 2018-03-29 |  | 2018-04-23 | 60000 |  | 2018-09-07 | 2018-09-07 | 2019-06-30 | 2019-07-31 | 2240000 |  | Amber | Amber | Green | Green | Green | Project is on track to deliver according to plan. It will start closing and transition activities in July.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2549 | Workplace 2020 - Device Refresh | Employment and Workplace | Financial Management | Establish a sustainable funding model by implementing a workforce Personas model in order to modernise and rationalise the End User Computing device fleet | Closed - Completed | 2019-06-28 | Hybrid - Agile and PRINCE2 | 2017-12-04 | 2018-02-28 |  | 2018-03-23 | 100000 |  | 2018-08-02 | 2018-08-02 | 2019-03-29 | 2019-06-30 | 2360000 |  | Amber | Amber | Green | Green | Green | The project was delivered according to plan, it is on closing and transition activities according to plan.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2550 | Workplace 2020 - Communication and Collaboration | Employment and Workplace | Communication | Leveraging on Office 365 investments and existing collaboration tools ​to shift from traditional phone systems to soft phones, and integrate with existing collaboration solutions and platforms | Closed - Terminated | 2019-06-28 | Hybrid - Agile and PRINCE2 | 2017-11-27 | 2018-06-29 |  |  | 40000 | [5 empty] | 0 | [6 empty] | The project has been closed as it was descoped from the Workplace 2020 program.
Q4 18-19 | Energy Safe Victoria | ESV | 2551 | Certificates of Electrical Safety | Emergencies and Safety | Management of Process | Review and replacement of existing legacy system into ESV's ESVConnect constituent portal. | Delivery |  | Agile | 2018-02-05 | 2018-05-04 | 2018-03-29 | 2018-04-18 | 0 | 384000 | 2018-04-22 | 2018-04-22 | 2018-11-15 | 2019-07-21 | 0 | 2577087 | Green | Green | Green | Green | Green | Minor delay to delivery but otherwise on track
Q4 18-19 | Public Transport Victoria | PTV | 2552 | PTV Digital Workplace - Email and Calendar | Transport and Vehicles | Communication | This project will transition all PTV staff from Windows 7 & Lotus Notes to Windows 10 Office 365 and Notes 9. This project is PTV's component of a DEDJTR wide program. | Delivery |  | PTV Investment Lifecycle | 2017-03-10 | 2017-08-27 |  | 2017-08-27 | 55836 |  | 2017-08-28 | 2017-11-16 | 2018-10-12 | 2019-06-27 | 2444164 |  | Amber | Amber | Green | Green | Green | The project is in close out.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2561 | Digital Cadastre Modernisation Project | Property and Planning | Knowledge Management | The Digital Cadastre Modernisation project will build a fully digital cadastre. Stage 1 Back Capture will transform registered plans and surveys into LandXML files. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-02-12 | 2018-09-30 |  | 2018-09-30 | 0 | 200000 | 2018-11-16 | 2018-11-16 | 2023-12-30 | 2022-12-30 | 0 | 45000000 |  |  | Green | Green | Green | STAGE 1 Back Capture is on track to deliver according to plan. Procurement is in progress for STAGE 2 Adjustment, STAGE 3a Integration, STAGE 3b Maintenance and STAGE 4 Automation.
Q4 18-19 | Public Transport Victoria | PTV | 2562 | Metropolitan Train Control (Metrol) Replacement | Transport and Vehicles | Systems Management | Replacement of the Metrol signalling control system with a Core Train Control and Monitoring System (TCMS); Replacement of Train Operational Reporting System (TOPS) with Performance Reporting System (PRS); Upgrade of the PRIDE passenger info system. | Delivery |  | PTV Investment Lifecycle | 2005-07-01 | 2006-08-21 |  | 2006-08-21 | 1100 |  | 2007-03-06 | 2007-03-06 | 2018-07-31 | 2020-08-26 | 92498900 |  | Amber | Amber | Amber | Amber | Amber | The project is reviewing the contract change proposal put forward by the vendor and preparing all the related documentation to enable delivery to continue.
Q4 18-19 | Eastern Health | EH | 2563 | Single Billing System Project | Health | Data Management,Development and Integration ,Financial Management | Deliver a single billing system to replace up to 17 legacy systems used for patient accounts billing for Eastern Health | Delivery |  | PRINCE2 | 2017-07-01 | 2018-02-04 | 2018-03-28 | 2018-03-28 | 508851 |  | 2018-04-17 |  | 2020-06-30 |  | 6839088 | 7280136 | Amber | Amber | Green | Green | Green | Project is tracking in accordance with plan
Q4 18-19 | Coliban Region Water Corporation | Coliban Water | 2564 | Billing CRM SRM System Project | Environment and Water | Customer Relationship Management | The project will design and adopt new business practices and technology for billing, revenue, customer solutions and customer service to enable the organisation to efficiently and effectively deliver value to customers | Delivery |  | Agile | 2018-02-04 | 2018-08-31 | 2018-11-16 | 2018-11-16 | 700000 |  | 2018-12-03 | 2018-12-03 | 2020-02-10 | 2020-03-10 | 0 | 3465392 |  |  | Green | Green | Green | Project on track
Q4 18-19 | Melbourne Water | MELB Water | 2565 | Asset management system upgrade | Environment and Water | Assets/Materials Management | Asset management core system upgrade to current version | Closed - Completed | 2019-05-14 | Agile | 2017-10-18 | 2018-03-26 |  | 2018-05-18 | 0 |  | 2018-05-18 | 2018-05-18 | 2019-03-05 | 2019-05-14 | 2122131 | 1638048 | Green | Green | Amber | Green | Green | Project successfully delivered and has now closed.
Q4 18-19 | Coliban Region Water Corporation | Coliban Water | 2567 | Digital Customer Metering Program | Environment and Water | Data Management | To automate manual meter reading to improve business intelligence, asset management and network planning | Delivery |  | PMBoK | 2016-01-18 | 2017-07-25 |  | 2017-07-25 | 72000 |  | 2017-07-25 |  | 2023-06-30 |  | 5448000 |  | Green | Green | Green | Green | Green | Program is on target
Q4 18-19 | Westernport Region Water Corporation | WPR Water | 2568 | Business Transformation Project | Government and Economy | Systems Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | WPW is looking to replace its current ICT managed services environment services solution which includes Part 1: Corporate System Replacement and Part 2: IT Managed Services environment | Delivery |  | PRINCE2 | 2017-07-01 | 2018-05-07 | 2018-01-30 | 2018-03-19 | 2089200 | 135000 | 2018-05-07 | 2018-05-07 | 2020-06-30 | 2020-06-30 | 0 | 3124734 | Green | Green | Green | Green | Green | Preferred software implementation partners procured.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2570 | Justice eProcurement Implementation (JEPI) Project | Law and Justice | Management of Process | Implementation of department wide electronic sourcing and contract management system. | Delivery |  | Project Management Excellence | 2016-06-30 | 2017-11-24 |  | 2017-11-24 | 0 |  | 2018-01-01 | 2018-01-01 | 2018-11-12 | 2019-04-12 | 1530000 | 1803800 | Amber | Amber | Green | Green | Green | Business Go Live for Contract Management completed as scheduled in mid-February 2019. The pilot for electronic sourcing has been slowed to enable the contract management system to be embedded prior to commencing the pilot. This pilot is currently being planned to complete by August/September 2019 and is subject to the approval of a change request.
Q4 18-19 | Department of Health and Human Services | DHHS | 2576 | Human Capital Management System | Employment and Workplace | Human Capital / Workforce Management | Implementation of a cloud based Human Capital management system will uplift and modernise the department's human resources systems and deliver consistent human resources services across the department and secondly across the Victorian Public Service. | Delivery |  | Agile | 2017-11-30 | 2018-06-04 | 2018-03-29 | 2018-03-29 | 300000 |  | 2018-04-03 | 2018-04-03 | 2020-06-30 | 2019-12-31 | 8987000 | 9437876 | Amber | Amber | Green | Amber | Amber | Project is progressing but has had a scope change and is being re-baselined as a result.
Q4 18-19 | Grampians Rural Health Alliance | GRHA | 2578 | DjHS Patient Administration System Upgrade | Health | Investment Management | Upgrade of Patient Administration System at Djerriwarrh Health Services, including moving to a region hosted environment. | Delivery |  | PMBoK | 2017-11-27 | 2017-12-23 |  | 2017-12-23 | 0 |  | 2018-06-26 | 2018-06-26 | 2019-05-10 | 2019-08-09 | 1200000 |  |  | Green | Green | Green | Green | The project has been re-baselined due to complex data migration issues. The project steering committee has approved the revised project delivery date. The project is on track.
Q4 18-19 | VicRoads | VicRoads | 2579 | Service Oriented Licencing and Registration (SOLR) | Transport and Vehicles | Development and Integration | Purpose of this project is to create a modern services based platform to work in parallel with VicRoads Registration and Licencing mainframe system. | Initiated |  | Agile | 2018-06-06 | 2019-06-17 | 2019-08-30 |  | 0 | [12 empty] | An independent program review to ensure quality assurance and validation of architecture and benefits of the program has been concluded by KPMG and they have provided R&L stakeholders with the Commercial and Technical findings. These findings are being reviewed by R&L and a SOLR Business Case is currently in progress.
Q4 18-19 | Transport Accident Commission | TAC | 2580 | Employee Experience & Enablement | Transport and Vehicles | Customer Initiated Assistance | Application Remediation project will deliver an upgraded technical foundation by moving the TAC to Windows 10 and Office 365. It will ensure all TAC applications are compatible with Windows 10 and are deployed onto new or existing hardware. | Delivery |  | PRINCE2 | 2018-03-26 | 2018-04-03 |  | 2018-04-04 | 0 |  | 2018-06-01 | 2018-06-01 | 2018-10-31 | 2019-09-30 | 1864995 | 1644779 | Green | Green | Green | Green | Green | As at the end of June 2019 the overall project is considered to be tracking as green. The remaining deliverables are limited to the upgrade of the Sun Systems for Finance and the eWFM upgrade to Rapid Recovery (RR) telephone staff. Immediate Focus on both the device deployment and planning for the system upgrades will be coordinated together for Finance and Rapid Recovery for the target Go Live in August and project closure activities in September.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2581 | 50 Franklin Street Fit-out | Law and Justice | Organisational Management | Multi staged IT fit-out for new premises at 50 Franklin St to co-locate Corrections Victoria staff and other DJR business units (17 level building). | Closed - Completed | 2019-04-30 | Project Management Excellence | 2018-03-07 | 2018-04-16 |  | 2018-04-16 | 0 |  | 2018-04-17 | 2018-04-17 | 2018-12-31 | 2019-04-30 | 4587466 |  | Green | Green | Green | Green | Green | The site has opened and is fully operational. The project is now in closure.
Q4 18-19 | Department of Health and Human Services | DHHS | 2582 | Victorian Alcohol and Drug Collection Implementation | Health | Data Management,Reporting | The Victorian Alcohol and Drug Collection (VADC) implementation supports Victorian-Government funded alcohol and drug treatment service providers to submit data to the Department each month in accordance with the specification and business rules. | Closed - Completed | 2019-06-30 | PRINCE2 | 2016-05-27 | 2016-12-31 |  | 2017-06-22 | 130900 | 161700 | 2017-07-01 | 2017-07-01 | 2018-12-31 | 2019-06-30 | 727000 | 1555898 | Red | Amber | Amber | Green | Green | The project has been successfully delivered to schedule and within budget.
Q4 18-19 | Public Transport Victoria | PTV | 2586 | TCMS Phase 2: Monitoring Improvements | Transport and Vehicles | Analyses and Statistics | Introduction of additional fault alerting and network monitoring capabilities in the TCMS. | Delivery |  | PTV Investment Lifecycle | 2018-02-08 | 2018-11-30 | 2018-11-21 | 2018-11-21 | 61851 |  | 2018-12-03 |  | 2019-12-13 |  | 0 | 988149 |  |  | Green | Green | Green | The project is on track to complete the commission of the Disaster Recovery Site on 06 July and the commission of the Main Control Site on 04 October.
Q4 18-19 | Eastern Health | EH | 2587 | RosterOn project | Health | Human Capital / Workforce Management | Implement a new rostering, time and attendance system for all areas of Eastern Health. Objective is to replace manual, disparate administrative processes with automated electronic systems. | Delivery |  | PRINCE2 | 2015-10-12 | 2018-08-10 |  | 2018-08-13 | 190135 |  | 2018-08-13 |  | 2020-09-30 |  | 0 | 4472865 |  | Green | Green | Green | Green | Project is tracking to schedule
Q4 18-19 | City West Water Corporation | CW Water | 2591 | HRIS (1003210) | Environment and Water | Human Capital / Workforce Management | The new system aims to support the strategic environment and address existing issues around departments not having a dedicated HR system to perform HR processes and reporting requirements. | Delivery |  | Waterfall and Agile | 2017-08-24 | 2018-04-12 |  | 2018-04-12 | 122000 |  | 2018-04-12 | 2018-04-12 | 2019-09-30 | 2019-08-15 | 2935906 | 2212667 | Green | Green | Green | Green | Green | Successful delivery of Employee Central and learning management. Project extended to conclude in August 2019 due to a business (PSC) decision to expand capability and deliver AD Integration. Project is on track to deliver by the agreed timeline Revised delivery time incorporates all closure activities.
Q4 18-19 | City West Water Corporation | CW Water | 2592 | HSEQ (1006412) | Environment and Water | Data Management | This project is focused on providing CWW with an integrated and consistent approach to managing Health, Safety, Environment, Quality & Risk frameworks (processes policies procedures etc.). | Delivery |  | Waterfall and Agile | 2017-08-24 | 2018-04-12 |  | 2018-04-12 | 93000 |  | 2018-04-12 | 2018-04-12 | 2019-02-01 | 2019-07-14 | 1213348 | 1513348 | Green | Green | Green | Green | Green | Project implementation delayed to 15/4. Revised delivery incorporates closure activities.
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2594 | HRIS Project | Government and Economy | Data Management,Human Capital / Workforce Management ,Human Resources,Organisational Management | The core outcomes include: a simpler flexible mobile friendly more comprehensive HR self-service processes; streamlined and efficient payroll operations processes; and a single source of authoritative workforce and organisational structure data. | Postponed | 2019-06-28 | PRINCE2 | 2017-11-13 | 2017-11-13 |  | 2017-11-13 | 0 |  | 2018-04-02 | 2018-05-01 | 2019-03-31 | 2019-06-30 | 1830000 |  | Green | Amber | Amber | Green | Red | Project placed on hold due to a significant issue that delayed the June delivery of the project. Active investigations to resolve the issue are underway.
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2595 | GEMS 2.0 Agile Design Studio Project | Government and Economy | Business Intelligence,Data Management,Knowledge Management ,Reporting | This project will deliver improved accessibility, user interface and user experience for the Global Engagement Management System (GEMS). | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-05-08 | 2018-10-02 | 2018-10-01 | 2018-10-01 | 1300000 |  | 2018-10-01 |  | 2021-06-30 |  | 3476500 |  |  |  | Amber | Amber | Green | The project is in delivery and is on track.
Q4 18-19 | VicRoads | VicRoads | 2596 | Human Resource Information System (HRIS) | Transport and Vehicles | Development and Integration ,Human Capital / Workforce Management ,Human Resources | Objective of this project is to implement a fully integrated centralised and mobile friendly solution to provide one stop shop for people and culture function | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-04-16 | 2018-11-30 | 2019-01-30 | 2019-01-30 | 0 |  | 2019-01-30 | 2019-01-30 |  | 2020-11-30 | 0 | 3977600 |  |  |  | Green | Amber | Overall project is Amber due to schedule impacts resulting from implementation of changes related to Department of Transport ( DoT) transition requirements. Action plan to move to green will be presented to Project Authority in July 19.
Q4 18-19 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering and Time & Attendance Project | Health | Management of Process | This project will introduce a software solution which will enable; process automation, improve accuracy and timeliness and provide better user experience through inclusion of mobile technologies as standard operating model. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 | 2018-07-11 | 2019-12-31 | 2020-12-31 | 3443281 |  | Green | Green | Green | Green | Green | Project progress to date is on schedule. Project Steering Committee approved schedule adjustment to 31 Dec 2020. There is no impact on project budget.
Q4 18-19 | South West Alliance of Rural Health | SWARH | 2599 | Barwon Health Rebuild of PROMPT Document Management System | Health | Document Management | Barwon Health is undertaking a full rebuild of the PROMPT document management system. The rebuild will ensure that the new PROMPT is extensible,maintainable and sustainable for future needs adding value to Health Services safety and quality programs. | Delivery |  | Agile | 2018-04-19 | 2018-05-30 |  | 2018-06-01 | 1 |  | 2018-06-04 | 2018-06-04 | 2019-06-30 | 2019-10-04 | 1300000 |  | Green | Green | Amber | Green | Green | Project is on track. Currently 60% of the project has been delivered. By next quarter the MVP (Minimum Viable Product) is expected to be produced before building of the new drafting and review features.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2602 | IAAS Transition | Government and Economy | Systems Management | Transition of IT infrastructure services to an external provider. | Delivery |  | PMBoK | 2017-09-01 | 2017-10-18 |  | 2017-10-18 | 0 |  | 2017-10-18 | 2017-10-18 | 2018-06-30 | 2019-07-31 | 834030 | 1038328 | Amber | Amber | Amber | Green | Green | Project is tracking to plan.
Q4 18-19 | Department of Health and Human Services | DHHS | 2603 | Regulatory Licensing and Registration Platform | Health | Systems Management | Replacement of the Radiation Registration and Licensing (RELIC) system utilised by the Environmental Health Regulation & Compliance Unit to administer their Act & legislation. Development of a platform configurable for other DHHS regulatory units. | Delivery |  | Agile | 2017-10-20 | 2017-11-05 |  | 2017-11-05 | 0 |  | 2017-11-06 | 2017-11-06 | 2019-06-30 | 2019-09-30 | 2400000 | 1500000 | Green | Amber | Green | Amber | Amber | Phased deployment of core functionality on track but schedule has been revised to finalise development of advanced functionality.
Q4 18-19 | Wannon Region Water Corporation | WAN Water | 2604 | Works Management System | Environment and Water | Assets/Materials Management | Replacing two legacy works management systems. | Delivery |  | PRINCE2 | 2017-07-01 | 2018-08-01 |  | 2018-08-01 | 50000 | 0 | 2018-08-01 | 2018-08-01 | 2018-12-14 | 2019-11-15 | 1200000 | 2006940 | Green | Green | Green | Green | Green | Project tracking well.
Q4 18-19 | State Revenue Office | SRO | 2615 | Wagering & Betting Tax | Government and Economy | Development and Integration | This project is providing the functionality required to collect and administer the new 8 per cent point of consumption wagering and betting tax, which comes into effect from 1 January 2019. | Delivery |  | PRINCE2 | 2018-07-11 | 2018-08-17 |  | 2018-09-12 | 38262 |  | 2018-09-12 | 2018-09-12 | 2019-09-06 | 2019-11-08 | 1727719 | 2087744 |  | Green | Green | Green | Green | Stage 4 was successfully implemented on 27 May 2019. The remaining work comprising two stages including one additional stage has been rescheduled due to the priority of implementing the 2019 State Budget initiatives and other work. Additional funding was approved to complete the project in 2019-20.
Q4 18-19 | State Revenue Office | SRO | 2619 | Digital Duties Program | Government and Economy | Development and Integration | This project is delivering system enhancements with the aim of achieving 100 per cent digital lodgement for processing and determining duty on land transfer transactions. | Delivery |  | PRINCE2 | 2018-07-01 | 2018-10-12 | 2018-10-10 | 2018-10-10 | 47078 |  | 2018-10-10 |  | 2020-01-17 |  | 1396256 | 1936609 |  |  | Green | Green | Amber | Enhancements to the PEXA gateway to enable the processing of complex transactions were successfully implemented on 17 June 2019. Planned work on the remaining project stages was delayed by the concerted focus and effort required in the lead-up to implementing the changes to the gateway. The remaining stages will commence in Q1 2019-20 with additional funding provided to complete them.
Q4 18-19 | State Revenue Office | SRO | 2620 | Digital Customer Services | Government and Economy | Development and Integration | This project, part of the State Revenue Office's wider digital transformation strategy, is providing customers with online services where they can manage their Land Tax records. . | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-11-06 | 2018-10-10 | 2018-11-11 | 2018-11-11 | 264727 | 163539 | 2018-11-11 | 2018-11-11 | 2020-06-29 | 2021-06-03 | 0 | 5575461 |  |  | Green | Green | Green | Release 1 of Amendments Online (My Land Tax) was successfully delivered on 27 May 2019. The public release of My Land Tax is scheduled for late August 2019. Subsequent releases have been rescheduled due to priority being given to implementing 2019 State Budget initiatives and other work. The project will now extend into 2020-2021 and there has been a small increase in the project budget.
Q4 18-19 | State Revenue Office | SRO | 2621 | AutoPay | Government and Economy | Development and Integration | This project is delivering an online application enabling customers to set up instalment payment plans, with a range of periodic payment options, for their assessments. | Delivery |  | PRINCE2 | 2016-02-15 | 2017-05-08 |  | 2017-05-08 | 13984 |  | 2017-05-08 | 2017-05-08 | 2019-03-25 | 2020-06-30 | 1023919 | 1029285 |  | Amber | Amber | Amber | Amber | One final stage remains to be delivered - AutoPay for Debt: Work on this stage has been impacted by competing project resource requirements and consequently has been placed on hold. It is planned to recommence work in Q1 2019-20.
Q4 18-19 | Hume Rural Health Alliance | HRHA | 2622 | Northeast Health Wangaratta Patient Administration System (PAS) | Health | Organisational Management ,Business Intelligence,Data Management,Financial Management,Management of Process ,Records Management ,Routing and Scheduling,Security Management ,Tracking and Workflow | A Patient Administration System (PAS) replacing a current end of life PAS. The replacement PAS will be adopted by 7 health services within the Central Hume Region | Initiated |  | PRINCE2 | 2018-08-01 | 2019-02-28 | 2019-08-09 | 2019-08-14 | 75000 | [12 empty] | Planning study with vendor completed with relevant documentation being approved.
Q4 18-19 | Hume Rural Health Alliance | HRHA | 2623 | West Hume Patient Administration System (PAS) | Health | Organisational Management ,Business Intelligence,Data Management,Financial Management,Management of Process ,Records Management ,Security Management ,Tracking and Workflow,Routing and Scheduling | A Patient Administration System (PAS) replacing a current end of life PAS. The replacement PAS will be adopted by 7 health services within the Hume Region | Initiated |  | PRINCE2 | 2018-08-01 | 2018-12-31 |  | 2019-07-06 | 250000 | 2200000 | [11 empty] | Project governance structures have been established. Recruitment of Project Director underway. Feasibility study of options about to commence.
Q4 18-19 | Hume Rural Health Alliance | HRHA | 2626 | Albury Wodonga Health Patient Administration System (PAS) | Health | Organisational Management ,Business Intelligence,Data Management,Financial Management,Management of Process ,Records Management ,Security Management ,Tracking and Workflow,Routing and Scheduling | A Patient Administration System (PAS) replacing a current end of life PAS. The replacement PAS will be adopted by Albury Wodonga Health | Initiated |  | PRINCE2 | 2018-08-01 | 2020-08-31 |  |  | 1700000 | 250000 | [11 empty] | Feasibility study of options underway
Q4 18-19 | South West Alliance of Rural Health | SWARH | 2627 | Barwon Health North | Health | Development and Integration | This project involves the build of a new healthcare facility including the fit-out of all ICT such as cabled and wireless network infrastructure workstation endpoints AV systems and a Kiosk Ticketing System. | Delivery |  | PRINCE2 | 2014-05-06 | 2014-12-01 |  | 2015-03-01 | 1 |  | 2016-04-01 |  | 2019-08-30 |  | 1153000 |  |  | Green | Green | Green | Green | Project is on track and ICT costs remain within budget
Q4 18-19 | South West Alliance of Rural Health | SWARH | 2628 | SWARH Storage and Compute - Tranche 2 | Health | Data Management,Development and Integration ,Systems Management | Program seeks to replace technical components that are past/facing end-of-life, utilise current & new technologies to improve service availability, sustainability & reliability, and refresh the SWARH organisation – its people, processes and tools. | Delivery |  | PRINCE2 | 2018-09-28 | 2018-10-15 |  | 2018-10-15 | 0 |  | 2019-01-15 | 2019-01-15 | 2019-04-30 | 2019-09-30 | 1189000 | 1239000 |  | Green | Green | Amber | Amber | The project has been re-baselined to address implementation issues the revised delivery date has been approved by the steering committee . The rollout of Barwon Health may be delayed due to system application issues that are currently under review.
Q4 18-19 | VicRoads | VicRoads | 2629 | Sunsetting Regulations | Transport and Vehicles | Development and Integration ,Management of Process | Regulations under the Road Safety Act 1986 are automatically revoked on the 10th anniversary of their making. This program will implement the remade regulations into VicRoads and ensure necessary changes are made by partner and government agencies. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-07-02 | 2018-08-17 |  | 2018-09-17 | 0 |  | 2018-09-17 |  | 2020-01-31 |  | 9075000 |  |  | Amber | Red | Red | Red | Overall project status is Red due to risks and issues associated with competing priorities on vendors and resources. The current regulatory sunset dates may be extended.
Q4 18-19 | Transport Accident Commission | TAC | 2630 | Data Analytics | Transport and Vehicles | Business Intelligence | Implement an Enterprise Data Warehouse (EDW) that will contain the single source of truth for TAC's data. The program will also implement enterprise data policies and governance to ensure that data is of a high quality. | Delivery |  | PRINCE2 | 2018-06-01 | 2018-06-30 |  | 2018-07-03 | 0 | 1195727 | 2018-07-03 | 2018-07-03 | 2019-11-30 | 2021-06-30 | 5700000 | 13804273 |  | Green | Green | Amber | Green | As at the end of June 2019 the overall project is considered to be tracking as green.
Q4 18-19 | Department of Premier and Cabinet | DPC | 2631 | DPC - Digital Office Upgrade Project | Employment and Workplace | Collaboration | The Digital Office Upgrade project will deliver a new technology environment for the Department of Premier and Cabinet.. This project involves an upgrade to Microsoft Windows 10 operating system and the cloud-based Office 365 suite of applications . | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-08-01 | 2018-09-16 |  | 2018-09-16 | 0 |  | 2018-09-17 | 2018-09-17 | 2019-03-29 | 2019-08-30 | 2300000 | 2420000 |  | Amber | Green | Green | Green | Digital Office Upgrade successfully migrated core Department of Premier and Cabinet personnel, the Office of General Counsel, Government House and teams affected by machinery of government changes (post election) to Windows 10 and Office 365. Changes to the DPC project team and the need for extra effort on the next set of planned activities required the project schedule to be re-baselined to the end of August 2019. However the estimated cost to complete the project remains within the approved project budget.
Q4 18-19 | V/Line Corporation | V/Line | 2632 | Performance Hub | Transport and Vehicles | Analyses and Statistics | Establishment of centralised data repository & predictive and prescriptive analytics capability for V/Line operations | Delivery |  | Agile | 2018-07-01 | 2018-08-17 |  | 2018-08-19 | 98930 |  | 2018-08-19 | 2018-08-19 | 2019-06-29 | 2020-06-30 | 1490500 | 3165260 |  | Amber | Amber | Amber | Green | Additional funding for 4TEL PIDS secured. Workshop held to recover from issue with Datalogger data migration.
Q4 18-19 | South East Water | SE Water | 2639 | Asset Register Implementation Phase 1 - 2 | Environment and Water | Assets/Materials Management | The full scope will deliver a unified Asset Register. The first phase will deliver an Asset Register for the Digital Utilities Program to provide a real-time source for asset data repository and management solution. | Delivery |  | PMBoK | 2018-08-27 | 2018-10-23 |  | 2018-10-26 | 0 | 45280 | 2018-11-22 | 2018-11-22 | 2019-07-31 | 2020-02-28 | 0 | 2545680 |  |  | Green | Green | Green | System interface design is well underway. In order to gain economy of scale Phase 2 scope has been integrated with phase 1. Due to this phase 1 timeframes have been extended.
Q4 18-19 | VicRoads | VicRoads | 2640 | Customer Notification Platform (Formerly Customer Correspondence) | Transport and Vehicles | Development and Integration ,Management of Process | Establishment of a print ready platform and migration of customer correspondence | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-08-06 | 2018-10-25 | 2019-03-04 | 2019-03-04 | 0 |  | 2019-03-05 | 2019-03-05 |  | 2019-09-30 | 0 | 1340000 |  |  |  | Red | Green | Overall project status is Green. Procurement activities complete, with contracts awarded to successful vendor. Working with vendor to develop detailed project plan.
Q4 18-19 | Department of Health and Human Services | DHHS | 2641 | Clinical Technology Refresh | Health | Investment Management | Replacement of clinical services technology assets for the Victorian acute public health sector. | Closed - Completed | 2019-06-30 | PRINCE2 | 2018-02-01 | 2018-05-01 |  | 2018-05-01 | 1 |  | 2018-07-01 |  | 2019-06-30 |  | 11999999 |  |  | Green | Green | Green | Green | Project has been delivered successfully to schedule.
Q4 18-19 | Department of Health and Human Services | DHHS | 2642 | Security Operations Centre (SOC) | Health | Security Management | The Security Operations Centre Project will implement a security system to 24 health sector organisational groups to support identification, detection and protection from cyber security threats. | Delivery |  | PRINCE2 | 2017-10-01 | 2018-01-01 |  | 2018-01-01 | 1 |  | 2018-02-01 | 2018-02-01 | 2019-07-31 | 2019-09-30 | 2499999 |  |  | Green | Green | Green | Green | RFQ was released on the 25 March 2019 on schedule and closed on 10 May 2019. Contract finalisation planned for 30 September 2019.
Q4 18-19 | VicRoads | VicRoads | 2643 | Enterprise Risk Management (ERM) | Transport and Vehicles | Management of Process ,Organisational Management | The Enterprise Risk Management (ERM) project will deliver a VicRoads-wide platform solution for business area with agreed business requirements. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-07-16 | 2018-10-31 | 2019-05-31 | 2019-05-31 | 0 |  | 2019-06-03 |  | 2019-09-30 |  | 2285000 | [5 empty] | Green | Overall project is Green following on boarding of the professional services partner. Project plans have now been re-baselined for remainder of 2019 and the project team is well underway with design/build phases for initial and ongoing delivery across all business functions.
Q4 18-19 | Department of Health and Human Services | DHHS | 2645 | Future Workplace Enablement | Property and Planning | Systems Management | The department seeks to implement an agile working fit out combining technology, accommodation services and people and culture policy to create a collaborative environment to work. | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-09-19 | 2019-05-30 | 2019-08-30 |  | 0 | [12 empty] | Planning and mobilisation activities are in progress.
Q4 18-19 | Department of Health and Human Services | DHHS | 2646 | Service Management Platform (SMP) | Community Services | Management of Process | The project will provide enterprise service management, contact centre management and workforce management capabilities to enable the newly formed Customer Support Branch to provide all business-as-usual, repeatable and essential corporate activities | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-02-01 | 2018-12-25 | 2018-10-23 | 2018-10-23 | 0 |  | 2018-11-09 | 2018-11-09 | 2019-07-12 | 2019-09-30 | 6910000 |  |  |  | Green | Amber | Green | Project is progressing to revised, agreed schedule.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2647 | End User Computing - Phase Two | Government and Economy | Communication | The objectives of the project are; 1. Address remote access shared mail boxes and upgrade domino backend servers. 2. Uplift systems including Microsoft Office, OneDrive, SharePoint. 3. Relocation of PABX. | Closed - Completed | 2019-06-30 | PMBoK | 2018-08-06 | 2018-12-31 | 2019-01-01 | 2019-01-01 | 1075800 | 698264 | 2019-02-28 | 2019-01-01 |  | 2019-06-30 | 377553 |  |  |  |  | Green | Green | Project tracked to plan and is now closed.
Q4 18-19 | VicRoads | VicRoads | 2648 | Drink Drug Initiative Program (DDIP) - Stage 3 | Transport and Vehicles | Management of Process | includes the implementation of outstanding drink driving legislation changes from Transport Legislation Amendment (Road Safety Rail and Other Matters) Bill 2017 and the Transport Legislation Amendment (Better Roads Victoria and Other Amendments) Bil | Delivery |  | PRINCE2 | 2018-07-30 | 2018-10-31 |  | 2018-10-31 | 0 |  | 2018-11-05 | 2018-11-05 | 2020-05-29 | 2020-02-28 | 6200000 | 7212963 |  |  | Amber | Amber | Red | Project is in Red status due to resourcing constraints and tight delivery time frame as a result of commencement of legislation changes (1st December 2019) . Working with Project Authority to generate options to minimize impacts on schedule and budget.
Q4 18-19 | Public Transport Victoria | PTV | 2649 | Mobile myki | Transport and Vehicles | Development and Integration | Implementation of a digital myki for Android smartphones that utilises near field communication technology to integrate with existing myki ticket barriers and card readers across multiple transport modes. | Delivery |  | PTV Investment Lifecycle | 2018-05-25 | 2018-05-25 |  | 2018-05-25 | 0 |  | 2018-05-28 | 2018-05-28 | 2019-03-30 | 2019-07-30 | 3708303 |  |  | Green | Red | Green | Green | The project is in close-out phase going through the administrative close-out processes and transition gates and delivering the variations that were ordered.
Q4 18-19 | CenITex | CenITex | 2650 | Fortify Improving Speed to Market via Automation | Government and Economy | Tracking and Workflow | Business process automation to reduce time and cost for customer ordering to provisioning cycle, including back-end service fulfilment automation | Delivery |  | PRINCE2 | 2018-07-16 | 2018-10-31 | 2018-09-19 | 2018-09-19 | 0 |  | 2018-09-20 | 2018-09-20 | 2019-06-30 | 2019-12-30 | 1492000 | 3759625 |  |  | Green | Green | Green | Design and build of automation capabilities has commenced with internal consumption of services now available for SDDC and SDN. Existing error prone processes have been automated to improve uniformity & time to deliver. The SmartGuard provisioning automation has cutover 32,000 end user client at end Q4. Reduction of manual processing significantly reduced & continues until December 2019. A project variation increasing funding was also approved during the last quarter increasing the budget to almost $3.76M
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2651 | Millenium Replacement | Government and Economy | Financial Management | To move the Millennium General Ledger (GL) used by WSV IBU & Agents off the DXC managed mainframe to Oracle Financials (on-premise). | Closed - Completed | 2019-06-07 | PMBoK | 2018-06-15 | 2018-09-30 |  | 2018-10-02 | 205604 |  | 2018-10-02 | 2018-10-02 | 2019-05-31 | 2019-06-07 | 963500 |  |  |  | Green | Green | Green | Project tracked to plan and is now closed.
Q4 18-19 | Environment Protection Authority | EPA | 2652 | EPA's Digital Transformation Program | Environment and Water | Systems Management | EPA’s Digital Transformation program seeks to realise the EPA ICT Strategy and enable the organisation to deliver on the goals of EPA’s ‘Our Environment, Our Health’ Organisational Strategy. | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-10-01 | 2019-04-30 | 2019-05-31 |  | 3300000 | 19687000 | [11 empty] | The initiation for the Digital Transformation Program is now complete. All business case inputs were submitted to the board as part of the Integrated Business Case. The EPA Board has provided positive indication for final approval of the Integrated Business Case. All milestones for Phase 2 have been completed and signed off. This includes closing out relevant foundation builds, including Engineering and Service Management. The accelerated work for Phase 3 has completed the first stages as part of Phase 2, including the CRM Accelerated Build, Waste Tracker Prototype and Website MVP planning. The team is ready to start delivery through the integrated delivery team starting 1st July. Key Achievements: Go-Live for the foundation build for Service Management portal for IT Service Management and a new ServiceNow instance for managing ITSM processes; Successful showcases for the accelerated work, including demonstration of out of the box capabilities for Dynamics and the Waste Tracker prototype; Approval (in principle) of the Insight Strategy, requiring further clarification before full endorsement. Work to be carried over: IDAM Capability - foundation build for the identity and access management to be moved to phase 3, following further detailed assessments of products; HCM Go-Live will be pushed to July.
Q4 18-19 | Department of Health and Human Services | DHHS | 2653 | Website Replatforming | Health | Communication | Redesigning and replatforming key strategic departmental websites to deliver improved service delivery, enhanced functionality, reduced costs and meet business and customer needs aligning with the department's digital strategy. | Delivery |  | Agile | 2018-09-29 | 2018-12-31 | 2019-02-15 | 2019-02-25 | 1 | 76800 | 2019-02-25 | 2019-02-25 |  | 2019-10-30 | 0 | 1498500 |  |  |  | Green | Green | Project is progressing to schedule. Planned delivery end date and costs are for stage 1 work only.
Q4 18-19 | Department of Health and Human Services | DHHS | 2654 | ICT Fit out of Orange Door Sites | Community Services | Communication | An implementation project to set up hubs sites in Barwon, Bayside Peninsula, Inner Gippsland, Mallee and North-East Melbourne areas as a result of the Family Violence Royal Commission. | Delivery |  | PRINCE2 | 2017-05-01 | 2017-05-01 |  | 2017-05-01 | 0 |  | 2017-11-01 | 2017-11-01 | 2018-12-31 | 2019-09-30 | 1565074 |  |  | Green | Green | Green | Green | Project is progressing to revised scheduled.
Q4 18-19 | Department of Health and Human Services | DHHS | 2655 | Infrastructure Resilience | Community Services | Systems Management | A project of work to uplift the current IT Resilience capability to proactively manage the departments management of, and response to, unplanned IT outages. | Delivery |  | PMBoK | 2018-03-11 | 2018-07-17 |  | 2018-07-17 | 123082 |  | 2018-07-18 | 2018-07-18 | 2019-06-30 | 2020-06-30 | 1837861 | 3485000 |  | Green | Green | Amber | Amber | Project is reporting amber due to vendor deliverable delays. Increased costs due to additional agreed scope. Expect project to return to green in next reporting period.
Q4 18-19 | Victorian Building Authority | VBA | 2656 | Building Activity Management System (BAMS) | Government and Economy | Customer Relationship Management | The BAMS project focuses on the replacement of the legacy Permit Levy System due to legislative reforms taking effect on 1 July 2019. The VBA will become the entity responsible for collection of levy from applicants and issuing of building permits | Closed - Completed | 2019-06-30 | Hybrid - Agile and PRINCE2 | 2018-07-01 | 2018-09-14 | 2018-07-24 | 2018-07-24 | 82800 |  | 2018-09-17 |  | 2019-06-30 |  | 2000000 | 3500000 |  | Green | Green | Green | Green | All development sprints have been completed. User Acceptance Testing (including external stakeholders and users of the system), End to End Testing and Final Acceptance testing have been completed, ready to go live on 1 July 2019
Q4 18-19 | Department of Premier and Cabinet | DPC | 2657 | Labour Hire Licensing - Online | Employment and Workplace | Data Management,Development and Integration ,Human Capital / Workforce Management ,Management of Process ,Organisational Management | This project will develop a web-based service for the Labour Hire Licensing Authority. | Closed - Completed | 2019-06-30 | Hybrid - Agile and PRINCE2 | 2018-03-19 | 2018-10-12 | 2018-09-05 | 2018-09-06 | 150000 |  | 2018-11-08 |  | 2019-06-30 |  | 2900000 | 2750000 |  |  | Green | Green | Green | The project is tracking to proposed timelines and delivery dates.
Q4 18-19 | Melbourne Polytechnic | MelbPoly | 2658 | Network Modernisation (Tertiary Wide Area Network) | Education | Communication | Installation of new WAN to modernise connectivity across Melbourne Polytechnic tertiary campuses | Closed - Completed | 2019-06-16 | PMBoK | 2018-09-03 | 2018-10-18 |  | 2018-10-18 | 0 |  | 2018-11-30 | 2018-11-30 | 2019-05-17 | 2019-06-16 | 2997752 | 2997825 |  |  | Green | Amber | Green | All works completed on time. No outstanding risks or issues.
Q4 18-19 | Service Victoria | SerVic | 2661 | Service Victoria Horizon Two - white labelling payment and membership onboarding | Government and Economy | Customer Initiated Assistance | Following Horizon One, the next phase sees the extension & take-up of platform capabilities & expanding the breadth of online services.New capabilities include white label payments, membership onboarding & transactions.Project is on time & on budget. | Closed - Completed | 2019-06-30 | Agile | 2018-07-01 | 2019-04-12 | 2018-08-10 | 2018-08-10 | 0 |  | 2018-10-22 |  | 2019-06-30 |  | 5571610 |  |  |  |  | Green | Green | The project has been delivered on time and on budget.
Q4 18-19 | Melbourne Water | MELB Water | 2662 | Digital Asset Management | Environment and Water | Assets/Materials Management,Records Management | Implement a single source of truth for management of rich media information about Melbourne Water assets | Postponed | 2019-05-13 | Agile | 2018-06-29 | 2019-04-30 | 2019-07-05 |  | 0 | [12 empty] | Evaluation of a number of respondents to an RFS (request for service) is underway. None of the responses fall within Melbourne Water's budget allocation, which may necessitate scope refinement and/or business case resubmission.
Q4 18-19 | Victorian Health Promotion Foundation | VicHealth | 2663 | Core Systems Replacement Project | Health | Customer Relationship Management | Replacement of VicHealth's ageing contract/grant and project management applications with an integrated solution supporting SRM, Program & Project Mgt, Grants & Contract Mgt, Documents & Records Mgt, Mgt Reporting & Analysis and Finance Applications | Delivery |  | PRINCE2 | 2018-03-01 | 2018-05-02 |  | 2018-05-02 | 150000 |  | 2018-05-23 |  | 2020-06-30 |  | 2100000 |  |  | Green | Green | Green | Green | Project continues to track on target and as per schedule.
Q4 18-19 | Melbourne Water | MELB Water | 2664 | Server Remediation Program | Environment and Water | Data Management | Program of works to remediate server environments at Melbourne Water. Goals are to optimise server utilisation, reduce server numbers and reduce server numbers managed on premises. | Initiated |  | PRINCE2 | 2018-08-21 | 2018-12-13 |  |  | 0 | [12 empty] | Successful completion of 2 key Statements of Work (SOW) related to SQL 2008 environments and decommissioning of server. New Statements of Work (SOW) are currently being finalised for further SQL 2008 remediation work and Window 2008 operating system upgrades.
Q4 18-19 | Melbourne Water | MELB Water | 2665 | Online Customer Portal | Environment and Water | Communication,Content Management,Customer Initiated Assistance | Melbourne Water has been undergoing a Customer Transformation over the past three years to transform approach to a Customer Focus model. Online Customer Portal was identified as a key system component to enable Customers to self-serve and offer a qui | Closed - Completed | 2019-06-30 | Agile | 2018-09-26 | 2018-10-08 |  | 2019-02-13 | 0 |  | 2019-02-13 | 2019-02-13 |  | 2019-06-30 | 0 | 1507639 |  |  |  | Amber | Green | Project closed after successfully delivering the infrastructure required for the customer portal. A new project business case currently being developed which will provide the static content for the customer and community portal.
Q4 18-19 | Ambulance Victoria | AVS | 2666 | Enterprise Resource Planning Project | Health | Human Capital / Workforce Management | Key resource planning and management systems are no longer meeting the changing needs of the organisation. The aim of the project is to introduce a future strategic enterprise resource management solution. | Initiated |  | PRINCE2 | 2018-02-01 | 2019-06-30 |  |  | 320000 | 343634 | [11 empty] | Business Case for the delivery phase has been approved. Vendor for the Telemetry solution has been selected and contract execution is imminent. Vendor selection for the Rostering and Claims management is underway.
Q4 18-19 | Ambulance Victoria | AVS | 2667 | Predictive Analytics Capability | Health | Business Intelligence | Establish organisational real time decision support along with predictive analytics capability. The introduction of modern data analysis will ensure critical information can be provided to paramedics when they need it. | Initiated |  | PRINCE2 | 2018-04-10 | 2019-05-29 | 2019-07-22 |  | 400000 | [12 empty] | The procurement phase of the project is complete. Implementation partner and a panel of providers has been appointed to commence the delivery of the project. Planning for the delivery phase will commence late July 2019 to be completed over next 2 years.
Q4 18-19 | Ambulance Victoria | AVS | 2668 | ICT Disaster Recovery | Health | Systems Management | Uplift the capability of Ambulance Victoria's critical ICT systems and adapt the ICT business operating model to meet the needs of our ambulance service improving our ability to maintain service delivery and patient care during technology failures. | Closed - Completed | 2019-06-30 | PRINCE2 | 2018-03-01 | 2018-07-27 |  | 2018-07-30 | 0 |  | 2018-07-31 |  | 2019-06-30 |  | 2267954 |  |  | Green | Green | Green | Green | The project has been successfully delivered to schedule.
Q4 18-19 | Department of Education and Training | DET | 2669 | Connected Learners Program | Education | Communication | Renewing Wi-Fi and virtual conferencing in all schools, and improving regional internet bandwidth connectivity. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-07-01 | 2017-07-31 |  | 2017-07-31 | 500000 |  | 2017-08-01 | 2018-08-01 | 2021-05-31 | 2021-05-31 | 83039000 |  |  | Green | Green | Green | Green | Equipment installation for virtual conferencing has been completed for the schools and is in progress for regional offices & IT training centres. Wi-Fi installations and site upgrades are also on track and the overall status is green. The project will be transitioning to business as usual in the next reporting period with all major components delivered. The remaining business as usual activity will incorporate the continued adoption program for the use of the technology in the classroom.
Q4 18-19 | Ambulance Victoria | AVS | 2670 | Cybersecurity Improvement Program | Health | Security Management | Introduction of changes to work practices improvements to existing security tools and development of a sustainable cybersecurity capability to ensure secure data and reduce the impact of cybersecurity threats on our ambulance service. | Closed - Completed | 2019-06-30 | PRINCE2 | 2018-03-01 | 2018-07-27 |  | 2018-07-30 | 0 |  | 2018-07-31 |  | 2019-06-30 |  | 2942316 |  |  | Green | Green | Green | Green | The project has been successfully delivered to schedule.
Q4 18-19 | Ambulance Victoria | AVS | 2678 | Analytics Uplift Project | Health | Business Intelligence | Investment in data analytics to drive performance improvement, including the introduction of enhanced dashboard reports, development of an app and an uplifted organisational maturity and capability for reporting and analytics functions. | Closed - Completed | 2019-06-30 | Hybrid - Agile and PRINCE2 | 2016-06-27 | 2017-03-02 |  | 2017-03-03 | 0 |  | 2017-04-03 |  | 2019-06-30 |  | 4604879 |  |  | Green | Green | Green | Green | The project has been successfully delivered to schedule.
Q4 18-19 | Ambulance Victoria | AVS | 2679 | ICT Infrastructure Transformation Project | Health | Systems Management | Increase the availability and performance of technology infrastructure and services to improve reliability of our service and support better patient care. | Closed - Completed | 2019-06-30 | PRINCE2 | 2018-03-01 | 2018-07-27 |  | 2018-07-30 | 0 |  | 2018-07-31 |  | 2019-06-30 |  | 2729030 |  |  | Green | Green | Green | Green | The project has been successfully delivered to schedule.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2680 | WorkSafe 2030 Horizon One Technology Platforms | Government and Economy | Systems Management | The first phase of WorkSafe Transformation Program is the delivery of a new system to enable inspectors access to deeper information to operate more efficiently, online system for customers to obtain licenses and businesses to calculate premiums. | Delivery |  | PMBoK | 2018-07-01 | 2018-09-30 |  | 2018-10-01 | 9410000 | 9410000 | 2018-10-01 | 2018-10-01 | 2019-06-30 | 2019-10-31 | 68488125 | 85272011 |  |  | Red | Red | Amber | Overall status is amber driven by the delayed schedule to implement the technology platforms.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2682 | Premium Calculation System Upgrade | Government and Economy | Systems Management | Enhancements to ACCtion replica and the Premium Calculation System (PCS). | Delivery |  | PMBoK | 2018-07-01 | 2018-11-30 |  | 2018-12-01 | 0 | 475813 | 2018-12-01 |  | 2019-09-30 |  | 1350000 | 1993000 |  |  | Green | Green | Green | Project is tracking to plan.
Q4 18-19 | VicRoads | VicRoads | 2686 | Health, Safety and Environment Management System | Transport and Vehicles | Human Capital / Workforce Management | The Safety Management System Project will incorporate Safety and Risk modules such as; Incident and Hazard Management Audit Inspections & Checklists Risk Management Workers Compensation & Injury Management and the Safety Management Toolkit. | Postponed | 2019-06-14 | PRINCE2 | 2018-04-30 | 2019-04-08 | 2019-08-05 |  | 0 | [12 empty] | Project is on hold. Awaiting final clarifications of outstanding items.
Q4 18-19 | Victoria Police | VicPol | 2687 | Mobile Automatic Number Plate Recognition | Law and Justice | Development and Integration | The Mobile Automatic Number Plate Recognition project will facilitate the roll out of an integrated automatic number plate recognition and in car video system to 220 vehicles. | Delivery |  | PRINCE2 | 2017-06-30 | 2017-10-02 |  | 2017-10-02 | 0 |  | 2017-10-03 |  | 2021-07-01 |  | 36617000 |  |  |  | Amber | Green | Green | Phase 4 Implementation is currently in progress and on-track
Q4 18-19 | Department of Education and Training | DET | 2688 | eduHub v2 | Education | Data Management | DET has committed to a national standard for delivery of data to third party vendors e.g. COMPASS. This Learning Services Architecture (LSA) will be delivered by a modern programming interface to these third parties using a standard framework. | Initiated |  | PMBoK | 2016-02-02 | 2019-09-30 |  |  | 0 | [12 empty] | Proof of Concept completed successfully and early requirements gathering and initial development phases are in progress. Test planning is in progress. Activities are on schedule towards the implementation phase.
Q4 18-19 | Department of Education and Training | DET | 2689 | Next Generation Schools Administration - Program Establishment Phase | Education | Development and Integration ,Management of Process ,Organisational Management | The Next Generation Schools' Administration project is working to define the future state policy process and systems for Victorian government schools' administration. | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-08-01 | 2019-06-28 | 2020-06-30 |  | 0 | [12 empty] | The project is in the initiated stage and its status is green. Business Requirements continue to be documented and developed. High level Design and the draft procurement strategy is also being finalised at this stage.
Q4 18-19 | Department of Education and Training | DET | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management | Procurement and implementation of a replacement Asset Information Management System. | Initiated |  | PRINCE2 | 2017-08-01 | 2019-07-31 |  |  | 0 | [12 empty] | AIMS Invitation to Supply responses were received from suppliers in November 2018 and subsequently evaluated. The Evaluation process has four stages and will be completed by end July 2019 resulting in a preferred supplier being recommended and subsequently approved. Implementation is due to commence in the 3rd quarter of the 2019 calendar year.
Q4 18-19 | Department of Education and Training | DET | 2691 | InfoSafe Program - Phase 1 | Education | Data Management,Development and Integration ,Security Management | DET has established an Information Security and Privacy Program (the InfoSafe Program). It includes the Implementation of: •Privacy Action Plan •Protective Data Security Plans (PDSPs) under the VPDSF •gaps identified by PricewaterhouseCoopers-PwC | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-07-02 | 2020-08-28 | 2019-06-28 | 2019-06-28 | 2050000 | [12 empty] | The program roadmap is being updated to incorporate all the amendments required in line with complexity and range of stakeholder engagement to support the development of standards. Activities in progress are: •continued development of IS standards •process corporate third party supplied assessment •development of program roadmap and schedule for 19/20 •progress SIEM in production; Configure Alyne for supplier compliance and conduct compliance on IAR top 40 •plan executive level PIR to document key findings for future campaigns •continued development of ISMS to document operational functions.
Q4 18-19 | Victoria Police | VicPol | 2692 | Alcohol and Drug Impaired Driver Information System (ADIDIS) | Law and Justice | Data Management | ADIDIS is the enhancement/replacement of the Alcohol and Drug Impaired Driver Information System. | Delivery |  | PRINCE2 | 2016-11-28 | 2017-12-22 |  | 2017-12-22 | 0 |  | 2018-05-15 |  | 2019-12-04 |  | 2213000 |  |  |  | Green | Green | Green | This project is tracking to deliver on time and budget.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2694 | Prison Industries Enhancement Project | Law and Justice | Management of Process | The primary purpose of the PIE project is to deliver value for money prison services by exploring opportunities for Prison Industries (PI) cost recovery, as well as through promoting PI as a preferred supplier. | Delivery |  | Project Management Excellence | 2016-01-02 | 2017-07-27 |  | 2017-07-27 | 0 |  | 2017-07-28 | 2017-07-28 | 2019-05-30 | 2019-07-31 | 5745200 | 4224332 |  |  | Green | Green | Green | The project has a total of 6 streams. 2 project streams have been delivered. Delivery of technology solutions is underway for all 4 remaining project streams. Delivery end date has been revised by 2 months (July 2019) due to delays in procurement and network infrastructure readiness. Deliverables have been revised to align with Prison Industries priorities for current and future work, which are on track. These include agriculture pilot solution, online sales and warehouse solutions ready for business testing & rollout, and a Point of Sale proof-of-concept. A new project (Prison Industries Enhancement Phase 2) is commencing in September 2019 to continue delivery of Prison Industries key initiatives. This will continue business verification and roll out of the solutions out across industries, and will continue to build on the new technology foundation by expanding solutions to deliver new capabilities.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2695 | Youth Justice Assessment System | Law and Justice | Business Intelligence | Design and build the Youth Justice Assessment system (YJAS) enabling electronic input, maintenance and storage of Risk Assessment data, moving away from the paper based assessments. | Delivery |  | Project Management Excellence | 2018-02-01 | 2018-03-22 |  | 2018-03-22 | 0 |  | 2018-03-26 | 2018-03-26 | 2019-02-28 | 2019-07-30 | 1704500 | 1363600 |  |  | Amber | Green | Green | Phase 1 (Version 1.0) of the Youth Justice Assessment system went live on 4th Feb 2019 on schedule. Phase 1 deliverables included: Version 1.0 (All Assessment Forms, Screens, Workflow, and Assessment Reports) went live in Production on schedule on 4 February 2019. Version 1.1 (Review) was released into Production on 18 March 2019. Version 1.2 (Client Matching) was released into Production on 12 April 2019. Version 1.3 (Criminal History) was released into Production on 14 June 2019. Version 1.4 (Management Reporting & Audit) was released into production 5 July 2019. Version 1.5 (Compliance Reporting) is scheduled for Production release 30 July 2019.
Q4 18-19 | CenITex | CenITex | 2696 | Privileged Access Management | Government and Economy | Security Management | Implement a Privileged Access and Endpoint Management solution to protect the confidentiality, integrity and availability of customer information | Initiated |  | PRINCE2 | 2018-10-01 | 2018-10-23 |  |  | 0 | [12 empty] | Preferred supplier selected, project will not kick off until the last week of July 2019. Following kick-off project will be baselined and delivery will commence Q1 FY19/20.
Q4 18-19 | CenITex | CenITex | 2697 | Priority Site Network Uplift | Law and Justice | Assets/Materials Management | Deliver a cost-efficient and future state network architecture solution designed to improve end user experience and cater for planned additional network services | Delivery |  | PRINCE2 | 2018-10-01 | 2018-12-18 |  | 2018-12-19 | 0 |  | 2019-03-01 |  | 2019-11-30 |  | 1650000 |  |  |  |  | Green | Green | All of CBD and metro sites have been successfully refreshed; regional sites underway, currently at 65% with all sites scheduled for implementation.
Q4 18-19 | CenITex | CenITex | 2698 | Software Defined Network - Data Centre Stage 2 | Government and Economy | Assets/Materials Management | Stage 2 - Complete work implementing the network architecture that provides agility, visibility and automation of software defined networking - additional scope/migrations | Delivery |  | PRINCE2 | 2018-10-01 | 2018-11-27 |  | 2018-11-28 | 0 |  | 2018-12-12 |  | 2020-06-30 |  | 2900000 |  |  |  | Green | Green | Green | Stage 2: Migration of all equipment to the new environment will Occur July thru November subject to customer approvals. On schedule to complete by end of Dec 2019 Stage 1 was ID 2418. This will allow decommissioning of the problematic & failing infrastructure with a more resilient & robust platform.
Q4 18-19 | CenITex | CenITex | 2699 | Software Defined DC Stage 2 | Government and Economy | Assets/Materials Management | Continue the transformation of Cenitex's hosting services into a modern Software defined data centre including extending capabilities in the Cloud using AWS technologies and disaster recovery - additional scope/migrations | Delivery |  | PRINCE2 | 2018-10-01 | 2018-11-27 |  | 2018-11-28 | 0 |  | 2018-12-12 |  | 2020-06-30 |  | 3637481 |  |  |  | Green | Green | Green | Stage 2 project: Additional servers & rationalisation of infrastructure that were not part of stage 1 scope - ID2545: Migration of services has commenced as planned with another 100 customer migration schedule for July. This will continue through until Dec 2019, subject to customer endorsement of migration schedule with a total of another 900 services. Hosting service operational and platform being consumed by new services (Digital Desktop/ Horizon). Build of AWS disaster recovery service underway as legal consumption of service established for WoVG.
Q4 18-19 | CenITex | CenITex | 2700 | Virtual Desktop Transformation | Government and Economy | Assets/Materials Management | Refresh and upgrade of current virtual desktop infrastructure to improve customer service performance, efficiency and cost-effectiveness of the ICT service | Delivery |  | PRINCE2 | 2018-10-01 | 2018-10-23 |  | 2018-10-24 | 0 |  | 2018-10-30 | 2018-11-30 | 2019-06-30 | 2019-11-30 | 1766000 |  |  |  | Green | Green | Green | Design completed & build almost completed with service verification on the new SDDC platform underway. SDDC platform was a dependency before this service could be established. Cenitex & customer cutovers to follow in Q1/Q2 FY 19/20.
Q4 18-19 | Victoria Police | VicPol | 2702 | Data Centre Relocation | Law and Justice | Data Management | Data Centre Relocation to a colocation facility including White Space fitout (IT equipment placement) , servers, storage and network refresh. | Delivery |  | PRINCE2 | 2018-03-27 | 2018-06-23 |  | 2018-07-26 | 0 |  | 2018-07-26 |  | 2019-12-30 |  | 15339000 |  |  |  | Green | Green | Green | The project is progressing on track with no issues to report. All infrastructure and communications links have been installed and main frame relocated to the new data-centre. Migration of applications to the new environment is in progress. The project is 74% complete.
Q4 18-19 | Game Management Authority | GMA | 2704 | Replacement of the Game Licensing System | Business and Industry | Customer Relationship Management | Replacement of the Game Licensing System (GLS) project has arisen because of the need to remove the high corporate risk associated with the age of the system and the lack of system documentation and technical support. | Initiated |  | PRINCE2 | 2018-09-07 | 2019-03-31 | 2019-06-27 |  | 30000 | [12 empty] | The GLS project business case (contract) was approved by the GMA Board on 27 June 2019 and project will start delivering in Q1, 2019-2020.
Q4 18-19 | VicRoads | VicRoads | 2706 | Role Based Access Project | Transport and Vehicles | Security Management | Establish role based access for various systems | Delivery |  | PRINCE2 | 2018-07-15 | 2018-11-15 |  | 2018-11-15 | 0 |  | 2018-11-18 | 2018-11-18 | 2019-12-30 | 2019-12-27 | 1300000 |  |  |  | Green | Green | Green | Overall status remains Green. Focus remains on documenting VicRoads Applications and their associated Application Privileges. Further work is on hold while the impacts of organisational changes (DoT) are understood.
Q4 18-19 | VicRoads | VicRoads | 2707 | Driver Licencing System Enhancements | Transport and Vehicles | Systems Management | Purpose of the project is to enhance the current Driver Licencing System and improve the stability of the system. | Delivery |  | PRINCE2 | 2018-07-15 | 2018-11-15 |  | 2018-11-15 | 0 |  | 2018-11-18 | 2018-11-18 | 2019-06-30 | 2020-03-27 | 1200000 |  |  |  | Green | Green | Amber | Overall project is tracking Amber due to schedule delays as a result of competing priority around other legislative projects. Project completion date has been extended to March 2020 due to a need to complete other legislative initiatives before this project can be implemented.
Q4 18-19 | Court Services Victoria | CSV | 2708 | Resolving Disputes Digitally at VCAT | Law and Justice | Analyses and Statistics ,Customer Relationship Management,Records Management ,Routing and Scheduling,Tracking and Workflow | A digitally enabled service model to increase access to justice and facilitate an ADR triage model for early and timely resolution of disputes. It will enable digital and online engagement, and provide in-person services if required. | Closed - Terminated | 2019-06-30 | Agile | 2018-02-01 | 2019-05-01 |  |  | 0 | [12 empty] | Funding for this project has not yet been approved, and is expected to be subject to Government consideration in the 2019-20 Budget.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2709 | Data Warehouse Oracle Upgrade | Government and Economy | Data Management | The project is upgrading the current legacy Oracle databases and relocating them to the Exadata platform for the data warehouses of Worksafe and the Agent information systems. | Delivery |  | PMBoK | 2017-07-01 | 2017-12-31 |  | 2018-01-01 | 197218 |  | 2018-01-01 | 2018-01-01 | 2019-01-31 | 2019-07-31 | 1173547 |  |  |  | Amber | Green | Green | Project is tracking to schedule and budget.
Q4 18-19 | Victorian Curriculum and Assessment Authority | VCAA | 2711 | Digital Assessment Library (DAL) Platform | Education | Content Management,Forms Management,Knowledge Discovery ,Reporting ,Tracking and Workflow | The DAL platform will provide an assessment platform for assessment tools to aid in identification and diagnosis of student learning opportunities to inform strategies to improve learning outcomes. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-06-01 | 2018-07-01 |  | 2018-07-01 | 0 |  | 2018-10-30 |  | 2020-02-28 |  | 1250000 | 1365804 |  |  | Green | Green | Green | The DAL was successfully trialled in five schools in late June. Feedback was positive with students able to complete the tests and valuable feedback was received to guide further development of the platform and test content. The assembly and migration of existing assessment content is complete and this will comprises the initial release of the platform. Delays in delivery of functionality from the platform vendor have been an ongoing issue. Development will continue beyond the June trial launch with the scheduling of the development of further functionality currently in planning. The vendor for the Privacy Impact Assessment (PIA) has delivered an initial draft for discussion which highlights the need for a number of measures to be taken to ensure student staff and school privacy. The drafted recommendations will be actioned by a new project privacy working group.
Q4 18-19 | Transport Accident Commission | TAC | 2712 | IAAS Transition (TAC) | Transport and Vehicles | Systems Management | Transition of IT infrastructure services to an external provider | Closed - Completed | 2019-06-30 | PRINCE2 | 2017-09-01 | 2017-10-18 |  | 2017-10-18 | 0 |  | 2017-10-18 | 2017-10-18 | 2018-06-30 | 2019-06-30 | 1346480 | 1375335 |  |  | Amber | Green | Green | Project is complete and came in within budget.
Q4 18-19 | South East Water | SE Water | 2713 | HRIS Solution | Environment and Water | Human Resources | Implement the SuccessFactors product as the HRIS solution for all employees. | Delivery |  | Agile | 2018-11-07 | 2019-01-21 |  | 2019-01-21 | 0 | 283726 | 2019-01-21 | 2019-01-21 |  | 2020-03-31 | 0 | 2730131 |  |  |  | Green | Green | The performance goals and learning modules are preparing for go live in July. This will allow 19/20 performance plans to be created in the new HRIS system. The employee central component build is being finalised and will progress in to test in August.
Q4 18-19 | Department of Health and Human Services | DHHS | 2715 | Family Safety Victoria online system of Tools for Risk Assessment and Management (TRAM) | Community Services | Forms Management | The online system of Tools for Risk Assessment and Management (TRAM) will allow workers who come into contact with victims of family violence to undertake and store family violence risk assessments in an online environment. | Closed - Completed | 2019-06-28 | Agile | 2017-09-04 | 2017-12-22 |  | 2017-12-22 | 0 |  | 2018-04-02 | 2018-04-02 | 2019-03-29 | 2019-06-28 | 1749073 | 1870000 |  |  | Green | Green | Green | The project has successfully delivered its intended result and closeout activities are underway.
Q4 18-19 | Melbourne Water | MELB Water | 2717 | Identity and Access Management | Environment and Water | Security Management | Implement an Identity and Access Management solution for the Enterprise to enable role-based permissions | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-07-18 | 2019-04-01 | 2019-04-30 |  | 0 | [12 empty] | Business case is almost complete and will soon be provided to senior management for endorsement.
Q4 18-19 | Department of Health and Human Services | DHHS | 2718 | Clinical Grade Network Project | Health | Data Management,Security Management | Facilitate simple secure interconnection of networks between health services and standardise the WAN across the sector providing a repeatable architecture. To provide the foundation to enable improvements in cybersecurity and monitoring. | Initiated |  | PRINCE2 | 2019-01-01 | 2019-07-26 |  |  | 0 | 892000 | [11 empty] | Project is on track and on budget. The project is at risk of delay due to resource recruitment constraints.
Q4 18-19 | Southern Metropolitan Cemeteries Trust | SMCT | 2727 | Vision2020 | Health | Data Management | Provision of 6 IT governance models & frameworks to enable achievement of business strategies and to derive the optimum value from current and future IT assets in an integrated and governed manner. Deploy data warehouse & master data repository. | Delivery |  | PMBoK | 2019-02-25 | 2019-02-27 |  | 2019-02-27 | 0 |  | 2019-02-28 |  | 2020-06-30 |  | 1752000 |  |  |  |  | Green | Green | •Total scope re. human resource business process suite (Empower 1B/2) to be assessed and costed. Impact to overall program to be assessed. •Hypercare for Payroll project in-progress. BAU support model defined and is being tested. •Progress achieved on all defined Vision 2020 work streams.
Q4 18-19 | Yarra Valley Water | YV Water | 2728 | Asset System Upgrade | Environment and Water | Assets/Materials Management | Upgrade Maximo to supported version and platform stabilisation. | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-08-17 | 2019-12-10 | 2018-12-10 | 2019-12-10 | 120000 | 120000 | [11 empty] | Delivery in Progress
Q4 18-19 | Metropolitan Fire and Emergency Services Board | MFESB | 2729 | SAP HANA Enterprise Cloud | Emergencies and Safety | Systems Management | Upgrade and migrate the existing SAP environment to the HANA Enterprise Cloud (HEC) to modernise the SAP environment and implement Single Touch Payroll functionality ensuring reporting to the ATO has commenced by the required date. | Delivery |  | MFB Project Management Excellence (PME) | 2019-04-01 | 2019-04-30 |  | 2019-04-30 | 0 |  | 2019-05-15 |  | 2019-12-31 |  | 6358725 | [5 empty] | Amber | The project is a week behind schedule. This is not impacting critical path and remediation is progress to bring this back on schedule. The project is tracking to budget. It is currently in the final stage of Cycle 1 Sandbox Migration (including testing). All identified project risks have mitigation processes in place.
Q4 18-19 | Department of Environment, Land, Water and Planning | DELWP | 2730 | VGV Going Digital Project | Property and Planning | Management of Process | Valuer-General Victoria Valuation Portal project will transfer paper-based valuation requests and records into a digital system. | Delivery |  | Hybrid - Agile and PRINCE2 | 2017-06-30 | 2017-09-30 |  | 2017-11-30 | 88000 |  | 2018-11-30 |  | 2019-12-30 |  | 1500000 |  |  |  |  | Green | Amber | The business case is being revisited due to the proposed change in solution technology used.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2752 | Windows 10 Office 365 | Law and Justice | Systems Management | Modernisation of the DJCS End User Computing environment deploying Windows 10 Office 365 (including Outlook) to approximately 11700 staff. | Delivery |  | Project Management Excellence | 2018-11-01 | 2019-04-12 |  | 2019-04-12 | 0 |  | 2019-04-15 |  | 2020-09-30 |  | 8000000 | 9618661 |  |  |  | Green | Green | The project is slightly ahead of the approved deployment schedule. As at 30 June 2019, 3703 devices (36.6%) have been migrated to Windows 10 and 1461 (12.5%) users have been migrated to Outlook. Outlook deployments are scheduled to catch up to Win10 in December 2019. Deployments to metro/regional Justice Service Centres has commenced. DJCS is adopting the Cenitex GSP Service Catalogue effective 1 July 2019.
Q4 18-19 | CenITex | CenITex | 2753 | VicGov Digital Desktop through Unified Endpoint Management | Government and Economy | Systems Management | Deliver a platform that will allow for the management of any device anywhere - providing an end user experience that is simple seamless and secure. | Delivery |  | PRINCE2 | 2018-04-01 | 2018-05-29 |  | 2018-05-30 | 0 |  | 2018-06-19 |  | 2019-09-26 |  | 1570230 | 1530229 |  |  |  | Green | Green | The change of approach as reported in Q3 was endorsed by the ELT via a business case variation with rollout to Cenitex staff to validate the service and for Cenitex to perform the design, build and initial support for this project. Pilot Cenitex users now on this new service. Support will transition to a 3rd party vendor which is currently in market procurement. A component of the project has descoped resulting in a reduction to budget of $40,000.
Q4 18-19 | Alfred Health | ALFRED | 2754 | Implement eTQC Phase Two program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Collaboration ,Communication,Data Management,Knowledge Discovery ,Management of Process ,Reporting ,Tracking and Workflow | Development and implementation of Phase Two of the electronic-Timely Quality Care (eTQC) project that optimises products introduced in phase 1 and explands EMR scope to improve clinical real-time data capture management and patient care services | Initiated |  | PRINCE2 | 2019-01-01 | 2019-06-30 |  | 2019-07-01 | 0 | 5051100 | [11 empty] | Initiation is COMPLETE with delivery starting in Q1 2019/20.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2755 | EUC Strategic Upgrade | Government and Economy | Business Intelligence | Objectives of the project include; 1. Technical install of Microsoft Office 2019 and basic training materials for all users. 2. Integrate IPads and IPhones with Office 365. 3. Microsoft Active Directory. 4. Microsoft OneDrive and SharePoint. | Delivery |  | PMBoK | 2019-03-01 | 2019-03-01 |  | 2019-03-01 | 0 |  | 2019-03-01 |  | 2020-06-30 |  | 2110950 | 4413500 |  |  |  | Green | Green | Project is tracking to plan
Q4 18-19 | State Revenue Office | SRO | 2756 | myGov Integration & Digital Assessments | Government and Economy | Development and Integration | This project will enable SRO customers to link their myGov account to SRO services and enable Land Tax assessments to be sent digitally to a myGov Inbox. | Delivery |  | PRINCE2 | 2016-06-01 | 2017-01-31 |  | 2017-07-24 | 90000 | 74013 | 2017-07-24 |  | 2019-08-23 |  | 1279000 | 1182955 |  |  |  | Green | Red | The final stage of the project was successfully implemented on 27 May 2019. However an environmental issue emerged after go live that impacted adversely on other SRO online services and it was decided to rollback the services that were deployed in that stage whilst the cause was investigated and remediation action determined. The services will be redeployed in Q1 and Q2 of 2019-20, with any functional improvements considered for the 2020 Land Tax issue cycle. Additional funding will be required to complete the project.
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2765 | Pet Exchange Register (PER) | Government and Economy | Data Management,Development and Integration ,Management of Process ,Reporting | To deliver a Pet Exchange Register that meets MVP requirements by 3 June 2019, is operational & compliant by 1 July and fully functional by 30 August 2019. The Domestic Animals Amendment (Puppy Farms and Pet Shops) Act. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-06-01 | 2018-07-02 |  | 2019-01-03 | 0 |  | 2019-01-04 | 2019-02-18 | 2019-08-30 | 2019-08-30 | 1300000 |  |  |  |  | Green | Green | The Pet Exchange Register project is currently on track to deliver all key milestones. Both 'Build' and 'Implement' activities are being undertaken for the final release.
Q4 18-19 | Transport Accident Commission | TAC | 2766 | Wireless Network Replacement | Transport and Vehicles | Customer Initiated Assistance | Wireless Network Replacement (60 Brougham St, Geelong). Review the current state of the wireless and wired networks resulting in recommendations of hardware, configuration & software. Then purchase new network hardware & software. | Delivery |  | PRINCE2 | 2018-05-24 | 2018-05-24 |  | 2018-05-24 | 0 |  | 2018-05-25 | 2018-05-25 | 2019-06-30 | 2019-08-30 | 1369000 | 1410000 |  |  |  | Green | Green | On Track. Change request prepared and approved to extend schedule and increase budget slightly for replacement switches.
Q4 18-19 | VicRoads | VicRoads | 2767 | Registration and Licence Data Quality Project | Transport and Vehicles | Data Management | Purpose of this project is to ensure customer’s driver licence data is accurate and of high-quality and secure. This activity is necessary to support accurate data share within Victoria and nationally through Commonwealth services such as the NDLFRS. | Closed - Completed | 2019-06-28 | Hybrid - Agile and PRINCE2 | 2019-01-07 | 2019-01-21 |  | 2019-01-21 | 0 |  | 2019-01-22 |  | 2019-06-28 |  | 3750000 |  |  |  |  | Amber | Green | The program has completed its FY 19 deliverables which were presented to the Project Authority on 24th June 2019. Project Completed
Q4 18-19 | South East Water | SE Water | 2768 | Digital Utility Platform Build | Environment and Water | Customer Relationship Management | Complete the pilot platform build | Closed - Completed | 2019-06-20 | Agile | 2019-01-07 | 2019-01-21 |  | 2019-01-21 | 375000 |  | 2019-01-21 | 2019-01-21 | 2019-08-30 | 2019-05-30 | 1500000 |  |  |  |  | Green | Green | The platform has been completed for the customer portal build. Phase 1 Integration across IOT and DU Platform has been tested and accepted.
Q4 18-19 | Department of Premier and Cabinet | DPC | 2769 | IGNITE | Employment and Workplace | Collaboration | Integrated physical and digital office design for accessible, inclusive and productive workspaces that enable agile ways of working, including consolidation of majority of DPC branches into five floors of 35 Collins Street | Delivery |  | PRINCE2 | 2018-09-03 | 2018-09-13 |  | 2018-09-13 | 0 |  | 2018-09-13 |  | 2019-12-31 |  | 1500000 |  |  |  |  | Green | Green | The project is on track for stage 2 Go-Live on 5th August.
Q4 18-19 | Department of Health and Human Services | DHHS | 2770 | Windows 10 Upgrade | Community Services | Systems Management | To upgrade the department's standard operating environment on desktops and laptops to Windows 10. | Initiated |  | PRINCE2 | 2019-03-01 | 2019-06-15 |  |  | 250000 | [12 empty] | Planning and mobilisation activities underway.
Q4 18-19 | Department of Health and Human Services | DHHS | 2771 | Ongoing Development of DHHS Azure Framework and Microservices. | Business and Industry | Tracking and Workflow | With increasing number of projects utilising DHHS Azure Framework, ongoing investment is needed to the framework to ensure it's being maintained properly with regular updates on technology/features including the design/development of microservices. | Delivery |  | Agile | 2018-06-10 | 2018-06-30 |  | 2018-06-30 | 300000 |  | 2018-07-01 |  | 2020-06-30 |  | 1200000 |  |  |  |  | Green | Green | Project is progressing to schedule.
Q4 18-19 | Department of Treasury and Finance | DTF | 2772 | Office365 | Government and Economy | Communication,Collaboration | Implementing Office365 for DTF staff with Outlook and Skype for Business. | Delivery |  | PRINCE2 | 2018-09-03 | 2018-11-20 |  | 2018-11-21 | 70000 |  | 2018-11-21 |  | 2019-06-30 |  | 1200000 |  |  |  |  | Green | Green | As at Q4 the project has delivered all required components on time and under budget. The project achievement has been noted by senior executive.
Q4 18-19 | Victorian Rail Track | VicTrack | 2773 | ICT infrastructure replacement | Government and Economy | Organisational Management ,Systems Management | To replace the current ageing internal ICT infrastructure and deliver a flexible, secure and easy to manage solution to meet the business needs of VicTrack for the next five years, and provide a foundation for the future. | Delivery |  | VicTrack PMF | 2018-03-05 | 2018-05-17 |  | 2018-05-17 | 0 |  | 2018-08-06 | 2018-08-06 | 2019-06-30 | 2019-10-30 | 1800000 | 2500000 |  |  |  | Red | Green | Primary Data centre relocation is underway with network connectivity established. Hardware has been stood up in all four locations and is in the final stages of functional testing. Migration planning is underway.
Q4 18-19 | Victorian Rail Track | VicTrack | 2774 | Integrated Land, Lease and License System | Government and Economy | Assets/Materials Management | Replacement of Internal land asset tenure and property management system with integrated platform. | Initiated |  | VicTrack PMF | 2019-01-14 | 2019-10-07 |  |  | 0 | [12 empty] | Business Case being developed.
Q4 18-19 | Australian Centre for the Moving Image | ACMI | 2775 | ACMI Renewal Project | Culture, Sport and Recreation | Systems Management | This renewal project will overhaul our permanent exhibition dramatically improve the visitor experience integrate cutting-edge technology and expand our education programs. | Delivery |  | Hybrid - Agile and PRINCE2 | 2019-02-01 | 2019-05-27 |  | 2019-05-27 | 0 |  | 2019-05-27 | 2019-05-27 |  | 2020-05-04 | 7660000 | [5 empty] | Green | Project on target, Tender specifications issued and demolition works nearly complete.
Q4 18-19 | Department of Health and Human Services | DHHS | 2776 | Application Hosting Strategic Recommendations | Health | Systems Management | Some applications in the department are either aged or hosted on aged technology creating risk to supportability and security patching. Project to develop and implement remediation plans for these applications providing greater stability. | Initiated |  | Hybrid - Agile and PRINCE2 | 2018-12-12 | 2019-04-16 | 2019-10-31 |  | 63600 | [12 empty] | Planning and mobilisation activities underway .
Q4 18-19 | Department of Health and Human Services | DHHS | 2777 | Divisional Telephony Program | Community Services | Communication | Complete major upgrade of the telephony & contact centre platform to address a number of end-of-life unsupported phone systems, representing business risk, & increase features & functionality of Voice & Unified Communications services across DHHS. | Delivery |  | PMBoK | 2018-04-02 | 2018-06-05 |  | 2018-06-05 | 1 | 0 | 2018-09-03 |  | 2020-10-01 |  | 2300000 | 1423000 |  |  |  | Green | Green | Project is progressing to schedule and revised agreed budget.
Q4 18-19 | Victorian Rail Track | VicTrack | 2778 | RRCN IT and Security Uplift | Transport and Vehicles | Security Management ,Systems Management | Virtualization of servers and security segmentation for Regional Rail Connectivity Network (RRCN). The project will deliver a more secure network that is Victorian Protective Data Security Standards (VPDSS) compliant. | Delivery |  | VicTrack PMF | 2017-08-01 | 2018-06-19 |  | 2018-06-19 | 0 |  | 2018-06-25 |  | 2020-06-19 |  | 2600000 |  |  |  |  | Amber | Green | Lab installation in progress, about to commence testing and production design.
Q4 18-19 | Victorian Rail Track | VicTrack | 2779 | VicTrack Service Management (VSM) - Phase 1 & 2 | Government and Economy | Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Systems Management | To implement service management system that meets VicTrack operational and customer service obligations and facilitates decommissioning of duplicate system. | Delivery |  | VicTrack PMF | 2018-03-05 | 2018-09-10 |  | 2018-09-10 | 0 |  | 2019-08-01 | 2018-10-01 | 2020-06-01 | 2020-06-01 | 3000000 |  |  |  |  | Green | Green | Tender has been completed and contract negotiation is in progress.
Q4 18-19 | Victorian Rail Track | VicTrack | 2780 | Corporate end user computing refresh | Government and Economy | Systems Management | Replacement of VicTrack's end of life corporate laptop/desktop hardware and roll-out of Windows 10 to avoid business disruptions due to hardware failures. | Delivery |  | VicTrack PMF | 2018-03-05 | 2019-03-13 |  | 2019-03-13 | 0 |  | 2019-06-03 |  | 2020-06-01 |  | 2000000 |  |  |  |  | Green | Green | Hardware has been procured, SOE being developed, application packaging and testing in progress.
Q4 18-19 | Department of Health and Human Services | DHHS | 2781 | Digital Mail and Identity Verification | Community Services | Development and Integration | The implementation of an identity verification function to ensure clients can be identified and linked to a client record in the HiiP system when logging into the mygov portal which will enable digital mail for clients. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-06-12 | 2019-02-08 |  | 2019-02-08 | 850000 |  | 2019-04-22 |  | 2019-09-30 |  | 2297000 | [5 empty] | Amber | Project is progressing but has had a scope change and is being re-baselined as a result.
Q4 18-19 | Department of Health and Human Services | DHHS | 2782 | Specialised Disability Accommodation in HiiP | Community Services | Assets/Materials Management | Project is to enhance HiiP system to provide management capability of the Specialised Disability Accommodation including reporting capability. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-08-10 | 2019-03-21 |  | 2019-03-21 | 1 | 0 | 2019-04-08 | 2019-04-08 |  | 2019-08-02 | 0 | 1321000 |  |  |  |  | Green | Project is progressing to revised schedule.
Q4 18-19 | Hume Rural Health Alliance | HRHA | 2783 | Central Hume Partnership PAS Replacement | Health | Data Management | Replacement of the current legacy PAS for seven agencies in Central Hume: Alexandra Alpine Beechworth Benalla North East Tallangatta Yarrawonga | Initiated |  | Hybrid - Agile and PRINCE2 | 2019-08-05 | 2019-08-30 |  |  | 2400000 | 2200000 | [11 empty] | Contract negotiations and Project Team recruitment are underway.
Q4 18-19 | City West Water Corporation | CW Water | 2784 | Information Records Management (1006388) | Environment and Water | Document Management ,Knowledge Management ,Records Management | The IRM project will replace the TRIM records management system and introduce new functionality for data management and handling. | Initiated |  | PRINCE2 | 2018-02-14 | 2018-10-14 |  |  | 295035 | 571598 | [11 empty] | Trim replacement project, incorporating IRM framework establishment.
Q4 18-19 | VicRoads | VicRoads | 2785 | Dynamics 365 | Transport and Vehicles | Collaboration ,Customer Relationship Management,Tracking and Workflow | This initiative is to re-mediate the Dynamics 365 Product. An impact assessment will be conducted in consideration of the organisational changes including the moves to Service Victoria (SV) and Department of Transport (DoT). | Initiated |  | Agile | 2019-04-15 | 2019-08-26 | [15 empty] | Project initiation and procurement activities are ongoing.
Q4 18-19 | VicRoads | VicRoads | 2786 | Call Centre Transition | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Purpose of the project is to consolidate Call Centre contracts reduce risk from outdated systems hardware/software and improve business intelligence for a better customer experience. | Delivery |  | Hybrid - Agile and PRINCE2 | 2019-04-15 | 2019-05-30 |  | 2019-05-30 | 0 |  | 2019-06-03 |  | 2020-06-30 |  | 1020000 | [5 empty] | Green | Overall project status is Green. Although the project scope has had some minor additions there is no impact to the over all schedule.
Q4 18-19 | VicRoads | VicRoads | 2787 | Computer Licence Testing (CLT) Upgrade | Transport and Vehicles | Customer Initiated Assistance,Visualisation | This project is to upgrade the Computer Licence Testing (CLT) software and the dated Hazard Perception Test (HPT) videos to provide an enhanced customer experience and replace soon to be unsupported technology. | Initiated |  | Agile | 2019-04-15 | 2019-08-30 | [15 empty] | Overall project is Green. Procurement activities are ongoing.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2788 | Cherry Creek Youth Justice Redevelopment Project | Law and Justice | Systems Management | The Youth Justice Redevelopment Project, referred to as 'Cherry Creek', is new facility planned for construction on land 5kms east of the Little River locality. | Delivery |  | Project Management Excellence | 2017-04-03 | 2017-04-03 |  | 2019-06-20 | 0 |  | 2019-06-21 | 2019-06-21 | 2020-12-31 | 2021-04-08 | 8975000 | [5 empty] | Amber | Project is currently in detailed design phase/re-scoping and will be liaising with the relevant business units regarding ICT components to ensure departmental and operational designs and requirements are factored in and the final ICT scope falls within budget.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2789 | Chisholm Road Prison Project | Law and Justice | Systems Management | As part of the construction of the prison, this project will fit out ICT hardware to support the operation of the prison, to meet current standards and operational requirements. | Delivery |  | Project Management Excellence | 2017-07-01 | 2017-12-01 |  | 2017-12-01 | 0 |  | 2017-12-01 |  | 2022-06-30 |  | 13000000 | [5 empty] | Green | Project is currently in detailed design phase. With regards to ICT components the project is liaising with the relevant business units to confirm designs are adhering to departmental requirements and standards. Workshops with Corrections Victoria have identified ICT end user requirements for equipment and supporting infrastructure. Procurement of ICT will commence in late 2020.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2790 | New DPFC 106 Bed and Supporting Infrastructure Expansion Stage 1 | Law and Justice | Other | This project is for the fit out of ICT hardware to support the expansion and operation of the prison to meet current standards and operational requirements. | Delivery |  | Project Management Excellence | 2018-07-01 | 2019-06-30 |  | 2019-06-30 | 3000000 |  | 2019-07-01 |  | 2022-02-28 |  | 3000000 | [5 empty] | Green | The Community Safety and Building Authority (CSBA) is working with the relevant business unit to ensure compliance with all standards.
Q4 18-19 | Department of Premier and Cabinet | DPC | 2791 | HCM Implementation | Business and Industry | Human Capital / Workforce Management | DPC has embarked on a journey of positioning SAP’s SuccessFactors as its key HR platform. The implementation will enhance and promote self-services across managers and employees. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-03-09 | 2019-12-31 | 2019-05-10 | 2019-05-21 | 2890000 | 150000 | 2019-06-03 |  | 2019-12-31 |  | 2240000 | 2740000 |  |  |  |  | Green | Project is currently on track as per the planned scope and timelines which includes a 2 phase implementation strategy. Performance & Learning to be implemented first with the remaining modules to follow.
Q4 18-19 | VicRoads | VicRoads | 2792 | Registration and Licence Data Quality Project -Stage 2 | Transport and Vehicles | Data Management | Purpose of this project is to ensure customer’s driver licence data is accurate and of high-quality and secure. This activity is necessary to support accurate data share within Victoria and nationally through Commonwealth services such as the NDLFRS. | Initiated |  | Hybrid - Agile and PRINCE2 | 2019-06-24 | 2019-09-02 | [15 empty] | Detailed planning for stage 2 is currently underway.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2793 | Finance Platform Replacement | Government and Economy | Financial Management | Implementation of Oracle Cloud Financials in WorkSafe. | Initiated |  | PMBoK | 2019-05-01 | 2019-08-31 | [15 empty] | Project is tracking to plan.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2794 | Website Re-Platforming | Government and Economy | Communication | Replace and decommission WorkSafe's legacy websites/microsites and partner agency websites that currently use WorkSafe's legacy platforms. | Initiated |  | PMBoK | 2018-11-01 | 2019-06-30 | [15 empty] | Project is tracking to plan.
Q4 18-19 | WorkSafe Victoria | WorkSafe | 2795 | Inspectors Toolkit | Government and Economy | Communication | Implementation of the 2030 Inspector's Technology Kit, including purchase of iPads, iPhones and device configuration development. | Initiated |  | PMBoK | 2019-05-01 | 2019-06-30 | [15 empty] | Project is tracking to plan.
Q4 18-19 | Grampians Wimmera Mallee Water Corporation | GWM Water | 2796 | Urban Remote Metering Project | Environment and Water | Business Intelligence | Replace the existing V100 water meter with an all-in-one (water meter and communications) V200HT RTU on approximately 29,144 meters and to retro fit an electronic device on approximately 2,634 urban water meters | Delivery |  | PRINCE2 | 2018-11-01 | 2018-12-11 |  | 2018-12-11 | 9131 |  | 2018-12-11 |  | 2020-06-30 |  | 6871820 | [5 empty] | Green | Project is on track.
Q4 18-19 | Victorian Rail Track | VicTrack | 2797 | Transport and Government Secure Network (TGSN) | Transport and Vehicles | Routing and Scheduling | To upgrade VicTrack's fixed Telecommunications network. The current network has various elements which are obsolete or becoming obsolete there is lack of spare equiments and reduced vendor support. 3 years project to deliver new technology. | Initiated |  | VicTrack PMF | 2019-06-03 | 2019-10-01 |  |  | 0 | [12 empty] | Business Case is being developed.
Q4 18-19 | Transport Accident Commission | TAC | 2798 | System Stabilisation | Transport and Vehicles | Systems Management | System Stabilisation project is aimed at embedding a TAC Technology delivery model with planned releases to support the system changes and initiatives required for Scheme Performance and System Stabilisation. | Delivery |  | PRINCE2 | 2019-04-08 | 2019-05-23 |  | 2019-05-23 | 0 |  | 2019-05-23 |  | 2019-12-16 |  | 4300000 | 6545894 |  |  |  |  | Green | As at 30 June 2019 the project is tracking green against plan and will continue to focus on improving the scheme’s performance and stabilising operational issues and impacts over the course of the next 5 months.
Q4 18-19 | Department of Justice and Community Safety | DJCS | 2799 | Network Uplift Program | Law and Justice | Organisational Management | To get all DJCS sites on the same comparable level of capability to support Win 10 roll-out and to apply the same service delivery principles and services to all sites. Includes centralisation of file and print services and provision of WIFI. | Delivery |  | Project Management Excellence | 2018-11-01 | 2019-05-17 |  | 2019-05-17 | 0 |  | 2019-05-17 |  | 2021-06-30 |  | 6148000 | [5 empty] | Green | Program governance established and Steering Committee approved business case and funding for delivery. Procurement of equipment to support first tranche of Wi-Fi deployment complete. A potential issue that may impact delivery is the establishment of a cabling procurement contract. This is being monitored.
Q4 18-19 | Melbourne Water | MELB Water | 2800 | Asset management procurement | Environment and Water | Assets/Materials Management | Design and implement an asset management procurement capability inclusive of multiple integration points to other applications. | Initiated |  | Agile | 2019-04-18 | 2019-07-24 | [15 empty] | Outstanding 'as is' and 'to be' business processes currently being finalised. The project has also identified the need for Master Data documentation, which has not been previsously documented. Schedule to be updated to include these new requirements.
Q4 18-19 | Melbourne Water | MELB Water | 2801 | Image processing and analytics | Environment and Water | Assets/Materials Management | Image processing and analytics for sewerage assets. | Initiated |  | PRINCE2 | 2019-04-17 | 2019-08-20 | [15 empty] | Project is currently evaluating tender submissions. First phase of evaluation has completed and a shortlist of recommendations will be presented to the Project Leadership Team (PLT) for consideration.
Q4 18-19 | Melbourne Water | MELB Water | 2810 | Water transfer network automation | Environment and Water | Management of Process | Automation and optimisation of the water transfer network. | Delivery |  | PRINCE2 | 2019-04-01 | 2019-04-04 |  | 2019-04-04 | 230000 |  | 2019-04-04 |  | 2021-06-22 |  | 3880684 | [5 empty] | Green | Contract negotiations nearing completion. Design workshops held.
Q4 18-19 | Melbourne Water | MELB Water | 2811 | Online Customer and Community Portal | Environment and Water | Customer Initiated Assistance | The Customer and Community Portal has been identified as a key system component to enable Customers to self-serve and offer a quicker simpler way to interact with Melbourne Water services. | Initiated |  | Agile | 2019-06-30 | 2019-07-19 | [15 empty] | Team is working through agile sprints to develop an MVP (minimal viable product). This will be part of a soft launch to a small group for review, development and further testing.
Q4 18-19 | Department of Health and Human Services | DHHS | 2812 | Oracle Financials Upgrade | Community Services | Systems Management | Project is to upgrade the existing Oracle EBS R11 platform to Oracle ERP Cloud including replacement of custom module applications and decouple them from the Oracle Platform. | Initiated |  | PRINCE2 | 2019-05-20 | 2019-12-31 |  |  | 1885550 | [12 empty] | Planning and mobilisation activities are underway.
Q4 18-19 | Yarra Valley Water | YV Water | 2816 | Customer Experience Digital Platform (CXDP) | Government and Economy | Communication,Development and Integration | CXDP is a key piece of technology that will provide our staff and customers with a user friendly and intuitive interface into our core systems. | Initiated |  | PRINCE2 | 2018-07-01 | 2019-08-30 |  |  | 423240 | 453000 | [11 empty] | Procurement activities and evaluation of the RFT responses
Q4 18-19 | Department of Education and Training | DET | 2817 | Careers E-Portfolio | Education | Development and Integration | Implementation of an online platform ‘Careers e-Portfolio’ that will enable students in Year 9 to capture their career goals and plans, share their skills, experiences and accomplishments, and keep all the information they will need. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-07-02 | 2019-03-29 |  | 2019-03-29 | 0 | 302765 | 2019-03-29 |  | 2019-10-02 |  | 1168376 | [5 empty] | Green | Development and testing of the solution has been completed successfully. Rollout of the solution to schools is underway and it's on track to be completed as scheduled. The overall status of the project is green.
Q4 18-19 | Department of Education and Training | DET | 2819 | Kindergarten Information Management System (KIMS) Reform | Education | Development and Integration ,Financial Management | The KIMS Reform Project will replace an existing system and enable the delivery of a new Cloud based technology platform that will allow for funding distribution to Early Child Providers. | Delivery |  | Hybrid - Agile and PRINCE2 | 2018-04-26 | 2019-06-28 |  | 2019-06-28 | 0 | 787836 | 2019-06-28 | 2019-06-28 | 2020-03-27 | 2022-12-31 | 15637064 | [5 empty] | Amber | Project status is currently Amber due to the delay in contract execution with System Integrator vendor leading to a delay in an approved project schedule being completed. Vendor has now commenced and schedule is being completed, and Project will be move to an overall status of green once schedule has been approved and project can be baselined.
Q4 18-19 | Yarra Valley Water | YV Water | 2820 | Application Program Interface (API) Integration | Environment and Water | Systems Management | Foundational technology that will enable a faster mechanism for accessing data and functionality in our core systems | Initiated |  | PRINCE2 | 2018-10-01 | 2019-08-31 |  |  | 226930 | 261000 | [11 empty] | Procurement activities and evaluation of the RFT responses
Q4 18-19 | Yarra Valley Water | YV Water | 2821 | Enterprise Historian | Government and Economy | Systems Management | Application for the acquisition, storage, analysis and presentation of large volume of data from multiple backend systems, providing operational users and customers with access to contextualised data | Initiated |  | PRINCE2 | 2018-11-01 | 2019-08-30 |  |  | 240000 | [12 empty] | Procurement activities and evaluation of the RFT responses
Q4 18-19 | Yarra Valley Water | YV Water | 2822 | Distribution Management Communication (DMC) | Government and Economy | Communication | End-to-end solution that combines Device Communications, Device Management (IoT) and Operational Platform. | Initiated |  | PRINCE2 | 2019-05-01 | 2020-01-31 |  |  | 350000 | [12 empty] | Procurement activities and evaluation of the RFT responses.
Q4 18-19 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end to end business processes for MVP product across meter management, billing, reporting and alerts & alarms. | Delivery |  | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 | 2019-06-24 |  | 2020-02-28 | 0 | 5123000 |  |  |  |  | Green | Business process have all been defined for core capability and technical impacts have been assessed, with build commencing across multiple applications.
Q4 18-19 | Public Transport Victoria | PTV | 2824 | Rail Operational Performance Project (ROPP) | Transport and Vehicles | Systems Management | The objective of the new Rail Operational Performance Project (ROPP) solution is to provide an efficient, future proof system that enables compliance with the MR4 contract and supports the enterprise approach to rationalise the data management proces | Initiated |  | PTV Investment Lifecycle | 2018-07-02 | 2019-06-30 |  |  | 2200000 | [12 empty] | Options are being investigated following Business Requirements validation. DoT is exploring the use of the existing platforms as one of the ROPP potential solutions.
Q4 18-19 | Public Transport Victoria | PTV | 2825 | Automated Vehicle Monitoring Replacement (AVMR) | Transport and Vehicles | Analyses and Statistics | The tram Automatic Vehicle Monitoring (AVM) system is used for the preparation management and monitoring of all tram services across the tram network. It is a vital and central point for daily management of tram operations. | Initiated |  | PTV Investment Lifecycle | 2018-07-02 | 2020-06-30 |  |  | 2800000 | [12 empty] | Government has provided funding from the 19/20 State Budget to continue the development of AVMR options and business case.
Q4 18-19 | Goulburn Broken Catchment Management Authority | GBC MA | 2827 | Microsoft Dynamics 365 Transformation and Transition Project | Environment and Water | Financial Management | Transformation and transition of financial management information system to modern, integrated and fully supported ERP application environment to meet current and future operational needs across seven Catchment Management Authorities. | Delivery |  | PRINCE2 | 2017-07-01 | 2017-11-30 |  | 2017-12-14 | 40000 |  | 2018-04-01 |  | 2020-06-30 |  | 1287000 | [5 empty] | Green | Project on track
Q4 18-19 | Victorian Institute of Teaching | VIT | 2829 | Nexus - VIT Business Transformation | Education | Customer Relationship Management,Customer Initiated Assistance | VIT is developing a new CRM with the objective of providing an easy-to-use digital experience that will reduce regulatory burden for teachers and employers in Victoria | Delivery |  | Hybrid - Agile and PRINCE2 | 2019-01-01 | 2019-02-01 |  | 2019-02-13 | 0 |  | 2019-04-16 |  | 2021-04-15 |  | 8120445 | [5 empty] | Green | on track
Q4 18-19 | Department of Jobs, Precincts and Regions | DJPR | 2830 | Oracle Cloud Project | Government and Economy | Financial Management,Management of Process ,Reporting | The Business Systems Cloud Transformation project (Oracle Cloud) will replace the existing financial reporting systems with Oracle Cloud systems. | Delivery |  | Hybrid - Agile and PRINCE2 | 2019-01-01 | 2019-03-04 |  | 2019-03-04 | 0 |  | 2019-05-17 |  | 2020-05-04 |  | 6600000 | [5 empty] | Green | The project is in the procurement phase and is ramping up for implementation in the next quarter.
Q4 18-19 | Department of Health and Human Services | DHHS | 2831 | Housing Systems Financial Reporting | Community Services | Data Management | The objective of this project is to implement a consolidated Housing Financials Reporting solution. The scope covers both Property Expenditure and Customer Revenue reporting. | Delivery |  | Hybrid - Agile and PRINCE2 | 2019-02-04 | 2019-03-07 |  | 2019-03-07 | 0 |  | 2019-04-01 | 2019-04-01 | 2020-10-31 | 2020-10-30 | 3825943 | [5 empty] | Amber | Project is progressing but has had schedule delays.